|  | SUN Movement Multi-Partner Trust Fund |  |
| --- | --- | --- |

PROGRAMME1 QUARTERLY PROGRESS UPDATE

as of June  2014

| Participating UN Organization: | World Health Organization |
| --- | --- |
| Implementing Partner(s): | World Vision Uganda |
| Programme Number: | Program number – SUN – Window 2-010 |
| Programme Title: | Programme title – Strengthening Uganda Civil Society capacity to strengthen the scaling up Nutrition (SUN) |
| Total Approved Programme Budget: | US$___ USD 321,000______________ |
| Location: | Uganda |
| MC Approval Date: |  |
| Programme Duration: | 3 years | Starting Date: | March 2013 | Completion Date: | March 2016 |
| Funds Committed: | US$_________________ | Percentage of Approved: |  |
| Funds Disbursed: | US$_________________ | Percentage of Approved: |  |
| Expected Programme Duration: | 3 years | Forecast Final Date: | March 2013 | Delay (Months): | 6 months |

| Outcomes: | Achievements/Results: | Percentage of planned: |
| --- | --- | --- |
| A functional CSO platform with harmonised information and capacity to influence nutrition policy and action in favour of mothers and children by 2014 | During the period under review, UCCOSUN consolidated the central sub-regional information platform. In may, UCCOSUN joined other stakeholders and celebrated the Global Week of Action (GWA) on scaling-up nutrition in Uganda. On average, 80 people participated in each of the three events supported by UCCOSUN, involving religious leaders, government officials, Civil Society groups, community representatives , the private sector and legislators. Furthermore, UCCO-SUN engaged with the Office of the Prime Minister and UN REACH in the UNAP Scale Up Planning Approach (UNAP SUPA) small working group for training and customizing of the UNAP SUPA and also in the reviewing the Nutrition Advocacy and Communication Strategy. | 40 |
| An effective policy and legal frame-work from national level to the grassroots for improved nutrition governance by 2014 to support the scale-up of proven interventions in country | With the advancement of the East African Federation, UCCOSUN facilitated the Civil Society review of the East African Food and Nutrition Policy. We made contributions towards harmonization of scaling up nutrition provision in the sub-region that would facilitate implementation of the Uganda Nutrition Action Plan. |  |
| A stronger and sustainable multi-stakeholder dialogue from national level to the grassroots for better government accountability on nutrition investments by 2014 | Considering the centrality of early child-hood development, we supported a multi-stakeholder dialogues on providing school day meals for children in public schools. About 86 participants reviewed the draft government policy on school lunches and Commissioner in charge of basic education committed to put the recommendations at the policy table for action. The alliance engaged media in building the profile of scaling up nutrition through excursions and some of the articles are as per the links below. http://www.observer.ug/index.php?option=com_content&view=article&id=31804:-malnutrition-still-a-national-crisis&catid=58:health-living&Itemid=89 |  |
| A constituency with capacity to demand for the scale up of nutrition activities at the grassroots by 2014 | The UCCOSUN Secretariat organized an Annual General Meeting and reflected on progress as well as recommendations for future improvement. 32 members attended the meeting including a visitor from SUN secretariat called . Also by the end of the quarter, UCCO-SUN membership had grown to 42 registered organizations which participated in the Uganda Nutrition Action Plan- SUN Self assessment. The process took stock on the multi-sectoral approach on Scaling up Nutrition and we learnt that we were on track given the growing networking and information sharing between the different stakeholders in Uganda, including development partners, United Nations Agencies, Civil Society and the Private sector |  |

Qualitative achievements against outcomes and results:

UCCOSUN emerged as a stronger platform for joint advocacy on issues of scaling-up nutrition resulting from mobilization efforts and information sharing. Getting the media on-board with the relevant information also contributed towards changing people’s mind sets towards better nutrition outcomes.

The term “programme” is used for projects, programmes and joint programmes.