# RUNO Half Yearly Reporting 					TEMPLATE 4.3

[COUNTRY: Kyrgyz Republic]

PROJECT HALF YEARLY PROGRESS UPDATE

PERIOD COVERED: JANUARY – JUNE 2015

| Project No & Title: | PBF/Improving the Rule of Law and Access to Justice for Sustainable Peace - # 00085690 |
| --- | --- |
| Recipient Organization(s): | UNDP |
| Implementing Partners (Government, UN agencies, NGOs etc): | Ministry of Justice, President's Office, Parliament, Ombudsman Institute, State Personnel Service of the Kyrgyz Republic |
| Total Approved Budget : | 1,027,000 USD |
| Preliminary data on funds committed : | 218,714 USD | % of funds committed / total approved budget: | 21.30 % |
| Expenditure: | 161,913 USD | % of expenditure / total budget: (Delivery rate) | 15.77 % |
| Project Approval Date: |  | Possible delay in operational closure date (Number of months) | n/a |
| Project Start Date: | 1 January 2014 |  |  |
| Expected Operational Project Closure Date: | 30 June 2016 |  |  |
| Project Outcomes: | Outcome 1: Critical conflict sensitive laws and policies are adopted and amended in line with the international human rights standards to uphold the rule of law and ensure equitable redress of grievances; Outcome 2: Key rule of law/ justice institutions and civil society are capacitated to collaborate, build consensus and implement solutions towards improving access to justice, ensuring principles of fair trial, non-discrimination, inclusion and increased representation of women and ethnic minorities in public service; Outcome 3: Rights holders, especially the most vulnerable and marginalized, are empowered to better claim their rights through legal education, awareness raising and provision of state guaranteed free legal aid |
| PBF Focus Area (select one of the Focus Areas listed below) | 2.2. Democratic Governance |

# Qualitative assessment of progress

| For each intended outcome, provide evidence of progress during the reporting period. In addition, for each outcome include the outputs achieved. (1000 characters max per outcome.) | Outcome 1: A set of laws, reforming judiciary/justice system, enforcing peaceful and fair resolution of citizen's disputes and improving their access to justice, was passed in the 1st reading in Parliament committees. These laws were finalized with support of UNDP experts, taking into account international human rights standards, principles of civic engagement and UPR recommendations. UNDP also rendered assistance to the drafting process of a 2-year National Action Plan for the implementation of UNSC Resolution 1325, enhancing the role of women in promoting peace and security. To ensure checks and balances, the oversight function of the Legislative (Parliament) over Executive was enhanced through development of reporting guidelines of several Government agencies to the Parliament. Outcome 2: UNDP supported the Parliament in holding a series of inclusive public consultations with civil society, academia, and relevant state agencies on draft judicial reform laws, prior to the 1st reading. Trainings/informative sessions and expert advice on the process and content of judicial reform was provided by UNDP experts to CSO members, also those who were previously excluded from the judicial reform process (mostly representing vulnerable groups, such as women, children and PwD). This has led to an increased level of participation of CSOs in discussion of draft laws and preparation of comments forwarded to the Parliament Committees. To enhance CSO's capacity in monitoring the accountability and transparency of state agencies, as well as in effective communication and dialogue with state representatives, UNDP trained 230 members of 15 newly elected Public Councils under relevant ministries/agencies. Over 90% of trainees positively evaluated the quality of these trainings. Outcome 3: The project focused on building a sustainable base for the delivery of free legal aid on criminal and civil cases, through supporting development of the Ministry of Justice's strategy on legal education and raising the legal awareness of citizens; drafting of regulations of the Bar Council, its Ethics Commission, establishment of territorial Bar Associations in provinces; and launching of a pilot pro bono initiative in Bishkek. The actual delivery of free legal aid and advocacy for the rights of citizens in pilot localities is being prepared with the Bar Association. Outcome 4: n/a |
| --- | --- |
| Do you see evidence that the project is having a positive impact on peacebuilding? (1000 characters max.) | Evidence of project’s positive impact on peace building is the 5-time increase of the index of trust of citizens in Government and public agencies in 2014 (14,7) in comparison with 2013 (2,9) according to the National Strategic Studies Institute. This is due to more transparent and accountable work of the Government and more effective communication with citizens. The project contributed to this outcome by supporting Public Councils (PC), representing interests of citizens and civil society attached to each ministry/agency. UNDP assisted the Government’s Office in establishing a transparent and fair selection/recruitment of PC members and then provided relevant training. The members of the PCs have monitored the performance of state agencies on a regular basis, raised concerns on their abuse of power, misconduct, through their appeals to the Ministers and the Government. Additionally, the number of public dialogue consultations/meeting with CSOs on judicial reform increased. |
| Were there catalytic effects from the project in the period reported, including additional funding commitments or unleashing/ unblocking of any peace relevant processes? (1000 characters max.) | The project has drawn more attention of national authorities to the need of better strategic & financial planning of judicial reform. As a result, the package of additional procedural laws and a detailed budget was elaborated to enhance reform planning and implementation. As this project is limited to the drafting and adoption of laws, the need to support the further planning of reform implementation of these laws was discussed with the national partners. At their request, a new project was prepared which attracted funding from other donors, such as UK and USAID. |
| If progress has been slow or inadequate, provide main reasons and what is being done to address them. (1000 characters max.) | The implementation of the project is on track, however, several activities are delayed/postponed. Firstly, some of the activities related to the Parliament, which is currently finalizing its term and is predominantly focused on the elections, had to be postponed till the elections of new one in November 2015. Secondly, the issue of ethnic representation in public service revealed the need for more in-depth consultations with the national partners before activities are being launched. UNDP, together with other UN agencies, is continuing its efforts and advocacy with partners in this regard. The legal aid delivery in selected localities started with a delay, as it required the establishment of the new Bar Association, which has now started its work to prepare lawyers for this work. |
| What are the main activities/expected results for the rest of the year? (1000 characters max.) | The project will continue to support public consultations on and the drafting of judicial reform laws through expert advice, conflict-sensitive expertise, CSO engagement. It will further assist in development of oversight guidelines for the Parliament and Supreme Court on the enforcement of laws and judicial decisions. The dialogue platform established will become fully operational and will provide spaces for public discussions on emerging issues, including on Access to Justice of vulnerable groups, etc. The newly elected members of 11 Public Councils will further be trained and a conference will be held to monitor the progress of their work in fall 2015. Trial monitoring of cases strategically important for peacebuilding will be conducted by trained Ombudsman and NGO staff. Free legal aid lawyers will be dispatched to pilot localities to provide their services to the most vulnerable and media will hold advocacy campaigns on the rights of citizens to access justice and public service. |
| Is there any need to adjust project strategies/ duration/budget etc.? (1000 characters max.) | NO |
| What is the project budget expenditure to date (percentage of allocated project budget expensed by the date of the report) – preliminary figures only? (1000 characters max.) | Project budget expenditure as of 15 June 2015 is 170,513 USD (16.60% from total budget) |
| Any other information that the project needs to convey to PBSO (and JSC) at this stage? (1500 characters max.) | n/a |

INDICATOR BASED PERFORMANCE ASSESSMENT: Using the Project Results Framework as per the approved project document- provide an update on the achievement of key indicators at both the outcome and output level in the table below. Where it has not been possible to collect data on indicators, state this and provide any explanation in the qualitative text above. (250 characters max per entry)

|  | Performance Indicators | Indicator Baseline | End of project Indicator Target | Current indicator progress | Reasons for Variance/ Delay (if any) | Adjustment of target (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 Critical conflict sensitive laws and policies are adopted and amended in line with the international human rights standards to uphold the rule of law and ensure equitable redress of grievances | Indicator 1.1 Number of conflict-sensitive laws and policies adopted and amended, including: Criminal code, Criminal procedure code, Law on Free Legal Aid, Law on Misdemeanour, Law on the responsibility of judges, Law on Bar Association | 0 from priority judiciary law package | 5 laws and policies adopted and amended, of which at least two will have a direct impact on women’s rights, by end of June 2016 | 5 laws passed 1st reading in the Parliament committees, and were finalized taking into account UPR recommendations,and have undergone 6 public hearings (also in the regions) and the NAP for UNSC Resolution 1325 was drafted | The initial package of judicial reform laws expanded and UNDP now works on 9 laws: Criminal, on Misdemeanor, on Offences Codes, Laws on Responsibilties of Judges, on Amnesty, Registry of Convictions, Court Executors, Free Legal Aid, Bar Association. | To be revised as: "9 laws of priority judicial reform package and policies drafted or amended, of which at least two will have a direct impact on women’s rights, by end of June 2016 |
|  | Indicator 1.2 Parliament and Supreme Court oversees the implementation of key laws and judgements, including legal provisions on anti-discrimination | 1 oversight event conducted in line with parliamentary and court oversight standards, and no oversight guidelines drafted | at least 5 oversight events conducted in line with parliamentary and court oversight standards, and 2 oversight guidelines drafted and adopted by end of June 2016 | 1 event on Parliamentary oversight over laws and executive/accountable to Parliament bodies was held; guideline on reporting of Government before Parliament was piloted and adopted | n/a | n/a |
| Output 1.1 Key priority laws and policies pertaining to criminal justice, non-discrimination and human rights reviewed and amended in line with the Constitution of KR, international human rights standards and recommendations of UN human rights mechanisms | Indicator 1.1.1 Number of conflict-sensitive laws and policies adopted and amended. Activities focus on revision/amendment of the following laws: Criminal Code, Civil Code, Civil procedure code, Laws on State Guaranteed Legal Aid, Bar and Legal Practice, Bar and Leg | 0 from priority judiciary law package | 5 laws and policies adopted and amended, of which at least two will have a direct impact on women’s rights, by end of June 2016 | same as under indicator 1.1 | same as under indicator 1.1 | same as under indicator 1.1 |
|  | Indicator 1.1.2 |  |  |  |  |  |
| Output 1.2 The methodology for the conflict-sensitive review of draft laws is adopted and applied by the Parliament | Indicator 1.2.1 Availability of the parliament's instructions on the use of the conflict sensitive expertise; # of laws reviewed according to the conflict sensitive expertise | Instructions not currently available; 0 laws reviewed | Available; 10 by end of June 2016 | 4 laws are in process of conflict sensitive expertise, and have undergone 1st stage of conflict sensitive expertise, such as wide public dicussions to prevent possible conflicts | Due to the upcoming closure of the term of the current Parliament, it seems more meaningful to postpone the adoption of the instructions till the new Parliament is elected. As it starts its work in November 2015, it won't be able to review 10 laws | To be revised as: "Parliament's instruction on use of conflict sensitive expertise is available and 5 laws reviewed according to the expertise" |
|  | Indicator 1.2.2 |  |  |  |  |  |
| Output 1.3 The mechanism of independent oversight over implementation of laws by Parliament and civil society is established | Indicator 1.3.1 Availability of the parliament's instructions on oversight of implementation of laws; number of laws and judgements assessesed in terms of progress of implementation and number of corrective measures taken as a result by parliament and civil society | Instructions not currently available; 0 laws and judgements assessed | Available; 10 by end of June 2016 | 1 event on Parliamentary oversight over laws and executive/accountable to Parliament bodies was held; the guideline on reporting of Government before Parliament was piloted and adopted | Since the Output 1.3 contributes to the Outcome indicator 1, its indicator 1.3.1 duplicates Outcome Indicator 1.2, therefore it is proposed to keep Indicator 1.3.1 similar to Indicator 1.2 | Use the text of Outcome Indicator Target 2.1 - "At least 5 oversight events conducted in line with parliamentary and court oversight standards, and 2 oversight guidelines drafted and adopted by end of June 2016" |
|  | Indicator 1.3.2 |  |  |  |  |  |
| Outcome 2 Key rule of law/ justice institutions and civil society are capacitated to collaborate, build consensus and implement solutions towards improving access to justice, ensuring principles of fair trial, non-discrimination, inclusion and increased repres | Indicator 2.1 # of recommendations of dialogue platform that were jointly implemented by state institutions and civil society | 0 | 8 recommendations by end of June 2016 | 3 recommendations have been elaborated jointly by civil society and Government representatives: increased gender sensitivity, financial independence of the judiciary, and integration of alternate dispute resolution strategies in the judicial system. | To foster dialogue platform's ownership by civil society and public actors, more time was needed and thus, the delayed occurred. | n/a |
|  | Indicator 2.2 Percentage of representation of women and minorities in public service | 8% of ethnic minorities and 43% of women in the public service, as of January 2014 (State Personnel Service statistics) | increase by 10% by end of June 2016 | 7% of ethnic minorities and 43% of women in public service as of January 2015 (State Personnel Service statistics). The meetings to address this issue were held with several national partners, however, no concrete actions were identified yet. | The delays occurred due to the turnover of the staff at national partner institutions. The project will also need to hold more detailed consultations with the national partners on the need to address this issue. | Taking into account the slow progress in this area, it is proposed to decrease the target indicator to 3% for ethnic minorities and 5% for women. |
| Output 2.1 A dialogue platform established for consensus building between relevant duty bearers and rights holders to discuss and agree on solutions addressing discriminatory practices, impunity and unequal access to justice bringing together Government, judici | Indicator 2.1.1 # of recommendations of dialogue platform that were jointly implemented by state institutions and civil society; Level of trust between representatives of state institutions and civil society | 0 | 8 recommendations by end of June 2016 | same as under indicator 2.1 | same as under indicator 2.1 | same as under indicator 2.1 |
|  | Indicator 2.1.2 |  |  |  |  |  |
| Output 2.2 The capacity of Ombudsman Office and Public Advisory Councils, to monitor implementation of national legislation, UPR recommendations and to hold relevant institutions accountable, is developed through enhancing their independence, professional | Indicator 2.2.1 # of recommendations of the UPR review and other human rights mechanisms implemented | 14 UPR recommendations relevant to PRF (5.7, 5.8, 5.29, 5.35, 5.37, 5.104, 5.105, 5.112, 5.113, 7.19, 7.20, 7.25, 7.26, 7.29). | at least 10 by end of June 2016 | 9 out of these UPR recommendations, mostly relevant to justice reform are being addressed through efforts of Human Rights Council, civil society and Ombudsman | n/a | n/a |
|  | Indicator 2.2.2 |  |  |  |  |  |
| Output 2.3 State Personnel Service responsible for placement of public servants and selected state institutions supported to increase representation of minorities and women in public service | Indicator 2.3.1 Percentage of representation of women and minorities in public service | the same as under indicator 2.2 | increase by 10% by end of June 2016 | the same as under indicator 2.2 | the same as under indicator 2.2 | the same as under indicator 2.2 |
|  | Indicator 2.3.2 |  |  |  |  |  |
| Outcome 3 Rights holders, especially the most vulnerable and marginalized, are empowered to better claim their rights through legal education, awareness raising and provision of state guaranteed free legal aid | Indicator 3.1 # of complaints/cases documented and acted upon (including criminal and civil cases) with assistance of lawyers providing Free Legal Aid (disaggregated by gender, ethnicity and age) in 6 targeted areas | 2,533 cases/complaints were documented and acted upon with assistance of Free Legal Aid lawyers in 4 provinces, covering the project localities in 2014 (Chui, Osh, Batken, Jalal-Abad) | increase by 20% by end of June 2016 in 6 targeted areas | The system of Free Legal Aid is being built. The draft Free Legal Aid Law was discussed in the Parliament and the Bar Association and its territorial branches established; the lawyers are anticipated to start free legal aid delivery from July 2015 | Free legal aid delivery in the pilot areas hasn't started yet, as it required the establishment of the Bar Association and its territorial branches. This has happened only in June 2015 and the lawyers will now start their work in July-August 2015. | To be revised as: "increase by 20% of complaints/cases documented and acted upon (including criminal and civil cases) with assistance of lawyers providing Free Legal Aid in 4 provinces, covering targeted areas" |
|  | Indicator 3.2 Level of awareness of the vulnerable groups in selected 6 conflict prone areas of their rights to claim equal access to justice and public services | The average level of legal knowledge of women, youth and minorities is 3 out of 5 (Access to Justice assessment as of Sept. 2014) | increase by 20% by end of June 2016 | The strategy of legal awareness and education was drafted by MoJ with assistance of UNDP. The advocacy campaigns in pilot areas are to start in June 2015 |  | n/a |
| Output 3.1 Capacity building of lawyers associations (Bars), Ministry of Justice and other relevant institutions of free legal aid system to ensure better implementation of state guaranteed free legal aid system, envisaging equitable access for vulnerable g | Indicator 3.1.1 # of complaints/cases documented and acted upon (including cases of violence and misconduct, cases relating to reintegration of offenders) with assistance of lawyers registered by Free Legal Aid programme | 2,533 cases/complaints were documented and acted upon with assistance of Free Legal Aid lawyers in 4 provinces, covering the project localities in 2014 (Chui, Osh, Batken, Jalal-Abad) | increase by 20% by end of June 2016 | the same as under indicator 3.1 | Since the Output 3.1 contributes to the Outcome indicator 3.1, its indicator 3.1.1 shall be aligned with 3.1.1 for consistency | To be revised as: # of complaints/cases documented and acted upon (including criminal and civil cases) with assistance of lawyers providing Free Legal Aid (disaggregated by gender, ethnicity and age) in 4 provinces, covering targeted areas |
|  | Indicator 3.1.2 |  |  |  |  |  |
| Output 3.2 3.2 Legal aid provided and advocacy/awareness raising campaigns held (also through community media) to empower rights holders, especially minorities and women in 6 selected conflict prone areas, to better claim their rights for equal access to econom | Indicator 3.2.1 Level of awareness of the vulnerable groups in selected 6 conflict prone areas of their rights to claim equal access to justice and public services; # of complaints/cases documented and acted upon (including criminal and civil cases) by free legal a | same as under indicator 3.2 | increase by 20% by end of June 2016 | the same as under indicator 3.2 | the same as under indicator 3.2 | the same as under indicator 3.2 |
|  | Indicator 3.2.2 |  |  |  |  |  |
| Output 3.3 | Indicator 3.3.1 |  |  |  |  |  |
|  | Indicator 3.3.2 |  |  |  |  |  |
| Outcome 4 | Indicator 4.1 |  |  |  |  |  |
|  | Indicator 4.2 |  |  |  |  |  |
| Output 4.1 | Indicator 4.1.1 |  |  |  |  |  |
|  | Indicator 4.1.2 |  |  |  |  |  |
| Output 4.2 | Indicator 4.2.1 |  |  |  |  |  |
|  | Indicator 4.2.2 |  |  |  |  |  |
| Output 4.3 | Indicator 4.3.1 |  |  |  |  |  |
|  | Indicator 4.3.2 |  |  |  |  |  |

# Footnotes

Please note that where there are multiple agencies, only one consolidated project report should be submitted.

Approved budget is the amount transferred to Recipient Organisations.

# Funds committed are defined as the commitments made through legal contracts for services and works according to the financial regulations and procedures of the Recipient Organisations. Provide preliminary data only.

# 4 Actual payments (contracts, services, works) made on commitments.

5 PBF focus areas are:

PBF Focus Areas are:

1: Support the implementation of peace agreements and political dialogue (Priority Area 1):

(1.1) SSR, (1.2) RoL; (1.3) DDR; (1.4) Political Dialogue;

2: Promote coexistence and peaceful resolution of conflicts (Priority Area 2):

(2.1) National reconciliation; (2.2) Democratic Governance; (2.3) Conflict prevention/management;

3:Revitalise the economy and generate immediate peace dividends (Priority Area 3);

(3.1) Employment; (3.2) Equitable access to social services

4) (Re)-establish essential administrative services (Priority Area 4)

(4.1) Strengthening of essential national state capacity; (4.2) extension of state authority/local administration; (4.3) Governance of peacebuilding resources (including JSC/ PBF Secretariats)