GRZ-UN Joint Programme on GBV Phase II

MPTF ANNUAL programme NARRATIVE progress report

REPORTING PERIOD: 1 January 2021 – 31 December 2021

| Programme Title and Project Number |  | Country, Locality(s), Priority Area(s) / Strategic Results |
| --- | --- | --- |
| Programme Title: GRZ-UN Joint Programme on Gender Based Violence in Zambia Phase II Programme Number: 001124484/Output 0119404 MPTF Office Project Reference Number: 00120438 |  | (If applicable) Country: Zambia |
|  |  | Priority area/ strategic results – GBV Prevention and Response |
| Participating Organisation(s) |  | Implementing Partners |
| Organisations that have received direct funding from the MPTF Office under this programme International Labour Organization (ILO) International Organization for Migration (IOM) United Nations Development Programme (UNDP) United Nations Population Fund (UNFPA) United Nations Children’s Fund (UNICEF) |  | Government/CSOs/NGOs Gender Division, Judiciary Department, National Prosecution Authority (NPA), Ministry of Health (MoH), Ministry of Community Development and Social Services (MCDSS), Ministry of Home Affairs and Internal Security (MoHAIS Zambia Statistical Agency, Women for Change, Chisomo Community Programme, National Legal Aid Clinic for Women (NLACW), Young Happy Healthy and Safe (YHHS), Young Women Christian Association (YWCA), Zambia Information Communications and Telecommunications Authority (ZICTA), Zambia Centre for Communication Programmes (ZCCP), Zambia Disability HIV/AIDS Human Rights Programme (ZAMDHARP), Zambia National Men’s Network for Gender and Development (ZNMNGD) |
| Programme/Project Cost (US$) |  | Programme Duration |
| Total approved budget as per project document: US$6,711,169.01 MPTF /JP Contribution transferred as at 31 December 2021: $4,310,016 by Agency (if applicable) Not applicable |  |  | Overall Duration (36 months) |  |
| Agency Contribution by Agency (if applicable) |  |  | Start Date 04.12.2019 |  |
| Government Contribution (If applicable) In Kind |  |  | Original End Date 31.12.2022 |  |
| Other Contributions (donors) (If applicable) Not applicable |  |  | Current End date 31.12.2022 |  |
| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| Assessment/Review - if applicable please attach Yes, No Date: dd.mm. yyyy Not Applicable Mid-Term Evaluation Report – if applicable please attach Yes No Date: dd.mm.yyyy |  | Name: Shupe Makashinyi Title: Gender Programme Coordinator Participating Organisation (Lead): United Nations Development Programme (UNDP) Email address: shupe.makashinyi@undp.org |

CONTACT FOR THIS REPORT

Roland Seri

Deputy Resident Representative

UNDP, Lusaka, Zambia

P.O. Box 31966, Lusaka

Zambia

Tel: (260) 211-386200

Email: roland.seri@undp.org

List of Acronyms

BCC		: Behavioural Change and Communication

CBO		: Community Based Organisation

CEDAW	: Convention on the Elimination of All Forms of Discrimination Against Women

CPU		: Child Protection Unit

CSO		: Civil Society Organisation

CWACs	: Community Welfare Assistance Committees

GD		: Gender Division, Cabinet Office, Office of the President

EC		: Emergency Contraception

FTC		: Fast Track Court

GBV		: Gender Based Violence

GRZ		: Government of the Republic of Zambia

HMIS		: Health management Information System

HRC		: Human Rights Commission

ICB		: International Competitive Bidding

IEC		: Information, Education and Communication

IOM		: International Organization for Migration

ILO		: International Labour Organization

JP                    : Joint Programme

LAZ		: Law Association of Zambia

MoCTA	: Ministry of Chiefs and Traditional Affairs

MOH		: Ministry of Health (MoH)

MCDSS	: Ministry of Community Development and Social Services

MOHA            : Ministry of Home Affairs

MoJ		: Ministry of Justice

NHC		: Neighborhood Health Committee (NHC)

NLACW	: National Legal Aid Clinic for Women

OSC		: One Stop Centres

PEP		: Post – Exposure Prophylaxis

PPE		: Personal Protective Equipment

PWD		: People with Disabilities

PQA		: Project Quality Assurance

SGBV		: Sexual Gender Based Violence

SRHR		: Sexual Reproductive Health and Rights

SBCC		: Social Behaviour Communication Change

SASA		: Start, Awareness, Support and Action

TEVETA	: Technical Educational Vocational and Entrepreneurship Authority

UN		: United Nations

UNDP		: United Nations Development Programme

UNFPA 	: United Nations Population Fund

UNICEF        	: United Nations Children’s Fund

VLOSC	: Village Led One Stop Centre

VSU		: Victim Support Unit

WfC		: Women for Change

WHO		: World Health Organization

ZCCP		: Zambia Centre for Communications Programme

ZPS		: Zambia Police Service

GRZ-UN JP on GBV Phase II - Geographical Coverage Area

EXECUTIVE SUMMARY

The Government of Zambia-United Nations Joint Programme on Gender Based Violence (GRZ-UNJP-GBV) phase II (2019-2022) is a multi-partner programme designed to reduce the prevalence of Gender-Based violence (GBV) in Zambia. The Phase II GRZ-UNJP-GBV focuses on prevention and response of GBV cases at national and sub-national levels. The response component includes four key elements, namely: Fast Track Courts (FTCs), One Stop Centres (OSCs), Shelters, and Village Led One Stop Centres (VLOSCs). These are avenues for strengthening professional practice through capacity development of service providers such as police officers, social workers, medical workers, and legal officers to respond effectively, efficiently, and provide comprehensive services to GBV survivors.

GBV is a widespread human rights and development issue that transcends geography, class, culture, age, race and religion. The Anti Gender Based Violence Act No.1 of 2011 defines gender-based violence as “any physical, mental, social or economic abuse against a person because of that person’s gender”. There has been an increase in the number of cases reported to the Zambia Police from 2012 to 2020. However, there was a slight decrease of GBV reported cases during the reporting year as per the graph on Page 7.

In the reporting period the project supported the strengthening of child friendly services for child survivors as well as Best Interest Determination (BID) for unaccompanied and separated child migrant victims of GBV. In addition, the project capacitated 516 GBV survivors and those at risk in business development, which resulted in the formation of savings and credit groups and provision of start-up kits.

To strengthen community-based services, the project handed over two Village Led Anti-GBV and Community Development One Stop Centers (VLOSC) in Chamuka and Mumena chiefdoms out of the 3 planned for 2021, leading to provision of services including legal information, psycho-social counselling, basic health services and referrals.

Further, the project facilitated the finalization of key policy documents and guidelines.  The joint programme supported the Government in the development of the Children’s Code Bill to which Ministry of Justice is planning to present this Bill before Parliament early 2022. In addition, the project also supported the finalization of the minimum standards and policies to improve services for GBV survivors. The Baseline Survey and the Rapid Assessment of the Impact of COVID-19 on Gender Equality were also finalized during the reporting period. Upon completion of the baseline report the project technical team revised and refined the Monitoring and Evaluation (M&E) results framework for output indicators and setting project targets. Before refining the project results M & E Framework, the project was guided by the draft results framework in the project document, and lessons learned from the GRZ-UN JP on GBV Phase I.

To strengthen case handling and management systems, the programme supported capacity development of professionals involved in GBV cases. In total 293 (160F: 133M) service providers were trained on Multi-Disciplinary Guidelines and legal service provision resulting in, for example, the application of the Prosecutor’s Handbook on Sexual Violence to 922 GBV cases.

# The Government of the Republic of Zambia United Nations Joint Programme on Gender Based Violence Phase Two (II) (GRZ-UN JP GBV II).

# Purpose

The GRZ-UN Joint Programme on GBV Phase II was developed to provide a coordinated, consolidated, linked, sustainable and, strengthened package of response services and prevention mechanisms at, national, sub-national and community level that addresses Gender Based Violence (GBV). In addition, the programme is aimed to support institutional transformation to facilitate the implementation of Zambia Anti GBV Law (2011) through the establishment of an integrated and multi-sectoral mechanism for its implementation.

This consolidated Annual Progress Report for the GRZ-UN Joint Programme on Gender Based Violence in Zambia covers the period from 1 January to 31 December 2021. This report is in fulfilment of the reporting requirements set out in the Standard Administrative Arrangement (SAA) concluded with the Donor and the Memorandum of Understanding (MOU) signed by Participating UN Organizations and provides an assessment of the performance within the reference period. This Annual Report is consolidated based on information, data and financial statements submitted by Participating Organizations

The programme envisages a strengthened GBV prevention and response system linking community (Village Led One Stop Centres (VLOSCs), economic and social empowerment initiatives) and sub-national (health facility based One Stop Centres (OSCs), shelters, GBV specialised courts – ‘Fast Track Courts (FTCs’) services. OSCs and community response mechanisms will also conduct outreach to communities including migrant and refuge communities and link to community structures to promote the services and support prevention efforts. At the end of the programme, community and traditional leadership structures will be empowered to speak out against GBV and promote a culture of zero tolerance towards GBV. Ultimately, strengthened response services will counter GBV and provide an element of prevention as communities see action being taken.

The programme is implemented by various State and Non-State Actors and coordinated by the Gender Division (Former Ministry of Gender) in the Office of the President, with technical and financial support from five UN Agencies (ILO, IOM, UNDP, UNFPA, UNICEF) and Bilateral Cooperating Partners (Sweden and Ireland).

The programme contributes to two overall outcomes:

- GBV survivors and persons at risk (including children and adolescents) have increased access to and utilise quality GBV prevention and response services.

- GBV survivors, those at risk and communities are empowered to break the cycle of abuse.

# RESULTS

Statistics from Zambia Police

The programme has been the main vehicle for implementing the Anti-GBV Act of 2011 to enable a coordinated and multi-sectoral response to GBV. Increased awareness on GBV, laws in place and support services for GBV survivors and their families have led to a continued increase in the number of cases reported to the police from 12,924 in 2012 to 14,097 in 2013; 15,153 in 2014; 18,088 in 2015; 18,540 in 2016 to 21,504 in 2017; 22,073 in 2018; 25,121 in 2019 to 26,370 in 2020. However, there was a decrease of GBV reported cases during the reporting year (20,540 reported GBV cases in 2021) – (Zambia Police Service Report, 2021) See graph below.

According to the ZP-VSU statistics, Zambia recorded a steady increase in reported GBV cases from 12,924 cases in 2012 to 26,370 cases in 2020. However, the reported GBV cases reduced from 26,370 in 2020 to 20,520 in 2021, representing a 23-percentage reduction. The reasons for the reduction of GBV cases in 2021 will be ascertained by the 2022 project assessment.

ANNEX 1

Source: Zambia Police Victim Support Unit (ZP-VSU) Statistics 2012-2021

Outcomes 1 and 2 Overview:

The programme noted that service providers are now able to identify, probe, codify and isolate GBV cases as opposed to treating all GBV cases as general assault. This was assessed by the different reporting templates for various types of GBV cases. As a result, cases are now being referred accordingly, enabling survivors to receive appropriate services. This was observed during the joint GRZ-UN monitoring missions to project sites. The programme results have been achieved through direct and indirect contribution of the following results, at output level.

Output Results Contributing to Outcomes

Outcome 1: GBV survivors and persons at risk (including children and adolescents) have increased access to and utilize quality GBV prevention and response services.

Output 1.1 Target districts have increased capacity to deliver coordinated GBV services

During the period under review, the project supported the strengthening of services in One Stop Centers (OSC). There was an increase on the uptake of post GBV services in the project sites, where a total of 6,532 GBV Survivors, those at risk and community members were reached in 2021 compared to 4,271 reached in 2020. Other services accessed were Post Exposure Prophylaxis (PEP) for prevention of HIV transmission and emergency contraception to SGBV survivors. Among other reasons, this increase was due to capacity strengthening of OSCs staff and satellite health clinic workers at 5 facilities in Lusaka, Chipata, Mumbwa, Choma and Ndola.

As reported previously, DNA use for GBV cases is still very limited and the court proceedings are still heavily reliant on circumstantial evidence. Routine screening has continued to be given to survivors and appropriate action taken by care providers to suit various medical conditions.

Through sensitization campaigns, health workers are prioritizing GBV cases as stated below:

“We are excited as medical personnel for the training of health workers on the management of GBV cases as we now know what to do, how to identify and who to refer cases to when faced with a GBV case”

(Dr. Jonathan Mwansa – Arthur Davison Children’s Hospital - Ndola).

In addition, out of the target of ten (10), fourteen (14) community structures were mobilized, exceeding the year’s target on conducting dialogues and information sessions on GBV prevention and response services. Community members increased their knowledge and access to information on GBV, and the COVID-19 pandemic based on results from the pre- and post-training evaluations. The structures conducting the dialogue and information sessions included  community neighborhood watch; paralegal committees; traditional leaders;  marriage counsellors (Alangizi), Community Welfare Assistance Committees (CWACs); Neighborhood Health Committees (HHCs); Safe Motherhood Action Groups (SMAGs), Change Agents; Ant-GBV Champions; Community Crime Prevention Units, Ward Development Committees (WDC); Men’s and Boys’ Network, GBV/SEA monitors; Anti-GBV Task Force Teams, Community Child Protection (CCPs); Area Associations; Women’s Clubs; Village Development Committees and Religious Committees; Youth Friendly Corners.

Due to COVID-19, the supply chains were negatively affected, hence the delivery of child-friendly supplies to OSCs was delayed. However, the supplies, including toys, papers, and color pencils, were delivered to the MoH by the end of 2021 for distribution to the five OSCs.

To improve service provision, the programme supported survivors with various health services at the hospital and community based one stop centres in target districts and reached a total of 2,214 (1,717 female; 497 Male). The services included: Post Exposure Prophylaxis (PEP), Emergency Contraceptive (EC), management of wounds and cuts, psychosocial counselling, policing (including arrest of perpetrators), protection of child survivors and paralegal information especially for the survivors who opted to go ahead with litigation. This was due to the training of 145 service providers (79 Female: 66 Male) and NGO partners in multi-disciplinary GBV guidelines. These included health officers, police officers from the Victim Support Unit (VSU), prosecutors, social welfare officers and representatives from the Child Justice Forum (under judiciary). The trained service providers came from Solwezi, Mongu, Kabwe, Kalumbila, Kasama, Mansa, Choma, Chinsali, Senanga, Mumbwa, Chipata, Itezhitezhi, Ndola, Katete and Lusaka.

To strengthen coordination and improve ownership, the programme supported the engagement, coordination and facilitated chiefdom dialogues among traditional leaders and stakeholders during the development, finalisation and validation of minimum standards and guidelines for operationalisation of VLOSC. Trainings and orientation of traditional leaders, VLOSC Volunteers and community members are scheduled in Quarter one and two of 2022.  The minimum standards and guidelines will also contribute to sustainability of the interventions as the traditional leaders will support the work of the VLOSCs and ensure that the VLOSCs remain operational with community support long after the programme end.

To bring services closer to the community, the programme supported the establishment of three (3) VLOSCs in Chisamba at Chief Chamuka’s chiefdom, in Lundazi at Senior Chief Mwase Ntembwe’s chiefdom and in Kalumbila at Chief Mumena’s chiefdom. VLOSC are a hub for disseminating information, counselling, tracking, mapping, reporting, and following up GBV cases with relevant institutions to ensure that cases are handled as required under the laws of Zambia. The launches included the participation of high government officials, Cooperating partners and traditional leadership. See photos below of the launch of Chamuka and Kalumbila VLOSC.

Above: The former President of Zambia, His Excellency, Mr. Edgar Chagwa Lungu plants a tree with the UN RC, Dr. Coumba Mar Gardio to launch the Chamuka VLOSC at Chamuka in Chisamba district, 3 May 2021.

Below: Chief Mumena commissioning a Village Led One Stop Centre with the Irish Ambassador, Bronagh Carr in December 2021

As a result of establishing the VLOSC, a total of 311 (191 females, 120 males) received GBV services from VLOSC during the reporting period, exceeding the 2021 target of 110. The services provided included legal information, mediation, counselling, through the trained paralegals and referral to the VSU and health centres. In the fourth quarter of 2021, two GBV cases were referred to the Zambia Police Service in Chisamba district for prosecution. The traditional leaders embraced the community led initiative as mentioned below:

“The establishment of the Mumena village led one stop center in my chiefdom is a timely gift as GBV survivors will have a place to go when faced with violation in their homes…” said His Royal Highness Chief Mumena.

Output 1.2 GBV survivors have increased access to safe shelter

During the reporting period, the programme working with local implementing partners such as YWCA, NLACW, Women for Change, and Young Happy Health and Safe provided temporary safe shelter services to 627 (527 females, 100 males) GBV survivors, those at risk and community members against the 2021 target of 141. Other services provided in the safe shelters included medical aid, COVID testing, referrals, social services, psychosocial counselling, education support, legal advice, startup capital and information as well as escort to courts and reintegration back into families when it was ascertained that the environment was safe. These shelters are in Chipata, Chongwe, Lusaka, Kabwe, Kaoma, Mongu, Lundazi and Solwezi districts.

The project also supported the strengthening of eight temporary safe shelters, including in Kitwe, Chipata, Chipata Place of Safety, Mongu, Kaoma, Lusaka Children’s Shelter, Lusaka adult Shelter and Solwezi. The shelters were provided with COVID-19 PPEs, food, sanitation materials, household equipment and enhanced security. The project supported the erection of a perimeter wall fence at the Kitwe safe shelter, which enhanced security thereby making the place safer.

The Project, working in collaboration with Ministry of Community Development Social Services (MCDSS), Zambia Police - VSU and Child Protection Unit (CPU), supported 367 child GBV survivors to access alternative care options through case management. Services included safe shelter, re-integration, legal services, medical assistance, kinship care and psychosocial support among others. Of these, 289 were girls and 78 were boys.

Output 1.3 Target districts have increased capacity to deliver quality legal services

The project supported training on GBV case management of 538 legal service providers against a target of 115 during the reporting period to ensure provision of efficient justice delivery system for GBV survivors.  These included 10 Para-legal, 426 Prosecutors, 40 Adjudicators, 2 Social Welfare Officers and 60 best interest determination members. This capacity development of various stakeholders as listed has contributed to the provision of quality comprehensive legal services. In collaboration with Judiciary, National Prosecution Authority, Zambia Police, NLACW, the program fostered improved case management of GBV cases by the service providers. The topics included but not limited to the following: access to justice and barriers to victims accessing justice, human rights, and gender, GBV adjudicating skills for better GBV case management, national, regional, and international frameworks which address GBV and civil procedural issues on GBV.

In addition to the progress made above, the Project, working with the National Legal Aid Clinic for Women (NLACW) led a stakeholder consultative process to review the GBV training manual for local court and traditional court adjudicators to align it with current legislation and international best standards and practices.

Further the programme identified and supported a total of 611 GBV survivors out of a target of 1,500 with legal assistance. Legal assistance included legal advice, legal information, and legal representation before the anti-GBV Fast Track Courts and other courts of law.  The programme noted that 489 were cases of economic abuse (child neglect); while 122 were physical abuse, (rape, defilement and assault occasioning actual bodily harm). The low number reached was due to low reporting. The intervention will be accelerated in 2022 now that the project has a monthly reporting tool for all the implementing partners.

Outcome 2: GBV survivors, those at risk and communities are empowered to break the cycle of abuse

Output 2.1: GBV survivors and those at-risk access economic empowerment services.

The Joint programme supported various interventions for the continuity of economic activities in efforts to empower GBV survivors and those at risk of GBV to access economic empowerment services during the reporting period.

A total of 516 GBV survivors (456 females, 60 males) and those at risk were capacitated in business development in the project sites except for Chisamba, Chipata and Ndola to be reached in 2022. The survivors and those at risk were provided with capacity development interventions using the Gender +Entrepreneurship Together (GET) Ahead for Women in Enterprise tool, Community Savings Groups (CSG) and Community Based Trainings (CBT). The GBV survivors have been integrated in the MCDSS database for other social protection and empowerment programmes supported by Government and other co-operating partners. The interventions contributed towards improving entrepreneurship skills, understanding gender causality, and managing a sustainable enterprise as well as supporting and strengthening the formation of savings and credit groups. The beneficiaries are now better able to meet their basic needs of food, school requisites, paying fees charged at health facilities among others. These interventions have contributed towards increasing their resilience towards shocks and break the cycle of abuse.

In addition, the programme supported 398 GBV survivors (361 females, 37 males), and those at risk with enterprise start-up kits (working capital). The provision of start–up kits enabled beneficiaries to engage in businesses as espoused in their business development plans, increased incomes which have contributed towards achieving greater control over their lives and make decisions. The interventions contributed to breaking the cycle of abuse and violence at household and community level as evidenced during community dialogues where women and spoke freely about their experiences in the presence of men.

Further, to provide a comprehensive package of services, the same 398 beneficiaries above were also supported and strengthened by the programme in the formation of savings and credit groups. The capacity building on savings and credit groups provided opportunities for individuals in three main ways, namely: (i) Improving management of savings and credit groups; (ii) Promoting a culture of savings at individual and community level and (iii) Wealth creation at individual and community level. This has enhanced their ability to have financial and economic freedom thus removing the credit constraints that majority of women especially victims of GBV face in communities and districts. The women now have access to cash through their engagement in the savings and credit groups supported and formed by the project. Further the upcoming project assessment will address the impact of these savings and credit groups.

As a result of this capacity building in savings and credit (business management) a total of 42 savings and credit groups were formed during the reporting period leading to 516 GBV survivors and those at risk having increased access to credit and other economic empowerment services with an assurance of sustainability of their businesses.

Further, on increasing |ICT knowledge, the programme supported a total of 420 girls and women with ICT knowledge and online Gender Based Violence (OGBV) information. The programme, in partnership with the Zambia Information and Communication Technology Authority (ZICTA), conducted online GBV interventions in Chipata, Magwero for learners with disability, Petauke, and Lusaka.  ZICTA in partnership with Atsikana Network and She Entrepreneur facilitated a ToT on how to relay skills and knowledge on digital financial literacy, cyberbullying and digital footprint. This has led to a systematic mentorship programme for the girls. Further, this training has fostered linkages of girls and young women to other entrepreneurship and credit opportunities. Additionally, the training has led to increased awareness and self-efficacy among adolescent girls and women, who previously did not have access to ICT equipment and information.

Output 2.2 Community and traditional leadership structures have capacity to mobilise on GBV prevention

Traditional leaders are the custodian of culture, norms and are influential agents of change in communities. To ensure enhancement of traditional leadership engagement, the programme in collaboration with the Department of Chiefs and Traditional Affairs, Zambia National Men’s Network for Gender and Development, Zambia Cente for Communication programmes, Women for Change, and Young Happy Heathy and Safe sensitized a total of 2,120 (1,422 males, 698 females) traditional leaders on GBV and COVID-19 during the reporting period. The trainings took place in Chipangali, Chipata, Nalolo, Sesheke, Kabwe, Choma, Mumbwa, Chinsali, Itezhi-Tezhi and Chisamba districts. The sensitizations contributed to the adherence to COVID-19 guidelines and reduction in the spread of COVID-19 cases. Due to these sensitization campaigns communities were able to break the culture of silence in that women were able to discuss with their traditional leaders and their spouses’ issues of GBV, how to prevent and respond to the cases. Refer to ANNEX 4 below.

The community dialogues and engagements with women, girls, boys, and men in the communities, resulted in people challenging cultural norms that perpetuate a culture of violence against women and girls and encouraging early reporting of GBV cases. Refer to ANNEX 4.

Further, traditional leaders created referral links with religious leaders for counseling services to enable reintegration of survivors back to the communities from safe homes without fear of stigma and discrimination. The Women for Change and Zambia National Men’s Network working together with Zambia Police and Social Welfare, and traditional leaders retrieved 2 girls from child marriage in Rufunsa and Petauke districts.

The programme reached 1,708 (1,019 female, 689 males) spouses of traditional leaders on GBV and COVID19 during the reporting period. This led to community members speaking openly on GBV and its implications and how to prevent the vice. The awareness raising resulted in spouses of traditional leaders becoming change agents and advocates against GBV, child marriages and gender related violence. Nine women were included in decision making positions at community level for example at Misolo, Mumena, and Rufunsa anti-GBV and Community Development village led one stop centers. Capacity Development of 281 (181 males, 100 females) religious leaders with GBV and COVID-19 prevention and response information. In addition, the programme supported the capacity development of 120 (80 males, 40 females) political leaders with GBV and COVID-19 prevention and response information. As a result of this capacity development political leaders have added GBV as part of their messages in different constituencies of their districts, such as ward development committees.

Traditional leaders were also sensitized on GBV and COVID 19, because of these sensitizations, religious leaders mobilized communities to speak against GBV and sensitized community members on COVID19 prevention and response.

In addition, referral links have been established with other various service providers for continued counselling and follow up support such as social and economic empowerment for GBV survivors.

Following the 2021 General Elections, the programme engaged 45 members of Parliament on orientation and sustainability of the GRZ-UN JP on GBV interventions by linking the project interventions to Constituency Development Fund (CDF). Two Members of Parliament following this engagement provided furniture for the women community groups in Petauke and provided transport to pregnant women GBV survivors to health facilities for maternal and delivery services during the floods.

Further, the programme reached a total of 54,683 (33,684 females, 20,999 males) people with GBV/COVID-19 prevention and response messages due to participation in community structures The high reach resulted in broad dissemination of information on GBV and COVID 19 prevention and response services.

Going by the principle of Leave No One Behind, the programme also reached 528 (326 F and 202 M) Persons with Disabilities with knowledge on GBV prevention and response making them able to know what constitutes GBV and how and where to report GBV cases. These beneficiaries include learners with disability from the Magwero school of the blind and the deaf and Kabwe community.

Follow the link below for disability mainstreaming:

https://drive.google.com/drive/folders/1wP5scRcBz6ctJLCLOFGlcAzNbjRONc4S?usp=sharing

Output 2.3. Improved multi-sectoral coordination and governance related to GBV prevention and response

During the reporting period, the GRZ-UN JP GBV II programme implemented six (06) co-ordination mechanisms led by the Gender Division, aimed at enhancing coordination at national, provincial, district and community levels. Some of the co-ordination mechanisms included: half-yearly meetings with the programme implementing partners, GBV Technical Working Group (TWG) meetings led by the Gender Division and supported by the EU, Co-operating Partners on Gender Group, donors’ review meetings, UN and local implementing partners coordination meetings and the UN partner agency meetings. These efforts led to the Government working with various entities to jointly work on strengthening policies and guidelines such as the development of Gender Policy and its Implementation Plan.

In collaboration with other anti-GBV players including the European Union, World Bank and USAID, the programme supported the following polices and Guidelines:

- Minimum Standards Guidelines for operationalizing the VLOSC.

- Minimum Standards Guidelines for Anti-GBV Safe Shelters.

- The Guidance on Child Victims and Witnesses in Judicial Proceedings.

- The Guidance Note on case management for violence against children and GBV.

- Minimum Standards on the use of the GBV Funds.

- the Minimum Standards for One Stop Centers.

The above minimum standards will serve as a guide by providing appropriate operational procedures for service providers to provide quality anti-GBV services.

In addition, the project supported 13 districts to mainstream gender in their plans. This result was catalyzed by the presence of the Anti-GBV Task Force teams, Districts Gender Sub-Committees, and the high demand from districts for support on gender equality and gender mainstreaming.

The project continued providing support to GBV service delivery points through IMS (E-policing and DHIS2) being used to track GBV data.  The data capture has been completed by the police, Ministry of Health (MoH) and MCDSS. This process helped to manage the data for expedited processing or disposal of cases and for informed decision making.

The Gender Division continued to ensure an effective multisectoral response to GBV with programme support through ensuring the functionality of coordination mechanisms. The Division worked with the ten (10) Provincial Anti-GBV Task forces to strengthen the GBV Phase I established Provincial and District Anti-GBV Task Forces.

Through these coordination mechanisms, the Division continues to promote a harmonised and standardised response through ensuring compliance to Multi-sectoral GBV Guidelines developed in 2014 and referral guidelines developed in 2015. In this reporting period, the Gender Division commenced the review of the Terms of Reference for the Anti-GBV Task Forces.

At national level, the programme conducted the Third Project Steering Committee meeting on 27th May 2021. Among the decisions made at the meeting was the commitment by the Steering Committee to accelerate inclusion of Child Witnessing Guidelines in the Children’s Code Bill draft so that it can be part of the law and to approve the annual work plan and budget.

To enhance programme coordination, ten (10) joint review missions led by Government and UN agencies were conducted. In addition, best practices and areas of improvement were identified to be replicated. One recommendation was to replicate IEC material for Persons with Disability and to enhance engagement with them and allocate adequate funds to carter for this population. The cooperating partners and Civil Society Organisations were also part of these joint missions to Chipata, Chipangali, Lundazi, Choma, Itezhi-tezhi, Kalumbila, Petauke, Chisamba, Chinsali, and Ndola. Further, the programme conducted three joint review and planning meetings with implementing partners to review progress and identify bottlenecks and agree solutions. The review meetings also achieved the consolidation of the 2022 annual work plan and budget.

A donor review meeting led by Gender Division, consisting of members from the Embassies of Ireland and Sweden and the UN partner agencies, was conducted on 12 November 2021 to review progress on 2021 implementation and share ideas on acceleration of delivery. One recommendation from the donor review meeting was to conduct a Project Assessment instead of a full-blown mid-term evaluation. The programme will still conduct the end of Programme evaluation.

ANNEX 2                                       ANNEX 3                                  ANNEX 4

ANNEX 5

https://drive.google.com/drive/folders/1wP5scRcBz6ctJLCLOFGlcAzNbjRONc4S?usp=sharing

III) Evaluation, Best Practices and Lessons Learned

During the implementation period the Programme undertook a baseline and a Rapid Gender Assessment of the COVID-19 pandemic. The findings of the baseline supported the finalization of the M&E Framework, while the findings of the Rapid Gender Assessment contributed to the knowledge management of the effects of COVID-19 on gender and GBV.

The programme noted the use of Solar Power as energy for the community-based structures, savings and lending groups, involvement of other stakeholder such as church leaders in disseminating SGBV information, Male involvement in GBV programming as best practices. In addition, use of ICT for coordination meetings, data collection and online training were identified as promising and best practices.

Sustained engagement with high level government officials, Members of Parliament, traditional leaders, and spouses, has proved to be an effective tool about advocacy pertaining to legal and policy reforms as well as challenging the negative or harmful social and cultural gender norms.

Delivering As One - The Joint Programme has demonstrated the efficiency, effectiveness, and efficacy of the UN reform of Delivering as One as the five UN partner agencies have been able to leverage each other’s comparative advantage leading to optimal results in GBV prevention and response services.

Challenges Experienced with Project Implementation During 2021 and Mitigation Measures

The following table highlights the key challenges faced during the period under review:

| S/No | Challenge Description | Mitigation Measure |
| --- | --- | --- |
| 1 | Customary practices conflicting with anti-GBV messages. | To counter this challenge traditional leaders are being involved to deal with negative traditional practices such as initiation ceremonies for under-age girls and early marriages and allow engagement between traditional leaders and the judicial players to share ideas |
| 2 | Inadequate social service facilities and personnel especially in rural areas (police, health centres and formal courts) | the village led one stop centres and the trained customary adjudicators helped to address this. |
| 3 | Inadequate girls’ shelters to curb GBV/ Child Marriage. | Schools are being encouraged to provide safe boarding houses within school premises to girls coming from far places |
| 4 | Legal system protraction of cases leading to victims relocating to different places without a verdict | This is being addressed by the fast-track courts by reducing the duration of case disposal. |

Risks:

The programme envisioned that implementation delays may be experienced in the run up and post elections in 2021- After elections this risk ceased to exist. The programme has continued to observe the COVID-19 and corruption related risks while encouraging people to adhere to the 5 golden rules. (A full updated risk log for the Project during the implementing year is in Annex 6 below). The programme also provides Harmonized Approach to Cash Transfer (HACT) training to UN partner agency implementing partners. The HACT is one of the tools in the strategy that the UN has adopted to manage the risk at both programme and project level when working with Implementing Partners (IPs) and Responsible Parties (RPs).

ANNEX 6

Annex 7.0

IV) Qualitative assessment:

Overall, the Programme is on track in terms of implementation and achievements. The Programme experienced minor delays, largely due to compliance to guidelines and regulations pertaining to infrastructure development, including a new requirement of conducting the social environment and safeguard assessment, which were recently introduced by the UN family. The assessment needed to be conducted prior to the construction work could start.

Key sustained partnerships with various Government line ministries and civil society organisations has helped accelerate implementation and achievement of results. Timely feedback and input from co-operating partners on key documents and processes has enabled quality assurance in implementation, monitoring and reporting.

Further, the goodwill of traditional leaders, implementing partners and other stakeholders has also contributed to timely implementation of programme interventions.

In terms of cross-cutting issues and in keeping with the principle of Leaving No One Behind, the Programme has deliberately targeted Persons with Disabilities (PWD), migrants, refugees, and other vulnerable groups with information and GBV services. Additionally, in order to ensure inclusive service delivery, most capacity development interventions have included a component of the principle of Leaving No One Behind.

Programme staff have been participating in the national GBV Technical Working Groups led by the Gender Division. This has been effective in avoidance of duplication of interventions at national and sub-national levels.

Further, the Programme has benefitted from other co-ordination mechanisms such as the CP Group on Gender, UN Gender Theme Group and others, who have been supportive in terms of timely review of documents, reporting progress and other processes.

The Programme Steering Committee and UNCT have been instrumental in providing overall guidance and facilitating timely disbursement of funds for the smooth implementation of programme interventions.

| Results – Output Indictors | Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification |
| --- | --- | --- | --- |
| Output 1.1: Target districts have increased capacity to deliver co-ordinated GBV services. Output Indicator 1.1.1: # of hospital based OSC established Baseline: Baseline: 10 2021 Target: 0 Programme Target: 1 | 0 | Processes have commenced. Letter and BoQs have been completed and now in the process of selecting contractor |  |
| Output Indicator 1.1.2: # of hospital based OSC strengthened in the project districts Baseline: 0 2021 Target: 1 Programme Target: 3 | 5 | Lusaka, Mumbwa, Kabwe, Choma, and Ndola. MOH HQ provided supportive supervision and mentorship at facility level. | Project reports |
| Output Indicator 1.1.3 # of community structures conducting dialogues and info sessions on GBV services and prevention Baseline: 9 2021 Target: 10 Programme Target: 30 | 14 | Because of the reduced number of COVID-19 cases, GRZ/MOH had relaxed COVID-19 restrictions on community gatherings. Therefore, the community structures took advantage of this to reach more people. List the names of the community structures in the narrative. | Project reports |
| Output Indicator 1.1.4: # of OSCs which are made child friendly Baseline: 4 2021 Target: 2 Programme (2022) Target: 4 | 0 | Due to COVID-19, the delivery of child-friendly supplies was delayed. However, these have recently been delivered to the MoH for distribution to the four OSCs. | Project reports |
| Output Indicator 1.1.5: # of service providers trained on multi-disciplinary GBV Guidelines (disaggregated by type of service provider and sex). Baseline: 20 2021 Target: 300 130 paralegals 10 doctors 10 Nurses 10 Clinical officers 90 hospital based OSC staff, officers, 40 adjudicators 10 prosecutors Programme Target: 1,515 390 paralegals, 30 doctors, 30 Nurses, 30 clinical officers 270 hospital based OSC staff, officers, 120 adjudicators, 30 prosecutors, 615 Police officers | 293 service providers (160 Female: 133 Male): 60 paralegal officers 13 doctors 20 Clinical Officers 12 Nurses 83 VSU police officers; 19 prosecutors; 67 social welfare officers; 2 magistrates (child justice forum); 17 Shelter managers/NGOs/MCDSS/Youth & Sport | GRZ has new guidelines on affiliation of paralegals which has made the cost of training higher | Project Reports |
| Output Indicator 1.1.6: # of Minimum Standards and Guidelines developed for GBV service providers and facilities for operationalization of VLOSC Baseline: 0 Annual Target:1 Programme Target: 1 | 2 | Besides the minimum standards for VLOSC and Shelters, the Project also supported the MCDSS to finalise the minimum norms and standards for GBV and human trafficking that sets out appropriate operational procedures for quality GBV service provision. | Project reports |
| Output Indicator 1.1.7: # of Community Response Mechanisms (VLOSC) Established Baseline: 10 2021 Target: 3 Programme Target: 9 | 3 | Three (3) VLOSCs completed in 2021: Chief Chamuka VLOSC – Chisamba district. Chief Mwase VLOSC- Lundazi district. Chief Mumena VLOSC - Kalumbila district | Project reports, handover ceremony photos |
| Output Indicator 1.1.8: # of people accessing services at the Community Response Mechanisms (VLOSC) disaggregated by sex. Baseline: 113 2021 Target: 110 Programme Target: 600 | 311 (191 females, 120 males) | There was high demand for services due to the newly launched 2 VLOSC in Chisamba and Kalumbila and engagement by traditional leaders which has led to increased community mobilization. | Registers |
| Output 1.2: GBV Survivors have increased access to Safe Shelters Output Indicator 1.2.1: # of survivors that benefit from specialized services at the GBV shelters disaggregated by sex. Baseline: 1676 2021 Target: 141 Programme Target: 380 | 627 (527 females, 100 males) | This was due to increased awareness of the shelters and collaboration with other stakeholders, resulting increased referrals to the safe shelters. | Registers |
| Output Indicator 1.2.2: # of Anti-GBV shelters established for temporary housing of GBV survivors Baseline: 1 2021 Target: 1 Programme Target: 4 | 2 | Mumbwa and Lundazi established. To be launched in Quarter 2 of 2022. | Activity reports Field reports |
| Output Indicator 1.2.3: # of shelters strengthened for temporary housing of GBV survivors Baseline: 0 2021 Target: 4 Programme Target: 9 | 8 | These are the Kitwe, Chipata YWCA, Chipata Place of Safety, Mongu, Kaoma, Kabwe, Lusaka Children’s, Solwezi and Lusaka adults’ shelters. | Field visit reports Activity reports |
| Output Indicator 1.2.4: # of child GBV survivors supported to access alternative care options through case management disaggregated by sex. Baseline: 348 2021 Target: 91 Programme Target: 229 | 179 | child survivors were provided with GBV services to access alternative care through the case management systems. | MCDSS case management data |
| Output 1.3: Target districts have increased capacity to deliver quality legal services Output Indicator 1.3.1: # of Fast Track Courts established Baseline:6 2021 Target: 0 Programme Target: 4 | 0 | Based on the requirements in the 2021 UN Revised procurement and construction guidelines for quality assurance, due diligence procedures were undertaken including conducting of socio-environmental safeguard assessments; completion of BoQs for the FTCs; For quality assurance and to accelerate delivery, Project engineers for the construction have now been recruited. |  |
| Output Indicator 1.3.2: % of FTC that are operating in line with child friendly standards Baseline: 0 2021 Target: 60 % Programme Target: 100 % | 0 | Although the witness room provides for a conducive atmosphere for child witnessing, the programme is to fully equip the facilities to make them child friendly. Due to disruption in the global supply chain arising from the COVID-19 pandemic, the delivery of child-friendly supplies was delayed. However, these have recently been delivered to Judiciary for distribution to the FTCs. | Court records |
| Output Indicator 1.3.3: # of legal service providers trained Baseline: 9,292 2021 Target: 115 50 paralegals 20 prosecutors 25 adjudicators 20 social welfare officers Programme Target: 320 | 538 legal services providers trained. 10 paralegals 426 Prosecutors, 40 Adjudicators, 2 Social Welfare Officers 60 Best Interest Determination Panel Members | The use of virtual means enabled an increased outreach. | Training reports |
| Output Indicator 1.3.4: # of GBV survivors provided with legal services. Baseline: 1,200 2021 Target: 1,500 Programme Target: 4,000 | 611 clients (women 79; children 532). | This intervention will be accelerated in 2022 | Court Records |
| Output Indicator 2.1.1: # of GBV survivors and those at risk capacitated in business development disaggregated by sex. Baseline: 4500 2021 Target: 350 Programme Target: 500 | 516 (361 females, 37 males) | Increased demand for economic empowerment knowledge by GBV survivors due to robust sensitisation campaigns at community level. | Training Reports Attendance Registers |
| Output Indicator 2.1.2: # of GBV survivors and those at risk provided with enterprise (Income Generation Activities) start-up support disaggregated by sex. Baseline: 2446 2021 Target: 300 Programme Target 500 | 398 (361 females, 37 males) | Increased demand for economic empowerment knowledge by GBV survivors due to robust sensitisation campaigns at community level and provision of training and other capacity development activities. | Disbursement sheets monitoring reports |
| Indicator 2.1.3: # of GBV survivors and those at risk engaged in saving and credit groups disaggregated by sex. Baseline: 0 2021 Target: 350 Programme Target: 500 | 398 ((361 females, 37 males) | Increased demand for economic empowerment knowledge by GBV survivors due to robust sensitisation campaigns at community level and provision of training and other capacity development activities. | Attendance registers Training reports |
| Indicator 2.1.4: # of saving and credit groups supported to improve enterprises (Income Generating Activities) Baseline: 0 2021 Target: 20 Programme Target: 33 | 42 | Increased demand by existing savings groups for support and strengthening | Training reports List of Members for a Savings Groups Attendance list |
| Indicator 2.1.5: # of ICT Hubs established Baseline: 0 2021 Target: 0 Programme Target: 3 | 0 | Progress has been made towards establishing the ICT hubs such as identification of sites, procurement of furniture and equipment |  |
| Indicator 2.1.6: # of women and girls capacitated with ICT knowledge Baseline: 200 2021 Target: 200 Programme Target: 600 | 420 | The use of virtual platforms for capacity building contributed to increased number of participants | Activity reports Attendance lists |
| Output 2.2 Community and traditional leadership structures have capacity to mobilise on GBV prevention Output Indicator 2.2.1: # of traditional leaders sensitized on GBV and COVID-19 disaggregated by sex. Baseline: 0 2021 Target: 1,500 Programme Target: 4,213 | 2,120 (1422 males, 698 females) | Engagement with traditional leaders at chiefdom level contributed to increased reach which included others such as sub-chiefs, headpersons, and indunas | Attendance lists Activity reports |
| Output Indicator 2.2.2 # of spouses of traditional leaders’ sensitized on GBV and COVID-19 disaggregated by sex. Baseline: 30 2021 Target: 500 Programme Target 1,500 | 1,708 (1,019 females, 689 males) | Engagement with chiefs’ spouses at chiefdom level was cost-effective and contributed to increased reach. | Attendance lists Activity reports |
| Output Indicator 2.2.3 # of religious leaders sensitized on GBV and COVID-19 disaggregated by sex. Baseline: 40 2021 Target: 150 Programme Target: 350 | 281 (181 males, 100 females) | More demand for information by religious leaders contributed to increased reach. | Attendance lists Activity reports |
| Output Indicator 2.2.4 # of political leaders sensitized on GBV and COVID-19 disaggregated by sex. Baseline: 0 2021 Target: 60 Programme Target: 120 | 120 (Male:80 Females:40) | The Project leveraged the orientation programmes of the new office bearers and their willingness to receive more information | Attendance lists Activity reports |
| Output Indicator 2.2.5: # of people participating in community structures reached with GBV/COVID-19 prevention and response messages disaggregated by sex. Baseline: 0 2021 Target: 4,000 Programme Target: 10,000 | 54,683 (33,684 females, 20,999 males) | Intensified implementation using physical meetings as well as Radio, TV and virtual platforms used, such as Zoom and Microsoft Teams contributed to the increased reach | Attendance lists Activity reports |
| Output Indicator 2.2.6 # of community structures mobilized to challenge norms and cultural practices that sanction and perpetuate GBV and the low status of women and persons with disability. Baseline: 0 2021 Target: 10 Programme Target: 30 | 14 | There were more than 10 structures in the communities in need of capacity development to address negative cultural practices and norms. |  |
| Output 2.3. Improved multi-sectoral coordination and governance related to GBV prevention and response Output Indicator 2.3.1: # of district plans mainstreaming GBV. Baseline: 33 2021 Target: 8 Programme Target: 18 | 13 | This was due to presence of the Anti-GBV Task Force teams and the Districts Gender Sub-Committees and demand from districts for support on gender equality and gender mainstreaming | Activity reports |
| Output Indicator 2.3.2: # of policies/legal instruments/guidelines finalized Baseline: 0 2021 Target: 3 Programme Target: 9 | 6 | We leveraged other processes which had started prior to ensure that other policy documents were finalised | Programme implementation partner reports NPA and MCDSS data. |
| Output Indicator 2.3.3: # of service delivery points tracking GBV data on an MIS. Baseline: 1 2021 Target: 2 Programme Target: 6 | 2 |  |  |
| Output Indicator 2.3.4: # of Steering Committee meetings held Baseline: 0 2021 Target: 3 Programme Target: 6 | 1 | Could not hold other Project Steering Committees due to transition in government following the August 2021 general elections. | Attendance List |
| Output Indicator 2.3.5 # of Joint monitoring missions Baseline: 0 2021 Target: 4 Programme Target: 12 | 10 | More joint monitoring visits were undertaken during the time when there was a reduction in the COVID-19 cases | Mission reports Activity reports |
| Output Indicator 2.3.6 # of Joint planning and review meetings held Baseline: 0 2021 Target: 2 Programme Target: 6 | 3 | There was need for consolidation of annual targets and results and orientation of the IPs and UN partners agencies on the finalized Results Monitoring and Evaluation Framework. | Attendance Lists Minutes |

VI) A Specific Story (Optional)

Problem / Challenge faced:

Ms. Banda, a mother of two, got married in 2008. She is a victim of GBV, as the former husband was abusive. Ms. Banda narrates that her former husband used to abuse her physically by beating her and was not providing any support at home.

“In 2010, my husband even married another woman. After going through a lot of abuse, I decided to leave him and went to stay with my uncle in 2011 when I even fell pregnant,” she relates. Ms. Banda adds that she reported her former husband to the Victim Support Unit (VSU) of the Zambia Police about the GBV she was going through.

She explains that the police officers counselled the couple and the former husband promised to change, but he did not. Ms. Banda says she did not have enough capital to do a viable business rather only had money to buy the hair blower. “I was blowing people’s hair at home and was only able to manage to make K200 monthly. The money was not enough to take care of my children. Problems continued to an extent where the first-born child was taken to be kept by my uncle because the husband could not provide for the children,” She narrates.

Programme Interventions:

Economic empowerment.  Ms. Banda was trained by the Project through the programme in December 2020 in Enterprise skills (GET Ahead and Community Savings Groups) and subsequently empowered with a start-up kit of ZMW 2,000.00 Kwacha ($117.99 USD) in May 2021.

Upon being identified by the team leaders on the ground, she was included on the empowerment programme, a move which greatly transformed her life. Ms. Banda explains that after receiving ZMW 2,000.00 ($117.99 USD), she started a poultry business with 5-day old chicks in June 2021.

.

Result (if applicable):

She adds that after she raised the capital to ZMW 5,000.00 ($294.98 USD), she bought 100 chicks and the capital was raised to ZMW9,000.00 ($530.97 USD) in August 2021. “I bought 200 chickens in September 2021, and I have started selling. I am expecting to make ZMW18,000.00 Kwacha ($1,061.95 USD) from sales. I have been able to expand my business and pay school fees for my children,” She explains.

Ms. Banda relates that she is currently renting a poultry house and she plans to build her own poultry house from the profits.

Lessons Learned:

That economic empowerment can break the cycle of abuse. She explains that the empowerment fund she received has changed her standard of living as she has now become independent of her abusive spouse and broken the vulnerability to GBV.

See photos in ANNEX 4

ANNEX 6 – Video on Mainstreaming disability

https://drive.google.com/drive/folders/1wP5scRcBz6ctJLCLOFGlcAzNbjRONc4S?usp=sharing

VII) Other Assessments or Evaluations (if applicable).

During the reporting period, the programme supported preparation of a policy brief on the Impact of COVID-19 on GBV. One of the summaries of the findings and recommendations on school closures arising from COVID-19 (ZCCP Annual Report 2021) is that the study showed that extended closures of learning institutions impacted gender-based violence among adolescents. Because students and pupils were kept away from busy schedules and tight school rules particularly for those in boarding facilities, young people got exposed to would-be perpetrators. The girls were exposed to sexual abuse and teenage pregnancies while some simply strayed during daytime and engaged in illicit sexual activities. Others especially in rural areas were reported to go further and entered early marriages, as reported by some traditional chiefs.

VIII) Programmatic Revisions (if applicable) Not Applicable

IX)  Resources (Optional) Not Applicable

# Footnotes

The term “programme” is used for programmes, joint programmes and projects.

As per the JP team,  the donors agreed that the start date would be 4 December 2019

Because of the reduced number of COVID-19 cases, GRZ/MOH had relaxed COVID-19 restrictions on community gatherings. Therefore, the community structures took advantage of this to reach more people.

Refer to ANNEX 7 of list of local implementing partners of the GRZ-UN Joint Programme on GBV Phase II

Capacity Development includes the following activities - staff multi-disciplinary training, on-site mentorship, provision of COVID-19 PPEs, development of guidelines, co-ordination meetings, provision of office accessories

Community structures (Formal and informal) consist of Community Welfare Assistance Committees (CWACs), Neighborhood Health Committee (NHCs), Safe Motherhood Action Groups (SMAGs), Community Crime Prevention Units (CCPU), Ward Development Committees (WDCs), Men’s/Boys Network, GBV/SEA monitors, Anti-GBV Task Forces, Community Child Protection (CCPs), Area Associations, Women’s Clubs, Disabled Persons Organizations (DPOs), Community Based Organization (CBOs), Traditional Counsellors and Multi-Functional Task Teams.

Strengthening may include one or two of the following: capacity development activities such as staff multi-disciplinary training, on-site mentorship, provision of COVID-19 PPEs, development of guidelines, co-ordination meetings, provision of office accessories

Community structures consist of Community Welfare Assistance Committees (CWACs), Neighborhood Health Committees (HHCs), Safe Motherhood Action Groups (SMAGs), Community Crime Prevention Units, Ward Development Committees (WDC), Men’s/Boys Network, GBV/SEA monitors, Anti-GBV Task Forces, Community Child Protection (CCPs), Area Associations, Women’s Clubs, Village Development Committees and Religious Committees, Youth Friendly Corners.

Child-friendliness in this context means availability of the following: trained and specialized staff working with children (mandatory), child-friendly designated rooms/space and child-friendly equipment, furniture, and toys, talking walls/child-friendly messages and guidelines on how to work with children (any one of these).

Services to be accessed at the VLOSC include Legal information, psycho-social counselling, and basic health services.

Specialized services provided at the GBV shelters include housing, mental health, psycho-social support, referrals to other services etc.

Lundazi (IOM), Chinsali (IOM), Kalumbila (IOM), Mumbwa (YWCA) and Choma (UNDP)

Strengthening of the Anti-GBV Shelters includes two or more of the following services or interventions: construction/refurbishment of the physical infrastructure, provision of office accessories, provision of shelter supplies, capacity development, including providing training in business skills. Kitwe (YWCA), Chipata (02-YWCA), Lusaka (02-YWCA), Mongu (YWCA), Kaoma (YWCA), Chongwe (YWCA), Nakonde (YWCA) and Mansa (YWCA).  Chinsali (IOM), Chililabombwe (YWCA), Kalumbila (UNDP), Mongu/Senanga (YWCA), Mazabuka (YWCA), Choma (UNDP/UNFPA), Itezhi Tezhi (UNDP/UNFA), Lundazi (IOM) and Mumbwa (YWCA).

Alternative care options include kinship care, foster care, community-based care (including child-headed households), residential and independent or group living. Partners will also capture data on children who have been reintegrated with their birth family.

Training will mean capacity strengthening in the following: Multi-disciplinary Management of GBV, GBV Case Management, Best Interest Determination for Vulnerable Migrant Children, Human Rights and gender, handling of child Victims, TEVET paralegal training and witnesses and operationalization of VLOSCs.

Start Up support refers to financial/ material resources.

Chiefs, headmen, group leaders and sub chiefs.

Chiefs, headmen, group leaders and sub chiefs.

Definition political leaders confined to civic leaders Councillors, Mayors, MPs.

Community structures (Formal and informal) consist of Community Welfare Assistance Committees (CWACs), Neighborhood Health Committee (NHCs), Safe Motherhood Action Groups (SMAGs), Community Crime Prevention Units (CCPU), Ward Development Committees (WDCs), Men’s/Boys Network, GBV/SEA monitors, Anti-GBV Task Forces, Community Child Protection (CCPs), Area Associations, Women’s Clubs, Disabled Persons Organizations (DPOs), Community Based Organization (CBOs), Traditional Counsellors and Multi-Functional Task Teams.

Community structures consist of Community Welfare Assistance Committees (CWACs), Neighborhood Health Committee (HHC), Safe Motherhood Action Groups (SMAGs), Community Crime Prevention Units, Ward Development Committees (WDC), Men’s/Boys Network, GBV/SEA monitors, Anti-GBV Task Forces, Community Child Protection (CCPs), Area Associations, Women’s Clubs

Gender mainstreaming GBV will entail planning and budgeting for anti GBV interventions in the district development plan/Investment Framework.

The policies, legal instruments and guidelines include: 1. Anti-GBV Act, 2. Minimum Standards and Operations for Shelters, 3. Guidelines for operationalization of the GBV Fund, 4. Minimum Standards and Operations for VLOSC, 5. ZP-VSU GBV Training Modules, 6. Prosecutors Handbook 7. Community Savings Groups Manual 8. Guidelines on the Protection of Child Victims and Witnesses 9. Gender Bench Book

Service delivery points relate to places where survivors get services, such as ZP-VSU, Courts, VLOSC, Health facilities, NGOs, OSC etc.

# Text boxes

V) Indicator Based Performance Assessment: