## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to the secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality results reports please follow the next guidelines: a) The narratives should be a well written, succinct summary clarifying what was done during the reporting period and the results achieved. It should highlight the JP achievements. It should also specify scope and beneficiaries. b) Factual, evidence-based reporting against the outcome and output and corresponding indicators in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not should be provided. d) Factual, evidence-based reporting against the outcome results and its alignment with the overall SERP joint workplan, and linkage to reporting on global-level SERP indicators. e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not. g) Reflect on innovation. Avoid generic and standard descriptions. Rather, present well documented features of successful innovative solutions truly new for you and which could enable replication efforts.
3 | Please fill out all sections of the reporting template before submitting to the secretariat via email to: nina.andersen@undp.org and cc.: maria.herrera@undp.org
B
DEADLINE: MARCH 31 ST, 2022
1 | ALL projects receiving funds in late 2020 and in 2021 must complete an ANNUAL report as per the end of the calendar year with a reporting period : date of start until 31 December 2021.
2 | The joint programmes which completed their activities in 2021 should deliver a FINAL report by March 31 at the latest and will not be obligated to provide an annual report.
3 | The joint programmes completing activities in 2022 will be asked to submit a FINAL report (by 31 August 2022)
4 | ALL projects must report number of direct beneficiaries.
5 | ALL projects must provide an update on project indicators

## General Information
Programme Title & Project Number |  | Programme Duration
Programme Title: | Integrated social protection scheme to mitigate impacts of COVID-19 and increase most vulnerable households' resilience | Overall Duration (months) | 7 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 01.08.2021
MPTF Office Project Reference Number: | SM210505 | Original End Date (dd.mm.yyyy) | 01.04.2022
Country | Haiti | In case of NCE Current End date(dd.mm.yyyy) | 01.05.2022
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNICEF/FAO | National counterparts (government, private, NGOs & others) and other International Organizations | Ministry of Social Affairs and Labor (MAST in french), CARE International
Report Cleared By
o Name: | Fausta Baptiste
o Title: | Partnership and Development Finance (RCO)
o Email address: | fausta.baptiste@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19 (up to 500 words). | The MPTF funds were allocated in July 2021 to FAO and UNICEF, shortly before the earthquake and Tropical Storm Grace of August 14-16, 2021 that hit the department of Grand’Anse targeted by the MPTF project. Therefore, these disasters redirected programmatic efforts towards humanitarian response. The project adapted its targeting to prioritize most affected municipalities, i.e. Pestel (including Cayemites Islands) and Corail, following impact assessments reports (Departmental directorate of Civil Protection situation report #10, 25-08-2021; CARE Haiti Multi-Sector Rapid Needs Assessment). Households in these municipalities are dependent of agricultural activities to meet their basic needs and those of their children. In addition to the remaining adverse effects of COVID-19 mitigation measures in 2020, the disasters further reduced the poorest households’ ability to cover their basic needs and increased the likelihood of relying on negative coping strategies likely to affect women and children. Reorientation and budget revision: Backyard livestock has been considered both of higher value than cash transfers in the context, and culturally well accepted. This animal restocking activity complements the cash transfer component by UNICEF. A budget revision request was consequently submitted and granted in November 2021. Procurement process: The procurement plan with technical specifications was prepared including livestock, seeds and agriculture tools. Competitive bid solicitations were launched in 2021 for most items targeting the main agricultural season (starting in March 2022). Situation monitoring: After the disasters, it was necessary to conduct a household survey to ensure proper monitoring of the state of food security in the affected areas. Selection of beneficiaries: For nutrition interventions beneficiaries were defined based on municipalities’ total population to which the proportion of each of the selected target populations was applied. For acute malnutrition targets (20% of the population in a situation of moderate and severe acute malnutrition), the prevalence and corresponding incidence of each indicator were used. The selection of beneficiaries of the emergency cash and in-kind transfers (livestock) was based on SIMAST data, built on the National Index of Deprivation and Vulnerability adjusted to the impact of the earthquake. Validation of lists: UNICEF and CARE used SIMAST to select beneficiaries using the categorical targeting method (ex: women and/or adolescent headed vulnerable households with at least one child under 59 months, etc.) and community validation consultations of the final lists. Finalization of the lists and transmission to the Financial Service Provider: The 1,000 households list was finalized and sent to Digicel to activate the first payments. Many inconsistencies delayed the payments, and another layer of verification was necessary. Internal implementation of a beneficiary database management system and M&E: A social mobilization and communication for behavior change strategy sought to ensure cash transfers’ effective use for the program’s purpose. A sample of households are being monitored to estimate the use of cash for food diversification and access to health services. Strengthening links with regular programming and accountability: Most vulnerable groups (prioritizing women and children, including with disabilities) were targeted to complement basic food aid in coordination with WFP, leveraging on SIMAST.
2 | Purpose | Please describe the project general objective specifying its link to COVID-19 response. | In response to a shock-responsive social protection joint proposal submitted by FAO, UNICEF and WFP to the Secretariat of MPTF entitled “Integrated social protection scheme to mitigate impacts of COVID-19 and increase most vulnerable households' resilience, UNICEF and FAO received an amount of $410,400 out of $855,232 to implement a pilot project in Grande'Anse.
3 | Results: Outcome Level | Please include narratives describing the main project achievements against the project's overall goal (up to 300 words) | Provision of multi-sector cash transfers to support access to health, education, protection, nutrition and sanitation services, as well as essential non-food items, through referrals and messaging. Engage community associations in the design, monitoring/feedback and communication around cash transfers, including the provision of PSEA training at the community level and promoting the participation of women as main beneficiaries
3.1 | Results: Output Level | Please include narratives describing the main annual/ final results of each output included in the project document (up to 200 words) | • 956 vulnerable households affected by shocks received the first transfer. Full wallet holders received the 15,000 HTG but the mini ones received 9,000 HTG (7 failed, they had a balance on their account). • 3,000 families were sensitized on the promotion of sensitivity to the needs and rights of children. • At least 3,000 pregnant and lactating women are benefitting from the messages and supervision activities of the established and functional PCNBs across the target communes of the project. • Members of clubs for parents and/or pregnant/breastfeeding women and parents of malnourished children in the project area are sensitized on the importance of breastfeeding and culinary techniques based on products (nutrients) local. • 50 ASCPs, at the rate of 10 per target municipality, were trained and equipped with tools/work guides on IYCF and CMAM, and animation and management of PCNB.
3.2 | Results: Gender | Please include project Gender results and its linkage with COVID- 19 response. If applicable, refer to the project's gender equality marker and any impacts they may have had on programming quality and results (up to 150 words). | • The transfers are intended for the caregivers (biological parent or legal guardian), who are mostly women. These allowances are supposed to accompany the beneficiary children, may change if the latter change households. • The cash is not conditional but becomes an incentive that can help create demand from households for the accumulation of human capital linked to child nutrition. To this end, aligning with the Cash Plus approach, all beneficiary households of the cash transfer component will benefit from awareness sessions on good nutritional practices (ANJE and AEN, food diversification) to strengthen the impact of the 'intervention through a gendrer-responsive approach.
3.3 | Results: Direct Beneficiaries | Please include total number of DIRECT BENEFICIARIES disaggregated by gender, age , location (rural, urban, any other location). Please avoid duplicating beneficiaries ensuring the dissagregated data adds to the total presented. | TOTAL: 956 mothers and caregivers received cash transfers. 3,000 pregant and lactations women, 50 ASCPs for capacities building, 5,000 households were sentitized
3.4 | Results: Indirect Beneficiaries | Please include total number of INDIRECT BENEFICIARIES. Please clarify if these are estimated and/or verified. If possible, disaggregate beneficiries by gender. | TOTAL: 3,500 children, 5,000 households members
3.5 | Do not Harm | Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention. ( up to 100 words) | Use of SIMAST list and community revisions of beneficiary list is an effective approach to avoid exacerbation of inequalities and vulnerabilities
3.6 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken to achieve the expected results) Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms(use up to 150 words). | Mainly due to events that happened the last 8 months (assassination of the President, political turmoil, gang’s expansion, earthquake, scarcity of fuel and its impacts in all activities sectors, etc …) the project was delayed as operations were all directed to respond to the earthquake. The main challenges faced during this reporting period are mainly related to delays in (i) procurements of goods and services due to limited road access caused insecurity across the country, resulting in shortage and unavailability of goods and services, and (i) delays in the project start up due to limited availability of key partners including local leaders and official of the departmental level health directorate and civil protection directorate. More specifically, the project start up has been severally affected by delays in the verification and confirmation of the beneficiary lists due to internal administrative challenges.
3.7 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) (up to 250 words) | • The link between sensitive activities at the level of supply and specific activities at the level of demand for nutrition will allow the reinforcement of the referral and counter-referral system given that the health services receive downstream cases who are already malnourished and sometimes advanced. • This pilot integration model will serve as a lever for a well-targeted communication package to strengthen community penetration with well-defined objectives in terms of awareness-raising (abandonments, community child protection mechanisms, identification, referral and counter-referral in nutrition, adoption of EFPs, etc.) is analyzed. • The support strategy for adolescent girls in schools with an integrated package (eg SBCC, nutrition, WASH, SRH, etc.) will be strengthened in order to harmonize interventions for better synergy of action. • The areas of collaboration within the framework of the implementation of the PNPPS / Social Protection Programs and accompanying measures (health, nutrition, education) within the framework of the pilot project of Grand'Anse (PSARA) with a PLUS of UNICEF are analysed. The system that will be put in place is based on the recognition of children's rights to nutrition and food security and therefore targets children regardless of household arrangements, in practice the presence of an adult is required to request and receive assistance.
3.8 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 250 words) | This project is an opportunity to experience joint work between FAO and UNICEF in collaboration with the Adaptive Social Protection for Increased Resilience (PSARA) project which will be implemented jointly by MAST and WFP in the coming days in the same department. • IDETTE: psychosocial support and accompaniment and protection of children aged 3-17 accompanied by breastfeeding mothers who attend PNCBs (nutrition advice for babies) • TOYA Foundation: psychotherapeutic and/or psychosocial support for breastfeeding women who attend PNCBs and who have trauma crises caused by the negative impacts of the earthquake of August 14, 2021 • CARE • Integration opportunity and synergy with the project “Emergency Response in Child Protection in Grande Anse • CARE is responsible for the continuous monitoring of the implementation process in the field by supporting activities related to enrollment on the Mon Cash platform (creation of a Mon Cash account) and will also report to UNICEF any complaints (non-receipt assistance) and complaints from targeted teachers.
3.9 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken (up to 200 words). | Mechanism for complaints, claims and feedback/resolution: In order to strengthen transparency and accountability vis-à-vis the affected populations, a suitable mechanism for complaints, claims and feedback will be put in place to allow beneficiaries to raise their grievances and concerns in complete confidentiality. This mechanism will allow beneficiaries who have not received assistance to report it so that their cases can be dealt with expeditiously. Complaints related to potential abuse of power, fraud & corruption and GBV will be handled in accordance with the partner's internal procedures and in transparency with UNICEF. Monitoring & Evaluation Mechanism: In order to improve the quality of implementation and draw lessons for scaling up, a monitoring & evaluation plan will be developed, which will take into account all the components of the intervention. Verification survey: In addition, a payment verification survey will be conducted with a representative sample of beneficiaries after each distribution cycle, using the most appropriate communication channels. The information generated will inform the project implementation process especially the financial reconciliation.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place (Up to 100 words). | Challenges encountered in the implementation of the project within the 8-month timeframe. However, and despite efforts to speed up activities including adjusting activities through a budget revision, as per mid-March 2022, 75% of planned activities are ongoing and yet to be completed. Ongoing activities that might not be finalized by 31 March 2022 include cash and in-kind transfers for households. A 1 month extension was granted.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | Nutrition and child protection activities included from UNICEF regular ressources: • Support the referral mechanism to and from cash assistance to essential services, with a focus on access to health services, education (schools and temporary learning spaces) and support psychosocial. • Promotion of health, nutrition, care and hygiene practices, including the use of services, through training and sensitization of community members.

## Project Indicators
Please include ALL indicators in the project document. Include the indicators and Baseline, Planned Target and Actuals for both OUTCOME and OUTPUT levels. "Actuals" refer to the total figures achieved for each indicator. Include separate actuals for 2021 and for 2022 (if applicable). Explain if targets were not achieved. Include means of verification. Use as many outputs cells as needed to present all project indicators.
| INDICATORS DESCRIPTION AND DATA | DATA: ACTUALS 2021 | DATA: ACTUALS 2022 (if applicable) | TOTAL actuals (agreggated 2021 and 2022 if applicable ) | Reasons for Variance with Planned Target (if any) | Source of Verification
pilot integrated social protection scheme mitigates the socioeconomic impacts of COVID-19 and increase most vulnerable households' resilience to shocks, in Grand'Anse, contributing to the implementation of the PNPPS at national level
Indicator:
Baseline:
Planned Target:
Output 1. Institutionalization and implementation of PNPPS by the Ministry of Social Affairs and Labor (MAST) in Grand'Anse
Indicator 1.1: | Existence of a budgeted PNPPS departmental action plan under the patronage of the Social Protection Sectoral Table is available
Baseline: | no
Planned Target: | yes | 0 | to be confirmed by end of project
Indicator 1.2: | Existence of a Departmental Sectoral Table of the PNPPS set with a functional coordination mechanism
Baseline: | no
Planned Target: | yes | 0 | to be confirmed by end of project
Indicator 1.3: | Existence of concrete governance mechanism at national and departemental level (Grand'Anse) of the MAST that are leverage to strengthen , regulate, coordinate, and manage social protection initiatives
Baseline: | no
Planned Target: | yes | 0 | to be confirmed by end of project
Indicator 1.4 | Existence of a comprehensive framework for the financing of the PNPPS National plan and the Grand'Anse plan
Baseline: | no
Planned Target: | yes | 0 | to be confirmed by end of project
Indicator 1.5 | Existence of a complete targeting of vulnerable households (desegregated by sex) in Grand'Anse through the updated information system (SIMAST )
Baseline: | no
Planned Target: | yes | 0 | to be confirmed by end of project
Output 2 Support the development of a budgeted PNPPS departmental action plan in Grand'Anse under the patronage of the Social Protection Departmental Sectoral Table
Indicator 2.1 | % of male and female households practicing improved agricultural technologies
Baseline: | 0%
Planned Target: | 40% of beneficiaries | 0 | to be confirmed by end of project
Indicator 2.2: | # of women that received equipment and training for small gardening and livestock |  |  |  | After the budget revision and the decision to distribute goats, it has been agreed for vulnerable household to receive 2 goats each. With the budget available, 387 households are now targeted. | Distribution lists
Baseline: | 0
Planned Target: | 400 | 0 | 387 | 387
Indicator 2.3 | # of households that sensitized on good food utilization practices
Baseline: | 0 | 0
Planned Target: | 2000 |  | to be confirmed by end of project
Indicator 2.4 | % of women operating viable income generating activity
Baseline: | 0
Planned Target: | 50 | 0 | to be confirmed by end of project
Output 3 Strengthen MAST at central level and Grand'Anse department levels, to regulate, coordinate and manage social protection initiatives through improved governance
Indicator 3.1 | Number of youth organizations participating in planning and monitoring processes
Baseline: | 0
Planned Target: | 30 | 0 | to be confirmed by end of project
Indicator 3.2: | Number of community- based organizations participating in coordination mechanism for the child sensitive social protection programme |  |  |  |  | Project implementation report
Baseline: | 0
Planned Target: | 10 | 0 | to be confirmed by end of project
Indicator 3.3 | Number of children 6-23 months. that received MNPs |  | No data yet
Baseline: | 0
Planned Target: | 8000 | 0 | to be confirmed by end of project
Indicator 3.4 | Number of children 6-23 months screened at community level and referred to health facilities | 0 | 2870
Baseline: | 0 | 0 | 0
Planned Target: | 50000 | 7019 | 7019
Indicator 3.5 | Number of community members sensitized on nutrition- sensitive interventions (infant-young child feeding practices). | 0 | 1991
Baseline: | 0 | 0 | 0
Planned Target: | 200 | 4883 | 4883
Indicator 3.6 | Number of members of communal coordination mechanism for social protection trained in child sensitive social protection in the targeted municipalities
Baseline: | 0
Planned Target: | 20 | 0 | to be confirmed by end of project
Indicator 3.7 | # of children with increase children's school participation (school enrolment and regular school attendance)
Baseline: | 0
Planned Target: | 3000 | 0 | to be confirmed by end of project
Indicator 3.8 | Number of Outreach and communication (C4D) implemented towards behavioural change
Baseline: | 0
Planned Target: | 10 | 0 | to be confirmed by end of project
Indicator 3.9 | %of Women, men, girls and boys who participated in Gender based violence prevention and response
Baseline: | n/a
Planned Target: | 90% | 0 | to be confirmed by end of project
Output 4 The project is monitored and evaluated in all its components
Indicator 4.1 | Existence of a systematic tracking of activities for effective targeting, allocation and use of tools and equipment provided to beneficiaries is ensured
Baseline: | no
Planned Target: | yes |  | to be confirmed by end of project
Indicator 4.2: | Existence of a results-based monitoring matrix where each result (output and outcome) is assigned with specific indicators with baseline and targets and means of verification is finalised at the inception phase
Baseline: | no
Planned Target: | yes |  | to be confirmed by end of project
Indicator 4.3: | # of monthly activities reports finalized and shared
Baseline: | 0
Planned Target: | 6 | 0 | to be confirmed by end of project
Indicator 4.4 | Number of joint monitoring visits organised
Baseline: | 0
Planned Target: | 1 | 0 | to be confirmed by end of project

## Communication
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant.
The mother-to-mother clubs supported by the project are spaces aimed at bringing parents together around infant and child health issues, with a focus on nutrition behavior change. The project used established spaces to conduct messaging on breastfeeding, and prevention of malnutrition amongst pregnant and lactating women, and children under the age of 5, sanitation and covid-19 prevention. The mother-to-mother spaces are used as venue for promoting men and women dialogue around nutrition and health seeking good practices, and promotion of men and women role models in relation to parental care of children under the age of 5.
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well as picture material please make sure you include all credits and share them in high resolution.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board