## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to the secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality results reports please follow the next guidelines: a) The narratives should be a well written, succinct summary clarifying what was done during the reporting period and the results achieved. It should highlight the JP achievements. It should also specify scope and beneficiaries. b) Factual, evidence-based reporting against the outcome and output and corresponding indicators in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not should be provided. d) Factual, evidence-based reporting against the outcome results and its alignment with the overall SERP joint workplan, and linkage to reporting on global-level SERP indicators. e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not. g) Reflect on innovation. Avoid generic and standard descriptions. Rather, present well documented features of successful innovative solutions truly new for you and which could enable replication efforts.
3 | Please fill out all sections of the reporting template before submitting to the secretariat via email to: nina.andersen@undp.org and cc.: maria.herrera@undp.org
B
DEADLINE: MARCH 31 ST, 2022
1 | ALL projects receiving funds in late 2020 and in 2021 must complete an ANNUAL report as per the end of the calendar year with a reporting period : date of start until 31 December 2021.
2 | The joint programmes which completed their activities in 2021 should deliver a FINAL report by March 31 at the latest and will not be obligated to provide an annual report.
3 | The joint programmes completing activities in 2022 will be asked to submit a FINAL report (by 31 August 2022)
4 | ALL projects must report number of direct beneficiaries.
5 | ALL projects must provide an update on project indicators

## General Information
Programme Title & Project Number |  | Programme Duration
Programme Title: | Protection of the most vulnerable population through real-time needs analysis and the definition of adapted interventions | Overall Duration (months) | 6
Programme Number (if applicable) | 129536 | Start Date (dd.mm.yyyy) | January - June 2022
MPTF Office Project Reference Number: |  | Original End Date (dd.mm.yyyy) | N/A
Country | Dominican Republic | In case of NCE Current End date(dd.mm.yyyy) | N/A
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNICEF, UNFPA, UNDP, FAO and WFP. | National counterparts (government, private, NGOs & others) and other International Organizations | Ministerio de Agricultura como al Sistema Nacional para para la Soberanía y Seguridad Alimentaria y Nutricional (SINASSAN)/Superate/ CONEP, ANJE y AMCHAMDR AIRD, INTEC, INABIE, SIUBEN, CONANI, PUCMM, OPS-INCAP, CONASSAN, Listín Diario, Cáritas Dominicana, Comedores Económicos, Gabinete De Coordinación De Políticas Sociales de Vicepresidencia, Ministerio de Salud Pública, Ministerio de Cultura, Banco de Alimentos y el Consejo Interreligioso de Seguridad Alimentaria y Nutricional (CISAN).Ministerios de Educación, de la Juventud, de la Mujer, Procuraduría General de la República, CONANI, Good Neighbors, Mujeres por la Igualdad de Derechos, Red Iberoamericana de Personas con Discapacidad Física/ SIUBEN
Report Cleared By
o Name: | Mildred Samboy
o Title: | Partnerships and Development Finance Officer/ UNRCO
o Email address: | mildred.samboy@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19 (up to 500 words). | The 6th round of SEIA for 2022 reflected the recovery and resilience of the vulnerable population with Social Cohesion Fund, at least 2,084 people (1,184 women and 900 men) benefited directly, and 3,972 people indirectly. The monitoring of COVID-19 recovery strategies, as well as the recovery of services and the provision of updated data on children and adolescents, is key to the definition of government assistance to for the period 2023-2027.1001 vulnerable families have received food assistance through food kits and nutricional talks and counseling with the objective of improving their understanding of the importance of a diversified diet in la Romana and Montecristi. 60 families have been supported to create their own vegetable garden inside their houses. This project contributed to the protection of the most vulnerable population, mitigating the deterioration of livelihoods and ensuring that they have the capacity to satisfy their basic needs. This support has been coordinated in an inclusive and sustainable, and was carried out through the analysis of needs in real time and the definition of adapted interventions, with a focus on women in situations of vulnerability and on the reinforcement of care services and prevention of gender-based violence and sexual abuse.
2 | Purpose | Please describe the project general objective specifying its link to COVID-19 response. | This project foster that The Dominican Republic has a permanent monitoring and diagnosis system on the socioeconomic effects of the COVID-19 emergency for relevant and timely decision-making while promoting social cohesion. (SDG 1.5, 17) That Vulnerable population improves its nutritional status through joint actions to address acute malnutrition, promotion of nutritionally intelligent food, guarantee of food availability and recovery of rural livelihoods (SDG 2). As well as Women, children and adolescents in vulnerable situations improve their capacity for resilience and protection against COVID-19, violence, and exploitation with access to protection services (SDG 3, 5 and 16)
3 | Results: Outcome Level | Please include narratives describing the main project achievements against the project's overall goal (up to 300 words) | The 6th round of SEIA for 2022 reflected the recovery and resilience of the vulnerable population With the Social Cohesion Fund, at least 2,084 people (1,184 women and 900 men) benefited directly, and 3,972 people indirectly.SEIA informs the government on relevant interventions in education, health, nutrition and generation for the recovery of pre-pandemic levels by covid-19 services to the pre-pandemic level. The monitoring of COVID-19 recovery strategies, as well as the recovery of services and the provision of updated data on children and adolescents, is key to the definition of UNICEF assistance to the government for the period 2023-2027.Through the Plan for the Reduction of Acute-Malnutrition, screening, monitoring and treatment with RUTF-food was carried out for boys and girls between 6 months and 5 years of age and pregnant and lactating mothers where they were registered in the APP-Nutre-MUAC; the nutritional surveillance system is strengthened. Through the construction of 6 family farming shadow houses, vulnerable groups belonging to Supérate-Social programs have been strengthened in several provinces. The GABSA-Policy-Brief was prepared by specialists, managing decision-makers to align policies-programs. 1001 vulnerable families have received food assistance through food kits and nutritional talks and counseling with the objective of improving their understanding of the importance of a diversified diet in la Romana-Montecristi. 60 families have been supported to create their own vegetable garden at their houses.
3.1 | Results: Output Level | Please include narratives describing the main annual/ final results of each output included in the project document (up to 200 words) | Output 1.1.1- Mapping of the country's institutions in the phases of prevention, preparation, response and recovery to disasters, considering both the National Prevention, Mitigation and Response System, as well as the Social Protection System. Output 1.1.2- Carried out jointly with MEPyD/SIUBEN the 6th round of SEIA to monitor the impact of COVID-19 on households in the most vulnerable conditions. Output 1.1.3- Transferred to MEPYD/SIUBEN the SEIA methodology for monitoring future impacts on vulnerable populations and strengthened their technical capacities for leadership of the next rounds. Output 1.1.4- One report completed on monitoring of national strategies for response and recovery from the effects of the COVID-19 Output 1.1.5- One report completed on the recovery of services targeted to the most vulnerable population Output 1.2.1- 6 community works financed with the participation of the beneficiary communities and contributions from the municipalities. Output 2.1.: WFP provided family and individual nutritional counseling to prioritized vulnerable families. Output 2.2.: Food and nutritional assistance has been provided in the form of 15 days family food kits and through family vegetable gardens. Output 3.1.- UNFPA/UNDP: Officials trained in preparation and care in response services to VAWG in emergency contexts Output 3.2.- UNFPA/UNDP: Mapping of VAWG remote care services, protocol in harmonization process, strengthening of the VAWG MMujer team Output 3.3.- UNFPA/UNDP: RRSS and face-to-face campaign for civil servant and citizen awareness for action against VAW in emergency contexts Output 3.4.- An assessment of the Helpline carried out and 1,600 people assisted with mental health.
3.2 | Results: Gender | Please include project Gender results and its linkage with COVID- 19 response. If applicable, refer to the project's gender equality marker and any impacts they may have had on programming quality and results (up to 150 words). | The projects financed with the Social Cohesion Fund mainly provided training opportunities and livelihoods to 1,184 women for 57.0% of the total direct beneficiaries, through the creation of a solidarity purchase club; the adaptation of an exhibition booth for the sale of craft products; household waste management; the construction of a community tube well; the creation of recycling points for plastic and other solid waste; the adaptation of housing for ecotourism, all these interventions in vulnerable communities in the municipalities of Laguna Salada, Santa Cruz de Barahona, Polo, Distrito Nacional, Las Terrenas and Neyba. The 6th round of the SEIA survey allows disaggregation by sex, therefore, 55.3% of the interviewees are women and the remaining 44.7% are men. This tool also allows you to filter all the information by migrants and people with disabilities. Work was carried out in close collaboration with the Ministry of Women, attending to the needs expressed by the Directorate for Prevention and Attention to Violence in its experience with the management of the COVID 19 crisis. Work was also carried out in coordination with the communication department of the Ministry of Women so as not to duplicate efforts and integrate the campaign within the framework of its national campaign "Living Without Violence, It's Possible". 20 women and 6 men, from different government institutions such as the Ministry of Women, Ministry Economy Planning and Development, Ministry of Health , Attorney’s office and Civil Defense, participated in a 3 day workshop on gender based violence during emergency contexts. The workshop took place during the 22, 23 and 24th of June and iIt reflected the needs and opened the discussion of the challenges the different institutions that offer GBV prevention and attention go through. 1 Mapping of remote GBV attention services that includes the Ministry of Women, National Police, Attorney’s Office and 911. As of August 2021, there is a significant increase in the use of the emergency line *212 with respect to the figures of the previous year, in December 2021 there were 50.2% more calls than the same month of 2020. It was strengthened by care team for victims of GBV of the Ministry of Women through necessary resources such as computer equipment and training for the victim care staff (40 people from the Provincial and Municipal Offices and 24 from the emergency line *212). During the months of confinement, reports of GBV decreased drastically. To promote reporting and attention to people interested in receiving information or support on gender-based violence in emergency situations, a campaign was organized with the Ministry of Women in which 400 T-shirts and 30,000 flyers were delivered.
3.3 | Results: Direct Beneficiaries | Please include total number of DIRECT BENEFICIARIES disaggregated by gender, age , location (rural, urban, any other location). Please avoid duplicating beneficiaries ensuring the dissagregated data adds to the total presented. | Total: 67,150 Women: 12,566 (18%) Men: 10,891 (16%) Undefined: 43,693 (65¦%) Through territorial attention in the First Level Centers, NGOs and INAIPI, 22,209 (35% girls, 35% boys, 30% undefined) boys and girls were evaluated, where 625 have been diagnosed 625 boys and girls with acute malnutrition and 1451 with risk of malnutrition; 3670 women have been recruited where 589 have been diagnosed and treated with AD. -For the selection of the beneficiaries of the project for the shadow houses of Family Agriculture, associations and groups made up of women were prioritized. For the shade houses, 73 people benefited: Between the ages of 20-59 = 53 people and 60 or more = 20 people Gender: 49 female (%) and 24 male (%) -A total of 21 people benefited from the Construction of the Collection Center, 11 men (52%) and 10 women (48%). -The training on healthy eating was attended by a total of 634 participants, 377 women (59%) and 257 men (41%). WFP was able to attend more than 4,345 participants during the food kits distribution. Of these 54% were women, 839 were infants from 0 to 59 months, 1,466 were children from the age of 5 to 17 and 128 were elders with more than 65 years.A social media campaign in Facebook, Instagram and Twitter (22 - 30 of June) reflected a total of 39,868 indirect beneficiaries. FB = 17,940. IG =21,174. TWITTER = 754 organic impressions. The information shared was centered on GBV during emergency context and how/where to access the attention necessary as well as how that attention should be.
3.4 | Results: Indirect Beneficiaries | Please include total number of INDIRECT BENEFICIARIES. Please clarify if these are estimated and/or verified. If possible, disaggregate beneficiries by gender. | Indirectos: Total 3,972 (estimado) Indirectly, some 300 family members of the participants benefit from the productive units, plus some 790 people who will acquire food at a lower price and better quality.
3.5 | Do not Harm | Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention. ( up to 100 words)
3.6 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken to achieve the expected results) Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms(use up to 150 words). | COVID-19. Regarding the risks linked to COVID, security protocols and prevention measures will be implemented (presentation of the vaccination card, wearing a mask, distance between people, handwashing, etc.) to reduce the risk of contagion. In addition, through electronic means, communication materials that FAO has generated during the Covid-19 pandemic will be disseminated with the beneficiary community groups, in relation to the measures and practices to be considered at the level of farms and collection centers. Participants who present symptoms will be invited not to appear in the formations until they are quarantined. Difficult procurement services The UNS has signed long term agreements with international companies with the capacity to carry out the activity. Extreme time constraint for implementation. Indicators that are measurable in the short term Difficulty in logistics and purchase of food due to delays due to COVID-19. SNU has agreements with local suppliers to mitigate the risk of food purchase delays Extreme weather events. Shadow houses are a means of production in a controlled environment to resist the ravages of the climate. The shadow houses were conceived with the reinforcement of the infrastructure against strong winds and direct solar incidence, proximity to safe water sources associated with the application of good practices for resilient and sustainable agriculture (including high-efficiency irrigation systems). In addition, the history with which extreme weather events have been triggered (except for droughts) in these territories in the months in which the activities will be implemented is of low occurrence. Tensions derived from the selection of direct beneficiaries. The number of direct beneficiaries per community makes it necessary to choose only a few among a greater number of people with the same needs. For this, FAO and SUPERATE have planned mitigation actions that favor the selection of direct beneficiaries chosen by the community itself, as a result of a participatory and inclusive process and given the possibility that some may desert or show a low level of commitment or lack of interest in the community. participation, manage to replace him using the same mechanism.
3.7 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) (up to 250 words) | The construction of the collection center will allow producers to increase their income and productivity. The GABSA Policy Brief was prepared by FAO specialists in SSAN, managing to promote decision makers to align policies and programs related to food. The NUTREMUAC APP was created to record the screening, follow-up and treatment of children, pregnant and lactating mothers who have been measured with the MUAC tape to diagnose acute malnutrition. This tool has managed to update the data on acute malnutrition in the country. For the development of similar initiatives under an inflation scenario, it is convenient to plan an additional percentage that mitigates or covers the rise in food and other item prices so that it is not necessary to reduce the amount of initially projected assistance. There is a gap of knowledge in GBV from the institutions and personnel that work on emergency response. Training, sensitizing and offering tools for action preventing GBV and guidelines for attention and response to first line emergency responders is necessary. The workshops showed the need to continue building capacities in different gubernamental institutions from national and local levels on GBV response during emergencies.
3.8 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 250 words) | For the elaboration of the 6th round of the SEIA survey, the updating of the questionnaire was carried out in coordination with the MEPyD and SIUBEN, this allowed integrating the visions of both the government and UNDP/UNICEF. Likewise, the collection of information was directly with SIUBEN, taking advantage of its knowledge and operations in the collection of information. To provide support to vulnerable communities through local organizations, the fund for social cohesion and community solidarity, granted funds to a group of 6 NGOs from Red Actua: ADELVA, Cáritas, CESAL, COPADEBA, INSALUD and World Vision that carried out works crucial for the survival and socioeconomic recovery of 6 communities that live in vulnerable conditions and whose conditions worsened due to the pandemic situation in the municipalities.The joint inter-agency work between UNDP and UNICEF creates synergies and adds value to the government's technical assistance. It should be noted that the joint work makes it possible to make visible the most at-risk populations, such as children and adolescents, people with disabilities, migrants and other excluded groups that are excluded from public programs. Work was carried out in close collaboration with the Ministry of Women, attending to the needs expressed by the Directorate for Prevention and Attention to Violence in its experience with the management of the COVID 19 crisis. Work was also carried out in coordination with the communication department of the Ministry of Women so as not to duplicate efforts and integrate the campaign within the framework of its national campaign "Living Without Violence, It's Possible". The project worked in conjunction with a variety of sectors including the Ministry of Agriculture, World Vision and Universidad Evangelica. These partnerships were created to multiply the efforts at the local level according to their strengths and specific topic knowledge, for example rapidly identified families that were in strong need of immediate assistance in the territories and creating nutritional counseling materials rapidly. This project was developed in coordination with the Ministry of Public Health (MSP), the National Health Service (SNS) and 21 NGOs that have been trained in community management of acute malnutrition with the guide adopted by the MSP for community management. of acute malnutrition. Similarly, the Nutritional Surveillance System has been implemented in First Level Centers in conjunction with the MSP and SNS.The project was developed in coordination with the Government's Supérate Program, allowing the progress of the activities and the selection of the beneficiaries. This allowed synergy with another similar initiative, increasing its scope. Similarly, he favored the ongoing negotiations to raise funds with the government.
3.9 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken (up to 200 words). | The construction of the collection center will allow producers to increase their income and productivity. The GABSA Policy Brief was prepared by FAO specialists in SSAN, managing to promote decision makers to align policies and programs related to food. The NUTREMUAC APP was created to record the screening, follow-up and treatment of children, pregnant and lactating mothers who have been measured with the MUAC tape to diagnose acute malnutrition. This tool has managed to update the data on acute malnutrition in the country. For the development of similar initiatives under an inflation scenario, it is convenient to plan an additional percentage that mitigates or covers the rise in food and other item prices so that it is not necessary to reduce the amount of initially projected assistance.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place (Up to 100 words). | General Information Participating Organizations FAO UNDP UNICEF WFP FAO UNDP UNICEF WFP UNFPA N/A Narrative CN_IV. El rol crucial de UNFPA Si bien el número máximo de agencias implementadoras de este programa se limita formalmente a 4, el UNCT reconoce el rol central de UNFPA y su valor añadido en todo lo que tiene que ver con la integración de la perspectiva de género y la prevención y respuesta a la violencia basada en género. UNFPA es la agencia que lidera, con el PNUD, el Grupo Interagencial de Género, y coordina el grupo interagencial de Violencia Basada en Género, de conformidad con las directrices del IASC y las prioridades del país. UNFPA ha sido un socio clave durante la formulación del Plan de Respuesta y ha estado involucrada en el diseño de este programa. En un país como Republica Dominicana y en el contexto actual, el SNU necesita contar con el expertise de las 5 agencias que aquí se presentan para implementar este programa con éxito. Así, de no poder ser UNFPA una agencia receptora para este fondo, el UNCT propone que lo sea a través de una de las otras 4 agencias a través de un acuerdo “agencia-agencia”. UNFPA UNFPA es la agencia que lidera, con el PNUD, el Grupo Interagencial de Género, y coordina el grupo interagencial de Violencia Basada en Género, de conformidad con las directrices del IASC y las prioridades del país. UNFPA ha sido un socio clave durante la formulación del Plan de Respuesta y ha estado involucrada en el diseño de este programa. En un país como Republica Dominicana y en el contexto actual, el SNU necesita contar con el expertise de las 5 agencias que aquí se presentan para implementar este programa con éxito. Erased: Así, de no poder ser UNFPA una agencia receptora para este fondo, el UNCT propone que lo sea a través de una de las otras 4 agencias a través de un acuerdo “agencia-agencia”. UNFPA UNFPA is the lead agency, with UNDP, the Interagency Group on Gender, and coordinates the interagency group on Gender-Based Violence, in accordance with the IASC guidelines and the country's priorities. UNFPA has been a key partner during the formulation of the Response Plan and has been involved in the design of this program. In a country like the Dominican Republic and in the current context, the UNS needs to have the expertise of the 5 agencies presented here to implement this program successfully. Erased: Thus, if UNFPA cannot be a receiving agency for this fund, the UNCT proposes that it be through one of the other 4 agencies through and “agency-agency” agreement. RBM Lead Participating Organization Output 3.1. 3.1.1 3.1.2 3.1.3 3.1.4 Output 3.2 3.2.1 3.2.2 3.2.3 3.2.4 Output 3.3. 3.3.1 3.3.2 UNDP UNFPA The lead participating organization was changed from UNDP to UNFPA for the listed outputs and indicators
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | UNICEF provided financial resources and incorporated its technical teams to implement the MPTF-funded interventions. These additional resources provided by UNICEF allowed for a greater reach of the interventions.The diagnosis, treatment and follow-up of children, pregnant women and lactating mothers who have been registered in the NUTREMUAC APP has allowed continuous monitoring of patients and updated data by provinces to create strategies to improve nutritional status. of these boys, girls, pregnant and lactating mothers. Mercatodo, the food kits provider, donated: the transportation of the food kits distributed in La Romana to 60 families for a total of RD$ 70,000, RD$20,000 for the bags the food kits were packed into, and an additional food kit for 73 dollars, for a total of US$1,733.

## Project Indicators
Please include ALL indicators in the project document. Include the indicators and Baseline, Planned Target and Actuals for both OUTCOME and OUTPUT levels. "Actuals" refer to the total figures achieved for each indicator. Include separate actuals for 2021 and for 2022 (if applicable). Explain if targets were not achieved. Include means of verification. Use as many outputs cells as needed to present all project indicators.
| INDICATORS DESCRIPTION AND DATA | DATA: ACTUALS 2021 | DATA: ACTUALS 2022 (if applicable) | TOTAL actuals (agreggated 2021 and 2022 if applicable ) | Reasons for Variance with Planned Target (if any) | Source of Verification
Output 1.1
Indicator 1.1.1: Mapping of the country's institutions in the phases of prevention, preparation, response and recovery to disasters, considering both the National Prevention, Mitigation and Response System, as well as the Social Protection System.
Baseline:
Planned Target:
Indicator 1.1.2:
Baseline:
Planned Target:
Indicator 1.1.3: Transfer of SEIA to the government | The advances in delivering the SEIA-Red Actua survey to the MEPyD will be measured as a percentage. For the lifting of the 6th round of SEIA Red Actua. | 0% | 100% | 100% | N/A | Report / PowerBI
Baseline: 0%
Planned Target: 100.0%
Indicator 1.1.4. One report completed on monitoring of national strategies for response and recovery from the effects of the COVID-19 |  | 0 | 1 | 1 | N/A | Report
Baseline: 0
Planned Target: 1 |  | 0 | 1 | 1
Indicator 1.1.5. One report completed on the recovery of services targeted to the most vulnerable population |  | 0 | 1 | 1 | N/A | Report
Baseline: 0%
Planned Target: 1
Indicator 1.2.1: Small fund for social cohesion and community solidarity with NGOs | Through the NGOs of Red Actúa, a fund will be implemented to allow them to have quick resources for projects of construction or rehabilitation of small-scale community infrastructure at the local level. | 0 | 5 | 6 | N/A | Report / Videos
Baseline:0
Planned Target: 5
Indicator 1.2.1: Small fund for social cohesion and community solidarity with NGOs | Through the NGOs of Red Actúa, a fund will be implemented to allow them to have quick resources for projects of construction or rehabilitation of small-scale community infrastructure at the local level. (Number of people in a vulnerable condition with temporary employment) | 0 | 400 | 120 | N/A | Report
Baseline: 0
Planned Target: 400
Indicator 1.2.1: Small fund for social cohesion and community solidarity with NGOs | Through the NGOs of Red Actúa, a fund will be implemented to allow them to have quick resources for projects of construction or rehabilitation of small-scale community infrastructure at the local level. (Number of women in vulnerable conditions with temporary employment) | 0 | 200 | 70 | N/A | Report
Baseline: 0
Planned Target: 200
Indicator 1.2.1: Small fund for social cohesion and community solidarity with NGOs | Support for social cohesion in vulnerable communities through organizations that work to overcome poverty, improve livelihoods, empower women, among other related issues (Number of Communities benefited) | 0 | 5 | 6 | N/A | Report / Videos
Baseline: 0
Planned Target: 200
Output 1.3 onwards
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.
| INDICATORS DESCRIPTION AND DATA | DATA: ACTUALS 2021 | DATA: ACTUALS 2022 (if applicable) | TOTAL actuals (agreggated 2021 and 2022 if applicable ) | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 2
Output 2.1 Education Strategy and Nutritional Counseling
Indicator 2.1.1. Nutritional counseling workshops to improve the eating habits of populations at a higher level of vulnerability due to COVID-19. | Measure the people reached with nutritional counseling workshops related to improvements in eating habits. | 0 | 1000 | Not applicable | It was possible to reach more people thanks to the coordination of activities with other activities and community processes. | Counselling card report and delivery food assistance reports.
Baseline: 0 |  | 0 | 0 | Not applicable
Planned Target: 240 |  | 0 | 240 | Not applicable
Indicator 2.1.2. Community communication workshops to improve healthy eating habits of populations at a higher level of vulnerability due to COVID-19. | Measure the people reached with community workshops and communication initiatives in behavior change related to improvements in eating habits. | 0 | 4345 | Not applicable |  | Counselling card reports.
Baseline: 0 |  | 0 | 0 | Not applicable
Planned Target: 4,240 |  | 0 | 4240 | Not applicable
Output 2.2. Food and nutritional assistance in emergencies
Indicator 2.2.1. Unconditional food assistance to the vulnerable population affected by the COVID-19 emergency. | Measure vulnerable people reached with direct food assistance provided through food kits. | 0 | 4568 | Not applicable | Actual numbers of peoples reached were higher than the one estimated at the beginning of the project. | Delivery report on site.
Baseline: 0 |  | 0 | 0 | Not applicable
Planned Target: 4,000 |  | 0 | 4000 | Not applicable
Indicator 2.2.1. Unconditional food assistance to the vulnerable population affected by the COVID-19 emergency. | Measure the number of food kits delivered to the most vulnerable people | 0 | 1001 | Not applicable | The provider donated an additional kit. | Delivery report on site.
Baseline: 0 |  | 0 | 0 | Not applicable
Planned Target: 1,000 |  | 0 | 1000 | Not applicable
Indicator 2.2.2. Strengthening of diet diversification tools through urban gardens in communities affected by the COVID-19 emergency and with high levels of vulnerability. | Measure the number of diversification tools through urban gardens that have been created, restored or maintained during implementation | 0 | 60 | Not applicable
Baseline: 0 |  | 0 | 0 | Not applicable
Planned Target: 60 |  | 0 | 60 | Not applicable
Output 2.3
Indicator 2.3.1: Number of boys, girls, pregnant and lactating women evaluated nutritionally. | Through territorial attention in the First Level Centers, NGOs and INAIPI, people are evaluated to capture cases of malnutrition and be treated. 22,209 boys and girls have been recruited, where 625 have been diagnosed, 625 boys and girls with acute malnutrition and 1,451 at risk of malnutrition; 3670 women have been recruited where 589 have been diagnosed and treated with AD. | 18 | 25.879 | 43.879 | Non applicable | UNICEF
Baseline: 18.000
Planned Target: 19.000
Indicator 2.3.2 Numero de CPN's incorporados a la Vigilancia Nutricional | An expansion of the Nutritional Surveillance System is carried out, where the first 40 are strengthened and 20 more CPNs are added, along with their staff, a follow-up is provided for monitoring and implementation. | 40 | 20 | 60 | Non applicable | UNICEF
Baseline: 40
Planned Target: 60
Output 2.4 |  |  |  |  | N/A | Listado Beneficiarios
Indicator 2.4.1: Number of shadow houses built and functional. | 6 family farming production units were built for vulnerable groups belonging to the Supérate social programs in the provinces of: San Juan, Constanza, Monte Plata, San Pedro de Macorís, María Trinidad Sánchez and La Altagracia. | 0 | 6 | 6
Baseline: 0
Planned Target:6
Indicator 2.4.2: Number of people trained in shade house construction techniques and agricultural production sustainable | Training in shade house construction techniques and sustainable agricultural production | 0 | 50 | 73 | N/A | Listado Beneficiarios
Baseline: 0
Planned Target: 50
Indicator 2.5.1: Number of Commercialization Plans | "Marketing plans as a mechanism that allows producers to market the vegetables demanded by potential buyers, as well as guarantee that they meet the required requirements by its buyers and guarantee the production of the volumes demanded" | 0 | 6 | 0 | N/A
Baseline: 0
Planned Target: 6
|  | 0 | 15 | 0 | The training could not be carried out nor the commercialization plans were pending for the next project UTF/DOM/022/DOM
Indicator 2.5.2: Number of people trained in associative management, commercial negotiation, value addition.
Baseline: 0
Planned Target: 15
Indicator 2.5.3: Number of collection centers built and functional. |  | 0 | 4 | 1 | Only one collection center could be built due to the rise in the prices of construction materials.
Baseline: 0
Planned Targeted: 4
Indicator 2.5.4: Number of people trained in the construction of a collection center. |  | 0 | 50 | 0 | N/A
Baseline: 0
Planned Targeted: 50
Indicator 2.6.1: Revised GABSA Guide Number people trained in construction of collection center. |  | 0 | 1 | 1 | N/A
Baseline: 0
Planned Targeted: 1
Indicator 2.6.2: Number of educational materials edited and printed. |  | 0 | 3 | 10 | N/A
Baseline: 0
Planned Targeted: 3
Indicator 2.6.3: Number of institutions participating in the dialogues. |  | 0 | 15 | 15 | N/A
Baseline: 0
Planned Targeted: 15
Indicator 2.6.4: Number of people trained with at least 50% women in nutrition and diet |  | 0 | 150 | 634 | N/A
Baseline: 0
Planned Targeted: 150
Outcome 3
Output 3.1
Indicator 3.1.1: | 1 capacities plan designed
Baseline: | 0
Planned Target: | 1 | 0 | 1 | 1
Indicator 3.1.2: | Number of public servants participating in the training |  |  |  |  | https://dominicanrepublic.unfpa.org/es/news/realizan-jornada-de-capacitaci%C3%B3n-para-eficientizar-la-atenci%C3%B3n-remota-de-casos-de-violencia-en https://docs.google.com/document/d/1TWCAzEyJJpEOXb0l_lGGLCNyKYCsIBT8/edit#heading=h.pfk4gjr1ydak
Baseline: | 0
Planned Target: | 25 | 0 | 34
Indicator 3.1.3: | Survey, coordination and critical path instrument package designed
Baseline: | 0
Planned Target: | 1 | 0 | 1
Indicator 3.1.4: | Number of certified people. Number of people participating in the Seminar
Baseline: | 0
Planned Target: | 20 | 0 | 34
Indicator 3.1.5: | Number of public servants participating in the training |  |  |  | It was decided to work with groups of 20 people (a total of 40 trained officials) to facilitate a more participatory methodology. | Listados de participación, informe
Baseline: | 0
Planned Target: | 50 | 0 | 40 | 40
Output 3.2
Indicator 3.2.1: | Package of information materials and dissemination of the remote care protocol.
Baseline: | 0
Planned Target: | 1
Indicator 3.2.2: | Mapping of remote care services to GBV available.
Baseline: | 0
Planned Target: | 1 | 0 | 1
Indicator 3.2.3: | Number of public servants participating in the training
Baseline: | 0
Planned Target: | 25
Indicator 3.2.4: | At least 2 institutions strengthen/update or create protocols for handling remote assistance lines in each institution for cases of violence against women, adolescents and girls.
Baseline: | 0
Planned Target: | 2
Indicator 3.2.5: | Number of public servants participating in the training |  |  |  |  | Listados de participación, informe
Baseline: | 0
Planned Target: | 15 | 0 | 24 | 24
Output 3.3
Indicator 3.3.1: | 1 communication and awareness campaign designed
Baseline: | 0
Planned Target: | 1 | 0 | 1
Indicator 3.3.2: | 1 Paquete de materiales de comunicación producidos y publicados.
Baseline: | 0
Planned Target: | 1 | 0 | 1
Indicator 3.3.3: | 1 communication and awareness campaign designed |  |  |  |  | Campaign Materials
Baseline: | 0
Planned Target: | 1 | 0 | 1 | 1
Output 3.4
Indicator 3.4.1: | Evaluation report and documentation of the Contigo Family Helpline prepared and approved by UNICEF |  | 1 | 1 |  | ISAMT reports
Baseline: | 0 | 0 | 1 | 1
Planned Target: | 1 | 0 | 1 | 1
Indicator 3.4.2: | Contigo Help Line Value and Documenation Report Elaborated and Approved | 0 | 1 | 1 |  | ISAMT reports
Baseline: | 0 | 0 | 1 | 1
Planned Target: | 1 | 0 | 1 | 1
Note on A67: ====== ID#AAAAeGxv50Y Leticia Mera Zouain (2022-08-08 15:35:55) Listo UNICEF

## Communication
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant.
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well as picture material please make sure you include all credits and share them in high resolution.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board
UNFPA DOMINICAN REPUBLIC
Emergency contexts and Gender Based Violence: Improving attention to cases of violence in emergency contexts
During the implementation of the MPTF joint project UNFPA Dominican Republic developed communication materials that supported the workshop “Improving attention to cases of violence in emergency contexts”. Within the framework of this action, we developed a campaign on social media with messages aimed at guiding public servants about their role and the correct way to act to provide an effective response to cases of violence in emergency contexts, who are vulnerable in these contexts and how to help them, highlighting good practices to take into account. Likewise, we prepared and distributed emergency backpacks containing basic supplies for the prioritized population in cases of emergency.
Communication materials developed by UNFPA DR:
Logo
Workshop materials
Participation certificate
Photographies
Social media campaign
Press release
Press release links
Emergency backpack kit
UNDP
As part of our visibility efforts for our initiatives funded through MPTF we:
- We supported a door to door campaign led by the Ministry of Women to raise awareness about GBV and available resources/help lines for victims. The campaign is called "Vivir sin Violencia es posible" and it includes flyers, visits to communities and other P2P efforts.
Products: https://drive.google.com/drive/folders/1LA9c_o-vagIhJ3FWAP1UDnixehvjimIi?usp=sharing
- We produced success stories that will be shared on social media, UNDP an UN's website about some of the initiatives that were funded through the project.
Products: https://we.tl/t-Cx78RrIqSb
UNICEF DOMINICAN REPUBLIC
After the launch with the Ministry of Health of the Plan for the Reduction of Acute Malnutrition, training and educational materials were made to support primary health centers and NGOs as well as families with children under 5 years old and pregnant and lactating women, Human life stories were capture and all materials and information is provided on a landing page created for this successful plan.
Landing Page
Testimonies
Potographies
Press release
Brochure
Instructive video