## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to the secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality results reports please follow the next guidelines: a) The narratives should be a well written, succinct summary clarifying what was done during the reporting period and the results achieved. It should highlight the JP achievements. It should also specify scope and beneficiaries. b) Factual, evidence-based reporting against the outcome and output and corresponding indicators in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not should be provided. d) Factual, evidence-based reporting against the outcome results and its alignment with the overall SERP joint workplan, and linkage to reporting on global-level SERP indicators. e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not. g) Reflect on innovation. Avoid generic and standard descriptions. Rather, present well documented features of successful innovative solutions truly new for you and which could enable replication efforts.
3 | Please fill out all sections of the reporting template before submitting to the secretariat via email to: nina.andersen@undp.org and cc.: maria.herrera@undp.org
B
DEADLINE: MARCH 31 ST, 2022
1 | ALL projects receiving funds in late 2020 and in 2021 must complete an ANNUAL report as per the end of the calendar year with a reporting period : date of start until 31 December 2021.
2 | The joint programmes which completed their activities in 2021 should deliver a FINAL report by March 31 at the latest and will not be obligated to provide an annual report.
3 | The joint programmes completing activities in 2022 will be asked to submit a FINAL report (by 31 August 2022)
4 | ALL projects must report number of direct beneficiaries.
5 | ALL projects must provide an update on project indicators

## General Information
Programme Title & Project Number |  | Programme Duration
Programme Title: | Immediate response to sustainable economic reintegration of young women in Chile | Overall Duration (months) | 18
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 01.01.2021
MPTF Office Project Reference Number: | MPTF_00209 | Original End Date (dd.mm.yyyy) | 05.04.2022
Country | Chile | In case of NCE Current End date(dd.mm.yyyy) | 30.06.2022
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UN Women, ECLAC, ILO and FAO. | National counterparts (government, private, NGOs & others) and other International Organizations | The Ministry of Labor and Social Security, the Ministry of Women and Gender Equity, the Ministry of Social Development and Family and their different services and programs (Chile Valora, Bolsa Nacional de Empleo, SENCE, Programa Mujeres Jefas de Hogar, Programa de 4 a 7, SERNAMEG, SENAMA), the Production Development Corporation (CORFO), the Ministry of Economy, the Export Promotion Bureau (ProChile), from the Ministry of Foreign Affairs and the Agriculture and the Livestock Development Institute (INDAP) from the Ministry of Agriculture. United Federation of Workers - CUT, the Confederation of Production and Trade - CPC. From the private sector, the WEPs Companies Network, the Global Compact Network, the Companies from the Gender Parity Initiative (IPG), and CPC. Local governments and the different services at a territorial level, in the Municipality of Renca in the Metropolitan Region and the Municipality of Padre Las Casas in the Araucanía Region. The Implementing partners are Innovacien and Fundación Emplea, Casa de la Mujer de Huamachuco, Programa de 4 a 7 San Pedro de Atacama, Fundación Datos Protegidos.
Report Cleared By
o Name: | Maria Jose Torres
o Title: | UN in Chile Resident Coordinator
o Email address: | torres8@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19 (up to 500 words). | The MPTF program was successfully implemented and reached many sectors of society (public, private, civil society, and communities). It made progress in different areas of gender equality, providing tools to improve women's economic opportunities, promoting leadership of micro-entrepreneur women, working with their businesses to include a gender perspective in their operation, raising awareness in the population in care co-responsibility issues, and generating information to guide the design of local and global policies. One significant outcome of the program is related to the partnerships and collaboration networks that were created during its implementation and are still in place after the project's conclusion. The coordination of networks with different sectors and actors, the private and public sectors, employers and workers organizations, civil society, communities, and other initiatives from the UN, were crucial for creating better economic opportunities for women from the sectors most affected by the pandemic (heads of the household, migrants, women from rural areas, and caregivers). The MujeresEmplea.org virtual platform consolidated the offer of work and training opportunities, access to funds, and subsidies to entrepreneurship and care services (with more than 100 updated publications), with more than 67,000 visits during the implementation period. In parallel, the Activa Empresarias platform was created to connect the demand of products and services of large companies with the supply of companies led by women. A pilot training, mentoring, and community care services program was successfully designed and implemented. It positively impacted the insertion of women into the labor market. It allowed their economic activation mainly in three communes of Chile with high female social vulnerability rates (Renca, Padre las Casas, and San Pedro de Atacama). More than 9,000 women were trained in digital skills for employment and/or entrepreneurship, and more than 350 women were mentored for their labor insertion. The job fairs for women offered more than 33,000 job openings, to which more than 3,000 women applied. The childcare service was available in the selected territories to facilitate the access of their caregivers to training and work opportunities, providing care to 125 children per day. A network of 300 women was trained and certified in care services, laying the foundations to establish a national caregiver's network, which the Government of Chile is currently promoting. Awareness-raising and promoting care co-responsibility had a great reach among companies in the selected territories and the general population, promoting gender equality through communication plans and workshops designed for each target audience. The challenges faced during the implementation were overcome with measures that allowed to complete the program. Considerable adjustments were made, and lessons were learned in coordinating the actors and initiatives that allowed a faster implementation of the activities, especially in the territories. The information obtained and the methodologies used in the project are used to create public policies on women's labor insertion, decent labor, and care.
2 | Purpose | Please describe the project general objective specifying its link to COVID-19 response. | The project aims to promote greater women's and young women's economic empowerment. Its purpose is "For women and young women to improve their economic empowerment through greater participation in the labor market, especially in the technology and digital fields, and access care services under the framework of socio-economic recovery, immediate response and coordination for COVID-19."
3 | Results: Outcome Level | Please include narratives describing the main project achievements against the project's overall goal (up to 300 words) | Outcome 1 Job, training, entrepreneurship, and care service offers were gathered in a virtual platform with more than 67,000 visits from more than 26,000 users, reducing the distance between public and private offers. The ActivaEmpresarias platform was created to connect the demand of products and services of large companies to the supply of companies led by women, where more than 250 companies signed up. The employability and entrepreneurship conditions of more than 9,000 women were improved through digital skills training. In this respect, a coaching and mentoring program was provided to help 355 join the labor market. On the other hand, awareness was raised on gender issues through several activities in companies that were part of the network of institutions for gender equality. Outcome 2 It was designed and developed a care pilot program, which is included in the labor integration pilot program. 125 vacant places per day were offered for childcare in the selected communes for 68 women/mothers, helping them to participate in the labor market. Also, a network of 300 caregivers was established all over Chile. Technical guidance and training programs in the selected municipalities, to the community leaders, and representatives from the private sector allowed progress in care co-responsibility in the territories, including care as a priority in the local agenda. The campaign to raise awareness and promote co-responsibility reached more than half a million people in Chile daily.
3.1 | Results: Output Level | Please include narratives describing the main annual/ final results of each output included in the project document (up to 200 words) | In order to economically activate women in the country various initiatives were carried out. An integrated and accessible virtual platform was created that gathers information on employment, training, entrepreneurship and care services https://mujeresemplea.org/. Various virtual job fairs were also held with more than 25,000 job offers for women and a virtual fair for female entrepreneurs with 386 companies led by women offering their products and services. Together with the Government of Chile, the collaborative platform https://activaempresarias.org/ was created, which provides the opportunity to connect large companies and companies led by women to carry out commercial transactions of products and services, promoting women's businesses. Two month-long digital skills training programs were conducted, training 1,534 women. The two-month mentoring, and orientation process was designed and implemented for more than 350 women. 196 women became part of the labor market, representing 75% of the women who completed the program. Also, shorter trainings on innovation, technology, digital skills, and women's labors rights were carried out. In entrepreneurship, three people were trained to become tutors for the program Start and improve your business - SYB, who in turn trained 186 women. Business Digitization programs were also carried out within the Activa Empresarias platform for entrepreneur women. To facilitate the knowledge of labor and trade union rights for women in Chile, the campaign “Labor Rights with Gender Equality: Together and Organized We Are Stronger” was launched with the Central Unitaria de Trabajadores (CUT). Care pilots were designed at the community level, creating 125 childcare vacancies. Technical assistance was provided to the three communes associated with the project which now have strengthened skills and capabilities to continue working on care co-responsibility matters. At the same time, a mapping of supply and demand for childcare services was prepared, including recommendations to implement solutions. Several instances of awareness and training were developed for different actors to understand the challenges and opportunities of care services and promote social co-responsibility in these issues. A training program was developed in partnership with the Central Unitaria de Trabajadores (CUT), which included two workshops for 120 domestic workers. Educational documents on labor rights with a gender perspective were elaborated. Three cycles of workshops, aimed at various target audiences, were held in the territories, addressing co-responsibility and active parenting from a masculinity and gender perspective. The creation of a local network of 300 women caregivers was achieved with the formal certification of their professional competencies.
3.2 | Results: Gender | Please include project Gender results and its linkage with COVID- 19 response. If applicable, refer to the project's gender equality marker and any impacts they may have had on programming quality and results (up to 150 words). | This project's outcomes are within the Gender Equality and Women's Economic Empowerment (GEEW) framework. The gender equality marker for this project is 3. This project aims to improve women's empowerment by participating in the workplace and increasing the offer of care services. The project has a significant component to create awareness and promote co-responsibility in care. The launch of advertising campaigns, gender awareness-raising workshops in the companies and the communities, and the workshops for municipal workers impact not only the women of each sector but in the communities where they are implemented and in the general population. SERP indicators: Regarding the global indicators of the United Nations System Plan for Economic Recovery in the Framework of the Pandemic (SERP Plan), the MPTF project contributes to the Third Pillar, "Economic Response and Recovery," specifically in the promotion of decent, safe, and sustainable labor for women, in supporting sustainable small companies led by women, and promoting entrepreneurship in women of rural areas. 1. Indicator 3.1: Reinforcement of employment policies and a proper regulatory environment for economic recovery and decent labor, especially in sectors where women are more exposed to COVID. Although the project focused on creating a rapid response to the impact of the crisis generating actions that contribute to the labor insertion of women, especially young women, migrants, residents of rural areas, and members of indigenous communities, it also generated evidence to create policies that promote decent labor. Through the training pilot program that provides training and labor insertion opportunities for women of the target population in STEM areas, the generated evidence can be used to create policies that promote decent labor in these sectors, also helping to close the digital gender gap. The escalation of the program through the comprehensive labor insertion pilot program to 34 communes of the Metropolitan Region stands out. Moreover, the training and certification activities of women that belong to the caregivers' network moved in line with the improvement of work conditions for women towards decent labor conditions. The same happened to the creation of material that addresses women's labor rights. In addition, considering that one of the most frequent barriers to the participation of women in the workforce is their unpaid care and housework responsibilities, the actions with the public sector to design a strategy to coordinate the existing services at a community level and provide a fast implementation solution, are initiatives that, if successful, can be easily replicated in other sectors of the territories. 2. Indicator 3.2: Number of companies from the private sector and workers from the formal and informal sectors supported during and after the COVID-19 pandemic. In this global indicator, progress was made in the work conducted with women entrepreneurs providing training opportunities in several areas. One of them is the incorporation of their businesses and facilitating their positioning as vendors for more demanding markets (large companies), promoting the growth of their businesses. In the second stage, one of the goals is to reach international markets with the help of ProChile. Progress was made by providing online training to more than 9,000 women, giving them access to better work conditions and formal job opportunities in some cases. The certifications obtained by women caregivers will allow them to formalize their jobs and care services and undertake new business ventures if they decide to do so.
3.3 | Results: Direct Beneficiaries | Please include total number of DIRECT BENEFICIARIES disaggregated by gender, age , location (rural, urban, any other location). Please avoid duplicating beneficiaries ensuring the dissagregated data adds to the total presented. | Direct Beneficiaries: 49,922 persons Mujeres Emplea Platform 26,604 Job fair users 12,562 Digital skills training 9,697 Entrepreneurship training 535 Care co-responsibility training 275 Training - ESO Observatory 7 Care Pilot program - Children 75 Care Pilot program - Women 68 Participatory dialogs 99 Total People 49,922 Job fair/Workshops Participant Companies 459 Total Companies 459 Data is disaggregated by geographic area and age: - Central zone beneficiaries: 31,909 - Northern zone beneficiaries: 1,936 - Southern zone beneficiaries: 3,379 - Beneficiaries from undetermined zones: 12,698 Four groups can be identified when disaggregating by age: - Beneficiaries younger than 14 years old: 75 - Beneficiaries between 18 and 35 years old: 7,080 - Beneficiaries between 36 and 55 years old: 5,863 - Beneficiaries older than 55 years old: 394 - Beneficiaries of undetermined age: 36,510 Finally, in the framework of the training pilot, 29% of the beneficiaries are indigenous women and 19% are migrant. On the other hand, 84% of participating women live in urban areas and 16% in rural areas.
3.4 | Results: Indirect Beneficiaries | Please include total number of INDIRECT BENEFICIARIES. Please clarify if these are estimated and/or verified. If possible, disaggregate beneficiries by gender. | All the indirect beneficiaries of the program correspond to the entire population of the communes selected by the program, plus the workers from the companies that have attended the gender issues awareness-raising workshops. Total estimated: 1,128,885 Estimated population in San Pedro de Atacama: 10,434 Estimated population in Renca: 160,847 Estimated population in Padre las Casas: 82,110 Estimated workers from participating companies: 42,525 Participants (buyers) of Feria de Emprendedoras: 4,800 Reach of the Care Co-responsibility Campaign: 527,453 (daily) Visibility of the Project in Networks: 232,004
3.5 | Do not Harm | Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention. ( up to 100 words) | As mentioned, the pandemic has disproportionately affected women because they have had to assume care responsibilities, and they have often had to leave the labor market. The intervention focused on improving women's conditions to improve their financial situation. It focused on women who identified themselves as the most affected, specifically women from rural areas, indigenous women, and migrants. Direct work was carried out with the selected territories, developing participatory dialogues to identify the needs and priorities from an intercultural approach with territorial relevance. This made it possible to implement the interventions with the precaution of not harming specific groups in the communities and adjusting the activities to each context. Systematic work was done with local governments, with whom gender equality priorities were identified to successfully implement the project. Through this work, it was also possible to learn about specific characteristics of their population, which made it possible to adjust the activities to better benefit the entire community, particularly considering the high percentages of the migrant population, and indigenous peoples living in each of the territories. The work with the companies made it possible to make visible their role regarding gender equality matters and to make them aware of the importance of personnel hiring and acquisition processes that are not biased by gender. This allowed to achieve adequate labor integration processes and safe workspaces for women. Likewise, a permanent relationship was established with women participating in the pilot and the municipalities where they lived, through the individualized mentoring programme, which allowed us to identify complex situations on time and to provide the required support or make the appropriate referrals in each case. Finally, the care services provided were managed considering initiatives underway in the selected territories, ensuring: high quality services, sustainability over time, communitarian validation and met the necessary conditions for children´s care. In summary, the work took place at a territory level, considering the needs and particularities of the intervened population and communities, which significantly impacted the groups most affected by the pandemic and addressed their challenges.
3.6 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken to achieve the expected results) Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms(use up to 150 words). | At the start of the program, one of its main challenges was the lack of information on the situation due to the pandemic and the needs of women in the selected territories. Due to this, some modifications to the initial design had to be made on-site, considering an intersectional gender approach of the project and the specific characteristics of the population of the selected communes. An example of this was extending the target population to all the women of the territories. One main challenge was the social distancing measures in place due to the health crisis. This was identified in the risk management matrix, and several activities took place remotely. However, some in-person activities had to be adjusted to meet these measures, arrange larger spaces for care services, and reduce the number of participants. The intense electoral process identified in the risk matrix led to a delay in the arrangements with the local governments that took office in 2021. Different partners were identified in the territories to implement the project and accelerate its execution to mitigate those risks. Several challenges were found in the training pilot program. Some of these challenges were external to the project, such as the low access level of the participants to technology devices, computers, and Internet connection; especially in rural zones of the selected territories; the lack of interest of some women in STEM areas or to get formal jobs, the economic reactivation situation experienced in the country gave women less time to attend the courses and heterogeneity in terms of their digital skills. Several measures were put in place to revert these situations, devices with internet access were delivered and public spaces were arranged with computers and Internet access, in rural and urban areas, for women to attend their courses and devices with Internet connection were also provided. Regarding internships, the main challenge was having offers within the selected territories, making it a priority for women not to spend time or money on transportation, and promoting economic reactivation in the communes with a gender perspective. A new modality was offered to women because it was observed that they were more interested in getting a job than in internships, and one of the alternatives offered was to offer a monetary incentive to women actively looking for a job or that were able to get a job thanks to the program. Another challenge in care was that the information available locally to develop a roadmap with the supply and demand of care services was not sufficiently disaggregated to design public policies. Thus, other sources of information had to be used.
3.7 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) (up to 250 words) | One of the innovative practices is articulating and coordinating the different programs offered to women. These efforts involve the different public and private institutions in the framework of ongoing initiatives that must be promoted or improved. The coordination of these programs provides a broad range of possibilities for women to receive training, access job offers, entrepreneurship funds, and care services. The close work with private companies has provided a clear idea of the worker's profiles that they are looking for to align with the training offers provided by the program. The project has allowed the internal coordination of initiatives and to give continuity to others in collaboration with the Migration MPTF, another inter-agency program led by the ILO, and the NODO Project, led by the UNPD. The Work Program of the Division for Gender Affairs of ECLAC, once completing this program, includes technical assistance to the commune of Renca to design community care policies. At a territory level, the articulation of local initiatives that reduced preparation times for their implementation can also be highlighted. Similarly, the use of the installed capacity in the territories, such as the use of facilities with Internet and computers where women can complete their training courses. In the same line, the articulation with the workers of other initiatives accelerated implementation times due to their knowledge of the local reality in the territories. There is also an opportunity for entrepreneurs of each territory to work together to generate value chains for their benefit. This experience was first developed in San Pedro de Atacama. An innovative practice within the project's implementation framework is the design of a community-based pilot program (training-internships/labor insertion - access to care services) to promote the coordination of different institutions at a local level and the different departments within municipalities to promote economic reactivation with gender perspective in the communes. Regarding the training pilot program, a series of adaptations were made to match the training courses with the requirements of companies. The contents of the training programs were adapted based on the information gathered regarding the digital literacy of the participating women and the high heterogeneity seen in the groups that participated in the program. One of the practices with the best was the distribution of technological devices with internet access, which eliminated one of the main barriers for women to complete the training and ensured access, especially for women from rural sectors or with less connectivity access. On the other hand, the importance of working on creating interest in self-paced learning, self-esteem, self-knowledge, and the empowerment of the women participating in the program through an ongoing guidance process with customized and group mentoring and with specific goals for each session is also highlighted. It must be mentioned that a significant milestone achieved by the Mujeres Emplea program in the Municipalities was making progress in the actions undertaken by the local governments in care issues and the commitment of the authorities to continue the same path. Given the success of the program and the results of the model's implementation in the pilot program's communes, it will be escalated to the Metropolitan Region, where the Regional Government will fund the pilot program's implementation, labor insertion, and care services in 34 communes.
3.8 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 250 words) | Creating strategic partnerships and networks is a vital part of the program. The partnerships established by the agencies at the beginning of the program were activated to create new networks during the project's implementation. Several programs were coordinated within the United Nations System, such as Tu Oportunidad, UN Women's Originarias, IMESUN from the ILO, the MPTF interagency program led by the ILO, and the NODO Project led by the UNDP. This program involved work with national and local government institutions, civil society organizations, workers and employers’ organizations, public and private companies, and other programs and agencies of the United Nations System. The project was implemented with the Ministry of Labor and Social Security, the Ministry of Women and Gender Equity, and the Ministry of Social Development and Family and their different services and programs. The project also included the participation of other public institutions according to the activities implemented, such as the Production Development Corporation (CORFO), the Ministry of Economy, the Export Promotion Bureau (ProChile) from the Ministry of Foreign Affairs and the Agriculture and the Livestock Development Institute (INDAP) from the Ministry of Agriculture. Within the scope of the project, a work plan for the constituents of the ILO (United Federation of Workers - CUT) and the Confederation of Production and Trade - CPC) was determined. The project had the collaboration and commitment from the private sector, especially from the WEPs Companies Network, Companies from the Global Compact Network, and Companies from the Gender Parity Initiative (IPG). One of the partnerships with the private sector was with Microsoft, which funded training courses for 400 women in technology areas. CLARO contributed with training courses and equipment for 850 women. Scholarships were obtained to train three facilitators who provided IMSUN training in the three selected communes. The ongoing offer of internships from the companies of the Gender Equality Network must also be mentioned. The implementation of the project has had the support and collaborative work of the corresponding local governments and the different services at a territorial level, especially in the Municipality of Renca in the Metropolitan Region, the Municipality of Padre Las Casas in the Araucanía Region, and the Municipality of San Pedro de Atacama in the Antofagasta Region. In terms of care, the partnership established with Casa de la Mujer de Huamachuco, a civil society institution led by women from the Huamachuco community in Renca, is also highlighted. Another important partnership was established with SENAMA to implement the 4-to-7 program in San Pedro de Atacama and Padre las Casas. The partnership of Chile Valora and SENCE provided certification to 300 women caregivers in Chile. Finally, we can highlight the partnership between the institutions that were part of the care co-responsibility awareness-raising campaign led by Metro de Santiago and the municipalities of San Miguel, La Pintana, Santiago, and Ñuñoa (see the partnerships chart).
3.9 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken (up to 200 words).
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place (Up to 100 words). | During the conversations with women in the mentoring programs, it was observed that women were more interested in accessing job opportunities than internships in the companies. This alternative was included as one of the paths to follow, and an economic incentive was associated with the active job-seeking process. This incentive is targeted at women who are actively seeking employment opportunities or who get a job through the Program. It is intended to cover their initial costs such as transportation and meals. In parallel, autonomous job-seeking has been promoted and supported through mentors' ongoing guidance.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | The program has mobilized a set of resources from private and public institutions: In a partnership with UN Women, CLARO Chile made a contribution of 850 digital skills online courses including a computer for each of the women part of the program, valued at USD 631,125. They also contributed with a Software Applications Development course for 25 women, valued at USD 13,001. The total contribution is USD 644,126. Microsoft committed to providing digital skills training courses for 400 women. It also considers giving its participants an account to use all Office suite applications (Word, Excel, Teams, PowerPoint, etc.) for free, valued at USD 222,609. 3 train-the-trainer scholarships from the ILO's Start and Improve Your Business (SIYB) program were provided, valued at USD 1,100 each, for a total of USD 3,300. The SENCE public service, in partnership with Chile Valora, certified the 300 women of the caregivers' network in the program. The service is valued at USD 93,168. In parallel, Universidad Santo Tomas, INACAP, and other institutions provided their facilities for these certifications, valued at USD 4,658. Considering a total contribution of USD 97,826. The Municipality of Renca also made a financial contribution of USD 4,484 to implement the care services at Casa de la Mujer de Huamachuco. All the resources mobilized for the project are valued at USD 972,345.

## Project Indicators
Please include ALL indicators in the project document. Include the indicators and Baseline, Planned Target and Actuals for both OUTCOME and OUTPUT levels. "Actuals" refer to the total figures achieved for each indicator. Include separate actuals for 2021 and for 2022 (if applicable). Explain if targets were not achieved. Include means of verification. Use as many outputs cells as needed to present all project indicators.
| INDICATORS DESCRIPTION AND DATA | DATA: ACTUALS 2021 | DATA: ACTUALS 2022 (if applicable) | TOTAL actuals (agreggated 2021 and 2022 if applicable ) | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1] | [5 empty] | National Employment Survey - INE Quarterly Report
Indicator: | Women's Labor Participation (National): Women in the Work Force (Working+Looking for a Job)/Female Population in working age (National) | 47.3% | 49.8% | 49.8%
Baseline: | 43.9%
Planned Target: | 48% | 48% | 48% | 48%
Indicator: | Women´s participation rate in Labor Market (Araucanía Region) | 40.2% | 44.1% | 44.1%
Baseline: | 35.7%
Planned Target: | 42.1% | 42.1% | 42.1% | 42.1%
Indicator: | Women´s participation rate in Labor Market (Antofagasta Region) | 50.7% | 52.2% | 52.2%
Baseline: | 44.6%
Planned Target: | 49.8% | 49.8% | 49.8% | 49.8%
Indicator: | Women´s participation rate in Labor Market (Metropolitana Region) | 52.9% | 55.1% | 55.1%
Baseline: | 44.9%
Planned Target: | 50.4% | 50.4% | 50.4% | 50.4%
Output 1.1 |  |  |  |  | The indicator was changed to number of visits instead of users considering that each visit had updated information | Information collected from Google Analytics MujeresEmplea.org
Indicator 1.1.1: | Number of visit in the platform | 13202 | 54067 | 67269
Baseline: | 0
Planned Target: | 70000 | 70000 | 70000 | 70000
Output 1.2 | [5 empty] | Partnership MoUs or agreements of implementation signed
Indicator 1.2.1: | Number of partnerships endorsed by RC and leading agency Reps. | 9 | 1 | 10
Baseline: | 0
Planned Target: | 10 | 10 | 10 | 10
Output 1.3 | [5 empty] | Reports of the registration on trainings in digital skills, STEM and Enterpreunership
Indicator 1.3.1: | Number of young low income women trained in technological, labor and women`s right and entrepreneurship areas | 699 | 1640 | 2339
Baseline: | 0
Planned Target: | 2000 | 2000 | 2000 | 2000
[5 empty] | This indicator was changed. Women insertion to the labor market is added to this indicator, due to the interest of women | Reports of the registration on mentoring and labor facilitation
Indicator 1.3.2: | Number of young low income women with internships completed and/or entering the labor market | 14 | 182 | 196
Baseline: | 0
Planned Target: | 400 | 400 | 400 | 400
Outcome 2
Indicator: | Number of care service demand and supply posts in the platform | 11 | 7 | 18 | The value of this indicator goes from 2,500 to 20, because in principle it corresponded to jobs in demand and offered on the platform. Now it corresponds to the number of care services included in the platform. It is closer to the reality of the services established in Chile. | Specific reports of care service cases posted in the platform
Baseline: | 0
Planned Target: | 20 | 20 | 20 | 20
Output 2.1 | [5 empty] | Copy of agreements uploaded to project M&E reports
Indicator 2.1.1: | Number of signed agreements between public and private care service initiatives and the project leading | 4 | 1 | 5
Baseline: | 0
Planned Target: | 5 | 5 | 5 | 5
Output 2.2 | [5 empty] | Verification and contrasting of project formulation components/parameters and Project M&E reports
Indicator 2.2.1: | Number of components of the strategy implemented, including parameters related to campaigns, workshops, polls, and technical assistance delivered at local governments (municipalities and regions) | 0.6 | 0.4 | 1
Baseline: | 0
Planned Target: | 1 | 1 | 1 | 1
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant.
Aylin Palma, from the commune of Padre Las Casas, participated in the digital skills training courses. She is an entrepreneur and now wants to work as an employee. Aylin joined the Program through an invitation sent by the Municipality. She remarks that the training courses have provided her updated information on how the digital world operates, which has been very important to become up to date with the new generations in new technologies, both for her business and the job she is seeking. She enjoyed the virtual modality of the Program because of the flexibility it provided, and she also appreciated the course's teaching methodology. She claims that the course has changed her and that her attitude towards life has improved. Now she feels like she can do more tasks independently and online to improve her work skills. https://drive.google.com/drive/folders/1wBAdxVtbKsVrfFYUnVUP4odDZuMDALcZ
2. Upload here: Communications and Visibility (OPTIONAL)
A video is attached showing the primary outcomes of the project presented during the International Seminar: Economic Recovery with Gender Perspective, an event to conclude the project that hosted several actors from other countries in the region that presented their initiatives and the outcomes obtained in other MPTFs.
https://www.youtube.com/watch?v=HmITRV40gaM
Different videos with the testimonies of the women that were part of the program are attached.
https://www.youtube.com/watch?v=xiTnyuBxoZM
https://www.youtube.com/watch?v=IVXgU_ZGR2w
https://www.youtube.com/watch?v=fC7ygQ0sAno
https://www.youtube.com/watch?v=Maj5YgA_Drg&t=22s
Social Media Cards
https://u.pcloud.link/publink/show?code=kZcnAQVZ2IPsjAtVxM0Fjl8O9WMCIBDlzCzX