## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to the secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality results reports please follow the next guidelines: a) The narratives should be a well written, succinct summary clarifying what was done during the reporting period and the results achieved. It should highlight the JP achievements. It should also specify scope and beneficiaries. b) Factual, evidence-based reporting against the outcome and output and corresponding indicators in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not should be provided. d) Factual, evidence-based reporting against the outcome results and its alignment with the overall SERP joint workplan, and linkage to reporting on global-level SERP indicators. e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not. g) Reflect on innovation. Avoid generic and standard descriptions. Rather, present well documented features of successful innovative solutions truly new for you and which could enable replication efforts.
3 | Please fill out all sections of the reporting template before submitting to the secretariat via email to: nina.andersen@undp.org and cc.: maria.herrera@undp.org
B
DEADLINE: MARCH 31 ST, 2022
1 | ALL projects receiving funds in late 2020 and in 2021 must complete an ANNUAL report as per the end of the calendar year with a reporting period : date of start until 31 December 2021.
2 | The joint programmes which completed their activities in 2021 should deliver a FINAL report by March 31 at the latest and will not be obligated to provide an annual report.
3 | The joint programmes completing activities in 2022 will be asked to submit a FINAL report (by 31 August 2022)
4 | ALL projects must report number of direct beneficiaries.
5 | ALL projects must provide an update on project indicators

## General Information
Programme Title & Project Number |  | Programme Duration
Programme Title: | Employment and Livelihood: An inclusive approach to economic empowerment of women & vulnerable populations in Indonesia | Overall Duration (months) | 15
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 01.01.2021
MPTF Office Project Reference Number: | MPTF_00209_00091 | Original End Date (dd.mm.yyyy) | 01.01.2022
Country | Indonesia | In case of NCE Current End date(dd.mm.yyyy) | 30.04.2022
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | ILO UNAIDS UNDP UNHCR | National counterparts (government, private, NGOs & others) and other International Organizations | Ministry of Women Empowerment and Child Protection Ministry of Manpower Coordinating Ministry for Political, Legal and Security Affairs The Ministry of Cooperatives and SMEs Employers' Association of Indonesia (APINDO) Catholic Relief Services Church World Services Atma Jaya University (AJU) PLHIV and Key Population networks: JIP, GWL-Ina, Sanggar Swara, Inti Muda, Opsi, IPPI, IAC, PKNI, Rumah Cemara, YKB, Spirita, and ELSAM
Report Cleared By
o Name: | Valerie Julliand
o Title: | Resident Coordinator
o Email address: | valerie.julliand@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19 (up to 500 words). | Despite operational challenges due to the COVID-19 pandemic, the Employment and Livelihood project (hereunder project) funded by the UN COVID-19 MPTF has achieved or exceeded most of its performance targets. It has provided necessary support to vulnerable groups who had been affected by the pandemic and promoted an inclusive recovery. In fact, 2,411 people have benefitted from entrepreneurship and business development training programmes of the project (Output 1), overshooting the target of 2,000, by the end of the project. It is worth mentioning that 149 refugees (112 Male and 37 females) and 249 PLHIV and key populations, 35 people with disabilities benefited from the entrepreneurship training. Of the 1,405 people who completed basic entrepreneurship (SIYB) training, 85.8% of the trainees generated business plans. 61.8% of them took steps to start or improve businesses. 57.6% of them increased income after training. Further, the project co-organizes a venture competition and pre accelerator program and assisted 24 women-led enterprises. It also invited 74 youth to benefit from youth entrepreneurship boot camp. Skills training was provided to 2,312 target beneficiaries (e.g., refugees, PLHIV and key populations, and people with disabilities) against the target of 1,650 (Output 2). According to post-training survey to which 1,755 beneficiaries responded, 82.5% expect increase in income after 6 months. Success stories and video testimonies of the beneficiaries are on the project website (https://employmentandlivelihood.id). The beneficiaries included 182 refugees with skills training, of which 60 were women. 95 refugees completed digital marketing training, 59 refugees learned WordPress for E-commerce training, and 28 refugees benefitted from barista training. 195 people with disabilities and 131 PLHIV and key populations have benefitted from the skills training offered by the project. The project promoted an inclusive recovery at two levels: policy and regulations, as well as people’s behaviours (Output 3). The Equal Employment Opportunities Guide 2004 was updated with technical assistance of the project, broadening the topics covered by the guide and reflecting the recent international labour convention on violence and harassment at work (C190). A policy paper on inclusive workplace has been concluded after rounds of consultation with representatives from the government, companies, business groups, trade unions, and communities. A series of workshops on inclusive workplace were organized in 3 provinces (I.e., Banten, DKI Jakarta, and West Java) in which human resource managers and labour inspectors participated. Following the workshops, a declaration of commitment and an action plan were developed by labour inspectors and human resource managers in 3 provinces. High-level policy dialogue on inclusive recovery was held twice in partnership with a large media company. While the project ends in April 2022, it is important that UN agencies follow up with these policy discussions and monitor, and support where appropriate, stakeholders’ actions. In addition, the project raised awareness of people on gender equal and inclusive workplaces without discrimination. A total of 169,288 people, many of them are human resource managers, participated in 19 webinars that targeted private sector managers who may influence employment practices and work culture. 56.6% of those who registered and directly joined webinars were women. The majority of people viewed webinars through YouTube and there is no knowing of their gender and age profile. A 60-minute nation-wide radio programme featured refugee issues. 15 individuals from the PLHIV and key populations communities have been trained to carry out awareness raising sessions on inclusive workplace. An online learning platform on inclusive workplace (https://kusumabuana.org/ruang-belajar/) was launched in December 2021, which benefitted 1,033 people. Policy advocacy campaign on inclusive workplace reached 13,622 people from diverse groups including the government, companies, business groups, trade unions, and communities of PLHIV, KPs, and people with disabilities. 100 trade union members were trained by the project and acted as campaigners. They invited 2,206 co-workers to participate in workplace meetings on gender equality and inclusive workplaces, and generate 1,797 social media posts, which were shared 6,457 times, received 53,593 likes and 9,868 comments.
2 | Purpose | Please describe the project general objective specifying its link to COVID-19 response. | The project aims to ensure that in the time of socio-economic crisis, no one - particularly women and other vulnerable groups - is left behind. It supports the vulnerable groups of people who are affected by the pandemic, including women, youth, refugees, migrant workers, people living with HIV, key populations most vulnerable to HIV and people living in disadvantaged regions. It intends to achieve the objective through three levels of interventions: 1) national and systemic changes - regulations; 2) indirect – behaviour changes of relevant actors; and 3) direct – empowering the disadvantaged groups of people. With this design, the project intends to generate lasting impact, inclusive recovery from the pandemic.
3 | Results: Outcome Level | Please include narratives describing the main project achievements against the project's overall goal (up to 300 words) | The outcome statement of the project is the following: Indonesia’s most vulnerable population (e.g., women, youth, refugees, people living with HIV, key populations and rural residents) are empowered and have recovered from the adverse impact of the COVID-19 crisis and benefited from an inclusive labour market. According to the Ministry of Manpower, 29 million workers were affected by the public health crisis, either job loss or cuts in hours of work and wages in August 2020. Given the size of the project budget (i.e., USD 1.7 million), the project took two-fold strategies to maximize the project impact and achieve the outcome-level results. Indeed, it provided direct support (e.g., training) to over 3,650 most vulnerable groups, while promoting an inclusive recovery by improving policies and regulations and changing behaviours of employers and workers. An independent evaluation of the project objectively assessed the impacts of the project with the following findings: "At the individual and community level, the short-term interventions of the programme generated important changes in people’s livelihood opportunities, demonstrated in the early signs of increasing income found in ILO’s endline survey. The evaluation found that the programme indirectly brought impacts on its implementing partner capacity, including increased capacity to deliver online, wider partnerships and increased knowledge. Broader social and economic impacts are difficult to predict at this early stage, but the programme has helped a significant number of people to adapt to the economic impacts of the pandemic and shift to new and emerging digitalised jobs. The policy contributions of the ILO and UNAIDS initiatives are expected to pave the way for a stronger national response to equal opportunity with respect to gender and disability inclusion."
3.1 | Results: Output Level | Please include narratives describing the main annual/ final results of each output included in the project document (up to 200 words) | Output 1 (entrepreneurship and business development): Basic and intensive entrepreneurship training, venture competition and youth entrepreneurship bootcamp were implemented, benefiting 2,411 people (including 149 refugees and 249 PLHIV and key populations, as well as 35 people with disabilities). Of the 1,405 people who completed basic entrepreneurship (SIYB) training, 85.8% of the trainees generated business plans. 61.8% of them took steps to start or improve their businesses. 57.6% of them increased income after training Output 2 (Skills training for higher income): training partners rolled out skills training to vulnerable groups, reaching 2,312 participants. Post-training surveys were conducted by each training provider between October and December 2021, showing positive impact of the interventions. The beneficiaries included 182 refugees, 131 PLHIV and key populations, as well as 195 people with disabilities. According to a post-training survey to which 1,755 beneficiaries responded, 82.5% of the respondents expect increase in income after 6 months. Output 3 (Inclusive labour market): The advocacy activities of the project were delivered, achieving impact greater than the plan. The Equal Employment Opportunity Guidelines were revised to broaden the coverage of topics to include harassment and violence, PLHIV and key populations, and people with disabilities. A policy paper on inclusive workplace was developed through rounds of stakeholder consultation. High-level media events discussed inclusive recovery from the pandemic. In addition, webinars, workshops and social media campaign raised awareness of policymakers, labour inspectors, human resource managers, and workers on gender equal, discrimination-free, and inclusive workplaces. A nation-wide radio programme discussed refugee issues, which has raised awareness of citizens and possibly helped mobilise support for refugees
3.2 | Results: Gender | Please include project Gender results and its linkage with COVID- 19 response. If applicable, refer to the project's gender equality marker and any impacts they may have had on programming quality and results (up to 150 words). | Gender equality and women’s empowerment is the principal objective of the project (Gender marker 3). By design, the project favoured cis- and transgender women in the selection of beneficiaries so that at least 60 per cent of the beneficiaries of training (Output 1 and Output 2) were cis- and transgender women. It has nearly achieved this target: 59.2 % of the trainees were women. The entrepreneurship training was enriched by sessions on gender and inclusion. Furthermore, the She Disrupt event conducted by UNDP helps to empower women start-up co-founder. In addition, gender equality featured well in the webinar series and social media campaign. Further, the project’s evaluation report notes that policy initiatives are “expected to pave the way for a stronger national response to equal opportunity with respect to gender and disability inclusion”. It also points out that “sustainable results are evident in the heightened capacity of the key actors – media, government, employer groups and trade unions – to improve gender and inclusion in the workplace”.
3.3 | Results: Direct Beneficiaries | Please include total number of DIRECT BENEFICIARIES disaggregated by gender, age , location (rural, urban, any other location). Please avoid duplicating beneficiaries ensuring the dissagregated data adds to the total presented. | We request further guideline on how to count the beneficiaries. For instance, it is not clear how to categorize a young woman with disabilities living in a rural area without duplicating in counting. While we wait for clarification, the project reports the number of disaggregated beneficiaries as follows. Please note that the disaggregated data does not add up to the total. Basic entrepreneurship training (SIYB) was provided to in total of 1,405 people including: • 950 women and 35 transgender people • 626 youth • 149 refugees • 47 people living with HIV (PLHIV) and key populations • 15 people with disabilities Another basic entrepreneurship training provided for 711 people including: • 541 women, including 5 transgender; • 546 youths; • 202 people living with HIV & key population; • 20 people with disabilities Venture competition and pre-accelerator program • 24 women-led enterprises Youth entrepreneurship bootcamp • 74 youth Skills training for income provided to in total of 2,312 people including: • 1,309 women including 36 transgender people • 1,419 rural populations • 947 youth • 182 refugees • 195 people with disabilities. • 131 PLHIV and key populations Promotion of gender equality, non-discrimination and inclusiveness at workplaces • A total of 169,288 people participated in the webinars • 15 individuals from PLHIV and key populations communities have been trained as trainers who can carry out awareness raising sessions on inclusive workplace at companies • Project’s policy advocacy initiative on inclusive workplace reached a total of 13,622 people including government officials, businesspersons, trade union members, and communities of PLHIV, KPs, and people with disabilities • 2,206 workers participated in workplace meetings and discussed inclusive workplaces.
3.4 | Results: Indirect Beneficiaries | Please include total number of INDIRECT BENEFICIARIES. Please clarify if these are estimated and/or verified. If possible, disaggregate beneficiries by gender. | Entrepreneurship, business development and skill training benefited the participants directly and their family members indirectly. Assuming an average number of household members to be 4, estimated number of indirect beneficiaries of the entrepreneurship, business development and skill training reaches 18,104 people. Further, the revised equal employment opportunity guidelines, once adopted by the Ministry of Manpower, would indirectly benefit virtually all workers in the formal economy (n.b., 34.4 million male workers and 18.7 million female workers are in formal employment as of August 2021). In addition, the social media campaign of the project generated 1,797 social media posts, which were shared 6,457 times, received 53,593 likes and 9,868 comments by the end of December 2021. It could be that project’s messages might have reached at least 60,000 people.
3.5 | Do not Harm | Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention. ( up to 100 words) | The project carefully designed interventions, selected project partners and suppliers, and monitored activities and environmental impact of project activities so that the project did not cause any unintended harm to anyone. It adhered to the UN rules and regulations concerning procurement. The project has received no complaints from any community members where it operated. Rather, it helped reduce inequalities and vulnerabilities of the target population.
3.6 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken to achieve the expected results) Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms(use up to 150 words). | At the project design stage, we anticipated that the pandemic might reduce the capacity of training providers. We assessed the risk level as medium and rated likelihood as very likely. One of counter-risk strategies of the project was to engage additional training providers to overcome capacity issues. Indeed, instead of relying on a few partners, the project engaged diverse partners. It also opted for online training where feasible. While these strategies were effective to a certain extent, two waves of COVID-19 infections (June-August 2021, January-February 2022) and tightened government restrictions on meetings and events limited the delivery capacities of our partners. Operationally, the project had limited means to cope with delays because project partners were expected to comply with government regulations. The project could not engage additional providers to enhance delivery capacity because the fund had been committed to existing contracts. The project duration was extended to complete the delivery of outputs.
3.7 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) (up to 250 words) | This project was formulated and implemented against the backdrop of deepening UN reform at the country level in which coordination function of the RCO is strengthened and UN agencies were expected to operate as one UN. This joint project involving the four agencies was a test case in that regard. It is of interest of UN agencies to draw lessons from the project and improve future collaboration across agencies. The project has generated synergies as the four agencies brought strength (e.g., technical expertise and network of partners) to the project. Intensive discussions among technical staff members of the agencies at the project design stage, with effective coordination by the RCO and the lead agency, were among crucial success factors of the project. Commitment and dedication, and intensive conceptualisation work of the project designers set the cornerstone of the project. Coordination and collaboration in operations is another important element. The project budget was divided and managed separately by the agencies. Staff members involved in the project reported to their respective supervisors of the agency and performed project tasks on the top of their daily work. Thus, the RCO and the lead agency of the project coordinated activities without relying on conventional control tools (e.g. budget allocation, reporting lines and performance appraisal). Instead, the project relied on monthly and ad-hoc coordination meetings, work plans and dense communication among staff members. The capacity, high motivation and professionalism of project staff members were important success factor. Human factor cannot be underestimated in joint operations.
3.8 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 250 words) | The project “enabled stronger partnerships among the four UN agencies, linkages with other UN agencies, and provided opportunities for new partnerships and expanded networks to be forged”, according to the project evaluation report. Examples listed below are highlighted in the report. Through this project, new organisational partnerships and linkages have been formed, which provides mutual benefits in terms of attainment of objectives and outreach. For example, implementing partners of the UNAIDS, health advocacy foundation YKB, and JIP, a network of associations of PLHIV and affected populations, found mutual benefit from working together. YKB was able to connect with grass-roots communities and marginalised groups, involving members of these groups directly in project activity implementation. JIP was able to build its capacity as an advocacy association. Through this project, new relationships were formed between well-established trade unions and newer associations representing domestic workers and child labour concerns. New partnerships were also formed by the ILO with the Indonesia Business Coalition for Women’s Empowerment and the human resource managers association, GNIK. The TEMPO media group entered new relationships with UN agencies through this project. UNDP leveraged a new linkage with Moonshot Ventures and YCAB impact investors to obtain support for the "She Disrupts” women’s entrepreneurship initiative through the Australia-funded Indonesia Women Empowerment Fund (IWEF). UNDP also benefited from their linkages with UN WOMEN to gain their support to this venture, as well as with the Ministry of Women’s Empowerment, which will co-host the forthcoming website to launch the basic business training packages for public access.
3.9 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken (up to 200 words). | The project has implemented an independent project evaluation, following the OECD DAC evaluation guidelines. The team of evaluators reviewed relevant documents and interviewed key stakeholders including beneficiaries. Site visits were not possible due to travel restrictions. The evaluation rated highly of the project and provided recommendations as listed below: 1. Employ specific and focused selection criteria for beneficiaries – whether targeting the most vulnerable groups or emerging small business and individual enterprises. 2. Allocate more time for implementation, at least two years, to permit longer mentorship support and to enable impacts on income and business stability to occur and be assessed. Integrate skills training and business development support to support start-ups. 3. Ensure that the BLK Komunitas pilot process is fully documented for replication. 4. Encouraging project partners to continue supporting the trained community association representatives. 5. Continue to provide a mix of online and offline skills training. While online training enables a wider trainee reach, but offline is still preferred by those with limited internet access and technology and living in isolated remote areas. 6. Seek further joint programming opportunities building on the success of the project. Future joint programmes should maintain the mutual governance model adopted by the project and its collaborative implementation approach. 7. Review and reform administrative, financial and human resources management systems, towards increased country-level delegation and in favour of more flexible and adaptive management. 8. Consider shifting their staffing policy so that a pool of core staff is rapidly mobilised to new projects. 9. RCO needs to consider its staffing number and structure to play a leading role in supporting the UN partners in collaborative programming. 10. Seek ongoing donor funding for economic recovery from the pandemic.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place (Up to 100 words). | The project has maintained the initial strategies, targets, outcomes and outputs throughout the project implementation. The project duration was extended until the end of April 2022. Initial end date was 01 January 2022.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## Project Indicators
Please include ALL indicators in the project document. Include the indicators and Baseline, Planned Target and Actuals for both OUTCOME and OUTPUT levels. "Actuals" refer to the total figures achieved for each indicator. Include separate actuals for 2021 and for 2022 (if applicable). Explain if targets were not achieved. Include means of verification. Use as many outputs cells as needed to present all project indicators.
| INDICATORS DESCRIPTION AND DATA | DATA: ACTUALS 2021 | DATA: ACTUALS 2022 (if applicable) | TOTAL actuals (agreggated 2021 and 2022 if applicable ) | Reasons for Variance with Planned Target (if any) | Source of Verification
Output 1.1
Indicator 1.1.1: | Indicator 1.1.1: Of the entrepreneurship beneficiaries, 75% of them generate business plans and increase prospects of income, and at least 20% take steps to start or improve businesses (e.g. apply for loan or borrow money, purchase or rent business sites or equipment, hire staff, generate marketing material) and increase income within 3 months from the completion of the training. | The project provided basic entrepreneurship training to 1,402 people. 85.8% of the trainees (ToE-1 participants) generated a business plan. 61.8% of them took steps to start or improve businesses. 57.6% of them increased income after training. |  | The project provided basic entrepreneurship training to 1,402 people. 85.8% of the trainees (ToE-1 participants) generated a business plan. 61.8% of them took steps to start or improve businesses. 57.6% of them increased income after training. | The project engaged a network of experienced trainers, which helped achieve better than expected results. | Project administration record
Baseline: | Baseline: 0
Planned Target: | Planned Target: 75%
Indicator 1.1.2: | Indicator 1.1.2: ILO conducts SIYB training to 1200 beneficiaries | 1,405 950 women (67% of participants) 149 refugees (37 women, 112 men) 47 PLHIV 15 PWD |  | 1,405 950 women (67% of participants) 149 refugees (37 women, 112 men) 47 PLHIV 15 PWD | The project negotiated fees with the training providers and achieved higher value for money. | Project administration record
Baseline: | Baseline: 0
Planned Target: | Planned Target: 1200
Indicator 1.1.3: | Indicator 1.1.3: UNDP conducts training to 800 people | to be updated | Basic Entrepreneurship Training provided for 711 people including: 541 women, including 5 transgender; 546 youths; 202 people living with HIV & key population; 20 people with disabilities | Basic Entrepreneurship Training provided for 711 people including: 541 women, including 5 transgender; 546 youths; 202 people living with HIV & key population; 20 people with disabilities | Delay in implementation due to COVID-19 pandemic related restrictions, Some service providers didn't receive the target participants | Project administration record
Baseline: | Baseline: 0
Planned Target: | Planned Target: 800
Indicator 1.1.4: | Indicator 1.1.4: UNHCR and ILO conducts business development training for 30 women refugees | 37 |  | 37 |  | Project administration record
Baseline: | Baseline: 0
Planned Target: | Planned Target: 30
Indicator 1.1.5: | Indicator 1.1.5: UNDP conducts intensive training: Youth-led/women-led enterprises/start-ups through boot camp/mentoring/accelerator programs | 98 |  | 98 | Co-organized a venture competition and pre accelerator program to 24 women led-enterprises. Project invited 74 youth to benefit from youth entrepreneurship boot camp. | Project administration record
Baseline: | Baseline: 0
Planned Target: | Planned Target: 70
Indicator 1.1.6: | Indicator 1.1.6: ILO conducts intensive business coaching to 120 beneficiaries | 166 |  | 166 | The project negotiated fees with the training providers and achieved higher value for money. | Project administration record
Baseline: | Baseline: 0
Planned Target: | Planned Target: 120
Output 1.2
Indicator 1.2.1: | Indicator 1.2.1: Skills training for 100 women refugees | The project provided 184 refugees with skills training (95 refugees completed digital marketing training, 59 refugees Wordpress for E-commerce training, and 30 refugees barista training). 63 of them were women. |  | The project provided 184 refugees with skills training (95 refugees completed digital marketing training, 59 refugees Wordpress for E-commerce training, and 30 refugees barista training). 63 of them were women. | Effective ILO-UNHCR collaboration in planning, UNHCR's efforts to reach out refugee communities | Project administration record
Baseline: | Baseline: 0
Planned Target: | Planned Target: 100
Indicator 1.2.2: | Indicator 1.2.2: ILO-UNAIDS: Organize skills training for 100 people living with HIV and 100 participants from key populations that are most vulnerable to HIV | 132 PLHIV and key populations |  | 132 PLHIV and key populations | With only 6 months to complete training and demonstrate livelihood improvements immediately after the training, the project needed to be very creative in designing training and selecting participants to generate intended outcomes. When it is combined with pandemic situation and the geographic focus on East Indonesia, it further limited flexibility in training implementation. Carefully selecting right participants with the right attitude, motivation, and readiness to implement the skills gained from this training limited the number of beneficiaries the project could reach. The project provided digital skills training, fashion design training and other livelihood training for PLHIV and key populations. | Project administration record
Baseline: | Baseline: 0
Planned Target: | Planned Target: 200
Indicator 1.2.3: | Indicator 1.2.3: ILO: Organize skills training for at least 1350 rural residents, women and youth | - 1,099 cis- and transgender female (including 23 transgender female); - 1,314 rural residents; - 843 youth; - 167 people with disabilities. |  | - 1,099 cis- and transgender female (including 23 transgender female); - 1,314 rural residents; - 843 youth; - 167 people with disabilities. | Careful selection of competent training providers and timely monitoring of progress helped overshoot the target | Project administration record
Baseline: | Baseline: 0
Planned Target: | Planned Target: 1350
Output 1.3
Indicator 1.3.1: | Indicator 1.3.1: 6,000 beneficiaries improve their understanding on inclusiveness and non-discrimination, as well as their ability to spot malpractices at work. | 169,288 participants / viewers / listeners. 1,216 men and 1,585 women registered and directly participated in webinars through Zoom. Gender breakdown of the viewers on YouTube is unknown. |  | 169,288 participants / viewers / listeners. 1,216 men and 1,585 women registered and directly participated in webinars through Zoom. Gender breakdown of the viewers on YouTube is unknown. | Contents of webinars and awareness raising material are developed to attract attention of target audience. Engagement of active partners so helped to reach out far more than the target number of people. | Project administration record
Baseline: | Baseline: 0
Planned Target: | Planned Target: 6000
Indicator 1.3.2: | Indicator 1.3.2: ILO: At least 85% of employers can spot mal practices and know what to do to prevent discrimination and promote inclusiveness at work. (Quiz administered to webinar participants) | On average, 84.8% of the webinar participants answered right to quiz |  | On average, 84.8% of the webinar participants answered right to quiz |  | Project administration record
Baseline: | Baseline: 0
Planned Target: | Planned Target: 85%
Indicator 1.3.3: | Indicator 1.3.3: ILO: At least 85% of workers demonstrate sufficient knowledge on non-discrimination at work (Quiz administered to participants) | 98.8% of the participants answered to a survey that the meeting helped them understand more about gender equality, inclusion, and non-discrimination in the workplace. |  | 98.8% of the participants answered to a survey that the meeting helped them understand more about gender equality, inclusion, and non-discrimination in the workplace. |  | Project administration record
Baseline: | Baseline: 0
Planned Target: | Planned Target: 85%
Indicator 1.3.4: | Indicator 1.3.4: UNAIDS: At least 10 trainers are ready to carry out awareness raising sessions | 15 |  | 15 | 15 individual from the PLHIV and KPs communities have been trained to carry out awareness raising sessions on inclusive workplace. | 15 individual from the PLHIV and KPs communities have been trained to carry out awareness raising sessions on inclusive workplace.
Baseline: | Baseline: 0
Planned Target: | Planned Target: 10
Indicator 1.3.5: | Indicator 1.3.5: UNAIDS: At least 2,000 people accessed the learning platform in 2021 | 73 Number of visitors of the online learning platform as of 1 January 2022 (https://kusumabuana.org/ruang-belajar/) | 705 Number of visitors of the learning platform as of July 2022. 255 Total engagement on instagram on the promotion of the online learning platform on inclusive workplace. | 1033 | The learning platform was launched in December 2021. Throughout January-April 2022, UNAIDS coordinated with the implementing partner to increase the numbers of visitors of the learning platform through promotion on social media and during the series of workshops on inclusive workplace with human resource managers and labor inspectors in 3 provinces (Banten, DKI Jakarta, and West Java). Although the target has not been reached (1.033 out of 2.000), UNAIDS and the implementing partner are still and will continue to promote the use of the online learning platform through various social media channels regularly. UNAIDS and the implementing partner have discussed and raised this issue as reflection at our closing meeting, back in May 2022. | Insight report from the website and instagram account page.
Baseline: | Baseline: 0
Planned Target: | Planned Target: 2000
Indicator 1.3.6: | Indicator 1.3.6: UNAIDS: Policy advocacy campaign reaches at least 2,000 employees through KADIN and APINDO | 13622 |  | 13622 | Total numbers of people reached by the policy advocacy on inclusive workplace that include the government, companies, business groups, trade unions, and communities of PLHIV, KPs, and people with disabilities. | Attendance list of meetings and webinars. Internet-based outreach (Instagram, twitter, and YouTube).
Baseline: | Baseline: 0
Planned Target: | Planned Target: 2000
Indicator 1.3.7: | Indicator 1.3.7: ILO: Policy advocacy campaign reaches at least 2,000 workers through partner trade unions | 2,206 workers participated in workplace meetings. The campaign on gender equality and inclusive workplaces have generated 1,797 social media posts; shared 6,457 times; received 53,593 likes and 9,868 comments. |  | 2,206 workers participated in workplace meetings. The campaign on gender equality and inclusive workplaces have generated 1,797 social media posts; shared 6,457 times; received 53,593 likes and 9,868 comments. | 100 trade union members were engaged as campaigners who influenced at least 2,000 co-workers | Project administration record
Baseline: | Baseline: 0
Planned Target: | Planned Target: 2000
Indicator 1.3.8: | Indicator 1.3.8: A regulatory framework is established to promote workplace policy on Health (HIV, TB, COVID19, etc.). | A policy paper on inclusive workplace is produced. | A declaration of commitment and a set of action plan to promote the creation of workplaces that are inclusive are developed and agreed upon by human resource managers and labour inspectors in three provinces (Banten, DKI Jakarta, and West Java). | - A policy paper on inclusive workplace is developed. - A declaration of commitment and a set of action plan to promote the creation of workplaces that are inclusive are developed and agreed upon by human resource managers and labour inspectors in three provinces (Banten, DKI Jakarta, and West Java). | A policy paper on inclusive workplace consisting of situational analysis, gap & challenges, and recommendations has been produced and finalized in December 2021. As a follow up to the policy paper, throughout January-April 2022, UNAIDS and the implementing partner conducted a series of workshops on inclusive workplace with human resource managers and labour inspectors in 3 provinces (Banten, DKI Jakarta, and West Java). Following the series of workshops, a declaration of commitment and action plan were developed by labour inspectors and human resource managers in 3 provinces as the main reference for a regulatory framework on inclusive workplace. | Project report.
Baseline: | Baseline: 0
Planned Target: | Planned Target: 1
Indicator 1.3.9: | Indicator 1.3.9: At least 10 actions are agreed among government, workers and employers. | Actions to accelerate an inclusive recovery to be discussed at a high-level event in 2022 | Representatives of the government, workers' organization, and employers' organization reported or pledged 13 actions | 13 actions pledged/conducted Government: 1. Commitment to expand and ensure access to mass vaccination, to mitigate new variants, and to reach herd immunity. The increasing percentage of the vaccinated population will enable the government to gradually allow economic activities to start. 2. Strengthen community resilience through the creation of job opportunities and improved productivity as well as the development of better insurance schemes at all levels (micro to macro), from agriculture insurance for farmers, to social security insurance. 3. Build adaptive public assistance programs. Improving public assistance mechanisms to make it more flexible and to respond better to more/graver disturbances in the future. 4. Combine disaster risk reduction mechanisms with social protection and climate change adaptation efforts, from coping to transformative efforts. 5. Focus on several other game changers to strengthen the country’s resilience: 1) improvement of human resources, 2) promotion of green economy as part of climate change adaptation efforts including circular economy and waste management, 3) promote and accelerate digital transformation, 4) IKN (the development of new capital to accelerate economic development in Eastern Indonesia and remote areas). Trade union (Elly Rosita, KSBSI): 1. Conduct social dialog (bipartite) and develop collaboration with businesses, to find ways in which workers can contribute to the survival of businesses that in the end will ensure job opportunities for workers. 2. Encourage workers to open communication with the company to voice their grievances related to job losses due to the pandemic and to negotiate with the company in finding win-win solutions for both parties. Inform workers of the situations to help them understand how and to what extent their demands can be met by the company considering the economic situation due to Covid-19. 3. Introduce emerging new job opportunities, e.g. green jobs and digital jobs, to workers who lose their jobs, support adaptation process for workers to embrace new job opportunities, and support re-skilling of workers through BLKs. 4. Taking steps to ensure protections and decent wages for workers in the emerging work fields such as digital works. 5. Promote and ensure gender equality in the economic recovery from Covid-19. APINDO 1. Comply with government regulations and restrictions related to Covid-19 pandemic while at the same time try to address demands from trade union 2. Promote technology innovation and adoption of new technologies by business entities to adapt to the new mode of work (virtual) and the new trends of business transactions (digital) 3. Conduct upskilling and reskilling workers to enable them to adapt to new technology needs and demands. |  | Project administration record
Baseline: | Baseline: 0
Planned Target: | Planned Target: 10
Indicator 1.3.10: | Indicator 1.3.10: A regulatory gap analysis is conducted, and equal employment opportunity (EEO) guidelines are updated | EEO guideline is updated. https://www.ilo.org/jakarta/info/public/pr/WCMS_847252/lang--en/index.htm |  | EEO guideline is updated. https://www.ilo.org/jakarta/info/public/pr/WCMS_847252/lang--en/index.htm |  | Project administration record ILO website
Baseline: | Baseline: EEO guideline is not updated since 2004
Planned Target: | Planned Target: EEO guideline is updated
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant.
46 impact stories are published on the project web site:
https://employmentandlivelihood.id/results/stories
27 Video clips are also available on the web site:
https://employmentandlivelihood.id/videos
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well as picture material please make sure you include all credits and share them in high resolution.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board
Please visit the project web site:
https://employmentandlivelihood.id/