## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to the secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality results reports please follow the next guidelines: a) The narratives should be a well written, succinct summary clarifying what was done during the reporting period and the results achieved. It should highlight the JP achievements. It should also specify scope and beneficiaries. b) Factual, evidence-based reporting against the outcome and output and corresponding indicators in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not should be provided. d) Factual, evidence-based reporting against the outcome results and its alignment with the overall SERP joint workplan, and linkage to reporting on global-level SERP indicators. e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not. g) Reflect on innovation. Avoid generic and standard descriptions. Rather, present well documented features of successful innovative solutions truly new for you and which could enable replication efforts.
3 | Please fill out all sections of the reporting template before submitting to the secretariat via email to: nina.andersen@undp.org and cc.: maria.herrera@undp.org
B
DEADLINE: MARCH 31 ST, 2022
1 | ALL projects receiving funds in late 2020 and in 2021 must complete an ANNUAL report as per the end of the calendar year with a reporting period : date of start until 31 December 2021.
2 | The joint programmes which completed their activities in 2021 should deliver a FINAL report by March 31 at the latest and will not be obligated to provide an annual report.
3 | The joint programmes completing activities in 2022 will be asked to submit a FINAL report (by 31 August 2022)
4 | ALL projects must report number of direct beneficiaries.
5 | ALL projects must provide an update on project indicators

## General Information
Programme Title & Project Number |  | Programme Duration
Programme Title: | Acceleration of a Digital Social Services Delivery Model to address the needs of the most vulnerable in Kazakhstan | Overall Duration (months) | 8 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 02.12.2021
MPTF Office Project Reference Number: | 00129533 | Original End Date (dd.mm.yyyy) | 30.06.2022
Country | Kazakhstan | In case of NCE Current End date(dd.mm.yyyy) | 31.07.2022
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNDP UNESCO UN WOMEN | National counterparts (government, private, NGOs & others) and other International Organizations | Ministry of Labor and Social Protection of Population, Ministry of Digital Development, Innovation and Aerospace Industry, National Information Technologies JSC, Ministry of Health, Ministry of Justice, Ministry of Internal Affairs, Ministry of Education and Science, Human Resources Development Centre JSC
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19 (up to 500 words). | The COVID -19 MPTF-funded Programme in Kazakhstan developed an innovative Family Social Card digital platform capable of collecting, integrating, and processing information on the most vulnerable groups in Kazakhstan to provide targeted social support to key groups. The implementation of the programme consists of four main parts: Developing the Family Social Card methodology and obtaining data from government agencies; developing the scoring model to categorize families by social risk; creating a visualized dashboard to aid decision-making; and introducing a mobile application for social workers to monitor the provision of social services. The core of the Family Social Card methodology was a detailed gender-sensitive analysis of the social sector in the areas of health, education, social protection, employment, finance, justice, and agriculture. This analysis led to the compilation of 80 indicators that make it possible to describe a person's social status, taking a holistic view. Based on these 80 indicators, a scoring model was developed to classify families by social risk into five main categories: A - good, B - satisfactory, C - unsatisfactory, D - crisis, E - needs urgent help. Each category is associated with a specific state support measure aimed at improving the person's livelihood, i.e. from category E to category D and finally to category A. The centerpiece of the programme is the introduction of the Family Social Card dashboard - a tool for public officials that has real-time data to identify vulnerable families. The dashboard displays geospatial data and information about the family based on 80 indicators covering socioeconomic status, housing, education, social protection, and health needs, among others. This automated visualization was made possible through the integration of government databases, which eliminated the isolated approach and segmented understanding of families' vulnerabilities. A mobile application for social workers was piloted at the Nur Sultan Center for Social Service Delivery to improve efficiency, increase transparency, and improve monitoring of services. The mobile application is the first of its kind in Kazakhstan, functioning as a website and an application. It allows managers to assign tasks and create customized schedules for social workers based on families' needs. This tool eliminates the need for the current paper documentation, which increases the efficiency of work and makes it possible to create analyzes of services with one click. The developed Family Social Card digital platform is a govtech solution that helps decision-makers access consolidated data on vulnerable families in real time, with the aim of proactively providing social services to prevent the socioeconomic conditions of families from deteriorating. The solution provides a customized step-by-step scenario that combines government efforts in assisting families in need. Innovative tools such as AI, machine learning, and Big Data will help better analyze data and identify concrete social support measures to avoid duplication and improve satisfaction with the services provided.
2 | Purpose | Please describe the project general objective specifying its link to COVID-19 response. | The project aims to create a holistic, gender-sensitive, seamless and efficient system of effective social support for the most vulnerable groups in society in Kazakhstan, mitigating the impact of socio-economic shocks and upholding the principle UN of "leaving no one behind." The project prevents families from falling into the poverty trap and empowers local decision makers by providing them with real-time data on population categories in urgent need of support, which is a response to various shocks, including COVID -19 pandemic.
3 | Results: Outcome Level | Please include narratives describing the main project achievements against the project's overall goal (up to 300 words) | The overall goal of the project was to reduce inequalities and ensure inclusive delivery of social protection services to all. This goal was achieved as the Family Social Card platform enables local and state agencies to proactively deliver social assistance to those most in need. The platform consolidates real-time data from state databases and ensures transparent access to information about the socioeconomic status of families in Kazakhstan. This transparency of data on families in urgent need of state support ensures a transparent flow of public funds that eliminates any scope for rent-seeking. Methodologically sound categorization of families by level of social risk allows for targeting of support to those in urgent need (category D and E), while further reducing the vulnerability of those in other categories who are struggling to improve. The mobile application for social workers empowers the social protection workforce by improving the efficiency of services provided and increasing satisfaction with overall quality. Digitised collection of data on the types of services provided, the number of people targeted, and the resources needed allows for better analysis and recommendations to improve the way social services reach families in the field. The application allows social workers to reach families even in remote areas, as the tool has a geospatial feature that ensures monitoring of services provided based on location and evidence submitted. At the heart of the mobile application is the family feedback mechanism, as the tool allows the more than 20,000 social workers across the country to enter missing or incorrect data to improve the accuracy of government data.
3.1 | Results: Output Level | Please include narratives describing the main annual/ final results of each output included in the project document (up to 200 words) | The Family Card dashboard has been developed. Preparatory work has been done for the launch of the Family Social Card. This includes creating a scoring model to assess the level of vulnerability, updating data on families from the public registry to avoid data duplication, and developing a scientific methodology for the Family Social Card. The dashboard was initially tested. After the model proved successful, all consolidated government data on nearly 6 million families were included in the analysis. The dashboard has been rolled out and is currently available to decision makers, including government officials in districts and rural areas. The Family Social Card dashboard is available in a visualized form with heat maps based on the level of vulnerability of families. The dashboard allows selection from 80 indicators, including location, income, health status, etc., to visualize families and retrieve information about their condition on each indicator. A mobile application for social workers was created and tested in Nur-Sultan. The functionality of the application was adapted based on feedback from social workers and managers of the Center of the provision of social services.
3.2 | Results: Gender | Please include project Gender results and its linkage with COVID- 19 response. If applicable, refer to the project's gender equality marker and any impacts they may have had on programming quality and results (up to 150 words). | One of the most important consequences of COVID -19 was the increase in domestic violence against women. Digitalization of special social services for survivors of domestic violence is critical, especially in situations similar to the recent COVID -19 lockdowns when access to quality basic services is limited to help women who have no way to cope with or escape violence. Given the existing gender digital divide, women and girls, especially those facing multiple forms of discrimination, may not have access to a mobile phone, computer, or the Internet to access services or use them safely at home, as they may be closely monitored by the perpetrator and other family members. Therefore, it is important to ensure that the social worker has resources to contact and monitor such families and that the protocol for identifying survivors of violence is well thought out.
3.3 | Results: Direct Beneficiaries | Please include total number of DIRECT BENEFICIARIES disaggregated by gender, age , location (rural, urban, any other location). Please avoid duplicating beneficiaries ensuring the dissagregated data adds to the total presented. | 5 965 499 families were mapped to the Family Social Card who are direct beneficiaries of the services.
3.4 | Results: Indirect Beneficiaries | Please include total number of INDIRECT BENEFICIARIES. Please clarify if these are estimated and/or verified. If possible, disaggregate beneficiries by gender. | Around 11 million people are indirect beneficiaries of the programme (verified), including 2,242,000 people receiving pension; 532,000 people receiving disability benefits; 1,330,670 people receiving child support; 5,000,000 people registered with acute health conditions; 500,000 participants of employment programmes; 900,000 people receiving targeted social assistance, among others.
3.5 | Do not Harm | Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention. ( up to 100 words) | The Family Social Card intervention contributes to peace following “Do no harm” approach as the instrument targets most vulnerable groups of population reaching them with services in a proactive manner. The instrument reduces the possibility of conflict due to low socio-economic conditions as the government identifies families at risk and provides them with necessary services to prevent them falling into deeper crisis.
3.6 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken to achieve the expected results) Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms(use up to 150 words). | The main challenge was the short timeframe for project implementation, which was successfully overcome by thorough planning of project activities and discussion of project components with potential partners during project design. Amidst the developments in January, the focus of government agencies and resources was on dealing with the aftermath of the protests and unrest. As a result, there were difficulties in operational activities with government agencies, which delayed the negotiation and approval of documents. Another challenge was a change in the approach to the work due to the partner's refusal to conclude a responsible party agreement despite the fact that it was discussed early in the process. UNDP had to redesign the approach and take over the coordination and organization work entirely at the expense of its staff and the experts involved. In particular, the procurement process was organized to obtain 2 companies and 11 experts within an extremely tight deadline.
3.7 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) (up to 250 words) | The key lesson for the programme is to bring a national partner on board at the planning stage of the project so that they are engaged and accountable for results once the work plan is agreed upon. The programme ensured that national partners are involved at the stage of receiving deliverables from providers, so that the quality of the deliverables is relevant and applicable to the existing national context and eliminates the risk of parallel systems. It was also a lesson learned to budget resources for awareness raising and communication and knowledge products about the programme, including photo, video, and event costs. From an operational perspective, for a short duration project such as this, it is better to include all implementing partners in the project document so that partnerships can be based on agreement with implementing partners, rather than conducting a procurement that could take longer to complete and thus take up the already short timeframe of the project. The early involvement of the implementing partners in the project planning was very helpful for the project implementation.
3.8 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 250 words) | The project was carried out in close collaboration, co-creation, and co-ownership with national partners at the highest level, who helped shape and share responsibility for it. The project received high-level support and recognition from the President of Kazakhstan, who mentioned the Family Social Card in his annual State of the Nation Address, highlighting its catalytic effect in improving the well-being of the population and providing uniform, targeted social assistance. The government's main partners for the Family Social Card instrument are two ministries - the Ministry of Labor and Social Protection of the Population and the Ministry of Digitalization, Innovation and Aerospace Industry. In addition to these key partners, which ensure sustainability and ownership of the product at the national level, the project team in Kazakhstan has worked with other key partners, such as the Ministry of Education and Science, the Ministry of Internal Affairs, the Ministry of Justice, the Ministry of Finance, the Ministry of Health, and their sub-organizations. The project identified innovative partnerships with local experts and companies in the field of data science, machine learning, and information technology that allowed the product to be developed with full local expertise. The Fund's financial support facilitated the timely recruitment of various stakeholders, as the experts had not only theoretical knowledge of social protection systems, but also practical experience in the Kazakh context and existing relationships with key partners, which enabled the development of a viable product. The intervention complements the activities of the national government, as the Family Social Card is now included in the National Action Plan, which is based on the President's State of the Nation Address.
3.9 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken (up to 200 words). | UNDP Kazakhstan Country Office is part of an evaluation of UNDP support to social protection to be presented to the UNDP Executive Board in June 2023. The evaluation is being conducted by the Independent Evaluation Office (IEO), which is currently requesting documents and plans to conduct interviews with focal points in several countries. Together with Montenegro, Kazakhstan has been selected in the region for a detailed evaluation. The country-level analysis will provide a better understanding of the evolution of UNDP support, what ensures implementation and success, and what can be improved by reflecting on the factors that influence performance. UNESCO: Consultations, focus groups, and surveys were conducted with government officials, social workers, school psychologists, and parents from vulnerable groups to capture and assess the current status of education services provided.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place (Up to 100 words). | No major programmatic adjustments took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | UNDP: Due to the change in the original plan to attract a responsible party, UNDP took over all procurement activities and work with experts and suppliers, saving significant resources and allowing the project to be completed in a timely and efficient manner. UNESCO: Due to the shortened timeframe of the project, it was planned to work only on the methodology to identify educational weaknesses and risks of families, but as a result of the procurement carried out, some resources could be saved within the project. Therefore, it was decided to provide direct support to vulnerable groups by training parents who have children with disabilities in education, psychosocial and legal support to strengthen their resilience to future crises. In addition, art therapy workshops were offered to children with disabilities to enhance their cognitive and social development after the pandemic.

## Project Indicators
Please include ALL indicators in the project document. Include the indicators and Baseline, Planned Target and Actuals for both OUTCOME and OUTPUT levels. "Actuals" refer to the total figures achieved for each indicator. Include separate actuals for 2021 and for 2022 (if applicable). Explain if targets were not achieved. Include means of verification. Use as many outputs cells as needed to present all project indicators.
| INDICATORS DESCRIPTION AND DATA | DATA: ACTUALS 2021 | DATA: ACTUALS 2022 (if applicable) | TOTAL actuals (agreggated 2021 and 2022 if applicable ) | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1 The Family Social Card platform and applications are developed, Successfully launched, and tested by the government.
Indicator:
Baseline:
Planned Target:
Output 1.1 Preparatory activities for the platform creation are conducted, including the understanding of current processes, development of mathematical models, and scoring mechanisms.
Indicator 1.1.1: | Number of Ministries the databases of which are integrated to the Family Social Card platform |  |  |  | Despite the plan to integrate 3 databases, the databases of 8 Ministries were integrated during the project. It helped to increase the number of parameters for identifying vulnerable families. | The information systems of government agencies are integrated through the e-Government Gateway into Smart Data Ukimet (Government). The Operator of the Smart Data Ukimet is 'National Information Technologies' JSC
Baseline: | 0 | n/a
Planned Target: | 3 | n/a | 8 | 8
Indicator 1.1.2: | Number of vulnerable individuals mapped into the Family Social Card platform |  |  |  | During the planning of the results, it was assumed that an analysis on a limited number of vulnerable persons would be carried out in the pilot mode. The successful integration of 8 databases made it possible to reach significantly more vulnerable people (including in the context of families). | Source of information: Smart Data Ukimet data (provided by "National Information Technologies' JSC)
Baseline: | 0 | n/a
Planned Target: | 500000 | n/a | 3996702 | 3996702
Output 1.2 Family Social Card platform and consequent products (dashboards, mobile/ tablet applications) are developed.
Indicator 1.2.1: | Number of social workers using the Family Social Card mobile/tablet application |  |  |  | In coordination with the Ministry of Labor and Social Protection, UNDP provided a pilot in 1 region for 140 social workers. At the same time, the Ministry has planned a more large-scale implementation at the expense of budgetary funds. The inclusion of 140 employees was sufficient to demonstrate the effectiveness of the application. | Source of information: Smart Data Ukimet data (provided by "National Information Technologies' JSC). Verification was carried out by issuing logins/passwords for social workers
Baseline: | 0 | n/a
Planned Target: | 200 | n/a | 140 | 140
Indicator 1.2.2: | Number of public sector staff users of the Family Social Card platform |  |  |  | Thanks to coordination with 8 ministries and local municipal bodies, it was possible to provide large-scale access to the system for all stakeholders | Source of information: Smart Data Ukimet data (provided by "National Information Technologies' JSC). Verification was carried out by issuing logins/passwords for social workers
Baseline: | 0 | n/a
Planned Target: | 90 | n/a | 5206 | 5206
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant.
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well as picture material please make sure you include all credits and share them in high resolution.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board