## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to the secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality results reports please follow the next guidelines: a) The narratives should be a well written, succinct summary clarifying what was done during the reporting period and the results achieved. It should highlight the JP achievements. It should also specify scope and beneficiaries. b) Factual, evidence-based reporting against the outcome and output and corresponding indicators in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not should be provided. d) Factual, evidence-based reporting against the outcome results and its alignment with the overall SERP joint workplan, and linkage to reporting on global-level SERP indicators. e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not. g) Reflect on innovation. Avoid generic and standard descriptions. Rather, present well documented features of successful innovative solutions truly new for you and which could enable replication efforts.
3 | Please fill out all sections of the reporting template before submitting to the secretariat via email to: nina.andersen@undp.org and cc.: maria.herrera@undp.org
B
DEADLINE: MARCH 31 ST, 2022
1 | ALL projects receiving funds in late 2020 and in 2021 must complete an ANNUAL report as per the end of the calendar year with a reporting period : date of start until 31 December 2021.
2 | The joint programmes which completed their activities in 2021 should deliver a FINAL report by March 31 at the latest and will not be obligated to provide an annual report.
3 | The joint programmes completing activities in 2022 will be asked to submit a FINAL report (by 31 August 2022)
4 | ALL projects must report number of direct beneficiaries.
5 | ALL projects must provide an update on project indicators

## General Information
Programme Title & Project Number |  | Programme Duration
Programme Title: | Strengthening economic resilience and food security for women Home Based Workers and women farmers | Overall Duration (months) | 12 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 01.07.2021
MPTF Office Project Reference Number: | MPTF_00209: UN COVID-19 MPTF | Original End Date (dd.mm.yyyy) | 31.3.2022
Country | Pakistan | In case of NCE Current End date(dd.mm.yyyy) | 30.6.2022
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UN Women , UNFAO | National counterparts (government, private, NGOs & others) and other International Organizations | Ministry of National Food Security and Research Islamabad,Agriculture and Livstock Departments KP and Balochistan, Pakistan Village Development Program (PVDP) NGO partner Balochistan Rural Support Program (BRSP) NGO patner
Report Cleared By
o Name: | Julien Harneis
o Title: | Resident/Humanitarian Coordination (UN Pakistan)
o Email address: | harneis@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19 (up to 500 words). | The overall objective of the project was to strengthen economic resilience and food security for women Home Based Workers (WHBWs) and women farmers whose livelihoods have been affected by the Covid-19 pandemic, through linkages to existing government programs, cash grants, and skills training for initiating micro-enterprises. The project was being implemented in three districts of Khyber Pakhtunkhwa (Peshawar, Kurram and Swabi) and three districts of Balochistan (Quetta, Pishin and Lasbela).Through the project framework the project contributed to the interagency collaboration and partnership through alignment with the United Nations Sustainable Development Framework UNSDF 2018-2022” The project also promoted the ‘One UN’ approach, with UN agencies working in joint collaboration to achieve results under the overall coordination of the Resident Coordinator’s Office The period Jannuary-June 2022 followed an expedited plan where all the targets set for the project were either fully or over-achieved. As the groundwork in the previous quarter had been completed, the emphasis was laid on timely accomplishment of envisaged results. The project demonstrated considerable results following contextual realities driven and impact-oriented approaches. During the period, the major activities carried out by UN Women/FAO were; obtaining No-objection Certificate (NOCs) from the government for operating in the target districts, union/village councils identification/selection, coordination with all stakeholders to ensure complementarity of interventions at the field level, community mobilization, formation of village/union council committees, baseline survey and validation workshops, selection of partners, connection of WHBWs with available social safety nets operational in the country, awareness sessions with community, launching of Radio campaigns, cash transferring ,distribution of inputs, and training for women famers. Major challenges for UN Women included delayed acquisition of NOC to work in one of the target districts of Khyber Pakhtunkhwa i.e. Kurram which was ultimately dropped and targets shifted to other two districts; COVID-19 Omicron variant wave which prevented/delayed the field teams and UN Women provincial offices from visiting the field to roll out activities and monitor progress; cultural barriers to access and include women in the project activities, and delay in the selection of the financial service provider for the dissemination of cash grant. To overcome the delay challenge, No Cost Extension request was put up by UN Women through RCO which was granted by MPTF and the activities were completed as stipulated.
2 | Purpose | Please describe the project general objective specifying its link to COVID-19 response. | The purpose of the project was to strengthen economic resilience and food security for women Home Based Workers and women farmers whose livelihoods has been affected by the Covid-19 pandemic due to lockdowns and resultantly suspension/shrinking of economic activities. The project offered support through linking women beneficiaries with the existing programs, provision of cash grants provision of agriculture inputs i.e., distributing seeds,distribution of food processing kits,goats and skills trainings for revitalizing and up-scaling existing and initiating new micro-enterprises. The theory of change was that when women are provided with livelihood opportunities and social protection, they can become economically empowered, can supplement the family’s income, increase their food security, and contribute to lifting their families out of poverty. The provision of more opportunities to women in the form of education, better health, possession of assets, provision of credit, employment opportunities and political empowerment starts a 'virtuous cycle' for their family and for the country. In times of increasing food insecurity, it is important to ensure that the purchasing power of households is not affected tremendously. Women headed households, women with disabilities and transgender persons are at a greater risk of food insecurity which were specifically identified and targeted within the categories of HBWs and women farmers. In addition to immediate goals, the project included the gender transformative goal of sensitizing men towards increased responsibilities of women during lockdowns and encouraging them to share the caregiving and domestic responsibilities through attitude and behavior change and encourage them to allow women control over their income.
3 | Results: Outcome Level | Please include narratives describing the main project achievements against the project's overall goal (up to 300 words) | Main achievements included the connection of more than 10,000 WHBWs with available social safety nets operational in the country through community level awareness raising campaigns and direct facilitation which will lead to a sustainable flow of government run poverty alleviation and humanitarian support grants to these excluded women. One-time electronic cash grant transfer of PKR 17,000 to 4,500 WHBWs to inject in their family and businesses that were affected during to COVID 19 lockdowns has been used as a tool for economic recovery. Women who received them were keen and motivated to start businesses, which can fuel economic growth. Enhancing economic resilience through economic recovery solutions i.e., skills trainings supplemented with tool kits and linking WHBWs to local markets and other private companies to become part of their supply chains is deemed to have long-term impact on enhancing family incomes, food security and sustainable incomes. Radio campaigns were broadcasted through local radio channel targeting 5 million men and boys sensitizing them on caregiving in domestic responsibilities. 5 million+ digital messages were sent to women that enhanced their awareness on maternal and child health and nutrition as well as information on how to deal with the health impacts of the COVID19 pandemic. 566 hygiene/dignity kits were distributed among women with disabilities (WWDs) for increased/improved menstrual health. 5,000 HHs received vegetable kits each comprising of Tomato, Bottle Gourd, Bitter Gourd, Coriander and Peas. Additionally, 1,802 HHs received one goat each along with a feeding tub to start enterprise on small scale level 750 food processing kits were also distributed among women. These interventions had a direct and positive impact on the food security and nutritional status of the farmer communities. In collaboration with Agriculture Department, FAO organized different trainings and 500 women framers were trained.
3.1 | Results: Output Level | Please include narratives describing the main annual/ final results of each output included in the project document (up to 200 words) | The activities contributed considerably to the respective output level results. Through greater access of project beneficiaries to social safety nets and agri interventions it is expected that they will supplement family income and keep food purchasing power constant in times of economic crises. WHBWs and women farmers were equipped with much needed skills on entrepreneurship and business development supplemented with the one-time cash grants to revitalize their micro-enterprises lost during COVID. Through a rapid assessment exercise with 319 cash grant beneficiaries, 90% reported intentions to utilize the money in the current business and use for purchasing raw material, while profit would be utilized in dealing with inflation, adding in family income, and purchasing grocery items. Women farmers were also found satisfied with seeds, goats and food processing kits. During the project span beneficiaries were regularly provided with an opportunity to interact with the markets and it was noted that few of them were able to sell their products through such connections and increase their employability skills too. The media campaign was instrumental to sensitize men listeners to re-evaluate their current contributions in caregiving and domestic responsibilities at the household and work towards changing their behavior patterns to a more gender friendly division of labor. The project consistently adhered to the principle of leaving no one behind by targeting women from the least developed and vulnerable communities. 566 women with disabilities, both physical and mental, were identified and provided with Menstrual Hygiene Management (MHM) kits. It is hoped that these women beneficiaries are now aware of the importance of health and hygiene and feel included and socially empowered.
3.2 | Results: Gender | Please include project Gender results and its linkage with COVID- 19 response. If applicable, refer to the project's gender equality marker and any impacts they may have had on programming quality and results (up to 150 words). | Gender equality and women's empowerment is the principal objective of the project that focuses specifically on women Home Based Workers and women farmers. The direct beneficiaries are women whose livelihoods were affected/disrupted by the COVID 19 pandemic; and revitalization of the lost livelihoods will predominantly contribute towards COVID 19 response and recovery. The project includes the gender transformative goal of sensitizing men towards increased responsibilities of women during lockdowns and encouraging them to share the caregiving and domestic responsibilities through attitude and behaviour change.
3.3 | Results: Direct Beneficiaries | Please include total number of DIRECT BENEFICIARIES disaggregated by gender, age , location (rural, urban, any other location). Please avoid duplicating beneficiaries ensuring the dissagregated data adds to the total presented. | Please refer to beneficiaries sheet
3.4 | Results: Indirect Beneficiaries | Please include total number of INDIRECT BENEFICIARIES. Please clarify if these are estimated and/or verified. If possible, disaggregate beneficiries by gender. | Please refer to beneficiaries sheet
3.5 | Do not Harm | Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention. ( up to 100 words) | The do no harm principle was adhered to and the most marginalized and vulnerable women of various ethnic groups were included. A selection criterion was developed for identifying the beneficiaries. The selection prioritized high poverty rates, women headed households, women with disabilities and women who have never been part of any public safety net programmes. To ensure the support of men folks and avoid resistance from their towards women's engagement in the project activities, broader community level stakeholders were engaged through community participation processes including local leaders/influencers, men household heads and immediate men family members through awareness/sensitization sessions and media campaign.
3.6 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken to achieve the expected results) Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms(use up to 150 words). | The new COIVD-19 Omicron Variant wave prevented the field teams from visiting the field to roll out activities and monitor progress. The teams were vaccinated, and SOPs were followed to keep themselves as well as community members safe. NOC for District Kurram (for UN Women) was issued too late for the field level work to be conducted during the project period. The district was dropped, and its targets shifted the other two districts. Although both the agencies intended to align areas for project implementation, they were unable to do so because each agency had different outputs which required a different set of beneficiaries. Baseline results shared with each other, and joint baseline validation workshops conducted in both the provinces. Cultural constraints: accessing women to conduct HBW identification survey, in the two target districts, especially Swabi and Pishin was challenging. Women Social Organizers were taken on-board to fill out the HBW evaluation forms. For the cash transfer, verification of contact numbers of 40% HBWs was a time bound process. Responsible Parties hired more Social Mobilizers and announced Saturday as a working day; so, to meet the deadline of the activity. Due to the short project duration, the impact of the cash grant could not be captured and reported in the final report (though a rapid assessment was done, and findings included in this report). UN Women plans to do a follow-up after six months of the project’s conclusion to gauge the impact of the support extended.
3.7 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) (up to 250 words) | The project focused on the urgent and unmet needs of vulnerable and excluded WHBWs and women farmers whose livelihoods had been severely affected by the COVID pandemic. The emergency cash support and economic recovery solutions through skills enhancement, provision of tool kits and agri-inputs and connections with social services, markets and private sector proved to be an innovative model that could be replicated nationally and globally in similar circumstances due to immediate results produced under the current project. After receiving cash grants and agri-inputs coupled with skills on enterprise development, the beneficiaries intended to utilize the money in the current business and purchasing raw material, while profit was to be utilized in dealing with inflation, adding in family income, and purchasing edible items that could ensure food security in the times of crises. The two UN agencies brought together their comparative advantages to amplify the results and ensure cost and time efficiency. The combination of hard and soft components (soft skills trainings supplemented with cash grant and tool kits) complemented each other to demonstrate quick results in a short span of time and that’s what exactly was aimed. UN Women has already pitched this model to other donors for potential funding under the current floods’ emergency in the country which has affected the population including women whose livelihoods have been affected.
3.8 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 250 words) | The project from its inception worked very closely and strategically with relevant stakeholders i.e., government departments, civil society, and local community groups to create a sense of ownership among them which will ultimately add to the project’s sustainability. All the activities were framed in the manner that involved facilitation roles from the government service providers. Linkages of women beneficiaries with the available social services created partnerships with government social welfare and women development departments, EHSAAS/BISP (the country’s largest social safety net programme) and private sector companies. The collaboration and partnership with these institutions directly contributed to the project output and outcome level results as they supported project beneficiaries from their own schemes. The One-UN approach/partnership with FAO proved to be instrumental in amplifying results via synchronizing implementation approaches and build upon each other’s field presence and social capital present. Both agencies worked in close coordination, ensuring complementarity, at all the levels from planning to implementation and conclusion. The project has considerably responded to the pillar 3 of COVID 19 – Pakistan Socio-Economic Impact Assessment and Response Plan of 2020 - Economic Recovery: Protecting Jobs, Small and Medium Sized Enterprises and the most Vulnerable Productive Actors.
3.9 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken (up to 200 words). | A baseline study was conducted under the project both by FAO and UN Women. UN Women also conducted a rapid assessment to validate the effectiveness of the cash grant and skills trainings provided to the project beneficiaries.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place (Up to 100 words). | Nil
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | Total Project Budget - $1,700,000/ Final financial figure will be provided upon financial closure of the project.

## Beneficiaries
Direct Beneficiaries
| Khyber Pakhtunkhwa | Balochistan | Total | Remarks | Age brackets | PWDs
Women | 11479 | 9793 | 21272 | Project support activities | 18-55 years | 566
Women | 3 million | 2 million | 5 million | Media campaign | 18-55 years
Men | 3 million | 2.3 million | 5.3 million | Media campaign | 18-55 years
Indirect beneficiaries (@ 6.5 per household size)
| Khyber Pakhtunkhwa | Balochistan | Total | Remarks | Age brackets | PWDs
Men and women | 70070 | 60580 | 130650 | 6.5 per household size | includes all age brackets | Included in total
The breakdown of direct beneficiaries |  | Khyber Pakhtunkhwa | Balochistan
Number of women and excluded groups linked with available social services and operational social safety nets |  | 5071 | 5013
Number of women to whom one-time cash transfers are provided |  | 2800 | 1700
Number of women owned micro/small enterprises supported through economic recovery solutions to mitigate impacts of COVID19. |  | 200 | 100
Number of women trained on business development and entrepreneurial skills. |  | 150 | 50
Number of women-owned businesses linked with private sector companies. |  | 92 | 30
Number of disabled women provided with menstrual hygiene kits. |  | 416 | 150
Number of women assisted for small scale kitchen gardening, poultry, small ruminant livestock and food processing for value addition |  | 2500 | 2500
Number of women home-based workers and rural women trained in agro processing nursery raising, community vegetable gardens, honey bee keeping, establishing market linkages with small scale business |  | 250 | 250
Number of men reached through media campaign on sharing domestic responsibilities |  | 3 million | 2 million
Number of women reached through messaging campaign health and nutritional awareness |  | 3 million | 2.3 million

## Project Indicators
Please include ALL indicat+A2:G10ors in the project document. Include the indicators and Baseline, Planned Target and Actuals for both OUTCOME and OUTPUT levels. "Actuals" refer to the total figures achieved for each indicator. Include separate actuals for 2021 and for 2022 (if applicable). Explain if targets were not achieved. Include means of verification. Use as many outputs cells as needed to present all project indicators.
| INDICATORS DESCRIPTION AND DATA | DATA: ACTUALS 2021 | DATA: ACTUALS 2022 (if applicable) | TOTAL actuals (aggregated 2021 and 2022 if applicable ) | Reasons for Variance with Planned Target (if any) | Source of Verification
Output 1 | Vulnerable women and HBWs have improved access to social safety nets.
Indicator 1.1: | Number of women and excluded groups linked with available social services and operational social safety nets
Baseline: | 0
Planned Target: | 10000 | 0 | NA | 10084 | The target has been over achieved by 84 numbers. UN Women compiled data of more women than targeted to extend maximum benefit. | Government data, project records Monitoring reports from Project Delivery Units
Indicator 1.2: | Number of women to whom one-time cash transfers are provided
Baseline: | 0
Planned Target: | 4000 | 0 | 4500 | 4500 | Savings in the project funds allowed 500 more women to benefit from the cash grant | Records of the service provider Project records i.e. verification sheets, mobile sums , activity photographs, Monitoring reports from Project Delivery Units
Output 2 | Women farmers, HBWs and entrepreneurs have the skills and resources for increased economic participation.
Baseline: | 0
Indicator 2.1: | Number of women owned micro/small enterprises supported through economic recovery solutions to mitigate impacts of COVID19.
Baseline: | 0
Planned Target: | 300 | 0 | 300 | 300 | No variation | Beneficiary lists, attendance sheets, photographs, activity reports Monitoring reports from Project Delivery Units
Indicator 2.2: | Number of women trained on business development and entrepreneurial skills.
Baseline: | 0
Planned Target: | 200 | 0 | 200 | 200 | No variation | Beneficiary lists, attendance sheets, photographs, activity reports Monitoring reports from Project Delivery Units
Indicator 2.3: | Number of women-owned businesses linked with private sector companies.
Baseline: | 0
Planned Target: | 100 | 0 | 112 | 112 | The target has been over achieved. | Record of the companies/retail shops with whom linkages have been developed, Project records i.e. beneficiary lists, documentary proof of the selection process Monitoring reports from Project Delivery Units
Indicator 2.4: | Number of men reached through media campaign on sharing domestic responsibilities
Baseline: | 0
Planned Target: | 5 million | 2 radio programmes | 5 Radio programmes broadcasted having coverage of 3 million plus listeners | 7 Radio programmes broadcasted having coverage of 5 million plus listeners | Nil | Radio programs recordings, Radio channels outreach /coverage area estimates Monitoring reports from Project Delivery Units
Indicator 3.1: | Number of women reached through messaging campaign health and nutritional awareness
Baseline: | 0
Planned Target: | 5 million | 0 | 5.3 million | 5.3 million | Over 5.3 million text messages were sent, and some numbers were sent repeated text messages. The actual achieved value of 4.5 million is a conservative estimate considering average household size and sex ratio in the country. | Records of the service provider Monitoring reports from Project Delivery Units
Indicator 3.2: | Number of disabled women provided with menstrual hygiene kits.
Baseline: | 0
Planned Target: | 500 | 0 | 566 | 566 | Due to availability of funds, more women benefited | Beneficiary lists, activity reports and photographs Monitoring reports from Project Delivery Units
Indicator 2.5: | Number of women assisted for small scale kitchen gardening, poultry, small ruminant livestock and food processing for value addition
Baseline:
Planned Target: | 5000 | 0 | 5000 | 5000 | NA | List of beneficiaries/FAO database/pre and post distribtuion monitoring reports
Indicator 2.6: | Number of women home-based workers and rural women trained in agro processing nursery raising, community vegetable gardens, honey bee keeping, establishing market linkages with small scale business |  |  |  |  | Signed sheets/FAO database
Baseline: | 0
Planned Target: | 500 | 0 | 500 | 500 |  | Attendance sheet, photpgraphs, training report, training agenda
Outcoem level | Baseline Study for MPTF project | 1 | 0 | 1 |  | 1 Household baseline survey with food security indicators by UNFAO was conducted and triangulated with qualitative study with FGD and KII tools by UNWOMEN in six target districts of KP and Balochistan.
| Baseline validation workshop |  |  | 2 |  | 1 validation workshop organized in KP and 1 in Balochistan jointly by UNFAO and UNWOMEN MEAL team. Validation of findings of baseline and adaptive actions agreed with agriculture Extension, Livestock departments, Pakistan Baitul Mal, BISP,P&D department, PVDP NGO partner of UNWOMEN,BRSP partner NGO of UNWOMEN and project staff of six target districts of KP and Balochistan,
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant.
Turning women’s economic empowerment, a reality | Saiqa in her beauty parlour Photo Credits: UN Women, Pakistan
Saiqa (29), is a married young woman and a resident of Chashma Achozia, Quetta. Her husband has a disability due to which he cannot support his family’s livelihood. Saiqa had to shoulder the responsibility of being a bread winner for her family and raise her kids from the beginning. Under UN Women’s joint project ‘Strengthening Economic Resilience and Food Security for Home-Based Workers and Women Farmers’, Saiqa was imparted a skills-based training of flowers-making and a beautician course. A total of 20 home-based workers were trained for beautician course. To equip these women with the right tools, economic kits were also provided to the trainees as per their chosen courses. Some women were giving sewing kits or embroidery kits, while Saiqa was given a beauty kit which had all the tools used by beauticians from make-up to skin-care products/tools. By working as a home-based beautician, she is now able to make around Rs. 15000 (USD 68 – approx.) on a monthly basis. Despite the inflation, Saiqa is able to make a livelihood which is enough to support her family’s financial needs. In addition to her financial independence, she has gained her empowerment and agency to exercise her right to make decisions in the family. Her journey of empowerment serves a role model for other women to follow – to build back better and stronger
Transforming Agri-Food Systems and Fighting Hunger through Women empowerment in Balochistan Introduction of improved processing technologies and product Development: To reduce the post-harvest losses in fruits and vegetables and to diversify livelihood opportunities of the target farmers, a two-days training was imparted to 75 women and 25 men farmers on fruits and vegetable processing in the first quarter of 2022. The training has increased the skills, level of the participants in value added by processing their fruits and vegetables, which would normally get wasted or sold in the markets at lower prices during the market glut. 250 women were supported to develop tomato ketchup and mixed pickle from vegetables, as it’s a peak season of tomato, chilies, capsicum, and other vegetables. The farmers were provided with essential spices, packing, and packaging material. The farmers’ linkages were developed with local traders of the processed products. Due to COVID-19 pandemic and local traditions, the male counterparts of the women processors were used as agents for market linkages. In District Kurram, the Farmer Services Centers were used as a point for display and selling the processed products, apart from introducing them to local traders. The common facility centers were used for the collection of farmers’ products. The women processors received very good response from buyers during the pilot phase and have shown a commitment to continuing processing vegetables for sale in the market as well as for household consumption. The women have increased their income from processed products on average by 40 percent compared to the fresh sale. |  | Training on food processing Photo Credits: FAO, Pakistan | Tomato Ketchup made by women farmers after attending the food processing session. Photo Credits: FAO, Pakistan
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation https://www.fao.org/pakistan/news/detail-events/en/c/1543156/
Please produce and share a social media card(s). See an example below and visit our Trello Board.
Women making chili pickle in District Swabi
Joint baseline validation workshop in Peshawar
Goats distribution in district Pishin
Economic Recovery Toolkits distribution in district Swabi