## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to the secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality results reports please follow the next guidelines: a) The narratives should be a well written, succinct summary clarifying what was done during the reporting period and the results achieved. It should highlight the JP achievements. It should also specify scope and beneficiaries. b) Factual, evidence-based reporting against the outcome and output and corresponding indicators in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not should be provided. d) Factual, evidence-based reporting against the outcome results and its alignment with the overall SERP joint workplan, and linkage to reporting on global-level SERP indicators. e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not. g) Reflect on innovation. Avoid generic and standard descriptions. Rather, present well documented features of successful innovative solutions truly new for you and which could enable replication efforts.
3 | Please fill out all sections of the reporting template before submitting to the secretariat via email to: nina.andersen@undp.org and cc.: maria.herrera@undp.org
B
DEADLINE: MARCH 31 ST, 2022
1 | ALL projects receiving funds in late 2020 and in 2021 must complete an ANNUAL report as per the end of the calendar year with a reporting period : date of start until 31 December 2021.
2 | The joint programmes which completed their activities in 2021 should deliver a FINAL report by March 31 at the latest and will not be obligated to provide an annual report.
3 | The joint programmes completing activities in 2022 will be asked to submit a FINAL report (by 31 August 2022)
4 | ALL projects must report number of direct beneficiaries.
5 | ALL projects must provide an update on project indicators

## General Information
Programme Title & Project Number |  | Programme Duration
Programme Title: | Recovering Better and Inclusively from COVID-19 Through Gender Sensitive Social Protection System in Rwanda | Overall Duration (months) | 8 months
Programme Number (if applicable) | 127738 | Start Date (dd.mm.yyyy) | 31/07/2021
MPTF Office Project Reference Number: | MPTF_00209: UN COVID-19 MPTF | Original End Date (dd.mm.yyyy) | 31/03/2022
Country | Rwanda | In case of NCE Current End date(dd.mm.yyyy)
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UN Women and UNHCR | National counterparts (government, private, NGOs & others) and other International Organizations | 1) LODA (Local Administrative Entities Development Agency), 2) Legal Aid Forum; 3) FVA (Faith Victory Association), 4) Rwanda Women Network; 5) AJIPRODHO-JIJUKA and 6) ANSP+ (National Association supporting People Living with HIV)
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative
# | Questions | Guidance to respondents | Responses+D1:D2
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19 (up to 500 words). | The One UN Joint programme “Recovering Better and Inclusively from COVID-19 through Gender-Sensitive Social Protection System in Rwanda’’ helped to alleviate the socio-economic impacts that COVID-19 had imposed on the daily life of the most vulnerable persons, especially women, girls and refugees. The provided assistance enabled targeted families to recover together and better from COVID-19 through strong partnerships with the Government and CSOs. Strong partnerships with Government and CSOs contributed to the successful delivery of the project. As a result, 15,000 families of which 55% were from single female-headed households were refugee families and 1774 women-headed households from cross-border districts (Nyagatare, Musanze and Nyamasheke) were provided one-off cash-based transfers to cover their basic needs and improve the standards of their subsistence. Previously, majority of them heavily depended on daily wages which was later affected by the measures that were put in place to limit the spread of COVID-19. More than 80% of beneficiaries invested a portion of the cash they recieved in the agriculture sector such as buying small and big livestock and renting land for cultivating food and commercial crops. Others procured sewing machines for tailoring services while one beneficiary(female) initiated a small enterprise to produce commercial liquid soap, etc. This helped them to increase their resilience, self-confidence and esteem. As more than 90% of the Rwandan population have access to Radio Rwanda and it’s community radios, they indirectly had access to radio programmes and messages around raising awareness on gender-based violence(programme supported) that were disseminated through the aforementioned channels. This potentially increased awareness on gender-based violence, the national legal framework and various mechanisms put in place to address this issue at all levels. Messages were disseminated using different channels including national, community and private radios, mass media and community outreach meetings using a song on GBV prevention “Free My life” produced in partnership with 3 known artists one being a person with disabilities. Furthermore, 1,871 victims of gender-based violence or sexual abuse were supported in the area of entrepreneurship, school retention, legal assistance and representation in courts, psychology services, referral to relevant service providers and shelter in women’s safe rooms.
2 | Purpose | Please describe the project general objective specifying its link to COVID-19 response. | The One UN Joint programme “Recovering Better and Inclusively from COVID-19 through Gender-Sensitive Social Protection System in Rwanda’’ is a joint programme that aims at helping the most socially and economically vulnerable persons, especially women, girls and refugees to recover together and better from COVID-19 through a two-pronged but complementary approaches. These approaches focused on the provision of well-targeted gender-responsive social safety nets and addressing gender-based violence in all its forms as violence and deprivation are closely linked within the context of COVID-19.
3 | Results: Outcome Level | Please include narratives describing the main project achievements against the project's overall goal (up to 300 words) | UN agencies and partners have provided social protection to the families most impacted by COVID-19. Approximately 15,000 refugee families and 1,774 women-headed households were assisted with one-off cash assistance to facilitate their access to basic needs and improved living standards through increased family income and production. The programme also contributed to the national efforts to protect the most vulnerable women and girls from gender-based violence, sexual abuse and exploitation through increasing awareness on gender-based violence using different channels such as radio programmes and messages. Approximately 838 GBV Victims (including 208 men) were enabled to access psychosocial support and referral services, 50 victims received legal assistance and representation in courts; 942 teen mothers were provided with start-up capital, tool kits for income-generating activities and school materials aiming at improving learning conditions and retention of vulnerable teen mothers at school. The programme has also strengthened the entrepreneurial and economic capacity of the most vulnerable icnluding 41 female former domestic workers who lost their jobs during Covid 19 related lockdown through trainings in cooperative management and tailoring.
3.1 | Results: Output Level | Please include narratives describing the main annual/ final results of each output included in the project document (up to 200 words) | The results at output level are provided below per programme output
| Output 1. Expanded social protection services to the most vulnerable families affected by COVID-19 |  | UNHCR and UN Women in collaboration with their responsible partners contributed toward unlocking new opportunities for vulnerable women and refugees mostly affected by Covid 19 as their jobs, small businesses, and livelihood opportunities were frozen thus leaving them with very limited options to survive. As a result: • 15,000 refugees in camps and urban settings received from UNHCR and it partners one-off cash-based intervention assistance (cash transfers equivalent to USD 200,000) to lessen the economic impact of the COVID-19 and its related measures. The amount transferred to each of the targeted families was relative to the size of the family. On average each family received USD 30 in cash transfers to cover the family's basic needs including food and hygienic products during the COVID-19-related lockdowns. • Through the partnership between UN Women, LODA (Local Administrative Entities Development Agency) and CSOs vulnerable groups enhances the socio-economic conditions to improve their subsistence as follows: • 1,774 selected women-headed households from 3 cross-border districts namely Nyamasheke, Musanze, and Nyagatare were supported with an emergency cash transfer equivalent to RWF 266,100,000 (approximately USD266,100). Each household received RWF150,000 (approximately USD 150 which helped them to improve their living standards through but not limited to increased family income and production from recovered businesses or implementation of new income-generating activities. • SOLID Africa provided 3 nutritious and balanced diets daily to a minimum of 998 vulnerable patients (740 women and 260 men) and their caregivers per day to focus on their recovery and relieving the care burden of women as caregivers. Furthermore, the provision of 4,000 protective face masks, 2,400 flyers, and hygienic production promoted their basic hygiene as well as the correct use of masks. • The National Association Supporting People Living with HIV(ANSP+) strengthened the capacity of 41 former domestic workers from the City of Kigali who lost their source of living during the Covid 19 crisis through a 3-day training on entrepreneurial and tailoring skills and cooperative management as a minimum necessity for working in a legal and structured market. After a 4-month training, trainees were able to make different products such as dresses, shirts, shorts, bags, etc. Trainees are now initiating self-employment using the toolkit package including a tailoring machine and its accessories and a start-up capital equivalent to RWF 91,000(approximately USD90).
| Output 2. Service providers and communities have strengthened capacities and knowledge to prevent and respond to SGBV, violence against children, child abuse, exploitation and neglect |  | As a strategy to reach out to GBV victims and increase accountability at the community level, UN Women in collaboration with Rwanda Women Network (RWN), intensified awareness-raising on gender and GBV Prevention and response in the Covid 19 context using different channels and approaches. The following were achieved: • 838 GBV victims (630 females and 208 males) called for support from the hotline,392 victims were provided with psychosocial support, 446 cases were referred to relevant service providers and 21 women were accommodated by women's safe spaces for further support. • A radio spot and 3 radio talk show raising community awareness on GBV, and Sexual Exploitation and Abuse (SEA) were disseminated through the Radio programmes. This helped to reach more than 90 % of the adult population (estimated at 5 million) who increased their understanding of GBV and its consequences on women and families. • A song on GBV prevention in the context of the Covid 19 crisis “Free My Life” touches on different types of GBV including sexual violence and sexual abuse, as well as workplace sexual harassment. The song was disseminated through mass media and community outreach sessions conducted in 3 secondary cities reaching out to 2,535 individuals. In one month, it reached more than 108,000 views, received 110 comments, and 2,510 community members provided direct feedback on the awareness message. • The social media campaign on GBV also gained momentum on different platforms to reach out to community members with access to technology. From January to March 2022, 195,700 used RWN Hashtag, 495,700 Youtubers were aware of SGBV & SEA prevention and existing reporting channels (message #DuceIhohoterwa/#EndGBV) while 800 Twitter users listened to the RWN live Twitter Space on “preventing sexual and gender-based violence” • 50 GBV victims were provided with legal assistance and representation in courts and only 5 cases were won in court closed, others are still pending, waiting to appear in court but Legal Aid Forum will continue its support to those victims. • 21GBV victims directly benefited from the emergency support from 17 supported safe spaces which offer quality care from informed, victim-centered, and gender-sensitive staff. Other basic needs covered are food, shelter, transport to and from the referral institutions (IOSC and MAJ), etc. • 942 teen mothers in Nyagatare and Gatsibo districts (Eastern Province) were supported to improve their living conditions, regaining hope for life through the acquisition of toolkits, small livestock, or start-up capital to recover or start new income-generating activities. 500 vulnerable teen mothers who returned to school were supported with school materials including school bags and sanitary pads to improve the quality of their learning and school reintegration.
3.2 |  | Please include project Gender results and its linkage with COVID- 19 response. If applicable, refer to the project's gender equality marker and any impacts they may have had on programming quality and results (up to 150 words). | The project has contributed to commendable progress in integrating gender and empowerment of girls and women beneficiaries especially those affected by Covid 19. Specifically, 41 former domestic workers who lost their means of living during the Covid-19 crisis, enhanced their capacity in entrepreneurship and tailoring trade, 15,000 refugee families including 55 % single women-headed, and 1,774 women-headed households whose cross-border informal businesses were frozen thus leaving them with very limited options to survive, benefited from cash transfer to recover. In addition, 630 out of 838 SGB reported cases using hotlines are women and have benefited from psychosocial support and referral to relevant service providers while 50 victims received legal assistance and representation in courts. Furthermore, this project helped to strengthen the capacity of a women's organization (Rwanda women's network) to deal with GBV cases and build strong partnerships with different GBV service providers at the grassroots level. 942 teen mothers were also supported to regain hope for life.
3.3 |  | Please include total number of DIRECT BENEFICIARIES disaggregated by gender, age , location (rural, urban, any other location). Please avoid duplicating beneficiaries ensuring the dissagregated data adds to the total presented. | The total direct beneficiaries of the project is 22,340128 including 15,000 refugees' families (8,250 Female-headed households); 1,774 women-headed households in informal cross-border trade in the districts of Nyagatare, Nyamasheke, and Musanze; 41 former domestic workers who lost their means of living during Covid 19 related lockdowns; 838 out (630 females and 208 males) who called the tollfree line (between September 2021 and March 2022) were supported with psychological support, referral to different service providers and accommodation in women safe spaces. 50 females S/GBV victims were also supported with legal assistance and representation in courts and 10 cases were facilitated with a DNA test to search for paternity. 998 patients (739 women and 259 men) from 6 hospitals in the City of Kigali received 3 meals a day for 3 months, 942 teen mothers supported to regain hope for life, 88 service providers strengthened their capacity in S/GBV management and 2,535 community members were reached out through community outreach activities on GBV prevention and response.
3.4 | abuse, exploitation and neglect | Please include total number of INDIRECT BENEFICIARIES. Please clarify if these are estimated and/or verified. If possible, disaggregate beneficiries by gender. | The total estimated number of indirect beneficiaries is 5,558,596 persons. This includes 90% of adult Residents of Rwanda who listened to the radio spot and radio talk shows (this means more than 5 million) as per the RBA coverage estimated at 98% and around 54,000 family members of 15,000 refugees’ families supported with cash transfers, 6,386 family members of the 1,774 women-headed households supported with cash transfers (considering the average number of people living in female headed household (3.6 individuals) as per the population census report of 2012. In addition, 2,510 community members provided direct feedback on the song raising awareness on GBV prevention and response; 495,700 Youtubers who were aware of gender-based violence and sexual exploitation and abuse (SGBV & SEA) prevention and existing reporting channels (message #DuceIhohoterwa/#EndGBV)
3.5 | Do not Harm | Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention. ( up to 100 words) | The cash transfer approach helped to reduce family conflicts and abuse resulting from hunger. Beneficiaries were sensitized on the best way of managing the support received especially through increasing family dialogues and participatory decision making around the funds.
3.6 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken to achieve the expected results) Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms(use up to 150 words). | COVID-19 pandemic was a persisting challenge to the implementation of this project. Due to the new variants and the strengthened measures, activities were postponed but rescheduled and successfully conducted except one training for service providers. The use of technology to report and follow up project progress has been instrumental. Gender stereotypes and gender bias oftentimes based on traditional, religious, and cultural norms continue to limit the reporting of GBV cases leading to limited access to justice by women and girls. A strong awareness campaign using different channels has been conducted but there is still long way to go for mindset and social norms change. A further longstanding challenge is the long justice procedure; only 5 GBV cases out of 50 cases supported were closed at the court level while the remaining are still pending to be heard. To address this challenge, UN Women engaged Legal Aid Forum to continue providing legal assistance and representation of GBV victims in courts after the end of the project using its institutional resources. In addition to the above, there is still a big number of teen mothers who are in needy situations compared to available resources. This calls for continued advocacy and resource mobilization to increase the reach of this vulnerable group.
3.7 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) (up to 250 words) | Lessons learned from the project implementation including but not limited to the following: 1) Toll-free lines/hotlines are key to reaching the most vulnerable by providing them with the necessary support and referrals, especially GBV victims; 2) Local authority accountability towards GBV Prevention and response is paramount and helps to break the silence around GBV ; 3) Economic self-resilience for refugees and other vulnerable groups including women and girls remains a must for them to become economically empowered and live a dignified life free from discrimination and violence. 4) Livelihood interventions and resources are still needed to promote economic inclusion and build resilience to socio-economic shocks such as the impact of COVID-19 on vulnerable women and girls as well as refugees. 5) Enabling the environment remains a critical need for refugees and their host communities to facilitate a graduation pathway out of extreme poverty following LNOB principles 6) Support services need to be proactive and coordinated. Police, health, and social services should work together to identify women at particularly high risk, such as those who have previously faced violence at the hands of a partner. 7) Integrating GBV risk mitigation into COVID-19 response measures, alongside strengthened GBV prevention and response is critical to effectively addressing this double pandemic. 8) Family members of GBV victims, especially parents of the teen mothers, should be involved in awareness-raising sessions to change the stigmatization mindset | ]
3.8 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 250 words) | The purpose of emergency cash transfers to poor women-headed households is to contribute to improving and sustaining their living conditions by covering their emergency basic needs and starting small income-generating activities. To achieve this result, a strong partnership between the UN in Rwanda represented by UNHCR, Government institutions, and CSOs and different partners operated in the refugee camps and host communities. UN Women partnered with LODA, Local Government Structures, SACCO (Savings and Credits Cooperatives) from the targeted districts (Nyamasheke, Musanze, and Nyagatare ), and the National Women Council which were involved in the selection process of the beneficiaries and the cash transfers to selected women-headed households. Partnerships have been also strengthened with CSOs such as Faith Victory Association (FVA), The Legal Aid Forum(LAF), National Association of People Living with HIV(ANSP+), and Rwand Women Network (RWN) which from this project funds have been able to lead the process of supporting vulnerable girls and women, GBV victims especially teen mothers to recover from covid 19 effects. The partnership has also been built with Rwanda Cooperative Agency (RCA), ARTC Ruhuka to enhance the capacity of domestic workers in entrepreneurship skills and cooperative management and in psycho social support to teen mothers. To address GBV issues, strong partnerships with ISANGE ONE-STOP CENTERs (to offer comprehensive services), HAGURUKA, and Local authorities, the Rwanda National Police, the Rwanda Investigation Bureau (RIB) to handle GBV cases referred to them by Rwanda Women Network.
3.9 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken (up to 200 words). | No assessment was undertaken under this project. The project falls under the social protection area and has the aim to provide emergency support to vulnerable groups including women headed households, domestic workers, and GBV victims with a very short timeline. It was developed because of many covid 19 related studies and assessments conducted by the Government of Rwanda, the One UN as well as UN Women assessments.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place (Up to 100 words). | There was a plan to conduct an audit on the safety of women and girls in Kigali City and secondary cities to gauge the safety situation of women and girls in times of Covid 19 in public spaces. However, during this project implementation, UN Women realized that there were many studies and assessments made in the area and concluded to leave out this study and use the budget under that activity to increase grants to beneficiaries mostly affected by Covid 19 pandemic. These include (i) Gender Assessment of the Socio-Economic Response and Recovery Initiatives against Covid 19 in Rwanda (2021) , (ii) Socio-Economic Impact of COVID-19 on Women and Men in Informal Cross Border Trade in Rubavu, Rusizi, and Nyamasheke Districts, Rwanda(2021); (iii) Rapid Gender Asessement on the Impact of Covid 19 on Women and Men in Rwanda( 2020), (iv) Women Safety Audit In the City of Kigali (2019), (v) Women Safety Audit in Nyaruguru district (2021)
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## Project Indicators
Please include ALL indicators in the project document. Include the indicators and Baseline, Planned Target and Actuals for both OUTCOME and OUTPUT levels. "Actuals" refer to the total figures achieved for each indicator. Include separate actuals for 2021 and for 2022 (if applicable). Explain if targets were not achieved. Include means of verification. Use as many outputs cells as needed to present all project indicators.
| INDICATORS DESCRIPTION AND DATA | DATA: ACTUALS 2021 | DATA: ACTUALS 2022 (if applicable) | TOTAL actuals (agreggated 2021 and 2022 if applicable ) | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Indicator:
Baseline:
Planned Target:
Output 1.1 | Expanded social protection services to the most vulnerable families affected by COVID-19 |  |  |  | The variance between the actual and the target is caused by additional resources mobilised by UNHCR which helped form a basket fund reaching out 15,000 refugees | Project report (UN Women and UNHCR)
Indicator 1.1.1: | Number of new households including in refugee camps and hosting communities receiving conditional cash transfers from the programme
Baseline: | 0
Planned Target: | 2500 | 15000 | 1774 | 16774
Indicator 1.1.2: | Number of female domestic workers who had lost their jobs during covid-19 who regain other alternative livelihood through the programme |  |  |  | The figure on the beneficiaries at the planning level was overestimated for domestic workers who lost their jobs because of Covid 19. | UN Women and partners reports
Baseline: | 0
Planned Target: | 200 | 41 | 0 | 41
Output 1.2 | [5 empty] | UN Women and partners reports
Indicator 1.2.1: | Number of women and girls receiving post GBV care (disaggregated by type of services)
Baseline: | 1500 | 1500 | 1500 | 1500
Planned Target: | 3000 | 223 | 1337 | 1560
|  | 1723 | 2837 | 3060
Indicator 1.2.2: | Number of new SGBV cases reported through this programme funded toll free helpline |  |  |  | During covid 19 related lockdowns, more people called the toll-free line than planned and this reveals an increase in GBV cases resulting from limited movement and limited outside of home activities for men | UN Women and partners reports
Baseline: | 0
Planned Target: | 300 | 332 | 506 | 838
Indicator 1.2.3: | Number of partners trained and supported to monitor ,document and provide support to SGBV survivors |  |  |  | Due to Covid 19-related lockdown and given the short time of the project, one training session wasn't organized. Only 3 training sessions and a learning discussion were organized to agree on the concepts and mechanisms of GBV reporting. However, service providers collaborated in the preparation of community outreach in secondary cities and City of Kigali (2,535) | Project reports, Government guidelines on Covid 19 case management
Baseline: | 0 | 0
Planned Target: | 300 | 0 | 116 | 116 | The variance was due to COVID -19 prevention measures especially lockdown and limited gatherings as per government regulation. | UN Women partners reports
Output 1.3 onwards
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.
Note on A5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: As reflected in the prodoc, the Outcome is: Outcome 1 : Expanded access to social protection to households and communities most impacted by COVID- 19 whilst protecting women and girls from gender-based violence, sexual abuse and exploitation
Note on A6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please fill these three rows against the outcome

## Communication
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant.
One of the beneficiaries called MUKAMBABAZI Pelagie testified that before coming in tailoring training, she was traumatized by poverty without any source of income. During Covid 19 Crisis she lost all livelihood conditions, she couldn’t find anything to eat, and it was as if she was homeless. But now, she became a smiling person for she found another family where she can laugh. She is able to contribute to the payement of the rent, yet she lived with her young sister in the same house called the ghetto and she was mistreated by her sister. She is hopeful and believes that her future will be bright.
Former domestic worker equipped with tailoring skills. Photo credit: ANSP+
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well as picture material please make sure you include all credits and share them in high resolution.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
UN Women in Rwanda relieving the care burden on caregivers in public hospitals in response to the COVID-19 pandemic ¦ UN Women – Africa
https://africa.unwomen.org/en/stories/news/2022/05/how-un-women-led-social-protection-programme-helped-vulnerable-women-in-rwanda-overcome-impact-of-covid-19
https://www.newtimes.co.rw/featured/new-un-women-programme-sets-out-restore-hope-among-women-most-affected-covid-19
See - Fund's Trello Board
`
ANSP+ UN Women Rwanda CO, domestic workers in tailoring training
Distribution of school materials and Goats to teen mothers at Gatsibo District, Murambi Sector. Photo credit: AJIPRODHO-JIJUKA
The coordinator of ANSP+ delivering welcome note to the training on entrepreneurship and cooperative Mnagement. Photo credit: ANSP+
NYAGATARE District Vice Mayor Social Affairs Mrs. MUREKATETE Juliette and AJPRODHO board delegate Mr. MUVUNYI Eric giving the tailoring machines to the teen mothers. Photo credit: AJIPRODO_JIJUKA |  | Distribution of school material to teen mothers. Photo credit: AJIPRODHO-JIJUKA
Examples of some activities (mushroom culture, cabbage culture and small livestock managed by Women headed households who received cash transfers from LODA. Photos credit: LODA
| GBV Service providers after the 3-day training on GBV management. Photo credit: Rwanda Women Network |  | Mass media: Artists who produced the song on GBV dissseminated through mass media
Mass media: Artists who produced the song on GBV. Photo Rwanda Women Network
Note on A2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please provide an impactful story with testimonials from targeted groups as requested