## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to the secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality results reports please follow the next guidelines: a) The narratives should be a well written, succinct summary clarifying what was done during the reporting period and the results achieved. It should highlight the JP achievements. It should also specify scope and beneficiaries. b) Factual, evidence-based reporting against the outcome and output and corresponding indicators in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not should be provided. d) Factual, evidence-based reporting against the outcome results and its alignment with the overall SERP joint workplan, and linkage to reporting on global-level SERP indicators. e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not. g) Reflect on innovation. Avoid generic and standard descriptions. Rather, present well documented features of successful innovative solutions truly new for you and which could enable replication efforts.
3 | Please fill out all sections of the reporting template before submitting to the secretariat via email to: nina.andersen@undp.org and cc.: maria.herrera@undp.org
B
DEADLINE: MARCH 31 ST, 2022
1 | ALL projects receiving funds in late 2020 and in 2021 must complete an ANNUAL report as per the end of the calendar year with a reporting period : date of start until 31 December 2021.
2 | The joint programmes which completed their activities in 2021 should deliver a FINAL report by March 31 at the latest and will not be obligated to provide an annual report.
3 | The joint programmes completing activities in 2022 will be asked to submit a FINAL report (by 31 August 2022)
4 | ALL projects must report number of direct beneficiaries.
5 | ALL projects must provide an update on project indicators

## General Information
Programme Title & Project Number |  | Programme Duration
Programme Title: | Supporting Micro, Small and Medium Sized Enterprises in the horticulture sub-sector to build back | Overall Duration (months) | 9
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2021-07-01
MPTF Office Project Reference Number: |  | Original End Date (dd.mm.yyyy) | 2022-03-31
Country | Tanzania | In case of NCE Current End date(dd.mm.yyyy) | N/A
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | ILO, UNIDO, UNDP, UNCDF | National counterparts (government, private, NGOs & others) and other International Organizations | Tanzania Horticulture Association (TAHA) The Institute for Rural Development Planning (IRDP) The Tanzania Irrigation Commission Zanzibar Ministry of Trade and Industrial Development (MTID) Small and Medium Scale Industries Development Agency (SMIDA) Zanzibar National Chamber of Commerce (ZNCC)
Report Cleared By
o Name: | Zlatan Milisic
o Title: | RC
o Email address: | zlatan.milisic@un.org>
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19 (up to 500 words). | The main purpose of the project was to support horticulture sub-sector value chains. There are over 17.5 thousand (17,588) horticulture farmers in Tanzania. Horticulture is directly linked with the tourism sector, which was severely affected by the COVID 19 pandemic as the tourist sector is the key market for horticulture produce in Tanzania. The local economy in the targeted regions (i.e. northern zone and Zanzibar) is heavily reliant on tourism. The main target population groups of the project are women and youth as they form a dominant share of the agriculture employment force and were disproportionately affected by the pandemic overall. At the time of the project commencement, many farmers had closed their production. Because of sharp widespread decline in demand from traditional domestic markets due to the dwindling tourism activities, many MSMEs lost their incomes, had no access to inputs or financing. Remaining farmers who were able to produce at a low scale could not diversify their marketbase domestically or abroad because of insufficient productivity, poor product processing quality, gaps in standards or lack of certification and funding. Furthermore, the threat of post-harvest losses was heightened due to the poor state of post-harvest processing tools and handling facilities. Participating UN Organisations (PUNOs) partnered with key stakeholders to deliver activities intended to support the recovery of the value chains. The interventions focused on supporting farmers and processors to improve productivity and quality standards, adopt good business practices, new technologies and innovations, access required capital through preparations of feasible/bankable projects and open up alternative markets. Below are the key results of the project: Total of 1734 women and youth MSMEs in horticulture in Arusha and Kilimanjaro trained in General Agriculture Best Practices (GAPs). The training focused on chili production techniques including seedbed preparation, land preparation, nursery management, transplanting, pest management, farm management, scouting, post-harvest management. These trainings were key and prerequisite for diversifying local markets and accessing international markets. Additionally, the project supported the formation of MSME clusters to ease access to advisory services, capital and equipment. 490 MSMEs in horticulture were trained on financial literacy out of which 186 managed to access small loans from NMB Bank and equity bank. Additionally, 6 bankable projects owned by MSMEs in horticulture and tourism value chains were prepared and matched to commercial banks (NMB, CRDB and Equity banks). The total worth of the 6 projects is around US$ 6 million. Once funded, the projects will benefit approximately 719 members of the Tanzania Horticulture Association. Over 1000 farmers were registered on digital platforms to facilitate essential linkages across the supply chain - between small holder farmers, input suppliers, financial service providers and buyers – thereby enhancing the market and income generating opportunities for the MSMEs. Four market information guides were developed. The guides provide detailed information to buyers of horticulture produce looking for constant suppliers of horticulture products for their supermarkets or re-opening hotels. Chili Development Strategy for 2022-2025 was produced aiming to attract new capital into the horticulture value chain, which would benefit horticulture farmers in terms of employment, income and revenues. Tangible results include the following: Over 4139 small holder farmers, of which 62% are women, are back to work after COVID-19 disruptions. Chilli farmers gained an estimated revenue of Tshs. 852 million from sale of their crop. The export of chilies is expected to earn up to US $ 1.247 million in foreign income, and thus contributing to the country’s balance of payment
2 | Purpose | Please describe the project general objective specifying its link to COVID-19 response. | The main purpose of the project was to support the recovery and resilience of horticulture sub-sector value chains. Horticulture is directly linked with the tourism sector, which has been among those most affected by the COVID 19 pandemic. Any changes in tourism, directly affect communities deriving their livelihoods from the horticulture sub-sector. The local economy in the targeted regions (i.e. northern zone and Zanzibar) is heavily reliant on tourism. The main target population groups were women and youth as they form a larger share of the agriculture employment force, and overall were disproportionately affected by the pandemic.
3 | Results: Outcome Level | Please include narratives describing the main project achievements against the project's overall goal (up to 300 words) | The main achievement of this project has been the recovery of horticulture sub-sector value chains from the adverse impact of COVID 19 and strengthened capacities of to withstand future economic shocks. The project balanced interventions which addressed the immediate impact of COVID-19 on the MSMEs in horticulture and strengthened their resilience going forward. Through this project MSMEs in horticulture, including women and youth, in target areas received knowledge on entrepreneurial skills and practices to enhance their product quality and standards, improve productivity and processing. Small holder farmers were supported to gain access to essential inputs, equipment, infrastructure, services and capital. MSMEs adopted innovative digital solutions that expand market and income generating opportunities. The upgrading of the packaging facilities and access to quality infrastructure services have enhanced capacities of small holder farmers for penetration of new domestic and international markets. Feasibility studies for areas which can increase production of inputs, processing activities, packaging and storage, and access to transport to the markets (local and international) will serve as important refererence point going foward. The project facilitated the unlocking of funding from commercial and development banks easing access for target beneficiaries to required capital. Market information guides are expected to attract new buyers and additional capital into the horticulture value chain. Some specific examples of the results include: Over 4,600 small holder farmers, of which 62% are women, are back to work after COVID-19 disruptions. Chilli farmers gained an estimated revenue of Tshs. 852 million from sale of their crop. Additionally, the import of chilies is expected to earn up to US $ 1.247 million in foreign income, and thus contributing to the country’s balance of payment. 186 MSMEs in horticulture accessed small loans ranging between Tsh 500,000 to Tsh 1,000,000 from commercial banks whereby a total of Tsh 62 million was disbursed to MSMEs. Additional 6 bankable projects owned by MSMEs in horticulture and tourism value chains were developed and presented to commercial banks and are in the final stages of accessing loans worth US$ 6 million.
3.1 | Results: Output Level | Please include narratives describing the main annual/ final results of each output included in the project document (up to 200 words) | Main results for Output 1.1: • More than 1300 women and youth MSMEs in horticulture in Arusha and Kilimanjaro trained in General Agriculture Best Practices (GAPs). The training focused on chili production techniques including seedbed preparation, land preparation, nursery management, transplanting, pest management, farm management, scouting, post-harvest management. These trainings were key and prerequisite for accessing international markets. • 490 MSMEs in horticulture were trained on financial literacy out of which 186 managed to access small loans from NMB Bank and Equity bank. By the time of reporting the total loan accessed by the select MSMEs was Tsh. 62 million. • 1085 farmers were profiled and registered on the digital platform to enable them access input suppliers, and to enhance their business skills and ability to adopt innovative solutions • 6 bankable projects owned by MSMEs in horticulture and tourism value chains were prepared by undertaking detailed feasibility studies to inform the bankability of each. The 6 projects were submitted to NMB and Equity banks and are in final stages towards accessing a loan. The total worth of the 6 projects is around US$ 6 million. Once funded, the projects will benefit approximately 719 members of the Tanzania Horticulture Association. • Chili development strategy for 2022-2025 was developed to benefit over 17.5 thousand horticulture farmers in terms of employment, income and revenues. The strategy is seeking to bring in financing from diverse sources. Main results for Output 1.2. • 13 SMEs that include women and youth received training on Business Development Services (BDS) resulting into enhanced capacity to support horticulture and build resilience and recovery. • 1085 farmers were profiled and registered on the digital platform to enable them access input suppliers, and to enhance their business skills and ability to adopt innovative solutions Main results for Output 1.3. • Four (4) market information guides and the Chili development strategy for 2022-2025 were produced aiming to attract new capital into the horticulture value chain. The guides and the strategy provide detailed information to buyers of horticulture produces looking for constant suppliers of horticulture products for their supermarkets or re-opening hotels. • Three irrigation schemes were formed in Arumeru to support the small-holder farmers farming especially by women and youth • Topographic survey of a scheme and modernized irrigation facilities conducted, and farmers were trained on scheme management.
3.2 | Results: Gender | Please include project Gender results and its linkage with COVID- 19 response. If applicable, refer to the project's gender equality marker and any impacts they may have had on programming quality and results (up to 150 words). | 4,677 smallholder farmers including women and youth are back to work after COVID-19 disruptions. Out of which 2,900 (62%) are women.
3.3 | Results: Direct Beneficiaries | Please include total number of DIRECT BENEFICIARIES disaggregated by gender, age , location (rural, urban, any other location). Please avoid duplicating beneficiaries ensuring the dissagregated data adds to the total presented. | 4,677 small holder farmer, including 2,900 women (62%).
3.4 | Results: Indirect Beneficiaries | Please include total number of INDIRECT BENEFICIARIES. Please clarify if these are estimated and/or verified. If possible, disaggregate beneficiries by gender. | Over 13, 500 horticulture farmers who are members of the Tanzania Horticulture Association (TAHA) indirectly benefited from the interventions undertaken by this project.
3.5 | Do not Harm | Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention. ( up to 100 words) | Design and implementation of the project focused on capacity building and participatory approach; all project stakeholders (e.g. small holder farmers, community, local and central government ) were involved. Further, traditionally conflicting groups - small holder farmers and livestock keepers- were both involved as project stakeholders (as per the Project Risk and Mitigation plan), their interests were considered and mutual lasting solution agreed. The project has addressed issues of inequality (by providing sustainable income opportunities to marginalized rural communities) and vulnerability (as the rehabilitation of irrigation canals reduces the risk of flooding experienced before)
3.6 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken to achieve the expected results) Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms(use up to 150 words). | Challenges/Difficulties: • Some originally targeted MSMEs had completely closed businesses and left the area/business reducing the initially targeted group. This resulted in the variance across outputs in the numbers of beneficiaries reached (and likely to be reached) vs targeted. This issue is linked to the identified risk in the Project Risk Management Matrix of the “lack of data/limited understanding of the situation” which was addressed accordingly. • In some cases cost overruns resulted from reasonable and justified changes suggested by key stakeholders though the consultative process during the project implementation. • Climate and poor road conditions in the implementation rural areas impaired access for and to beneficiaries, which in some cases contributed to delays in the project activities.
3.7 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) (up to 250 words) | • Knowledge and technology transfer and adoption of innovation have proven imperative. Readiness to use digital tools to ensure continuity allowed businesses along the value chain to switch to new markets and survive during the pandemic. Going forward, promoting innovation and supporting knowledge and technology transfer should be considered in future sector specific interventions to promote resilience and sustainability of income generation for rural SMEs and small holder farmer • Small holder farmers in rural areas are willing and ready to learn and transform their operations but they need targeted capacity building and key public infrastructure and services. Small holder farmers should be involved in the design and implementation of transformative public projects. • Strategies to unlock extra funding that is potentially available are necessary to fill in the gap and/or expand the impact of interventions. • Short timeframe allocated for project implementation may limit the sustainability of the interventions on the ground if agencies do not have additional resources or existing mechanisms on the ground for monitoring and follow-ups.
3.8 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 250 words) | • UNCDF used the PPCP (Private, Public, Community Partnership) approach to deliver the project. The combination of technical assistance and the seed capital helped unlock extra financing from other stakeholders. In some district council, the local government authority (LGA), the Irrigation Commission of Tanzania, the community of farmers and BECL (private SME) made financial and in-kind contributions which supported the achievement of project results. • ILO and UNDP jointly implemented this project through partnership with the Tanzania Association of Horticulture (TAHA) who were spearheading all the planned activities on the ground. Through TAHA, the project was able to benefit select officials from the LGAs who were trained on addressing the emerging challenges brought by the pandemic, and promoting sustainability of reslience-building efforts. • UNIDO, in line with its Program for Inclusive and Sustainable Development (PISID), planned to leverage on the funding to extend support to the beneficiaries by bringing in more tangible impact at the institutional and ministerial level in Zanzibar.
3.9 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken (up to 200 words). | UNDP and ILO conducted an assessment on the chilli value chain feasibility, varieties, value chain, costs and market. The assessment aimed to facilitate the decision of farmers to invest into the chilli value chain and contribtued to the Chili development strategy for 2022-2025 formulation. UNIDO conducted an assessment study to both establish interventions which would result in sound impact and set a baseline. The assessment focused at two levels: • at institutional level - to identify gaps faced by business development strategies when providing services to MSMEs specifically on certification of produce. • at the level of Medium and Small Entrepreneurs (MSMEs) - to identify key challenges which limit MSMEs to access markets. Findings indicated that certification process to most MSMEs are not followed/granted due to the following barriers: business premises/ high cost involved/ informal business/ limited knowledge on the importance of certification, formalization and packaging material. The study was covered by UNIDO from its other sources but the assessment servved as in important input to the project and will inform the design of future interventions to addresss the identified challanges | >
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place (Up to 100 words). | Adjustment were made to support rehabilitation of key horticulture infrastructures in the project sites (e.g. irrigation and post harvest facilities) as per suggestions from key stakeholders. It was evident that without this key intervention, the project was prone to falling short of targeted/planned results.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | The funds were fully utilised for UNDP, UNCDF and ILO ($600,000). Although due to internal technical and other challenges UNIDO was not able to utliise its share of the funding ($200,000), it nevertheless contributed towards the results. Overall, the project activities and the funding from the COVID-19 MPTF was catalytic, additional funding was unlocked from project stakeholders including community of farmers, local and central government as well as the private sector (commercial banks).

## Project Indicators
Please include ALL indicators in the project document. Include the indicators and Baseline, Planned Target and Actuals for both OUTCOME and OUTPUT levels. "Actuals" refer to the total figures achieved for each indicator. Include separate actuals for 2021 and for 2022 (if applicable). Explain if targets were not achieved. Include means of verification. Use as many outputs cells as needed to present all project indicators.
7 | INDICATORS DESCRIPTION AND DATA | DATA: ACTUALS 2021 | DATA: ACTUALS 2022 (if applicable) | TOTAL actuals (aggregated 2021 and 2022 if applicable ) | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]: MSMEs in the Northern part of Tanzania and Zanzibar, engaged in horticultural production for the tourism industry, have enhanced capacity to respond to the short-term impact of COVID-19 and strengthened resilience to withstand future economic shocks |  |  |  |  | The differences between the actual and planned targets across the outputs are due to delayed commencement of the activities and some originally targeted SMEs had completely closed businesses and left thus reducing the initially targeted group. | Final Project Report
Indicator:
Baseline: | 0
Planned Target: | 4780 | 1820 | 2857 | 4677
Output 1.1 Targeted youth and women MSMEs in horticulture have strengthened capacity to restructure and diversify their business |  |  |  |  | While the overall number of beneficiaries exceeded the planned number, It was noted that, many female youth do not have access to gadgets and internet to enable them participate in trainings that are offered online | ILO&UNDP Mission Reports, Annual Report of the Tanzania Horticulture Association (TAHA)
Indicator 1.1.1:Number of MSMEs with enhanced knowledge on in General Agriculture Best Practices (GAPs), including women
Baseline: | 0
Planned Target: | 700/525 | 538 | 712/484 | 1734
Indicator 1.1.2:Number of MSMEs who received access to financial services and additional working capital |  |  |  |  | In most of the select areas, fewer farmers were reached in financial services initiative due to the fact that banks required collaterals or form of guarantees in order to fund farmers | UNCDF/BECL progress report supported with loan agreement with TADB Bank and NMB
Baseline:0 | 0
Planned Target: | 535 | 20 | 470 | 490
Indicator 1.1.3:Number of youth and women MSMEs with enhanced business skills and ability to adopt innovative solutions |  |  |  |  | The common use facilities for drying, packaging and transportation to markets were able to benefit more farmers hence increasing the impact of the project. | Final Project Report
Baseline:0 | 0
Planned Target: | 625 | 545 | 540 | 1085
Output 1.2: Business development services are enhanced to support MSMEs in horticulture to adopt innovative solutions in response to COVID-19
Indicator 1.2.1:Number of BDS providers and institutions with enhanced skills & improved technologies to support MSMEs in horticulture |  |  |  |  | At the beginning of the activity, 45 representatives from BDS providers and institutions representing horticulture farmers were identified and registered for the training. Only 13 were able to receive a full package of trainings - in 2021; some training sessions were rescheduled to March 2022 as to not clash with essential national events. However, the remaining registered participants still were not able to complete the course due to various reasons. | ILO ToT Reports
Baseline:0 | 0
Planned Target:45 | 45 | 13 | 0 | 13
Indicator 1.2.2:Status of the Farmers Digital Platform that links small holder farmers, input suppliers, financial services providers, and buyers.
Baseline:0 | 0
Planned Target: 1200 | 1200 | 697 | 650 | 1347 | As the activity was progressing, more farmers and service providers became aware on how to use and leverage digital platforms and expressed the interest to be registered | System Generate Reports by TAHA.
Output 1.3: Number of MDAs and private sector actors capacitated to design gender responsive socio-economic stimulus packages including generation and use of sex-disaggregated data
Indicator 1.3.1: Number of MDAs and private sector actors capacitated to design gender responsive socio-economic stimulus packages including generation and use of sex-disaggregated data |  |  |  |  | Feasibility studies for six value chains were conducted and presented to the Tanzania Agricultural Development Bank for funding. Once funded, the six projects are expected to impact and contribute directly to the growth and income of at least 500 MSMEs. Also, Chili development strategy for 2022-2025 was developed, and will benefit horticulture farmers in terms of employment, income and revenues. The strategy is expected to be financed from diverse sources. | ILO&UNDP Mission Reports, Annual Report of the Tanzania Horticulture Association (TAHA), feasibility studies and the Chili Development Strategy 2022-2025
Baseline:0 | 0
Planned Target:200 | 7 | 7 | 1 | 8
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant.
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well as picture material please make sure you include all credits and share them in high resolution.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board
Massive boost for horticulture sector (ippmedia.com)
Enhancement of Capacity for BDS providers in horticulture sector using tailor made programmes(Gender and Entrepreneurship Together (GET Ahead) inorder to support SME recovery and resilience
https://twitter.com/ILO_EASTAFRICA/status/1506550434063781890
https://twitter.com/ILO_EASTAFRICA/status/1506254326259453954