## OVERALL REPORTING INSTRUCTIONS (hidden)
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to the secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality results reports please follow the next guidelines: a) The narratives should be a well written, succinct summary clarifying what was done during the reporting period and the results achieved. It should highlight the JP achievements. It should also specify scope and beneficiaries. b) Factual, evidence-based reporting against the outcome and output and corresponding indicators in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not should be provided. d) Factual, evidence-based reporting against the outcome results and its alignment with the overall SERP joint workplan, and linkage to reporting on global-level SERP indicators. e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not. g) Reflect on innovation. Avoid generic and standard descriptions. Rather, present well documented features of successful innovative solutions truly new for you and which could enable replication efforts.
3 | Please fill out all sections of the reporting template before submitting to the secretariat via email to: nina.andersen@undp.org and cc.: maria.herrera@undp.org
B
DEADLINE: MARCH 31 ST, 2022
1 | ALL projects receiving funds in late 2020 and in 2021 must complete an ANNUAL report as per the end of the calendar year with a reporting period : date of start until 31 December 2021.
2 | The joint programmes which completed their activities in 2021 should deliver a FINAL report by March 31 at the latest and will not be obligated to provide an annual report.
3 | The joint programmes completing activities in 2022 will be asked to submit a FINAL report (by 31 August 2022)
4 | ALL projects must report number of direct beneficiaries.
5 | ALL projects must provide an update on project indicators

## General Information
Programme Title & Project Number |  | Programme Duration
Programme Title: | Building Forward Better: A Resilient Women and Youth Centred and Digitally Enhanced Value Chain Development in Vietnam | Overall Duration (months) | 15 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 01.02.2021
MPTF Office Project Reference Number: | MPTF_00209_00089 | Original End Date (dd.mm.yyyy) | 30.04.2022
Country | Vietnam | In case of NCE Current End date(dd.mm.yyyy) | 30.06.2022
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | IFAD and UNIDO | National counterparts (government, private, NGOs & others) and other International Organizations | - Ministry of Agriculture and Rural Development - Provincial People's Committees of Dong Thap province and Ben Tre province - Fruit enterprise associations - Farmers groups, Women’s Union, Youth Union, Farmers’ Union - Private sector - R&D and technological institutions
Report Cleared By
o Name: | Amanda Mindus
o Title: | Coordination and social development officer
o Email address: | amanda.mindus@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative
# | Questions | Guidance to respondents | the
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19 (up to 500 words). | After receiving the COVID-19 MPTF Fund in February 2021, UNIDO and IFAD started their internal and government approval processes, which were completed in June 2021. In parallel, both agencies kicked off the inception activities: including 3 consultation workshops with stakeholders; setting up 2 province PMUs and formulating detailed workplan/s; reviewing other ongoing projects to identify synergies; conducting 8 surveys and in-depth assessments along 2 fruit value chains (mango in Dong Thap and pomelo in Ben Tre), and selecting partners and service providers. The project was fully implemented from July 2021. A key area of implementation was the Dong Thap and Ben Tre provinces. Key partners included the Ministry of Agriculture and Rural Development (MARD), the Farmer’s Association, Women’s Union, Youth’s Union, digitalization/e-commerce platforms, Institute of Agriculture Engineering and Post Harvest Technology, Institute of Agriculture and Rural Development Policy and Strategy, Department of Agro Process and Market Development and identified actors of mango & pomelo value chains. The project placed rural women and youth who have been particularly impacted by the Covid-19 pandemic at the centre of attention. The focus was on developing a digitally enhanced model for building the mango and pomelo value chain in the Mekong Delta. Six representative unions of women, youth and farmers and 71 groups from the two provinces have been strengthened to jointly facilitate capacity-building activities on ICT and other technical skills given to producer groups, SMEs, wage labourers and entrepreneurs. 80 training courses to improve skills in production, business planning, financial management, e-commerce, etc. were organized for more than 2,500 members, of which 70% are women and youth. A by IFAD previously developed digital platform, called The One Cooperative One Product (OCOP), was used. The OCOP aims to utilize the ICT-based marketing application to promote and increase market access for mango and pomelo products. This platform was used and upscaled in this project. In addition, UNIDO provided technical assistance to develop a digital supply chain ecosystem platform for the value chain of tropical fruits. The platform enables actors such as businesses along the value chain, business services, and support institutions both technical and financial to access the platform. Via the platform, they can connect to business partners and/or access necessary support services and inputs. 6 training courses with 300 value chain actors on traceability were conducted to pilot a traceability app along the value chains. The project also supported the development of COVID-19-related production standards, quality compliance and processing technologies, and developed policy engagement to promote the status of women and youth in leadership positions in farmer's organizations and private enterprises. 10 Standard Operation Procedures (SOPs) from farm to market for mango and pomelo value chain were developed with 10 training modules. About 400 value chain actors received training on the SOPs. Furthermore, the SOPs were digitalized to develop e-learning courses to enable a wider spread of learners/stakeholders to access the content. Additionally, training courses for 490 households on the application of VietGap/GlobalGap were organized. 6 Production Unit Codes (PUC) and 2 Packing House codes (PHC) for export were developed for mango and green-skinned pomelo products in the 6 pilot areas. 2 cooperatives and 18 training courses on PUC & PHC were organized for 657 producers and packing houses. These interventions led directly to 43 farm-enterprise contracts and significantly increased the chances for women and youth to obtain higher-paid labour contracts and decent, safe working conditions. Farmer groups have adopted climate-smart fruit production technology and become more resilient to the effects of climate change and other external shocks. This was further enabled by piloting an intelligent pest and disease monitoring system (for 45 households) with integrated edge computing cameras, a smart water quality monitoring system and a smart water pumping system (for 15 households) in the area of 2 hectares. Moreover, the project’s interventions have improved the enabling business environment for women and youth, enhanced the competitiveness and safety of women and youth-led value chains, and increase value addition, and their access to markets. Intensive technical assistance (technical and equipment support) was provided to 6 selected women/youth-led enterprises and cooperatives to improve product packaging, apply proper post-harvest technology, increase the quality and shelf-life of products, and reduce post-harvest loss. A set of manuals on producing value-added products was developed to share good practices. These manuals were also digitalized to scale up dissemination in the Mekong River Delta provinces. 6 e-commerce platforms and 10 supermarkets/shop chains have been investigated and facilitated to the interested cooperatives, and enterprises for market linkage. An export promotion plan was developed with a model marketing plan which provide strategic recommendations to the targeted export markets and 6 exporters were coached to develop their export development plans for the targeted markets. Ultimately, women and youth are expected to increase their income and self-esteem through higher-skilled work and by becoming successful entrepreneurs. Together with advocacy and policy engagement, the social empowerment of women has gained concrete traction.
2 | Purpose | Please describe the project general objective specifying its link to COVID-19 response. | The goal is to create a model of a gender- and youth-centred and innovative fruit value chain, based on the experiences of this project in the Mekong Delta of Viet Nam, which can be scaled up for ‘recovering better together’ across the rural economy. The project would prioritize rural women and youth as the core target groups by (i) boosting their skills and capacities; (ii) offering COVID-19 safe working conditions and decent revenues and; (iii) most importantly, reducing barriers and opening a development pathway for women and youth to actively participate in modern and digitized economic activities. In addition, building forward better would result in (iv) greater safety of agricultural products for consumers. Demand for high quality and safe food is rising especially in urban areas as local markets receive more attention in Vietnam while export markets have been contracted as a result of the COVID-19 pandemic. Opportunities for a COVID-19 safe value chain include (i) COVID-19 sanitized and certified transport and tracing systems for agricultural produce and farm inputs; (ii) cold storage and packaging facilities to prevent goods from perishing; and (iii) digital extension and e-commerce (ICT) to mitigate the impact of physical distancing and to speed up trade.
3 | Results: Outcome Level | Please include narratives describing the main project achievements against the project's overall goal (up to 300 words) | Outcome 1: The project has enhanced an enabling environment for women- and youth-centred businesses. The Provincial Women’s Unions, Youth Unions and Farmer’s Unions of Dong Thap and Ben Tre provinces were mobilized to strengthen 75 farmer groups to more effectively represent the interest of women and youth and encourage their active participation in digitalized value chains and planning sessions at Commune, District and Provincial levels. They facilitated capacity-building activities for their members on ICT and other technical skills. 80 training courses to improve skills in production, business planning, financial management, and e-commerce, for example, were organized for more than 2,500 members, of which 70% are women and youth. The project enhanced the capacity of, and the accessibility to, women- and youth-focused support services for the digital OCOP platform and the digital supply chain ecosystem platform. In addition, a policy and advocacy platform was established and 5 dialogues were facilitated for (a) promotion and scaling up of women- and youth-centred value chains; (b) promotion of women’s leadership in economic development; and (c) encourage a shift in social norm/gender roles in sharing housework. Outcome 2: The project has enhanced women's and youth-led value chains' competitiveness, safety and sustainability. COVID-19 safe food standards, good practices and technologies were developed/promoted along the value chains. 10 Standard Operating Procedures (SOP) from farm to market covering a) disease management; b) cool chain; c) transportation; d) traceability systems; e) packhouse quality management; f) field practices for quality management and preparing training were developed and applied in the mango and pomelo value chains. About 400 value chain actors were trained on the SOPs. The training on SOPs aimed to shorten national supply chains, ensure the correct use of agro-chemicals, introduce more effective post-harvest handling and treatments to increase shelf-life, and upgrade quality control at all levels of the supply chain, and, ultimately, produce value-added products. The women- and youth-centred mango and pomelo value chains were upgraded through direct support for the application of good practices (SOPs, VietGaP/GlobalGab). In addition, two electronic supply chain management platforms were developed to establish a coordinated and digitally linked supply chain from farm to market. Outcome 3. The project has improved access to new markets for women and youth mango and pomelo producers through increased digital access to value addition, branding, promotion and e-commerce. Introduction of 4 new value addition models (e.g. dried mango, pomelo juice, pomelo oil, fresh mango, fresh pomelo). Six e-commerce platforms and 10 supermarkets/shop chains have been introduced to interested cooperatives and enterprises for better linking up to the market. One workshop and 9 business matching meetings were facilitated to link producers to existing and new buyers and processors. 14 long-term contracts between farmers and enterprises were established. An export promotion plan was developed with a model marketing plan which provided strategic recommendations to the targeted export markets. 2 manuals on branding were developed and 200 stakeholders were trained.
3.1 | Results: Output Level | Please include narratives describing the main annual/ final results of each output included in the project document (up to 200 words) | Output 1.1 Women-led farmer groups mobilized and strengthened through communication tools: 2 women’s unions, 2 youth unions, 2 farmer’s unions and 71 groups in Dong Thap province and Ben Tre province were guided by professional institutions to lead the surveys and organize 80 training courses to improve skills in production, business planning, financial management, e-commerce, etc. for more than 2,500 members. The collaboration and coordination among these representative groups were strengthened. Output 1.2 Enhanced capacity and accessibility of women and youth-focused support services: IFAD linked the provinces with the One Cooperative One Product (OCOP) digital platform to utilize the ICT-based marketing application. This was to promote and increase market access for mango and pomelo products. UNIDO provided technical assistance to develop the digital ecosystem platform for the tropical fruit value chains, piloted for pomelo and mango. The platform enables all types of actors such as enterprises along the value chain, business services, and support institutions both technical and financial to access the platform. Via the platform, they can connect to business partners and/or access necessary support services and information. In addition, 56 training classes were organized for 1,500 value chain actors to improve the capacity of women and youth in moving towards agricultural 4.0. The classes trained them in the application of digital technology to meet the market requirements and access markets. Output 1.3 Policy and advocacy platform established and maintained: 5 dialogues and 27 trainings with 847 female and youth participants were organized on (a) promotion and scaling up of women and youth-centred value chains; (b) promotion of women’s leadership roles in economic development; and (c) promotion of social norm change on gender roles in sharing the housework. In addition, 3 dialogues with financial institutions were organized to support 250 women/youth to access finance and support policies. A plan for the policy and advocacy activities has been developed for each province. Output 2.1 COVID-19 safe food standards, good practices and technologies developed/promoted along the value chain: 10 Standard Operation Procedures (SOPs) from farm to market for mango and pomelo value chain were developed with 10 training modules. About 400 value chain actors were trained on the SOPs. The SOPs were also digitalized and e-learning courses were developed to enable more learners/stakeholders to access them. In addition, training courses for 490 households on the application of VietGap/GlobalGap were organized. 6 Production Unit Codes (PUC) and 2 Packing House codes (PHC) for export were developed for mango and green-skinned pomelo products in the 6 pilot areas and 2 cooperatives. 18 training courses on PUC & PHC were organized for 657 producers and packing houses. Output 2.2 Women- and youth-centred value chains established and upgraded: The application of SOPs was piloted and will be upscaled to increase compliance capacity along the mango and pomelo value chain. In addition, technical support and VietGAP certification were provided for 155 households growing green skin pomelo covering an area of 84.36 ha, 11 households growing seasonal mango with an area of 4.58 ha and 3 cooperatives of mango production with a total area of 45ha. Support to implement a pilot application of 4.0 technology and smart equipment in green-skinned pomelo production was given. This included providing 100,000 QR code stamps to 100 households, an intelligent pest and disease monitoring system for 45 households with integrated edge computing cameras, a smart water quality monitoring system and smart water pumping system for 15 households in the area of 2 hectares, and 6 training courses on traceability for 300 VC actors. Output 3.1 Women and youth-led innovation through value addition, branding, promotion and e-commerce: An in-depth assessment to identify opportunities for value addition in the 6 selected women- and youth-led cooperatives and enterprises were conducted. Technical assistance (technical and equipment support) was provided for these cooperatives to improve product packaging, proper post-harvest handling, increase the quality of products, increase shelf-life of the product, and reduce post-harvest loss etc. 4 product innovations were developed and introduced: increased compliance capacity for fresh mango and pomelo export, pomelo oil, pomelo juice, dried mango. The market accthe ess was facilitated for 28 products. 4 manuals on produ ng value-added products were developed for sharing good practices in the MRD provinces. This information was also disseminated through a series of training. 2 manuals on branding were developed and 6 training courses were organized for 200 local management staffs, cooperatives and enterprises. Six e-commerce platforms and 10 supermarkets/shop chains have been introduced to interested cooperatives and enterprises for better linking up to the market. An export promotion plan was developed with a model marketing plan to provide strategic recommendations to the targeted export markets. 6 companies were coached for developing their export development plans.Technical support was provided to the Ministry of Agriculture and Rural Development to develop a road map of activities aiming at providing information and training tools to agencies, companies, cooperatives and associations for development of branding strategy for tropical fruit industry. Output 3.2 Farm-enterprise, enterprise to enterprise contracts established: One workshop and 8 buyer meetings were organized to identify potential buyers and to link producers to existing as well as new buyers and processors. 43 long-term MOUs farm to enterprise business relationships were signed. These were based on the principles of reciprocity.
3.2 | Results: Gender | Please include project Gender results and its linkage with COVID- 19 response. If applicable, refer to the project's gender equality marker and any impacts they may have had on programming quality and results (up to 150 words). | The project placed rural women and youth who have been particularly impacted by the Covid-19 pandemic at the centre of attention. From support to the establishment of norms and standards for COVID-19 safe and sustainable products, to building capacity of extension services, the project has ensured a thorough gender-sensitive analysis (including assessment of digital skills levels and access to ICT improvement which are central to the project) and interventions to specifically improve conditions of women in the fruits supply chain. The project pursued a gender-responsive approach in organizing any pieces of training, i.e. taking differential needs of women and men into account as to timing and safety considerations. The project engaged women and youth and promoted their role in the project not as mere beneficiaries but rather as leaders and partners of the project for the delivery of results.
3.3 | Results: Direct Beneficiaries | Please include total number of DIRECT BENEFICIARIES disaggregated by gender, age , location (rural, urban, any other location). Please avoid duplicating beneficiaries ensuring the dissagregated data adds to the total presented. | Women and youth in Dong Thap and Ben Tre provinces working along the mango and pomelo value chains are the core target beneficiaries and intended change agents of the project. 2,576 rural households, 99 cooperatives/groups, and 15 enterprises 8,646 beneficiaries (of which 3,300 female, 257 youth), of which - Ben Tre province: 4,271 beneficiaries (1,540 female, 127 youth) - Dong Thap province: 4,457 beneficiaries (1,760 female, 130 youth)
3.4 | Results: Indirect Beneficiaries | Please include total number of INDIRECT BENEFICIARIES. Please clarify if these are estimated and/or verified. If possible, disaggregate beneficiries by gender. | Moreover, rural small and medium enterprises including wholesalers, transportation, storage and local input suppliers will also benefit from the outputs of the proposed project. Total estimate: 20.913 indirect beneficiaries (9130 female and 749 youth)
3.5 | Do not Harm | Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention. ( up to 100 words) | The project liaised with the Farmers’ Union and the Women and Youth Unions at District and Commune levels to validate the project approach and interventions and to strengthen its impact on gender equality and empowerment of women. The identification of women and youth growers – and the groups they are part of – was greatly facilitated by these unions. The project provided skills training for women and young farmers and entrepreneurs and strengthened the capacities of their organizations, such as the Women’s Union and farmer groups/cooperatives. The project is expected to serve as a model to ensure more equality during the economic recovery process from the COVID-19 pandemic for women and young farmers which are among the most vulnerable groups. The project uses gender-sensitive language; follows equal representation principles in any photographs/other depictions and pays attention to not reproducing any (gender) stereotypes.
3.6 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken to achieve the expected results) Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms(use up to 150 words). | Due to the Covid-19 pandemic situation, there has been restricted international and local travels, which delayed the mission of consultants and service providers. More virtual meetings and increased use of e-communications, virtual training etc have been taken.
3.7 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) (up to 250 words) | The COVID-19 situation affected the project implementation in several ways. For example, it restricted local travel and made the physical presence of international experts impossible. In the region, there has been big congestion of agro-products at the border gates with China (a major export market) for customs clearance which was slow because the two governments have to strictly implement measures to prevent and control Covid-19. In addition, exports to other countries have been limited. Domestic consumption in the short term could not be changed immediately to meet the large volume of surplus due to non-export. The country's agricultural sector is needed to re-strategize to open new markets and meet the increased requirements in terms of quality and compliance to ensure food safety and create trust. The overall demand for high-quality and safe food is rising, especially in urban areas, as local markets in Viet Nam receive more attention while export markets have contracted as a result of COVID-19. Opportunities for a COVID-19 safe value chain include (i) COVID sanitized and certified transport and tracing systems for agricultural produce and farm inputs; (ii) cold storage and packaging facilities to prevent goods from perishing; and (iii) digital extension and e-commerce (ICT) to mitigate the impact of physical distancing and to speed up trade. Even though digitalized agriculture sector and rural areas are the government's top priorities, the implementation is fragmented due to the lack of coordination, resources and technical capability of the government institutions, business development service providers and the value chain actors. The application of digital technology along the value chain should aim to bring benefits to all the stakeholders (i.e. bringing more profit and business opportunities to the farmers and SMEs, supporting Government management and decision making, improving the transparency and traceability of the value chains/produce). The project is working to create such a digitized value chain model for policy advocacy and replication.
3.8 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 250 words) | Partnerships were envisioned during the implementation phase with both national and international institutions such as: (i) National Coordination Office for NTP-NRD and OCOP; (ii) Central Committee for Ethnic Minorities (CEM) for integration with the NTP-EMD; (iii) the Mekong Delta Coordination Committee (MDCC) established by the Prime Minister Decision on 12 June 2020; (iv) the Ministry of Agriculture and Rural Development (MARD) and the development partners under the International Mekong Delta Working Group (MDWG) for implementation of the Mekong Delta Agriculture Transformation Programme; (v) the World Bank’s Mekong Delta Integrated Climate Resilience and Sustainable Livelihoods Project working in both Ben Tre and Dong Thap provinces; the project “Green Innovation Centres for the Agriculture and Food Sector” (GIZ), the project “Enhancing Global Competitiveness of Vietnam’s dragon fruit through Improving Quality Infrastructure in the Value chain” (IFC), the project “Improving smallholder farmer incomes through strategic market development in mango supply chains in southern Vietnam” (ACIAR), the project "Traceability development for export" (DFAT), and the project "Safe food for growth" (Canada). In addition, the project’s scope is catalytic and fully compatible with the other country programs of IFAD and UNIDO in Vietnam. The IFAD-funded Adaptation in the Mekong Delta project (AMD) in Ben Tre and Tra Vinh provinces in the Mekong Delta has provided the basis and experience to develop and modernize the proposed value chain. IFAD through the AMD has promoted climate-smart, pro-poor value chain development including value chain finance approaches. UNIDO has established a Center of Excellence for mango harvesting, packing operations, storage and transport in the Mekong River Delta. In addition, UNIDO is providing technical assistance to increase the quality and standards compliance of the mango value chain in the region through Global Quality and Standards Programme (GQSP). In response to the Covid-19 challenges – and in line with the government’s dual goals (response and recovery) – the Ministry of Agriculture and Rural Development (MARD) foresees a continued restructuring of agriculture, utilizing cutting-edged technology, empowering its position in the supply chain, increasing the value-added and enhancing the competitiveness of Vietnamese agricultural products. A partnership model of 4 partners including the Ministry of Agriculture and Rural Development (MARD), the Women's Union, the Farmers' Union, and the Youth Union was established to facilitate agricultural product consumption. This has been a successful model to connect demand and supply in the context of the complicated development of the COVID-19 epidemic. The project could use this model and foster the partnership better.
3.9 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken (up to 200 words). | The PMUs have conducted a review of experience and lessons learnt from completed and on-going projects/programs in Ben Tre and Dong Thap provinces. A number of surveys and in-depth assessments on mango and pomelo value chains, including market assessment, have been conducted. In addition, the Project Completion Report (PCR) of the IFAD-supported Climate Change Adaptation in Mekong Delta (AMD) is a resourceful assessment of the on-going initiatives for the women and youth development.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place (Up to 100 words). | N/a
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | The Government and IFAD have approved a continued IFAD investment to the Mekong Delta, the Climate Smart Agriculture Transformation in Ben Tre and Tra Vinh provinces (CSAT) project, which is going to start and maximize impacts of the MPTF support. The MPTF project activities will be integrated with the CSAT programme which has mobilized partnership with DFCD, SNV and IDH. In additon, UNIDO is developing the 2nd phase of the Global Quality Infrastructure and Standard programme which continues to focus on increasing the compliance capacity of tropical fruit value chain in the Mekong River Delta.

## Project indicators
| Achieved Indicator Targets (2021-2022) | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1 Women and youth centred digitally enhanced business enabling environment |  |  | Project reports, PMU reports
Indicator: District agencies pursue and support women and youth centred business in at least one fruit value chain
Baseline:
Planned Target: Twelve Districts report concerted efforts by agencies in at least one fruit value chain | 14 districts
Output 1.1 Women led farmer groups mobilized and strengthened through digital communication tools | 2,576 rural households, 99 cooperatives/groups, and 15 enterprises 8,646 beneficiaries (of which 3300 women and 257 youth) |  | Project reports, PMU reports
Indicator 1.1.1: Number of organised women and youth partaking in the programme
Baseline:
Planned Target: 2,000 female and/or young fruit producers participate in the model value chain support programme by the end of 2021
Output 1.2 Enhanced capacity and digital accessibility of women and youth-focused support services (ICT, finance, extension, business advisory, skills development, etc.) |  |  | Project reports, PMU reports
Indicator 1.2.1: Frequency of using digital platforms to establish, maintain or use value chain relations
Baseline:
Planned Target: 80% of groups report using the digital platforms at least weekly | 100%
Output 1.3 Policy and advocacy platform for (a) the promotion and scaling up of women and youth centred value chains; (b) promotion of women’s leadership roles in economic development; and (c) the promotion of social norm change on gender roles in sharing housework |  |  | Project reports, PMU reports
Indicator 1.3.1: # of significant Provincial Resolutions promoting women and youth centred value chains
Baseline: |  |  | Project reports, PMU reports
Planned Target: One Provincial Resolution (per Province) articulating steps for promoting women and youth centred value chains | 2
Outcome 2 Enhanced competitiveness, safety and sustainability of women and youth-led value chains |  | The reporting time is at the same time of technical assistance have been provided. It means that there's not enough available information to measure the increase sale in $. It requires more time after the intervention to monitor better impact in terms of $ increased sales
Indicator: $ of sales, % increase is sales volume and value |  |  | Project reports, PMU reports
Baseline:
Planned Target: Target increase in $ of sales to be determined 30% increase in sales volume/value | 12% in sales
Output 2.1
Indicator 2.1.1: COVID-19 safe food standards, good practices and technologies developed/ digitally promoted along the value chain |  |  | Project reports, PMU reports
Baseline:
Planned Target: # of good practices, pre-and post-harvest technologies applied by the value chain operators | 10 SOPs, 2 new post-havest technologies, 2 VietGAP/Global Gap
Output 2.2 Women and youth centred digitally enhanced value chain upgraded
Indicator 2.2.1: # of value chains upgraded/created to explicitly benefiting women and youth producers |  |  | Project reports, PMU reports
Baseline:
Planned target: 1 model fruit value chain established | 2 value chains (mango, pomelo)
Outcome 3 Improved digital access to new markets for women and youth
Indicator: # of beneficiaries using digital access technologies |  |  | Project reports, PMU reports
Baseline:
Planned Target: 5 enterprises | 15 enterprises & cooperatives access to new markets through e-commerce platforms, QR code, websites, etc.
Output 3.1 Women and youth led innovation through increased digital access to value addition, branding, promotion and e-commerce
Indicator 3.1.1: # of diversified primary products / product market combinations |  |  | Project reports, PMU reports
Baseline: | 4 new innovative products introduced
Planned Target: 2 innovated primary products accessed to the markets | 28 products accessed to the markets
Output 3.2 Farm-enterprise, enterprise to enterprise contracts digitally facilitated and established
Indicator 3.2.1: # of producer – enterprise business relationships per producer group established digitally |  |  | Project reports, PMU reports
Baseline:
Planned target: 3 digitally facilitated business relationships with growth potential per producer group | 43 producer-enterprise contracts established
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant.
In 2018, Giong Trom Green-skinned Pomelo Cooperatives had a sale volume of 122 tonnes of pomelo, reaching revenue of 6.5 billion VND. While green-skinned pomelo is listed as one of 7 types of fruit trees to be developed in addition to coconut tree - the main tree of the province, the cooperatives and each of its participating households have been heavily affected by Covid-19. During the pandemic, the supply chain for pomelo was interrupted since market demand for food decreased, due to both reduced demand from international markets as well as from local consumers. Harvested pomelos could not be sold, causing waste and income losses to participating households. “Women had to stay home, doing housework and taking full-day care of their children since schools were closed. Many young people either lost their jobs or had to stay home without income.”- said Nguyen Van Bay - Head of Giong Trom Green-skinned Pomelo Cooperatives. Nguyen Thi Ven, one of the women in Giong Trom Cooperatives, faced the same difficulties during Covid-19. Her husband went to work in Ho Chi Minh City and then stuck there for 4 months due to prolonged lock-downs. Without her husband, all the burden fell on Ven’s shoulders. She was taking care of her 2 children and the pomelo farm all alone. When the project “Building Forward Better: A Resilient Women and Youth Centered and Digitally Enhanced Value Chain Development in Vietnam” was implemented in Giong Trom Green-skinned Pomelo Cooperatives, the participating households, including Ven, were supported to tackle some main challenges through a number interventions. Women, youth, and other members of the community have their capacity increased through hands-on training and guidance of good practices and the application of ICT. As a result, they are more confident and capable to apply the new knowledge in their farming, have a better understanding of e-commerce, and would be able to do their transactions online in the future. The practice of applying new practices such as smart fertilizer is introduced to the farmers in the Cooperatives. “Thanks to the project, I got to know about smart fertilizer. After joining a demonstration at my neighbor's pomelo farm and knowing about the fertilizer, I quickly started using it for my farm. This kind of fertilizer dissolves slowly, allowing the soil and the plants more time to absorb and make full use of it. The old fruit trees in my farm have been revived.” - shared Mrs.Ba, one of the women in the Cooperatives. A series of training to use digital tools in farming were also provided. At the same time, a smart pest monitoring system, combined with a watering control system, was supported to be installed in one central household. The comprehensive data it provides has benefited all other farmers in the area. Once they installed the app on their smartphones, they can all track the data such as the density of pests, water quality, and fluctuations in the temperature in the area. “I use the app to see changes in the environment and make better decisions for our crop. Therefore, we can save costs. With the new tool and knowledge, I am more confident to continue my work.” - said Mrs. Ven, showing the mobile app on her phone. Leaders of Giong Trom Cooperatives also registered their product code with VietGAP certification and use the QR code on every pomelo. This increases the credibility of their products and boosts consumption through wholesale and retail stores. The Cooperatives also joined the development of long-term farm-to-enterprise business relationships that are based on principles that support reciprocity and mutual benefits. Through the project, the Cooperatives has signed agreements with companies to sell pomelos. “The project is a new driving force for us to recover after Covid-19. We can regain our sale volume and also get other households in the areas to join the Cooperatives thanks to its benefit.” - said Mr. Bay.
Photos of story: https://drive.google.com/drive/folders/1PrVAZPlZa_ZEt7oPjG4QU3KyFVieLhkO?usp=sharing
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
Press clipping
NEWS VIDEOS
Opening of Dong Thap Mango Week: https://youtu.be/-pk187NQWf0 Rountables of Women and Youth on economic developments: https://youtu.be/VNjB1Q7ScEA IFAD and UNIFO supporting fruit consumption for farmers: https://youtu.be/Q79usaRwGf0 IFAD and UNIDO supporting smart agriculture: https://youtu.be/T8_D0dMQ43E Workshop on women and youth participation in fruit value chain in Ben Tre (from 17:00): https://youtu.be/exPHe6QYbxM Smart pest monitoring system in Ben Tre: https://www.youtube.com/watch?v=fEkAcMOCQrw Workshop on Digital Transformation in Agriculture: https://youtu.be/7mWgNMYiHzI
PROGRAMME SUMMARY VIDEOS
Ben Tre MPTF project summary: https://www.youtube.com/watch?v=7Xo5-34VFOc
Dong Thap MPTF project summary: https://drive.google.com/file/d/10W8Sytxs48V5Oq_QuFR0GuEKqb0iTgam/view?usp=drivesdk
NEWSPAPER ARTICLES
Bao Dong khoi (Dong Khoi Newspaper - Ben Tre Province) https://baodongkhoi.vn/trien-khai-du-an-mptf-ben-tre-21022022-a97096.html https://baodongkhoi.vn/hoi-thao-nhan-rong-mo-hinh-chuoi-gia-tri-ung-dung-cong-nghe-so-24052022-a100801.html https://baodongkhoi.vn/ung-dung-thiet-bi-thong-minh-vao-quan-ly-canh-tac-va-truy-xuat-nguon-goc-buoi-da-xanh-ben-tre-06052022-a99978.html https://baodongkhoi.vn/chia-se-gioi-thieu-ung-dung-cong-nghe-so-trong-nong-nghiep-08042022-a98899.html https://baodongkhoi.vn/hoi-thao-danh-gia-tac-dong-du-an-amd-08032022-a97711.html Bao Dong Thap (Dong Thap Newspaper) https://www.baodongthap.vn/kinh-te/unido-va-ifad-ho-tro-xay-dung-du-an-phat-trien-chuoi-gia-tri-trai-cay-tai-dong-thap-103188.aspx UN Vietnam https://vietnam.un.org/en/129977-unido-va-ifad-hop-tac-khoi-dong-du-moi-de-phat-trien-chuoi-gia-tri-trai-cay-tai-vung-dong https://vietnam.un.org/en/129976-unido-and-ifad-join-hands-launch-new-project-develop-fruit-value-chain-mekong-river-delta Đài phát tranh và truyền thình Đồng Tháp http://thdt.vn/mot-ngan-ho-dan-se-duoc-huong-loi-tu-du-an-ifad-va-unido-trien-khai-tai-dong-thap.html Tin tức miền Tây (The West News) https://tintucmientay.baoangiang.com.vn/unido-va-ifad-ho-tro-xay-dung-du-an-phat-trien-chuoi-gia-tri-trai-cay-tai-dong-thap-a323743.html Tạp chí Tài chính (Finance Magazine) https://tapchitaichinh.vn/tai-chinh-kinh-doanh/day-manh-xuc-tien-dau-tu-vao-linh-vuc-nong-nghiep-nong-thon-343511.html Sở Nông nghiệp An Giang (An Giang Agriculture) https://sonongnghiep.angiang.gov.vn/wps/portal/Home/2018/home/tin-chi-tiet/!ut/p/z0/fYyxDoIwGISfhpH0b4GWjiYkirgYEwNdTCUN_EJakGJ8fKuLcXG6u-8uRxSpibL6gZ326KweQ24Uv0hZlFCl9JCXnMIxLdLz9lTBrmBkT9T_QXjA2zyrDVGts948PakXZ53tbNejmeIRrxH8kAW9CUjHHq1f22Ud0NgP-I78PdjQ9xHkUgJQyliSZBnnQuSBvFUIANAUKANGpkE1L10R3_4!/#gsc.tab=0 Nông nghiệp Việt Nam (Viet Nam Agriculture) https://nongnghiep.vn/nang-cao-nang-luc-tuan-thu-cac-quy-dinh-doi-voi-xoai-xuat-khau-d288237.html Pháp luât Việt Nam (Viet Nam Law) https://baophapluat.vn/tieu-dung-va-du-luan/thi-truong-xuat-khau-xoai-cua-viet-nam-con-rat-lon-583490.html Dong Thap GOV https://dongthap.gov.vn/chi-tiet-bai-viet/-/asset_publisher/1mOzUrGkrdAE/content/id/11044829?plidlayout=34 Thanh Nien - Youth newspaper http://thanhnienviet.vn/2022/05/16/dong-thap-to-chuc-tuan-le-trai-cay-truc-tuyen/?zarsrc=31&utm_source=zalo&utm_medium=zalo&utm_campaign=zalo Industry and Trade https://congthuong.vn/khai-mac-tuan-le-xoai-va-trai-cay-chu-luc-dong-thap-177907.html
PHOTOS
All photos captions (word document): https://drive.google.com/drive/folders/13ntkulyNKwklYpN1XBXi2r-zuNIIv-1S?usp=sharing
A. General photos - Link to HD: https://drive.google.com/drive/folders/1Q-sDJjVoIvfeniV3_ooResBL6KtqC7BC?usp=sharing
B. Ben Tre photos - Link to HD: https://drive.google.com/drive/folders/1oVS9V6dTyzx82qG8iAfIw0bbbGpekWdf?usp=sharing
C. Dong Thap photos - Link to HD:https://drive.google.com/drive/folders/1DxaOsRK9qkZEmv4SRio4JRQQUZeNhG_B?usp=sharing