## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | INTERIM REPORT
DEADLINE:
4 | ALL Call 2 projects must complete an interim report
5 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Interim
Programme Title & Project Number |  | Programme Duration
Programme Title: | Socio-Economic Empowerment of Vulnerable Women in Ghor Al Safi through Improving Access to Safe and Green Public Spaces | Overall Duration (months) | 12
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2021-01-28
MPTF Office Project Reference Number:[2] | 22829-001 | Original End Date (dd.mm.yyyy) | 2022-01-14
Country | Jordan | Current End date(dd.mm.yyyy) | 2022-06-30
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UN-Habitat, UNOPS, and ILO | National counterparts (government, private, NGOs & others) and other International Organizations | Zaha Cultural Centre, the Southern Aghwar Municipality (also referred to as the Municipality of the Southern Jordan Valley), and Jordan River Foundation (implementing partner with ILO)
Report Cleared By
o Name: | Husam AlKayyali
o Title: | Partnerships & Development Finance Officer
o Email address: | husam.alkayyali@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Interim
# | Questions | Guidance to respondents | Responses | Comments
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | In response to the COVID-19 pandemic and growing vulnerabilities among marginalized women, UN-Habitat, UNOPS, and ILO have implemented the “Socio-Economic Empowerment of Vulnerable Women in Ghor Al Safi through Improving Access to Safe and Green Public Spaces” programme, in collaboration with Zaha Cultural Centre and the Municipality of the Southern Jordan Valley, who will manage the rehabilitated public space and community centre. The programme followed an integrated participatory approach that began with the UN-Habitat Public Space Site-Specific Assessment, which assessed the communities' perceptions of safety, accessibility, and inclusivity. Through interviews, community consultation sessions, and explorations, the design was participatorily developed. When presented with the design of the site in a consultation session, the community expressed a positive response, with one calling the project "every child's dream." After the finalization of the design and BoQs, the UN partners met with the Ministry of Planning and International Cooperation to receive approval of the programme, as part of a new regulation needed for local partners. Following this, in October 2021, the partners visited Ghor Al-Safi to reflect and discuss the next phase with the His Excellency the Administrator of the Southern Jordan Valley Brigade, local community representatives, and other stakeholders. In March 2022, UNOPS completed the rehabilitation of the public space and community centre, and have since conducted follow-up visits. The public space now includes inclusive play areas, shaded seating areas, a multi-use area designated for social and cultural activities and for a market, and a permaculture area. The multi-service community centre within the public space has been rehabilitated and expanded, and will host the tailored training for women and youth. Based on a community needs assessment conducted by Zaha Cultural Centre, the community centre’s package of services is being developed, whereby a core component will focus on livelihoods and business development. UN-Habitat has bought 10 market stalls and equipped the community centre with the necessary furniture and amenities to ensure that the planned activities are best accommodated. An official opening day is being organized. Additionally, 28 staff and community members have received Training of Trainers session on Business Development Services and138 women have been trained on the Women Do Business Programme. 32 business proposals have been funded following the ILO evaluation criteria. 132 job seekers (83% females) were linked to existing ILO employment platforms with specialized training sessions on grievance redress mechanism, labour rights, trade unions, and other decent work aspects, while 13 women were trained on professional caregiving. Training partner institutions (TPIs), including Zaha Cultural Centre, Development and Employment Fund, and Jordan River Foundation were targeted in a specialized training workshop to manage the WDB programme. Furthermore, UN-Habitat conducted a sustainable agriculture training at the newly rehabilitated public space. The knowledge acquired from these different trainings can be shared across the community. An MoU agreement between Zaha Cultural Centre and the Municipality of the Southern Valley has been signed. Accordingly, through this fund, this programme has established a communication platform between the UN partners, the community, local officials, and NGOs. | The Executive summary is comprehensive and well written but it should be shortened to 500 words maximum as per the guidelines. Currently, it is 1008 words. (COMPLETED: NOW 499 WORDS)
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | This programme endeavors to benefit the whole Ghor Al Safi population and the underserved neighboring communities. The public space and community center will directly benefit the 37,040 Ghor Al Safi inhabitants, of which 46% of the population are women. Post-implementation, the project will indirectly benefit at least 26,868 more people from the underserved communities of El-Mazraa, Al-Maamoura, and Ghor Fifa. These communities are classified as poverty pockets and, like Ghor Al Safi, do not have adequate and safe public spaces. This project's direct and indirect beneficiaries will be different groups of vulnerable women, Syrian refugees, vulnerable youth, people with disabilities, and women-headed microenterprises. The project will work closely with a local NGO to ensure a strong gender perspective of the deliverables and use their networks to reach the most vulnerable social groups. The project will also directly work with the Municipality and local NGOs to provide them with the capacity to target vulnerable and marginalized populations with their COVID-19 responses effectively. In the long term and post-implementation, it is expected that the whole of the Ghor Al Safi population and their underserved neighboring communities will enjoy improved access to safe, inclusive, and green public spaces and community centers. It is expected that the public space itself will have at least 10,000 visitors per year. This will be ensured through multiple events, such as a minimum of 15 market fairs and three annual festivals. Additionally, Wadi Hasa, located on the outskirts of Ghor Al Safi, is a significant tourist attraction across Jordan, especially for those living in the nearby Amman. It could thus draw in more visitors to the nearby public space and the various events that will be held, which will create an opportunity for women in Ghor Al Safi to promote and sell their products. 10 stalls have been purchased by UN-Habitat and a kiosk has been built to be used durng these market place events. During the reporting period, the programme has conducted a Site-Specific Assessment, which has directly engaged regular park users and those living within the walkable radius, and held two community consultation sessions in Ghor Al Safi to develop the design and operational plan. Due to the high number of COVID-19 cases and gathering restrictions during Ramadan, 8 participants from the Ghor Al Safi community attended the first community consultation session, four women and four men. After Ramadan, 66 participants from the Ghor Al Safi community attended the second community consultation session, 49 women and 17 men, with approximately 34% being between the ages of 17-25 years old (Youth). Additionally, a community needs assessment conducted by Zaha Cultural Center engaged 55 community members, 31 females and 14 males, whereby 19 members were between the ages of 17-25, 12 between the ages of 26-35, 13 between the ages of 36-45, 6 between the ages 46-55, and 2 between the ages 56-65. The recruited architectural firm has developed the detailed architectural design for the community center and the public space and has finalized the technical drawings and bidding documents. In addition, 17 women and 1 man received a three-day training on sustainable agriculture methods, which took place in the newly rehabilitated public space and community center in Ghor Al Safi and aimed to strengthen the local community’s capacities on green architecture and permaculture methods that can be implemented at the household level to provide livelihood opportunities and improve food security, thus decreasing COVID-19’s socioeconomic impacts, and fostering social advancement and cohesion among community members. The trainees can in turn transfer the knowledge to additional trainees and apply the newly acquired skills in a number of sites. As part of outreaching for potential beneficiaries for Women Do Business (WDB) training. 140 Women from Ghor Al-Safi applied for WDB training following the developed ILO criteria, whereby 139 of the applicants started the training with 138 of them completed the WDB training course. the patricipants submitted their business plans which were evaluated for seed funding, evaluation committee has evaluated the proposed plans, and 32 of them were funded to start up their own businesses (exceeded the target with 15). The funded businesses included food production, printing, garment, manufacturing, mosaic and others. Market Linkages/Bazar and Graduation Ceremony to celebrate the project businesses were conducted. For the ToT training in Business Development Service (BDS), 28 trainers have been identified from Zaha Cultural Center and other NGOs in Ghor Al-Safi for the ToT training, of which the 28 trainers, 20 females and 8 males, have completed the training and certified in the programme (with 3 trainers above the targeted 25 trainers). 19 trainers are from Ghor Al-Safi area (4 males, and 15 females) and 9 from Zaha Cultural Centre (4 males, and 5 females). 132 job seekers (83% of them are females) were linked to existing ILO employment platforms with specialised training sessions on grievance redress mechanism, labour rights, trade unions, and other decent work aspects, while 13 women were trained on professional caregiving. In addition to the trainers whose main role is conducting training for women entrepreneurs, the ILO WDB programme trained the training services providers (TSPs) and the training partner institutions (TPIs) to make sure that they will be able to manage the WDB training and liaising with the ILO and other TSPs in the country to coordinate the WDB training for future works. A training workshop targeted 3 TPIs with 13 participants from Zaha cultural centre (6 participants), Development and Employment Fund (3 participants), and Jordan River Foundation (4 participants). Following this training, and to make sure that Zaha Cultural centre has the privilege to manage and implement the WDB programme, a Memorandum of Agreement is prepared and cleared by ILO to be signed with Zaha Cultural Centers.
3.1 | Results: Outcome Level | Please include outcome level results achieved | The results of both outcomes will be achieved clearly post-implementation since they are more focused on long term impact and results, which can’t be currently measured.
3.2 | Results: Output Level | Please include output level results achieved | Results/deliverables under Output 1.1: Gender-inclusive, safe and accessible public space established in Ghor Al Safi: - A site-specific assessment was conducted on the project site. The report includes the findings and recommendations under the five dimensions of Use and User, Accessibility, Amenities and Furniture, Comfort and Safety, and Green Environment based on community perceptions was produced (please find attached). - The topographic survey for the site was conducted to document the exact levels in the site, and a Topographic Survey report was produced (attached). - A Community consultation session was held with the local community in Ghor El Safi on 19 April 2021 to listen to the community's needs and aspirations from the project and also to validate the findings of the Site-Specific Assessment. Due to the high number of COVID-19 cases and gathering restrictions during Ramadan, eight participants attended the session, including four women and four men. - The Conceptual Design of the public space and the community Centre was developed by the recruited architectural firm and presented to the Ghor Al Safi community. The feedback received from the local community was incorporated into the revised version of the design. - A second community consultation session was held with the local community on 19 May 2021, where the lead architect Dr. Rami Daher presented the design ideas and listened to the community's feedback. The consultation session was attended by 66 participants from the Ghor Al Safi community, including 49 women and 17 men, with approximately 34% being between the ages of 17-25 (Youth). - Additionally, a community needs assessment conducted by Zaha Cultural Centre engaged 55 community members, including 31 females and 14 males, whereby 19 members were between the ages of 17-25, 12 between the ages of 26-35, and 13 between the ages of 36-45, six between the ages of 46-55, and two between the ages of 56-65. - On 5 July 2021, UNOPS, in coordination with UN-Habitat, conducted a meeting with the engineering company contracted by UN-Habitat to discuss the preliminary design that was shared with UNOPS and provided insights and comments. Moreover, UNOPS conducted additional two meeting with the engineering company on 24 August and 6 September 2021, to further review the design specifically in terms of the availability of male and female separate facilities , safety of the structural design , accessibility for people with disabilities, and sustainability and accordingly requested some modifications in the design such as adjusting the bill of quantities to match the drawings, installation of Emergency Kits for lighting fixtures, using waterproof socket outlets inside the kitchen, modifying the electrical boards to add safety against electrocution as well as including grab bars for disability toilets. - On 15 September 2021, UNOPS received the final design documents from UN-Habitat, which were approved by UNOPS HQ on 6 October 2021. - By 10 October 2021, UNOPS developed an Environmental Management Plan (EMP) for physical infrastructure work, with the objective to implement infrastructure projects in a way that mitigates environmental damage. UNOPS also developed a Health & Safety, Social and Environment (HSSE) plan during the implementation of this project in order to better address environmental and health and safety-related issues. Both plans were included in the tendering package in preparation for launching the tender for the construction and rehabilitation works. - On 14 October 2021, UNOPS launched the tender for construction, which closed on 31 November 2021. However, the tender was canceled as the provided bids exceeded the budget. - On 18 October 2021, a no-cost extension was requested until 31 October 2022 in order to absorb the significant delays in the development of the design due to the Covid-19 pandemic accompanying measures. However, on 21 December 2021 UNOPS received the feedback that the extension is granted only until 30 June 2022 leaving UNOPS with only 81 days for concluding the construction and rehabilitation works. - On 1 December 2021, UNOPS re-launched the tender for the construction, which closed on 16 December 2021. - On 23 December 2021, through the UNOPS esourcing system requested the most technically compliant bidder with competitive prices to further reduce the provided costs if possible, which resulted in a 3% reduction in costs. - On 10 January 2022, UNOPS signed the contract for the rehabilitation of one public space and one community centre in Ghor Al Safi with the contractor. - To emphasize zero-tolerance toward Sexual Exploitation and abuse (SEA), and to mitigate the SEA risks associated with its infrastructure works projects, UNOPS integrated Prevention of Sexual Exploitation and Abuse (PSEA) measures within the project including specific SEA clauses in all its contracts with contractor and suppliers, outlining the prohibition of SEA and the obligation of contractors to prevent and report it. - On 14 February 2022 , UNOPS conducted awareness-raising sessions/training for the contractors on sexual harassment and PSEA (Protection from Sexual Exploitation and Abuse), including their obligation to report any allegations of SEA to UNOPS. Finally, UNOPS conducted sexual exploitation and abuse (SEA) risk assessment at the project location in Ghor Al Safi before commencing the works to support the contractor in identifying the appropriate mitigation measures for SEA and sexual harassment (SH). On the same day, UNOPS also conducted PSEA risk assessment to the project site. - On 31 March 2022, UNOPS handed over the rehabilitated public space and community centre in Ghor Al Safi to the beneficiary (The Municipality of the Southern Jordan Valley). - Between 1 April and 30 June 2022, UNOPS conducted regular follow up visits to the project site and community centre in Ghor Al Safi for any defects that may have appeared during the Defect Notification Period (DNP) and provided the necessary repairs. DNP is an integral part of UNOPS works and ensures the sustanability and maintenance of the project site. - On 20 June 2022, UNOPS provided the beneficiary with an Operation and Maintenance manual, as-built drawings, and warranties from the manufacturer i.e lighting, CCTV, etc.). - On 30 June 2022, UNOPS conducted an orientation session for the beneficiary's engineers on the electrical, mechanical, and water & sewage system of the building the usage of the CCTV, irrigation system, water circulation pumps, etc. Results/deliverables under Output 1.2: Market spaces and kiosks are developed and made available for women and people with disability to sell and promote their products: - Community needs assessment identified that a large portion of the community wants an E-Marketing training program as one of the micro-project entrepreneurship training sessions that should be provided. - Construction work for the market place and kiosk has been completed as the above output activities explain. A rollup has been produced to be placed in the market on opening day. -UN-Habitat has purchased 10 market stalls for the women to use. Results/deliverables under Output 2.1: Multi-service community center is enhanced to train women and build capacities: - A community needs assessment was conducted by Zaha Cultural Centre to have a better understanding of the community needs and priorities in terms of the most desired programmes and training to be offered to women and children post-implementation. A community needs assessment report that summarizes the identified needs and priorities of the different segments of the community, including women, youth, and children, were produced (attached). - Based on the assessment findings, an operational plan for the community center will be developed. -16 women and 1 man received a 3-day training on sustainable agriculture methods. • ToT training in Business Development Service (BDS) was conducted targeting 28 trainers, of which 20 females and 8 males, all of them have completed the training and certified in the programme. 19 trainers are from Ghor Al-Safi area (4 males, and 15 females) and 9 from Zaha Cultural Centre (4 males, and 5 females). • 140 Women from Ghor Al-Safi have identified for Women Do Business training following the developed ILO criteria, whereby 139 of the applicants started the training with 138 of them completed the WDB training course. • 137 business plans were submitted by the WDB beneficiaries, and evaluated for seed funding. 32 of them were funded to startup their own businesses. • 2-day market Linkages/Bazar and Graduation Ceremony to celebrate the project businesses was conducted for the WDB beneficiaries. • TSP workshop was conducted. A training workshop targeted 3 TPIs with 13 participants including Zaha cultural centre (6 participants), Development and Employment Fund (3 participants), and Jordan River Foundation (4 participants). • 16 of the WDB trainers (14 females, and 2 males) from Ghor AL-Safi were trained on providing career counselling and e-employment services • 132 job seekers (23 males, 109 females) were linked to ILO employment platform and trained on grievance redress mechanism, labour rights, trade unions, and other decent work aspects • 13 women from Ghor Al-Safi were trained on professional caregiver course • A Memorandum of Agreement has been finalized to be signed with Zaha Cultural Centers for managing and implementing the WDB programme. -UN-Habitat hs purchased equipment, furniture, and amenities to equip the community cetnre for the different training programmes and children activities.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | The main challenge encountered throughout the programme timeline was the COVID-19 safety concerns and Governmental mitigation measures. The impact of the pandemic on the programme was one of the risks identified in the Risk Management Matrix. Due to Government restrictions, the team conducting the Site-Specific Assessment could not observe the project site in the evening or at night. Therefore, the assessment relied on interviews and focus groups to understand the average number of park users, the quality of artificial lighting, and daily activities prior to the pandemic. Moreover, the architectural team contracted COVID-19, which delayed the planned activities until the team recovered. In addition to this, due to social distancing regulations and the Month of Ramadan, the first community consultation workshop had a limited number of community members. However, the second consultation workshop, which was held shortly after Ramadan, was well attended by the local community, especially women from Ghor Al Safi. During the different project activities, such as workshops, focus groups, and interviews, safety measures that included social distancing, provision of hygiene and sanitizers, and provision of masks, were ensured during any planned activity. Additionally, the ToT dates were shifted because of the time required for ILO to sign the implementation agreement with ILO implementing partner, the Jordan River Foundation. Moreover, ILO faced some difficulties reaching out and identifying trainers from Ghor Al-Safi who fit the selection criteria. To mitigate the second perceived risk of deeply rooted social norms hindering the implementation of the intervention, the implementing partners ensured that both men and women from the community were involved in the community consultation sessions to raise awareness amongst the community and influence social change. The third identified risk, regarding the weak institutional capacity and limited local authorities’ capacity to support the implementation of the programme, has been mitigated through the engagement of local authorities from the earliest stages of the programme and through the partnership with Zaha Cultural Centre as the operational organization from the start of the programme. To ensure that the partners follow the “Do No Harm” approach and avoid exacerbating inequalities and vulnerabilities, the programme began with the Site-Specific Assessment to analyse the context, identify the stakeholders and their interactions with one another, and, accordingly, ascertain the suitable activities that will have the positive impact while increasing the participation and engagement of the local community (especially women and people with disabilities). Furthermore, while preparing the Agreement of Cooperation with Zaha Cultural Center and planning the construction with the Municipality of the Southern Jordan Valley, the programme partners learned that, according to new regulations, all projects must be approved by the government. The UN partners submitted a request in November 2021 that is still being processed. However, there was an agreement with the government that implementation may begin but that the project could not be officially handed over until approval is granted. The programme team has thus concluded the planned activities and requested the support of the RC office to expedite the official government approval. | 1. Please define what JORISS is. 2. The brief exceeds 500 words, it is 677 words and we need to limit it to 500 words only. 3. please refer to some edits and amendments in red and striked. (COMPLETED EDITS TO REDUCE WORD COUNT TO 498)
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | The UN-Habitat Public Space Site-Specific Assessment generated findings on the five dimensions: 1. use and user, 2. accessibility, 3. amenities and furniture, 4. comfort and safety, and 5. green environment. The findings contributed to developing a gender-sensitive, inclusive, and accessible public space. The findings from the assessment have informed the design and ensured that the right solutions are in place for more inclusive, accessible, and safe public spaces. The assessment offered a platform for dialogue between the community, professionals, and the local authority, leading to changing mindsets and attitudes towards a "collective responsibility" to public spaces. The developed Public Space Site-Specific Assessment Report will be disseminated in English and Arabic to programme stakeholders, and planning entities in Jordan as the findings can provide a foundation whereby urban design becomes a solution to meet the community's needs rather than simply beautification. Additionally, UN-Habitat, UNOPS, and ILO will continue to disseminate and share the results with governmental and non-governmental partners through follow-up meetings, workshops, and social media. The project's participatory approach will be replicable throughout the different municipalities, with slight adaptations dependent on the needs of the communities and other stakeholders to successfully achieve the short and long-term impacts. Furthermore, the Site-Specific Assessment generated knowledge on implementing green architecture and permaculture assisting in harsh climates based on expert findings and community experience. This was used to build the capacities of representatives from the local community on the techniques and methods of green infrastructure and permaculture design principles. Moreover, the community needs assessment generated knowledge on the training programs and opportunities desired by the community. Additionally, based on the needed skills, local economic opportunities, market analysis skills development, and entrepreneurship training was offered to women using ILO tools and methods such as 'Women do Business' (WDB) and 'Start and Improve Your Business (SIYB). ILO entrepreneurship development programmes rely on training trainers' methodology whereby a network of capable and qualified BDS trainers is formed and trained by ILO-certified Master Trainers. This ensures the scalability and sustainability of the intervention and allows institutionalization of training programmes in existing BDS structures and monitoring of beneficiaries. The operational lessons and training programmes can inform and be adopted in future interventions across Jordan to equip young women and men with the necessary technical and entrepreneurial skills to enhance their socio-economic conditions. Furthermore, the principal purpose of this programme is to advance gender equality through the establishment of a gender-inclusive and accessible public space in Ghor Al Safi, the development of market spaces and kiosks for women and people with disability to sell and promote their products, as well as the enhancement of a multi-service community center to train women and build capacities. The expected outcomes of this programme are: firstly, the socio-economic conditions and wellbeing of vulnerable women will be enhanced by providing green spaces and livelihood opportunities, and secondly, the transferable livelihood skills and economic opportunities for women in rural areas will be increased.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | UN-Habitat, ILO, and UNOPS have developed implementing and consultative partnerships with Zaha Cultural Centre, the Municipality of Southern Jordan Valley, Jordan River Foundation, Turath Architecture, and Urban Design Consultants several local organizations in Ghor Al Safi. These partnerships have been developed to ensure that the programme outcomes are met, the sustainability of the programme post-implementation, and the catalytic impact of the programme, whereby the intervention can be replicated and expanded across Jordan post-implementation. Through this fund and its financial support, this programme could bridge the communication gap between local communities, governmental bodies, and private companies through the activities and the fostering of these partnerships. The participatory activities conducted between the different partners, consultants, and stakeholders allowed for a platform of exchange between the stakeholders to ensure that the outcomes and outputs of the programme were delivered. This programme is aligned with the response and priorities at the national level, including the “JNUP diagnosis report,” ‘Jordan 2025”, and the “UN Socio-Economic Framework for COVID-19 Response”. Additionally, this intervention, its participatory process, and its outcomes are aligned with the WHO COVID-19 Strategic Preparedness, And Response Plan, which highlights the erosion of social cohesion, limited access to education, and reduced income and security communities have experienced as one the key lessons for 2021. It additionally highlighted the disproportionate socioeconomic effect this pandemic has had on women. Furthermore, it is also aligned with the Global Humanitarian Response Plan, which considers the socioeconomic impact of COVID-19 on an already-vulnerable population. This programme considers the short and long-term effects of this socioeconomic impact, how it can be mitigated for the vulnerable communities in Ghor Al Safi and, through replication, across Jordan, as well as recognizes, as the GHRP does, the effect this on achieving the Sustainable Development Goals. This programme model could be used for similar responses at country or global levels, especially for gender-responsive interventions that aim to enhance the skills and employability of vulnerable women.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | This programme has conducted a Public Space Site-Specific Assessment for Ghor Al Safi Park (the site) and the surrounding area. The programme has additionally conducted a topographic survey of the site to understand the levels and determine the location and elevations of selected ground points to plot the features (buildings, manholes, fence-lines, etc.) as well as show the differences in elevations from the ground surface. Furthermore, to develop the operational plan for the community center and identify the training programs the community will most benefit from post-implementation, the programme has conducted a community needs assessment through a digital survey and produced a community needs assessment report. All the assessments and reports were translated into Arabic and English to disseminate and reach out to the broader audience of the project’s stakeholders.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | This programme has had to revise the proposed timeline due to delays caused by the increasing cases of COVID-19 and the resulting governmental mitigation measures/restrictions, as well as delays in signing implementation agreements and receiving governmental approval. This revision affected the initial Site-Specific Assessment timeline, mainly because the architectural team members conducting the Assessment contracted the virus during this period, which delayed the activities. This additionally included limiting the number of participants in the first community consultation session held in Ghor Al Safi to ensure the safety of all attendees and compliance with government restrictions. The programme team is doing their utmost to expedite the works and shift some activities, an extension until 30 June 2022 was granted to complete the project activities, and the timeline has been adjusted accordingly and the project's activities were concluded before the new end date.
5 | Resources (Optional) |  | Due to the limited fund, ILO has mobilized additional resources, noting that the total amount that can be proved through supporting documents is 70,000 USD provided by RBTC ILO. In addition, ILO is supporting the implementation of this project through its existing staff recruited by other projects.

## RBM-Interim
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
| This will be measured after the implementation of the project. |  | Will be verified through survey.
Indicator: Number of local community members demonstrating enhanced socio-economic conditions and social cohesion (disaggregated by gender, age, and nationality).
Baseline: 0
Planned Target: Direct beneficiaries: 37,040 inhabitants (where women represent 46% of the population) Indirect beneficiaries: > 26,868
Intermediate Outcomes: (I) Increased access to a safe, gender-inclusive, and green public space, community centre, and markets (II) Improved capacity of the target municipality and NGOs on the design of safe, gender-inclusive and green public spaces for women and people with disabilities | This will be measured after the implementation of the project. |  | Will be verified through post-implementation evaluation reports (by Zaha Cultural Centre), attendance sheets, and annual reports.
Indicators: (1) Number of Ghor Al-Safi population including persons with disabilities benefitting from the public space, community center and the local markets (disaggregated by gender and age). (2) Number of public spaces and community centers developed that enhance safety for women and persons with disabilities. (3) Number of Municipal staff and NGOs capacitated on the design of safe, gender-inclusive and green public spaces for women and people with disabilities
Baseline: 0
Planned Target: (1) 37, 040 (where women represent 46% of the population) (2) 1 pubic space and 1 community center designed and developed (3)10 participants
Output 1.1: Gender-inclusive, safe and accessible public space established in Ghor Al Safi | The first community consultation session/ workshop was attended by 16 participants, 8 women and 8 men, whereas the second community consultation session/workshop was attended by 66 participants from the Ghor Al Safi community, 49 women and 17 men. | Due to the Holy Month of Ramadan and the rising COVID-19 cases, the number of attendees from the local community attending the first session was low, but in the second consultation session the number of participants exceeded the planned target especially with the number of women participating in the session | Verified through attendance sheets, photos documenting the events, recorded contributions from participants
Indicator 1.1.1: Number of participants from the local community participated in sessions to design the public space (disaggregated by gender)
Baseline: 0
Planned Target: 65 participants (of which 50% women, 50% men, 25% youth, 10% refugees, 5% people with disabilities, and representatives from Ghor Al Safi Women’s Association for Social Development)
Indicator 1.1.2: Number of gender-responsive design alternatives for safe, inclusive and green public space developed through community engagement and participatory methodologies involving different stakeholders, including women’s groups. | The final detailed design has been finalized |  | Verified through conceptual design report and detailed design report, will be further verified through design review report (UNOPs), and BoQ document upon approval.
Baseline: 0
Planned Target: 3 design alternatives and 1 detailed final design
Indicator 1.1.3: Number of gender-responsive, safe, inclusive and green public spaces and community centres rehabilitated/ made accessible for local communities | 1 public space and 1 community centre were completed |  | Will be verified through building contracts, implementation progress reports and photos.
Baseline: 0
Planned Target: 1 public space and 1 community centre
Indicator 1.1.4: Number of green public spaces and community centres equipped with hygiene and sanitization items (COVID-19 response) | 1 public space and 1 community centre were completed |  | Will be verified through implementation progress reports and photos.
Baseline: 0
Planned Target: 1 public space and 1 community centre
Indicator 1.1.5: Number of users visiting the public space and community center (disaggregated by age and gender). | This will be measured after the implementation of the project. |  | Will be verified through the site-specific assessment questionnaires and post-implementation evaluation report
Baseline: 0
Planned Target: > 10,000 a year, of which 50% women, 20% men, 50% youth, 10% refugees, and 5% people with disabilities
Output 1.2: Market spaces and kiosks are developed and made available for women and people with disability to sell and promote their products | A multi-use area designated for the market space has been developed and a kiosk constructe. 10 market stalls have been purchased. The second indicator will be measured after the implementation of the project. |  | Verfied through (1) design drawings, bidding docs, and Will be verfied though photos, events conducted and (2) Will be verfied through survey
Indicator 1.2.1: (1) Number of stalls and display areas provided for economic and cultural activities. (2) % of increased income for women as a result of participating in the local market.
Baseline: 0
Planned Target: (1) 10 per event. (2) 25%
Indicator 1.2.2: % of increased income for persons with disablities running the provided kiosks. | This will be measured after the implementation of the project. |  | Will be verified through contract and survey.
Baseline: 0
Planned Target: 50%
Indicator 1.2.3: Number of local markets organized per year | This will be included in Zaha Cultural Centre's operational plan that is currently being developed. |  | Will be verified through operational plan, social media, photos, and post-implementation report.
Baseline: 0
Planned Target: >15 per year
Indicator 1.2.4: Number of women using the market space to sell their products | This will be measured after the implementation of the project. |  | Will be verified through submitted registration sheets and photos
Baseline: 0
Planned Target: >150 per year
| This will be measured after the implementation of the project. |  | Will be verified through women surveyed
Indicator: % of increased income for women due to improved access to livelihoods opportunities
Baseline: 0
Planned Target: 25%
Intermediate Outcome: Increased transferrable livelihood skills for vulnerable women in rural areas. | This will be measured after the implementation of the project. |  | Will be verified through women surveyed
Indicator: Number of women, youth, elderly, persons with disability who are benefitting from livelihoods training and the services provided by the community centre.
Baseline: 0
Planned Target: 25%
Output 2.1: Multi-service community centre is enhanced to train women and build their capacities | ToT training in Business Development Service (BDS) was conducted targeting 28 trainers, of which 20 females and 8 males, all of them have completed the training and certified in the programme. 19 trainers are from Ghor Al-Safi area (4 males, and 15 females) and 9 from Zaha Cultural Centre (4 males, and 5 females). 71.4% Women | Target exceeded by 3 (28 trainers instead of 25) | Implemetation Agreement with Jordan River Foundation. Attendance sheets List of trainers Certificates (once issued)
Indicator 2.1.1: Number of BDS trainers trained by certified ILO trainers on the WDB programme
Baseline: 0
Planned Target: 25 of which at least 50% women
Indicator 2.1.2: Number of women trained on the Women Do Business programme (WDB). | 140 Women from Ghor Al-Safi have identified for Women Do Business training following the developed ILO criteria, whereby 139 of the applicants started the training, with 138 of them completing the WDB training course. | Target exceeded by 13 (138 trainers instead of 125) | List of participating applicants and their data
Baseline: 0
Planned Target: Direct beneficiaries: 125 women through 6 training workshops of 12 days including 20 – 25 women per workshop. Indirect beneficiaries: > 700
Indicator 2.1.3: Number of women-led businesses supported through submitted business plans selected for grants provision and coaching. | 137 business plans were submitted by the WDB beneficiaries, and evaluated for seed funding. 32 of them were funded to startup their own businesses. 2-day market Linkages/Bazar and Graduation Ceremony to celebrate the project businesses was conducted for the WDB beneficiaries. | Target exceeded by 15 (32 bussinesses funded instead of 17) | List of projects sumbitted and funded signed fund document
Baseline: 0
Planned Target: 10%-15% of business plans submitted are selected (an average of 17 business plans may be selected for grant provision and coaching)
Indicator 2.1.4: Number of business start-ups supported | 137 business plans were submitted by the WDB beneficiaries, and evaluated for seed funding. 32 of them were funded to startup their own businesses. 2-day market Linkages/Bazar and Graduation Ceremony to celebrate the project businesses was conducted for the WDB beneficiaries. | Target exceeded by 15 (32 bussinesses funded instead of 17) | List of projects sumbitted and funded signed fund document
Baseline: 0
Planned Target: 17 businesses
Indicator 2.1.5: Number of women trained on childcare provision and supported to set up childcare facility to serve the center. | 13 women from Ghor Al-Safi were trained on professional caregiver course | Target exceeded by 9 (13 trainers instead of 4) | Attendance sheets, training report and photos.
Baseline: 0
Planned Target: > 4 women
Indicator 2.1.6: Number of trainees linked to existing employment information platforms and to trade unions during implementation. | WDB trainers (16 trainers: 14 females, and 2 males) from Ghor AL-Safi were trained on providing career counselling and e-employment services 132 job seekers (23 males, 109 females) were: -linked to ILO employment platform -Trained on grievance redress mechanism, labour rights, trade unions, and other decent work aspects |  | Attendance sheets, training materials and photos. Attendance sheets, training materials and photos.
Baseline: 0
Planned Target: Direct 125 women Indirect beneficiaries: > 700
Indicator 2.1.7: Number of women benefitting from the childcare facility per year. | This will be measured after the development of the community centre. |  | Will be verified through registration sheet and survey
Baseline: 0
Planned Target: > 70 women
Indicator 2.1.8:Number of Agreements signed to operate and maintain the public space and community centre with Zaha Cultural Centre and Municipality of the Southern Valley to ensure the sustainability of the project. | An MoU agreement between Zaha Cultural Centre and the Southern Jordan Valley has been signed to ensure the sustainability of the public space and community center. |  | Verified through signed MoU and operational plan
Baseline: 0
Planned Target: 1 with Zaha Cultural Centre and 1 with the Municipality of the Southern Valley
Indicator 2.1.9: Number of permanent economic opportunities created for the community of Ghor Al-Safi to operate the public space and community centre. | This will be measured after the implementation of the project. It will be included in Zaha Cultural Centre's operational plan. |  | Will be verified through signed contracts
Baseline: 0
Planned Target: 3 staff members and 1 security guard
Indicator 2.1.10: Number of community members received ToT training on green infrastructure techniques | 16 women and 1 man received a 3-day training on sustainable agriculture methods. | The participants were identified based on their interest and need for training. | Verified through attendance sheets and photos
Baseline: 0
Planned Target: 15 young men including at least 5 refugees
Indicator 2.1.11: Number of elected community committees established to oversee and support the operation of the community centre | Not started - This will be measured after the implementation of the project. The community consultation sessions showed that there is an interest in the community management of the public space. |  | Will be verified through community agreement with community representatives and agreement with Zaha Cultural Centre
Baseline: 0
Planned Target: 1 committee including at least 1 woman, 1 man, 1 youth from local community, 1 disabled person, 1 from refugees.
Indicator 2.1.12: Number of training programmes provided by Zaha Cultural Centre for women and children after the construction of the community center per year | Zaha Cultural Centre has conducted a community needs assessment and will develop an operational plan that includes the training programmes according to the community needs. |  | Will be verified through post implementation evaluation report, annual operational plan of the center
Baseline: 0
Planned Target: 25
Indicator 2.1.13: Number of community members and refugees benefiting from the community programmes by Zaha Cultural Centre per year | This will be measured after the implementation of the project. |  | Will be verified through post implementation evaluation report, annual operational plan of the center
Baseline: 0
Planned Target: > 3,000 per year, of which 50% women, 50% youth and 5% refugees.
Indicator 2.1.14: Number of disabled children benefiting from community center services provided by Zaha Cultural Centre after the construction of the community center per year | This will be measured after the implementation of the project. |  | Will be verified through post implementation evaluation report, annual operational plan of the center
Baseline: 0
Planned Target: At least 50 disabled children
Indicator 2.1.15: Number of visitors attending the 3 annual festivals organized by Zaha Cultural Centre | This will be measured after the implementation of the project. |  | Will be verified through photos, operational plan.
Baseline: 0
Planned Target: > 3,000 per festival

## Communication-Interim
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
First Workshop Web Story: https://unhabitat.org/jordanian-women-call-for-a-playground-and-market-in-public-space-consultations Furthermore, one of the women who received the Women Do Business training with ILO partners explained to UN-Habitat, “I have benefited a lot from this training” such as “how can I benefit […] and also benefit my local community? My service is not limited to myself and my home, it should also be facilitating for the community.” She explained how much the future community centre and market space will benefit herself, women in her community, and those in nearby neighbourhoods who need these opportunities.
2. Upload here: Communications and Visibility (OPTIONAL)
Project Launch: https://unhabitat.org/un-covid-19-response-and-recovery-fund-supports-a-project-to-alleviate-socio-economic-impact-of-the http://jordantimes.com/news/local/un-covid-response-fund-support-vulnerable-women-ghor-al-safi https://www.almamlakatv.com/news/58134-مشروع-بقيمة-850-ألف-دولار-لتخفيف-أثر-كوفيد19-الاجتماعي-والاقتصادي-في-الأردن https://en.royanews.tv/news/25943/2021-03-02 https://royanews.tv/news/239099 https://petra.gov.jo/Include/InnerPage.jsp?ID=58246&lang=en&name=local_news https://www.petra.gov.jo/Include/InnerPage.jsp?ID=32745&lang=en&name=en_news Community Consultation Workshops Coverage: https://twitter.com/UNHABITAT/status/1384859282680725508?s=20 https://twitter.com/UNHABITAT/status/1390293380379332613?s=20 https://twitter.com/UNHABITAT/status/1400437448803487751?s=20 https://twitter.com/UNHabitat_Ar/status/1384831194186014721?s=20 https://twitter.com/UNHabitat_Ar/status/1399970137294376961?s=20 https://www.facebook.com/UNHABITAT.Arabic/posts/4011909122197972 https://www.facebook.com/UNHABITAT/posts/10158147927677444 https://www.facebook.com/UnitedNationsJO/posts/2273356309473281 https://unhabitat.org/jordanian-women-call-for-a-playground-and-market-in-public-space-consultations Public Space and Community Centre Final Design Coverage: https://twitter.com/UNHABITAT/status/1437703480517480448 https://www.facebook.com/UNHABITAT/posts/10158426450392444 https://unhabitat.org/multi-agency-un-project-to-be-catalyst-for-developing-sustainable-resilient-livelihoods Permaculture Training: https://www.facebook.com/UNHabitatJORDAN/posts/pfbid028LtM5hq1XcEaGRz1VLiX2ECjWZ3VTFgRHbNeLZ9SqM7HdvY9YBqaR4c2w7sqS4s5l Opening day communication materials have additionally been produced.
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board