## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to the secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality results reports please follow the next guidelines: a) The narratives should be a well written, succinct summary clarifying what was done during the reporting period and the results achieved. It should highlight the JP achievements. It should also specify scope and beneficiaries. b) Factual, evidence-based reporting against the outcome and output and corresponding indicators in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not should be provided. d) Factual, evidence-based reporting against the outcome results and its alignment with the overall SERP joint workplan, and linkage to reporting on global-level SERP indicators. e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not. g) Reflect on innovation. Avoid generic and standard descriptions. Rather, present well documented features of successful innovative solutions truly new for you and which could enable replication efforts.
3 | Please fill out all sections of the reporting template before submitting to the secretariat via email to: nina.andersen@undp.org and cc.: maria.herrera@undp.org
B
DEADLINE: MARCH 31 ST, 2022
1 | ALL projects receiving funds in late 2020 and in 2021 must complete an ANNUAL report as per the end of the calendar year with a reporting period : date of start until 31 December 2021.
2 | The joint programmes which completed their activities in 2021 should deliver a FINAL report by March 31 at the latest and will not be obligated to provide an annual report.
3 | The joint programmes completing activities in 2022 will be asked to submit a FINAL report (by 31 August 2022)
4 | ALL projects must report number of direct beneficiaries.
5 | ALL projects must provide an update on project indicators

## General Information
Programme Title & Project Number |  | Programme Duration
Programme Title: | Mitigating socioeconomic impact of COVID19 on employment and income of own-account women workers in the informal economy. | Overall Duration (months) | 13 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2020-11-30
MPTF Office Project Reference Number: | 124712 | Original End Date (dd.mm.yyyy) | 2020-10-31
Country | Bolivia | In case of NCE Current End date(dd.mm.yyyy) | 2022-03-31
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | International Labour Organisation United Nations Development Programme UN Women | National counterparts (government, private, NGOs & others) and other International Organizations | National Confederation of Own-Account Women Workers Ministry of Labour and Social Welfare ACOBOL (Bolivian Councilwomen Association)
Report Cleared By
o Name: | Ignacio Trabadela
o Title: | PDFO RCO Bolivia
o Email address: | ignacio.trabadela@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19 (up to 500 words). | The Joint Programme (JP), until its conclusion at the end of march 2022, was executed smoothly and aimed at achieving the set objectives and indicadors. The JP managed to build relationships with important counterparts, and worked very closely with the target group (own-account women workers). The JP finalised its four studies (characterization of own-account women workers; sectors with potential for the establishment of formal enterprises; value chains with potential for employment; and, a mapping of laws, actors and programmes within the ecosystem in which own-account informal women workers operate in), which have all been published. UN Women conducted the study: Child care as a state responsibility. Case studies in the cities of La Paz and Santa Cruz de la Sierra which is in the process of being published. The capacity-building activities were succesful, and have all concluded and reached the set indicators. The JP managed to work with over 100 own account women workers in strengthening their digital skills. With the activities focused on business management skills, the JP reached over 300 own-account women workers. 563 own-account women workers have also strengthened their soft skills (in leadership, communications and strategic alliances) and deepened their knowledge in financial management. 798 elected members from local governments have increased their knowledge on the care economy with a focus on the situation of own-account women workers. A methodology of collective intelligence and innovation designed to improve access to financial and non-financial services of 85 own-account women workers, with UNDP acceleration Laboratories, was carried out. The beneficiaries of this process were part of the training process to improve digital skills developed by the ILO. The alliance with the productive development bank (BDP) has made it possible to generate different training processes in financial and non-financial services for groups of self-employed women who have the potential to access the financial system. This alliance has already demonstrated its benefits by training more than 440 women on different topics, generating 15 business models and, to date, allocating credits worth 172,875 Bs.
2 | Purpose | Please describe the project general objective specifying its link to COVID-19 response. | The JP's general objetive is to ensure that the socioeconomic impacts caused by COVID-19, on own-account informal workers, have been mitigated in the short term, and contribute to reducing them in the long term, to prevent them from falling into poverty, and strengthening gender equality and the empowerment of women. It is linked to Bolivia's Socio-Economic Response Plan, particularly with its links to the articulation in the support response to public policies and with the promotion of equality and inclusion.
3 | Results: Outcome Level | Please include narratives describing the main project achievements against the project's overall goal (up to 300 words) | Outcome 1 - By 2022, strategic govermental institutions have designed gender and social public policy proposals and programmes that promote the transition of own-account women workers from the informal to the formal economy, taking into account the care economy, in the cities and sectors identified by the programme. -At the end of the Programme, the JP developed two public policy proposals that can enable own-account women workers to transition to the formal economy. One of them is focused on the care economy and the other on cooperatives. Outcome 2 - By 2022, own-account women workers in the informal sector (in the urban areas of the cities of La Paz, El Alto, Cochabamba and Santa Cruz) will have the skills and abilities that will improve their employability and the generation of enterprises, so that they can access sources of decent work." -100+ women have participated in the digital skills capacity-building workshops. -Over 300 own-account participated in the business management courses. Outcome 3 - By 2022, own-account women workers (from the urban areas of the cities of La Paz, El Alto, Cochabamba and Santa Cruz) will have access to financial and non-financial mechanisms adapted to their needs, which will contribute to their formalization." -536 own-account women workers strenghtened their capacities in financial education (requirements to access loans and basic accounting management) and softs skills (advocacy, leadership, strategic alliances and communications) -A methodology of collective intelligence was designed with the UNDP Acelerator Lab to co-design solutions adapted to the own-account women workers needs. - The designed collective intelligence methodology was implemented with 85 women from La Paz, El Alto, Cochabamba and Santa Cruz to identify their needs and barriers to access to finantial and non-finantial mechanisms. Through a systemic approach own-account women workers also identified the main characteristics of solutions that would respond to their needs. - 93 own-acoount women workers accessed two digital solutions (47 applikate.io and/or 46 app-credit.com) to improve their financial control, business management and increase the chances to access credits adapted to theirs needs due to a better understanding of the finantial products and an integeal strengthening of their businesses. - 70 own-account women participated in especific workshops of BDP for having acces to their financial and non financial offer - 443 women accessed to support for improving their businesses models, through an integral taylor-made methodology focused on capacity streghtening for finantial inclusion. - 1 financial insitution (Banco de Desarrollo Productivo - BDP) has designed and adapted financial products and services, for women in general and in particular for own-account women workers
3.1 | Results: Output Level | Please include narratives describing the main annual/ final results of each output included in the project document (up to 200 words) | Output 1.1 - Evidence-based knowledge on the characterisation of own-account women workers in the informal economy, for the promotion of targeted public policies and programmes to address their needs in relation to formalization, social protection and co-responsibility for care, has been generated. -The study has been published. Output 1.2. - By the end of the Joint Programme, multi-stakeholder dialogue mechanisms with women's organisations, trade unions and the identified strategic governmental institutions, have been established at the regional and/or national level, to support the design of policies and programmes related to the transition to the formal economy of own-account women workers. -The JP worked has established dialogue mechanisms in order to develop public policies. Output 1.3. - By the end of the Joint Programme, the capacities of governmental institutions and other stakeholders to design and implement policies and programmes related to the care economy, that will support the formalization of own-account women workers, will have been strengthened." -798 elected members from local governments have increased their knowledge on the care economy with a focus on the situation of own-account women workers. An agenda on this topic was designed and the elaboration of a proposal on local programmes to promote the redistribution of unpaid care work and feminist guidelines for a public policy on care were elaborated. Output 2.1 - Studies to identify the emerging and most dynamic sectors of the economy, for the generation of entrepreneurship and labour insertion of women during and after the COVID-19 crisis, have been elaborated. -Studies generated. They have all been published. Output 2.2. - Own-account women workers in the informal economy with strengthened capacities that favor their labour insertion and establishment of enterprises, through the transfer of methodologies and tools in entrepreneurship, digitalization, green economy, among others identified in product 2.1, in alliance with institutions of economic empowerment for women, technical and vocational training centers and the Public Employment Service. -100+ women workers have strengthened their skills in digital services and activities. -Over 300 women participated in business management courses. Output 3.1 - Inclusive financial and non-financial products and services adapted to the specific needs of women in the target group, generated by the social innovation laboratories -6 innovative non-financial services that respond to the needs of the women of the target group were mapped,These services could be implemented according to the results of the of collective intelligence process. - 2 innovative digital non-financial services were selected according to the prioritization made by the own-acount women workers in the collective intelligence processes carried out with them. These services are taylor-made solutions that are focused on improving business finantial control, management and identifying finantial products according to the women business characteristics and needs. Output 3.2 - Measures that generate incentives for development finance institutions to design and/or adapt their financial product and services to the needs of own-account women, in alliance with the Bank of Productive Development (Banco de Desarrollo Productivo) and other private or public institutions of the financial sector. -The terms of the agreement with the Productive Development Bank that they have been encouraged to commit to modifying their incubation model to include socio-economic variables that are relevant to include own-account women workers in the financial system NO SE ENTIENDE BIEN ESTA ORACIÓN Output 3.3. - Women from the target group will have benefited from a financial education programme that improves financial management skills and the sustainability of monetary resources. - 563 own-account women workers strenghtened their capacities in financial education, deepening their knowledge about the requirements to have access to loans and learning about basic accounting management.
3.2 | Results: Gender | Please include project Gender results and its linkage with COVID- 19 response. If applicable, refer to the project's gender equality marker and any impacts they may have had on programming quality and results (up to 150 words). | Given the focus of the JP, all of the actions and activities focused on strengthening gender equality and promote the inclusion of women in diverse roles and institutions. The gender focus of the JP is strongly linked to Bolivia's SERP, as it aims to promote equality and inclusion, and is focused on the economic response and recovery, which emphasises the need to protect jobs, SMEs and informal sector workers.
3.3 | Results: Direct Beneficiaries | Please include total number of DIRECT BENEFICIARIES disaggregated by gender, age , location (rural, urban, any other location). Please avoid duplicating beneficiaries ensuring the dissagregated data adds to the total presented. | Digital Skills capacity-building courses: 109 own-account women workers. Age groups: 19-35: 70; 36-52: 32; 53-69: 7. Cities: Cochabamba: 22; La Paz: 60; Santa Cruz: 27. -All urban. Business management courses: 300+ women. -Evenly divided between the target cities (La Paz, El Alto, Cochabamba and Santa Cruz). Soft skills and financial education trainings: 563 own-account women workers from La Paz, El Alto, Cochabamba and Santa Cruz Age groups: under 35 = 245 / 36+ = 318
3.4 | Results: Indirect Beneficiaries | Please include total number of INDIRECT BENEFICIARIES. Please clarify if these are estimated and/or verified. If possible, disaggregate beneficiries by gender. | No indirect beneficiaries.
3.5 | Do not Harm | Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention. ( up to 100 words) | The JP was well-aligned to the Do No Harm approach, particularly as it does not expose people to the negative effects of interventions, and does not negatively affect the social fabric, the economy and the environment.
3.6 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken to achieve the expected results) Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms(use up to 150 words). | Political instability, due to the context of uncertainty caused by the presidential elections (which took place in October 2020), delayed coordination with government. -No political instability, in terms of the presidential election, was encountered. Nonetheless, there were difficulties in working with government counterparts, as many authorities had not been appointed and were active throughout 2021. The economic empowerment of own-account women workers increases beneficiaries' economic and financial autonomy within the family, which may lead to a change in traditional gender roles in the household and could lead to a risk of violence against women. -This risk has not materialised. The COVID-19 pandemic restricts mobility and the ability to hold face to face activities. -This risk did materialise. What was done to counteract it was to develop all of the capacity-building processes virtually, asking the beneficiaries if they had the possibility before doing so. The answers were mostly positive. When possible, a hybrid method was implemented, combining virtual and face-to face activities. When it wasn't possible, activities were implemented with biosecurity measures, depending on the level of COVID cases.
3.7 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) (up to 250 words) | Modify activities to fit well in the virtual world when possible, to cooperate closely with civil society organisations which may be strategic for the project, and to continually converse within the agencies of the JP to ensure most activities work with each other. Constantly engaging with organizations that represent the target group was crucial, as it allowed the JP to focus its activities on issues that were currently being demanded by own account informal workers. In addition, having as an ally the Confederation of own-account informal women workers was beneficial to bridging gaps with the government, as we were able to joint focus on issues of interest to the Confederation and public sector. Having a diagnosis on the needs of own-account women workers was key to design the training modules, and to build the Agenda to improve their situation that was shared with elected members from local governments. It seemed important too to have the feminist guidelines for care public policy validated by key stakeholders such as the National Platform for Care. Finally, a lesson learned was to expect some children to be with their mothers during the trainings: it was important to plan some activities for them so that women could focus on the trainings only. Generating alliances with banks such as the Productive Development Bank (BDP) has facilitated the effective access of self-employed women to the financial system. Although the process is still complicated for this population, and that there are still different intangible limitations, the fact of working with a bank such as BDP helps to align the training and transferred information with the conditions of the bank itself, and, in this way, increases the possibility to have access to credit. Due to the fact that most of the actions that UNDP has execute have been experimental, it has been very useful and efficient to work with the same women's groups that UN Women and the ILO also worked with. This made it possible to close the expectations of a significant group of self-employed women and to have a historical record of their progress.
3.8 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 250 words) | The JP worked with several partners that have been crucial for the development of the activites. Some of these are: -Confederation of own account women workers, with whom the JP coordinated to carry out a census within the organization, write a public policy proposal based on cooperatives, and for its members to participate in the capacity-building mechanisms. -ACOBOL: the CSO had a partner agreement to implement training activities in soft skills and financial education, to raise awareness among elected members of local governments on the care economy, and to make a proposal of public policy or local programmes to redistribute unpaid care work. -Banco de Desarrollo Productivo: An agreement was signed with the BDP in order to strengthen the mechanisms that favor the inclusion of women in the financial system, implementing a concrete improvement in the incubation model of women's enterprises that will allow them to access a loan, the committed portfolio is Bs. 4,250,000 equivalent to USD. 620.000.
3.9 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken (up to 200 words). | In addition to the four studies developed and the work that ACOBOL carried out with diagnoses to shape the content of trainings in soft skills and financial education, the JP has hired a team of experts on care to elaborate a study on early childhood public services in La Paz and Santa Cruz de la Sierra and their adequation to the needs of own-account women workers in the two cities. The study, named "Child care as a state responsibility. Case studies in the cities of La Paz and Santa Cruz de la Sierra" is in the process of being published. It was shared with key stakeholders such as the departmental government of Santa Cruz (Director for Gender among others) and the municipal government of Santa Cruz de la Sierra (Director of social development, elected members) as well as women's organizations and universities.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place (Up to 100 words). | None have been carried out
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | No additional resources have been mobilized, although the JP constantly engaging in potential opportunities and looked for further financing to expand the activities. This may be due to the fact that Bolivia is considered a middle-income and hence international cooperation is constantly on a declining curve.

## Project indicators
| INDICATORS DESCRIPTION AND DATA | DATA: ACTUALS 2021 | DATA: ACTUALS 2022 (if applicable) | TOTAL actuals (agreggated 2021 and 2022 if applicable ) | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Indicator: | Number of public policies or programmes, developed in consultation and coordination with governments, employers, workers and civil society representatives, that promote the effective transition from the informal to the formal economy of own-account women workers, submitted to the government for their enactment and efficent implementation in the sectors and cities identified.
Baseline: | 0
Planned Target: | At least 2 | 0 |  | 2 |  | Finished documents and products
Output 1.1
Indicator 1.1.1 | Number of assessments and studies carried out in consultation with government, workers, employers and civil society representatives, to generate reliable and accurate evidence about the target group's situation, needs and characteristics.
Baseline: | 0
Planned Target: | At least 2 | 2 |  | 2 |  | Finished documents + publications in 2022
Output 1.2
Indicator 1.1.2: | Number of agreements generated through the multi-stakeholder mechanism with women's organisations, trade unions, and the identified strategic governmental institutions, in order to promote the transition of own-account women workers from the informal to the formal economy.
Baseline: | 0
Planned Target: | At least 4 | 0 |  | 1 | Although only 1 agreement was signed, potential agreements were sent and presented to over 5 local governements which are awaiting a response for future action. | Finished documents
Output 1.3
Indicator 1.1.3.a: | Number of public policy proposals for social protection that identify an integral care system under a rights-based approach for own-account women workers, designed by the JP with effective and efficient standards.
Baseline: | 0
Planned Target: | 1 | 1 |  | 1 |  | Finished document
Output 1.3.
Indicator 1.1.3.b: | Number of own-account women workers of the informal economy who participate in the dialogue spaces for the design and validation of the proposals for public policies and programmes focused on meeting their needs towards formalization, social protection and an integral care system under a rights-based approach.
Baseline: | 0
Planned Target: | 150 | 0 |  | 97 | Our partner for this activity managed to gather 496 elected members from local governments for this activity but a smaller proportion of women, probably because they prioritized productive and reproductive work over the dialogues due to their lack of time during the week, as seen in the studies. | Report of dialogue spaces
Indicator 1.1.3.c: | % of own- acccount young women who participate in the dialogue spaces
Baseline: | 0
Planned Target: | 30% | 0 |  | 42.6% |  | Report of dialogue spaces
Outcome 2
Indicator 1: | Percentage of own-account women workers identified by the assessment on their characterisation in the informal economy, with strengthened entrepreneurial skills, that have established their own formal business or have joined a formal associative venture through the JP's technical assistance.
Baseline: | 0%
Planned Target: | At least 40% | 0 |  | - | The indicator could not be quantified, as the formalization of a business was difficult to achieve in the short execution period of the JP
Indicator 2: | Percentage of the trained (through 2.A) own-account women workers that have entered the formal labour market through the JP's technical assistance.
Baseline: | 0%
Planned Target: | At least 30% | 0 |  |  | The indicator could not be quantified, as the inclusion of own-account women workers in the formal labour market was difficult to achieve in the short execution period of the JP
Output 2.1
Indicator 1.2.1: | Number of studies to identify dynamic and emerging sectors in Bolivia with their corresponding skills needs, that are conducive to generate labour market inclusion and the establishment of sustainable formal entrepreneurial enterprises and ventures.
Baseline: | 0%
Planned Target: | At least 2 | 2 |  | 2 |  | Published documents on ILO website.
Output 2.2.
Indicator 2.2.A: | Number of own-account women workers in the target group that have effectively benefitted from entrepreneurship training at the end of the JP.
Baseline: | NA
Planned Target: | At least 170 |  |  | 170 | The activity exceeded expectations and the indicator | Finished documents and products
Output 2.2.
Indicator 2.2.B: | Number of own-account women workers in the target group that have effectively benefitted from skills development training to increase their employability at the end of the JP.
Baseline: | NA
Planned Target: | At least 170 | 109 |  | 170 | The activity exceeded expectations and the indicator | Finished documents and products
Outcome 3
Indicator 1: | Number of own-account women workers (from the urban area of the cities of La Paz, El Alto, Cochabamba and Santa Cruz) that reached access to inclusive and effective financial and non-financial mechanisms adapted to their needs | 0
Baseline: | NA
Planned Target: | At least 85 | 85 | 93 | 93 |  | Lists of women that reached access to non-financial mechanisms adapted to their needs (applikate.io and app-credit.com)
Output 3.1
Indicator 3.1.1: | Number of own-account women workers associated in ventures, that have been involved in the fast-prototyped mechanisms, have accessed agile financing for their jobs. | 0
Baseline: | 1
Planned Target: | 80 | 0 | 116 | 116 | 46 women were trained to use digital solutions (app-credit ) to access agile financing. Also, 70 women were supported by BDP Lab to improve their business models trough the use of an integral taylor-made methodology focused on capacity streghtening for finantial inclusion. | List of women that accessed to app-credit digital solutions and BDP report.
Output 3.2
Indicator 3.2.1: | Number of development finance institutions and commercial banks that have designed and/or adapted financial products and services, adapted to the needs of own-account women workers, based on the incentives developed by the JP.
Baseline: | NA
Planned Target: | 2 | 1 |  | 1 | The productive development bank (BDP) did designed and applied financial products and services adapted to the needs of women in general and particularly of own-account women workers. Part of this results is the improvement of the digital platform www.bdp.com.bo/mujerbdp/ wich offers financial and non financial products. BDP is one of the biggest Banks in Bolivia and it is the only bank focused on productive development. Working only with them was possible because they did have the will to pursue this kind of objectives, something other banks or financial institutions didn´t at that moment. However, the succes we had with BDP did become an incentive for other banks to look for us for starting a financial program especific for women. | Reports and pappers presented by BDP
Output 3.3
Indicator 3.3.A: | Number of own-account women workers trained in financial management through the financial education program developed by the project.
Baseline: | 0
Planned Target: | 425 | 263 |  | 563 |  | Report of the trainings
Indicator 3.3.B: | % of own- acccount young women workers trained in financial management
Baseline: | 0
Planned Target: | 30% | 34% |  | 43.52% |  | Report of the trainings
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant.
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well as picture material please make sure you include all credits and share them in high resolution.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board
All of the communicational products developed by the JP can be found here.
Some of these include: