## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to the secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality results reports please follow the next guidelines: a) The narratives should be a well written, succinct summary clarifying what was done during the reporting period and the results achieved. It should highlight the JP achievements. It should also specify scope and beneficiaries. b) Factual, evidence-based reporting against the outcome and output and corresponding indicators in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not should be provided. d) Factual, evidence-based reporting against the outcome results and its alignment with the overall SERP joint workplan, and linkage to reporting on global-level SERP indicators. e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not. g) Reflect on innovation. Avoid generic and standard descriptions. Rather, present well documented features of successful innovative solutions truly new for you and which could enable replication efforts.
3 | Please fill out all sections of the reporting template before submitting to the secretariat via email to: nina.andersen@undp.org and cc.: maria.herrera@undp.org
B
DEADLINE: MARCH 31 ST, 2022
1 | ALL projects receiving funds in late 2020 and in 2021 must complete an ANNUAL report as per the end of the calendar year with a reporting period : date of start until 31 December 2021.
2 | The joint programmes which completed their activities in 2021 should deliver a FINAL report by March 31 at the latest and will not be obligated to provide an annual report.
3 | The joint programmes completing activities in 2022 will be asked to submit a FINAL report (by 31 August 2022)
4 | ALL projects must report number of direct beneficiaries.
5 | ALL projects must provide an update on project indicators

## General Information
Programme Title & Project Number |  | Programme Duration
Programme Title: | UN COVID-19 MPTF: Protecting women & children: digitalizing & streamlining social services, and creating a unified platform for national care | Overall Duration (months) | 15 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2020-11-01
MPTF Office Project Reference Number: | 124359 | Original End Date (dd.mm.yyyy) | 2021-11-01
Country | Maldives | In case of NCE Current End date(dd.mm.yyyy) | 1 Feb 2022
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNFPA, UNDP, UNICEF | National counterparts (government, private, NGOs & others) and other International Organizations | Ministry of Gender Family and Social Services (MoGFSS), Ministry of Communication, Science and Technology (MCST), National Social Protection Agency (NSPA), CSOs
Report Cleared By
o Name: | Dr Nazneen Anwar
o Title: | Resident Coordinator a.i.,
o Email address: | anwarna@who.int
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19 (up to 500 words). | The Programme have made progress in safeguarding women from falling into poverty and protecting them from becoming vulnerable to violent situations due to prolonged socioeconomic and emergency situations by ensuring their economic and social freedom through receiving shock responsive social protection benefits. Through the targeted interventions with particular emphasis on driving digital service delivery and enhanced data driven decision making, improved achievement towards SDG 1 and 5. This was achieved through the following results: 1. Strengthened capacity of national stakeholders to act in changing social norms to prevent GBV and increase access to reproductive health and economic opportunities and empowerment of women. 2. Digitization support was provided for business continuity of key agencies such as Ministry of Gender, Family and Social Services (MoGFSS) and National Social Protection Agency (NSPA) to ensure social protection services were provided to vulnerable communities during this period. As a result, vulnerable groups such as those experiencing domestic violence or gender-based violence, persons with disabilities, single parents, etc., continue to receive support from the government via online and telephone means even when the government was exercising work from home modality. 3. The mapping of the referral system identified gaps in services which will be addressed in developing the GBV digital platform. Once launched in May 2022, the platform will allow for monitoring of trends and efficiency of services and provide safer and accessible options for survivors to seek services. 4. An online module, “Madhadhu” to establish a single-entry portal which facilitates data collection from local councils on the vulnerable communities in their islands was launched in Feb 2022. This will ensure those who require social protection services are attended to in a timely manner. In addition, through this process internal capacity of Local Government Authority’s (LGA) was built on provision of digital resources. 5. Access to economic empowerment opportunities for women entrepreneurs was increased, by producing videos with information most required by startups in setting up their businesses to ensure uninterrupted support for businesses during the pandemic. These videos supplemented the ongoing webinar series by Business Center Corporation (BCC) to provide short trainings for MSMEs online. The initiative complemented the ongoing activities led by project and the Ministry of Economic Development and funded by the Government of Japan, to increase the capacity for MSMEs to adapt to the new normal through featuring their products on their platform, coworking space and facilitating access to SME loans. Women’s Development Committees were equipped with skills to utilize Social Behavior Change (SBC) as a change strategy to elicit results for vulnerable groups including children, through the development an island-level action plan for interventions and results.
2 | Purpose | Please describe the project general objective specifying its link to COVID-19 response. | The COVID-19 pandemic deeply affected country and its fiscal, socio-economic fabric. It worsened pre-existing inequalities and in particular on the vulnerable population. Women were especially hit by the pandemic with 55% of women reported redundancy compared to 47% of men. Most likely pushing women and vulnerable groups to be out of the labor force, and a huge loss to the country and their families. As the UN Maldives COVID-19 Socio-Economic Response and Recovery Framework (SERF) outlines that there are several opportunities, if enabled, could leapfrog the Maldives to recover better and faster. This joint program is developed to address SERF Pillar 2, which is Protecting People: Social Protection and basic services, Protecting women. The purpose of the Joint Programme is to harmonize various digital technologies while linking it with national digitization plan so that the service delivery of social protection schemes and benefits can become efficient and resilient to future shocks. The Maldives social protection system has long standing cash benefits for targeted vulnerable groups including single parent, foster, disability allowances and old age and retirement pensions. However, it is not shock responsive or user friendly in an emergency situation, and thus has not been able to provide additional relief to the most vulnerable families affected by the pandemic. Considering the lessons learnt through the COVID-19 pandemic, the programme has supported the Government to initiate shock responsive, digitization of various social protection benefits and schemes service delivery.
3 | Results: Outcome Level | Please include narratives describing the main project achievements against the project's overall goal (up to 300 words) | While additional work is needed to ensure the implementation of a robust social protection system that is able to respond effectively and efficiently in crisis situations, through the initiatives undertaken as part of this project, the government ‘s capacity has increased. This is particularly the case thanks to digitalization. Data systems were strengthened allowing updated information that provides adequate and timely services to vulnerable communities. It also helps in providing evidence-based policy-making that will ensure efficiencies in the delivery of public services. Furthermore, an online mobile application is currently under development which will provide the basis for early identification and respond to the most vulnerable population at time of emergencies. In addition, streamlined services for GBV was initiated and strengthened through a referral mechanism and a digital mobile application to ease service seeking.
3.1 | Results: Output Level | Please include narratives describing the main annual/ final results of each output included in the project document (up to 200 words) | As part of the Social Norms change strategy, women’s self-help is being piloted in H.Dh. Kulhudhufushi. In addition, 6 out of 12 episodes on gender-based violence were developed and aired on national TV and various online platforms included dialogues led by men. 21 participants were trained on data sharing protocols and remote service delivery for the GBV mobile platform. 122 individuals have viewed the Instructional videos developed as self-help training materials for MSMEs covering topics ranging from business registration to specific technical information needed to set up startups in certain sectors such as agriculture, fisheries, local tourism, etc. through social media and the BCC website. 11 participants from the Government and CSO staff completed the introductory course on Social Protection which aimed at enabling people to better overcome poverty and social exclusion in both developing and developed countries. 157 participants from WDC along with local council (45 different islands within 5 Atolls) were equipped with skills to utilize Social Behavior Change as a change strategy to identify key issues, analyze them and to formulate responses to address them in a systematic way. Enhanced business continuity of key agencies through digitization support resulted in service continuation for vulnerable groups such as those experiencing domestic violence or gender-based violence, persons with disabilities, single parents, etc., receiving support from the government.
3.2 | Results: Gender | Please include project Gender results and its linkage with COVID- 19 response. If applicable, refer to the project's gender equality marker and any impacts they may have had on programming quality and results (up to 150 words). | During the COVID-19 longest lockdown period, 615 cases were reported to the Family Protection Authority which is a significant increase as compared to the 541 cases reported in 2019 . The “Madhadhu” online module that was developed as a single-entry portal enables data collection and regular monitoring of the welfare of domestic violence survivors, single parents, elderly, etc. through the local councils who are then able to send alerts to other government agencies such as MoGFSS, through the application in cases where further assistance is required.
3.3 | Results: Direct Beneficiaries | Please include total number of DIRECT BENEFICIARIES disaggregated by gender, age , location (rural, urban, any other location). Please avoid duplicating beneficiaries ensuring the dissagregated data adds to the total presented. | TOTAL estimated direct beneficiaries is 14,392. Estimated Disagregated by population group and age range (Female: 7611 Male: 6781, estimated age group 3442 (below 18), 10,950 (above 18)
3.4 | Results: Indirect Beneficiaries | Please include total number of INDIRECT BENEFICIARIES. Please clarify if these are estimated and/or verified. If possible, disaggregate beneficiries by gender. | TOTAL Estimated: 93100
3.5 | Do not Harm | Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention. ( up to 100 words) | To enhance digital service delivery, do no Harm principles was considered such as inclusion of: - survivor centered approach to service provision, response, and evaluation. - Measures were taken to prevent data misuse, such as limiting users’ access to certain terminals, developing data sharing protocols, integration of server security to reduce the risk of information breach, and the adoption of a policy on the application’s usage. - The videos produced ensured accessibility using local language and sign language interpretation. Furthermore, the video series was completely animated to prevent the spread of COVID-19 during the production period.
3.6 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken to achieve the expected results) Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms(use up to 150 words). | During the project period it was observed that many development partners had begun programmes related to social protection and services in the country. Hence, it was important to redirect efforts to avoid duplication and synergize programmes to maximize impact. Social protection services in the Maldives have been very fragmented and created many gaps in services. The training for service providers allowed better clarity on the type of information needed for the provision of survivor-centered services. Additionally, trainings aimed at strengthening the modes of service provision by providing capacity building specifically on supporting survivors remotely such as through hotlines. To overcome travel restrictions of large number participants from different islands to the host island to participate in the SBC programme, participants were divided into batches and trainings were conducted accordingly.
3.7 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) (up to 250 words) | The team has underestimated implementation delays due to COVID 19 and associated challenges. The Health Protection Agency (HPA) enforced strict COVID-19 measures and travel restrictions to local inhabited islands. The team tried to circumvent these through introducing digital technologies and access to e-learning material but it could not replace the direct face-to-face benefits of meeting the beneficiaries. Another key learning is to secure leadership and policy coherence support from the onset. Differences in approaches between the President Office and MOGFSS and NSPA caused delays and brought about missed opportunities, which ultimately affected the efforts to consolidate and build an integrated, efficient, inclusive and sustainable social protection system that would streamline and digitize the national social protection system in support of the Government’s recovery plan. One of the key learnings of the SBC programme was securing the buy-in of relevant partners to help support the training (logistical, administrative) which was ultimately crucial to ensure the success of the trainings.
3.8 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 250 words) | The project helped building stronger connections with both National Social Protection Agency (NSPA) and Maldives Bureau of Statistics (MBS), particularly on strengthening data collection systems through digitalization. This support has provided NSPA with access to consistently available, much needed data at the island level, to implement their social protection schemes. In addition, once the extended Beneficiary Portal Services through the mobile application is rolled out in June 2022, it will provide the basis of early identification and respond to most vulnerable population at time of emergencies or other. Similarly, MBS’s ability to collect national level data has been improved and further discussions are ongoing to expand on this support. Enhanced partnership with the Local Government Authority enabled the inclusion of local council members in the SBC training along with the Women Development Committees. Furthermore, the continued partnership facilitated in smooth implementation of women’s self-help piloted in Hdh. Kulhudhufushi as part of the Social Norms change strategy. An existing partnership contract with Social Policy Research Institute was further strengthened with the additional training component on Social Protection. Fostered partnership with BCC. The webinar series by BCC providing short trainings for MSMEs online during the pandemic were complimented by producing videos with crucial information required by startups in setting up business. This complemented the ongoing activities by the MED, funded by the Government of Japan, to increase the capacity for MSMEs to adapt to the new normal through featuring their products on their platform, coworking space and facilitating access to SME loans.
3.9 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken (up to 200 words). | NA
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place (Up to 100 words). | The scope of project intervention on activity 1.2.1 was revised to the existence of the mobile application on GBV because there will be no time to promote the usage of the platform within the project timeframe. To avoid duplication of similar activities by other developmental partners and ensure efficient use of resources, the planned dialogue series to engage policy makers and stakeholders on harmonizing and strengthening the social protection system was re-programmed to provide support to Maldives Bureau of Statistics (MBS) in their efforts to facilitate better data collection through local councils.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | NA

## Project Indicators
Please include ALL indicators in the project document. Include the indicators and Baseline, Planned Target and Actuals for both OUTCOME and OUTPUT levels. "Actuals" refer to the total figures achieved for each indicator. Include separate actuals for 2021 and for 2022 (if applicable). Explain if targets were not achieved. Include means of verification. Use as many outputs cells as needed to present all project indicators.
| INDICATORS DESCRIPTION AND DATA | DATA: ACTUALS 2021 | DATA: ACTUALS 2022 (if applicable) | TOTAL actuals (agreggated 2021 and 2022 if applicable ) | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1] | National protection system is shock responsive and government's ability to identify the vulnerable groups increased
Indicator: | % of beneficiaries accessing NSP services/schemes disaggregated by type and sex | example 15 | example 47 | total would be 62
Baseline: | 20%
Planned Target: | 75% disaggregated by type and by sex | 27% | 32% | 32%
Output 1.1 | Strengthened capacity of national stakeholders to take action in changing social norms to prevent GBV and increase access to reproductive health and economic opportunities and empowerment of women
Indicator 1.1.1: | Number of people reached with messages on social protection services
Baseline: | 0
Planned Target: | 100000 | 0 | 50000
Indicator 1.1.2: | Number of sessions lead by men and boys publicly on gender equality and prevention of violence against children and women
Baseline: | lead by boys = 0 lead by men= 0
Planned Target: | lead by boys = 12 lead by men = 12 | 0 | Lead by men = 6 | Lead by men = 6
Output 1.2 | Increased access to digital technology and platform for the most vulnerable populations including the children, elderly, persons with disability, people with mental illness and women and poor and strengthen data collection at all levels |  |  |  | To be launched in May 2022. This indicator was changed during the 2021 interim report because the promotion and usage of the app will fall outside of the time frame of this project
Indicator 1.2.1: | Existence of a GBV digital platform
Baseline: | 0
Planned Target: | Platform developed and launched | No | Platform developed, it will be launched in May 2022
Indicator 1.2.2: | Single entry digital platform established
Baseline: | No
Planned Target: | Yes | No | Yes
Indicator 1.2.3: | Percentage of people downloaded mobile app |  |  |  | The target will be reached once the mobile app is launched in June 2022
Baseline: | 0
Planned Target: | 75% | 0 | 0
Indicator 1.2.4: | Proportion of women using digital platforms to access social protection services
Baseline: | 0
Planned Target: | 45% | 0 | 45%
Indicator 1.2.5: | Number of people trained to use communication for development as a tool for social norm change |  |  |  | The slow improvement of the Covid-19 situation allowed for travel and participants from more islands to take part in the trainings
Baseline: | 0
Planned Target: | 25 | 64 | 93 | 157
Output 1.3 | Consolidate and build an integrated, efficient, inclusive, and sustainable social protection system based on the principles of universal basic income (UBI) towards a reformed, expanded, streamlined, and digitized national social protection policy in support of the Government’s recovery plan. |  |  |  | Policy changes will be supported once the National Social Protection Framework is completed.
Indicator 1.3.1: | Revised National Social Protection Policy published
Baseline: | Social Protection legislation exist, No policy in place
Planned Target: | Published | No progress | No progress
Indicator 1.3.2: | Number policymakers engaged on human rights based social protection |  |  |  | Other development agencies were undertaking similar initiatives with national partners within the same time frame. Hence, to avoid duplication and ensure efficient use of resources, the initiative was re-programmed to provide support to Maldives Bureau of Statistics (MBS).
Baseline: | 0
Planned Target: | 6 | 0 | 0
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant.
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well as picture material please make sure you include all credits and share them in high resolution.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board