## Sheet 1
Project Monitoring and Evaluation (M&E) Plan
| Project Title: | Building the MHPSS-Gender-Peacebuilding nexus: fostering wellbeing, non-violent, gender equitable masculinity and social restoration with young people in West Darfur, Sudan
| Project Results Framework |  |  |  |  | Targets and Achievements (Ensure gender and age disaggregation where possible) |  |  |  | Means of Verification and Data Collection |  |  |  | Responsible Focal Points
| Outcome/Output | Indicator | Indicator Description (from ProDoc) | Additional Indicator Comments/Clarification |  | Baseline Value (Gender and age diaggregated) | End of Project Target (Gender and age disaggregated) | Indicator progress in current reporting period |  | Means of Verification Description (From ProDoc) | Additional Means of Verification Comments/ Clarification | Frequency of Data Collection |  | Responsible UN Agency(ies) | Responsible Implementing Partners | Individual Focal Points
EXAMPLE | Outcome 1: Adolescents and young adults across ages, genders and tribes in El Geneina, West Darfur, take leadership roles in processes of psychological and social healing, inclusive dialogues and in shifting norms underpinning violent behavior, including militarized notions of masculinity. | Outcome Indicator 1a % change in trust score among surveyed youth assessing trust in family; the community; groups bonding (within ethnic groups); in groups bridging (trust across ethnic groups); and trust in the state | % change in trust score among surveyed youth assessing trust in family; the community; groups bonding (within ethnic groups); in groups bridging (trust across ethnic groups); and trust in the state | The primary target group are female and male adolescents (aged 15 to 19 years) and young men and women (aged 20 to 29 years) (50%f and 50%m) across tribal groups. Three interrelated outputs will feed into the outcome. |  | TBD | 50% young men and women (aged 20 to 29 years) (50%f and 50%m) | End of project report covering entire project duration |  | Baseline, endline study as well as surveys conducted with cohorts graduating from Peace Clubs | * baseline survy report * implementing partner quarterlt progress report | Twice. Once at beginning and once at end of project |  | UNFPA/IOM/WHO | UNFPA | xxxxxx@un.org
|  | Outcome Indicator 1b % change in conflict management score among surveyed youth | % change in conflict management score among surveyed youth | The primary target group are female and male adolescents (aged 15 to 19 years) and young men and women (aged 20 to 29 years) (50%f and 50%m) across tribal groups. Three interrelated outputs will feed into the outcome. | Targets and Achievements | TBD | 70% | End of project report covering entire project duration | Means of Verification | Baseline, endline study as well as surveys conducted with cohorts graduating from Peace Clubs | Community engagnment activities reports | Twice. Once at beginning and once at end of project | Focal Points | UNFPA/IOM/WHO | UNFPA
|  | Outcome Indicator 1c % chance in composite indicator assessing men’s attitudes and practices related to gender equality and violence | % chance in composite indicator assessing men’s attitudes and practices related to gender equality and violence | The primary target group are female and male adolescents (aged 15 to 19 years) and young men and women (aged 20 to 29 years) (50%f and 50%m) across tribal groups. Three interrelated outputs will feed into the outcome. |  | TBD | 6% (100% male) | To be complated in End of project report covering entire project duration |  | Baseline, endline study as well as surveys conducted with cohorts graduating from Peace Clubs |  | Twice. Once at beginning and once at end of project |  | UNFPA/IOM/WHO | UNFPA
|  | Outcome Indicator 1d % of youth taking leadership roles in their communities | % of youth taking leadership roles in their communities |  |  | TBD | 10% | To be updated in End of project report covering entire project duration |  | Stories/qualitative information taken from the community improvement committees. Committee members report and provide examples of enhanced cooperation. Surveys and community feedback Final baselines will be established within first two months of the project. |  | Twice. Once at beginning and once at end of project |  | UNFPA/IOM/WHO | UNFPA
| Output 1.1 Improved access to quality, non-discriminatory, age and gender responsive MHPSS services for conflict-affected adolescents and youth in including survivors of GBV | Output Indicator 1.1.1 Number od assessment on formal and informal MHPSS services conducted | Number od assessment on formal and informal MHPSS services conducted |  |  | 0 | 1 ( 1 Assesment conducted ) | To be upated in Bi-annual project progress report |  | assessment results Report |  | once during the project |  | WHO | FMOH/SMOH
|  | Output Indicator 1.1.2 Number of MOH staff and lay helpers trained | Number of MOH staff and lay helpers trained |  |  | 0 | 20 (MoH, 50%f, 50%m), 200 lay helpers (50%f, 50%m) | To be upated in Bi-annual project progress report |  | Monitoring visits, evaluation of system designed, including its implementation | Community engagnment activities reports | once during the project |  | WHO | FMOH/SMOH
|  | Output Indicator 1.1.3 Number youth receiving MHPSS services | Number youth receiving MHPSS services |  |  | 0 | 1,000 (50%F, 50%m) | To be upated in Bi-annual project progress report |  |  | Community engagnment activities reports | quartlerly based |  | WHO | FMOH/SMOH
|  | Output Indicator 1.1.4 Number of referral pathways established | Number of referral pathways established |  |  | 0 | 2 | To be updated in Bi-annual project progress report |  | Feedback from targeted beneficiaries, monitoring missions, evaluation of implementation of system |  | quartlerly based |  | WHO | FMOH/SMOH
|  | Output Indicator 1.1.5 % of youth reporting increased awareness of MHPSS | % of youth reporting increased awareness of MHPSS |  |  | 0 | 60% (f&m) | To be updated in Bi-annual project progress report |  | Feedback from targeted beneficiaries, results of feedback on training, evaluation of implementation of system | Community engagnment activities reports |  |  | WHO | FMOH/SMOH
| Output 1.2 Peer-led Living Peace Clubs are established and support adolescent boys and young men in coping with experienced trauma and stressors and promoting non-violent, gender equitable notions of masculinity | Output Indicator 1.2.1 % of adolescent boys and young men reporting positive change in coping with stressors; controlling aggression and frustration; reduction conflicts at home; sharing with other men in the group | % of adolescent boys and young men reporting positive change in coping with stressors; controlling aggression and frustration; reduction conflicts at home; sharing with other men in the group |  |  | TBD | 90% (m) | to be updated by end of the project |  | Baseline study report , post training survey, endline; | Community engagnment activities reports | Twice. Once at beginning and once at end of project |  | UNFPA | CDF/Y-PEER | semustafa@unfpa.org
|  | Out+I17+C17:H17 | # of adolescent boys and young men participating in Peace Clubs | youth peace clubs will be esablished in 6 communities in Genina locality 12 youth peace clubs will be estalished 6 clubs for adolecents (age 16-20 ) 6 clubs for youth age (21-25) indicators will be achived in three phase of clubs establishment |  | 0 | 180 (100%m) | 162 male |  | Project progress reports; attendance lists; project monitoring | training participants list peace club monthly progress report monitoring visits reports parners quarterly progress report quarterly progress reviw meeting | quartlerly based |  | UNFPA | CDF/Y-PEER | semustafa@unfpa.org
|  | Output Indicator 1.2.3 Research study on the social norms underpinning militarized notions of manhood and linkages between masculinity, conflict and peacebuilding conducted | Research study on the social norms underpinning militarized notions of manhood and linkages between masculinity, conflict and peacebuilding conducted |  |  | 0 | 1 | resarch study is onging , deskreviw completed , questionnare drafted , final report of the study will submitted by 25/12/2022 |  | Research study report document |  | once during the project |  | UNFPA | Amanitore organization | semustafa@unfpa.org
| Output 1.3 Youth take leadership roles within their community, providing opportunities for positive interaction between male and female youth from different tribal groups, promoting mutual understanding, trust, empathy and more resilient social ties | Output indicator 1.3.1 % of youth reporting improved dialogue within their community | % of youth reporting improved dialogue within their community |  |  | 0 | 50% (f&m) | To be updated in Bi-annual project progress report |  | Reports detailing the active engagement of the community committee in local activities. Stories/qualitative information taken from the community improvement committees. Committee members report and provide examples of enhanced cooperation. Surveys and community feedback |  | Twice. Once at beginning and once at end of project |  | IOM | DDRA | hharrington@iom.int
|  | Output Indicator 1.3.2 % of community members reporting increased awareness of what peace entails | % of community members reporting increased awareness of what peace entails |  |  | 0 | 65% (f&m) | To be updated in Bi-annual project progress report |  | Reports detailing the active engagement of the community committee in local activities. Stories/qualitative information taken from the community improvement committees. Committee members report and provide examples of enhanced cooperation. Surveys and community feedback |  | quartlerly based |  | IOM | Berghof Foundation and DDRA | hharrington@iom.int
|  | Output Indicator 1.3.3 Number of youth supported through capacity building activities | Number of youth supported through capacity building activities |  |  | 0 | 50 (50%f, 50%m) | To be updated in Bi-annual project progress report |  | Reports detailing the active engagement of the community committee in local activities. Stories/qualitative information taken from the community improvement committees. Committee members report and provide examples of enhanced cooperation. Surveys and community feedback |  | quartlerly based |  | IOM | DDRA | hharrington@iom.int
| Outcome 2: | Outcome Indicator 2a
Outcome Indicator 2b
Outcome Indicator 2c
| Output 2.1 | Output Indicator 2.1.1
Output Indicator 2.1.2
Output Indicator 2.1.3
| Output 2.2 | Output Indicator 2.2.1
Output Indicator 2.2.2
Output Indicator 2.2.3
| Output 2.3 | Output indicator 2.3.1
Output Indicator 2.3.2
Output Indicator 2.3.3
| Outcome 3: | Outcome Indicator 3a
Outcome Indicator 3b
Outcome Indicator 3c
| Output 3.1 | Output Indicator 3.1.1
Output Indicator 3.1.2
Output Indicator 3.1.3
| Output 3.2 | Output Indicator 3.2.1
Output Indicator 3.2.2
Output Indicator 3.2.3
| Output 3.3 | Output indicator 3.3.1
Output Indicator 3.3.2
Output Indicator 3.3.3
| Outcome 4: | Outcome Indicator 4a
Outcome Indicator 4b
Outcome Indicator 4c
| Output 4.1 | Output Indicator 4.1.1
Output Indicator 4.1.2
Output Indicator 4.1.3
| Output 4.2 | Output Indicator 4.2.1
Output Indicator 4.2.2
Output Indicator 4.2.3
| Output 4.3 | Output indicator 4.3.1
Output Indicator 4.3.2
Output Indicator 4.3.3
++