## Project Workplan
Project Workplan
Project Title: "Sudan Youth Citizen Observer Network: Strengthening Youth's Role as Peacebuilders and Promoters of Civic Space in Sudan's Transition"
Updated November 2022
Indicative Workplan (Indicate with an "X")
Project Results Framework |  | Partners/Focal Points |  |  | Location |  |  | Status | Q1 2022 |  |  | Q2 2022 |  |  | Q3 2022 |  |  | Q4 2022 |  |  | Q1 2023 |  |  | Q2 2023 |  |  | Q3 2024 |  |  | Q4 2023
Outcome/Output/Activity | Comments | Responsible UN Agency(ies) | Agency Focal Points | Implementing Partners | Locality(ies) | Village Cluster(s) | Village(s) | Planned, on track, off track, or completed (use dropdown list) | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan2 | Feb3 | Mar4 | Apr5 | May6 | Jun7 | Jul8 | Aug9 | Sep10 | Oct11 | Nov12 | Dec13 | Additional Comments
Outcome 1: Increased coordination among youth-led organizations, resulting in integration of youth perspectives on key political and peacemaking processes and public policy as well as the empowerment of young women to fully participate in monitoring and reporting.
Output 1.1 Youth-led partner organizations participate actively in national observer network; and state advisory bodies coordinate and represent youth perspective at state and national level.
Activity 1.1.1: Expand mapping to all civil society organizations and identify potential partners |  |  |  |  | All 18 of Sudan's states |  |  | Completed | [5 empty] | X | X
Activity 1.1.2: Continue mapping of civil society actors and activities on a rolling basis |  |  |  |  | All 18 of Sudan's states |  |  | On track |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
Activity 1.1.3:
Activity 1.1.4:
Activity 1.1.5:
Output 1.2 Youth-led partner organizations and youth citizen observers are trained to conduct non-partisan observation related to key, inter-connected political and peacemaking/building milestones in the transition, and apply their skills collect data and report on transition milestones and key events.
Activity 1.2.1 Produce training materials and train observers, who will subsequently train additional youth in their states per the cascade training model |  |  |  |  | All 18 of Sudan's states |  |  | On track | [8 empty] | X | X |  |  | X | X
Activity 1.2.2 Train a total of 216 youth in long-term observation methodologies and key processes related to the transition, peacebuilding and, if relevant, elections |  |  |  |  | All 18 of Sudan's states |  |  | On track | [10 empty] | X | X |  |  | X | X
Activity 1.2.3
Activity 1.2.4
Activity 1.2.5
Output 1.3 YCO Network, managed by national secretariat and youth-led partner organizations, produces public reports based on observer data regarding key political and peacemaking/building developments in the transition.
Activity 1.3.1 Support the YCO Network in producing reports and holding public events to share information and recommendations concerning youth priorities and the transition | The report will be distributed nationally and be coupled with press event | [6 empty] | On track | [11 empty] | X | X |  |  | X | X
Activity 1.3.2
Activity 1.3.3
Activity 1.3.4
Activity 1.3.5
Output 1.4 Facilitate establishment of the YCO Network components – the secretariat, the linkages between youth-led partner organizations, and the advisory bodies in order to create sustainable observer network capable of increasing scale of observation activities.
Activity 1.4.1 Train and support the secretariat as coordinating body of the overall YCO Network | [7 empty] | On track | [8 empty] | X | X | X | X | X | X | X | X | X
Activity 1.4.2
Activity 1.4.3
Activity 1.4.4
Activity 1.4.5
Outcome 2: Through coordinated YCO Network efforts, civic space for young women and men promoted and expanded.
Output 2.1 Improved confidence and ability among YCO partner organizations and youth to conduct effective outreach and public communications
Activity 2.1.1 Train partner organizations and build capacity to manage activities and organization | [16 empty] | X | X | X | X | X | X | X | X | X
Activity 2.1.2
Activity 2.1.3
Activity 2.1.4
Activity 2.1.5
Output 2.2 YCO Network engages with stakeholders and policy makers on process, key findings and recommendations for political reforms and peacemaking/building processes.
Activity 2.2.1 Train the Secretariat in effective outreach and advocacy | [17 empty] | X | X | X | X | X | X | X | X
Activity 2.2.2
Activity 2.2.3
Activity 2.2.4
Activity 2.2.5
Output 2.3
Activity 2.3.1
Activity 2.3.2
Activity 2.3.3
Activity 2.3.4
Activity 2.3.5
Outcome 3: Improved capacity of YCO and the representatives of youth-led partner organizations, particularly young women, to identify and mitigate conflict at a local and national level.
Output 3.1 Observers are trained in conflict mitigation which they share with YCO; together, these young people put their conflict mitigation training into practice by, for example, conducting outreach to government officials regarding early warning signs of potential violence.
Activity 3.1.1 Train Youth Citizen Observers in peacebuilding, early warning, and other conflict-related issues | [18 empty] | X | X
Activity 3.1.2
Activity 3.1.3
Activity 3.1.4
Activity 3.1.5
Output 3.2:
Activity 3.2.1
Activity 3.2.2
Activity 3.2.3
Activity 3.2.4
Activity 3.2.5
Output 3.3
Activity 3.3.1
Activity 3.3.2
Activity 3.3.3
Activity 3.3.4
Activity 3.3.5
Outcome 4:
Output 4.1
Activity 4.1.1
Activity 4.1.2
Activity 4.1.3
Activity 4.1.4
Activity 4.1.5
Output 4.2:
Activity 4.2.1
Activity 4.2.2
Activity 4.2.3
Activity 4.2.4
Activity 4.2.5
Output 4.3
Activity 4.3.1
Activity 4.3.2
Activity 4.3.3
Activity 4.3.4
Activity 4.3.5
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## Dropdowns (hidden)
Planned
On Track
Off Track
Completed