## Sheet 1
Project Monitoring and Evaluation (M&E) Plan Updated November 2022
Project Title: “Sudan Youth Citizen Observer Network: Strengthening Youth’s Role as Peacebuilders and Promoters of Civic Space in Sudan’s Transition”
| Project Results Framework |  |  |  |  | Targets and Achievements (Ensure gender and age disaggregation where possible) |  |  |  | Means of Verification and Data Collection |  |  |  | Responsible Focal Points
| Outcome/Output | Indicator | Indicator Description (from ProDoc) | Additional Indicator Comments/Clarification |  | Baseline Value (Gender and age diaggregated) | End of Project Target (Gender and age disaggregated) | Indicator progress in current reporting period |  | Means of Verification Description (From ProDoc) | Additional Means of Verification Comments/ Clarification | Frequency of Data Collection |  | Responsible UN Agency(ies) | Responsible Implementing Partners | Individual Focal Points
EXAMPLE | Outcome 1: Increased coordination among youth-led organizations, resulting in integration of youth perspectives on key political and peacemaking processes and public policy as well as the empowerment of young women to fully participate in monitoring and reporting. | Outcome Indicator 1a | Enhanced youth capacity and coordination because of network formation to report on transition priorities and form recommendations reflecting youth perspectives that influence public dialogue, policy and the transition. | For all indicators: Implementation delayed due to political and security developments in Sudan, the additional facilitation of Fast Track Consultations among youth and CSOs in preparation of future peacebuilding dialogue support that will benefit UN efforts, Eid holidays, and a delay in the first PBF payment transfer (March 31). |  | 0 | 1 network 1 national secretariat 20 actionable recommendations | YCO establishment continued in this reporting period as 10 organizations representing 9 states were convened for an orientation workshop in Khartoum. |  | National secretariat and youth-led partner organization network formed. Government reports and/or key informant interviews | Collection: # of actionable recommendations made for the Government of Sudan's policies, laws, and practices related to youth | Collection: Quarterly Analysis Quarterly
|  | Outcome Indicator 1b | Female YCO Network members are empowered to monitor and report on key political and peacemaking processes. |  | Targets and Achievements | 0 | 108 young women trained on local observation and actively engaged in peacebuilding efforts in their local communities | Delays in the contracting process with partners have resulted in delayed further training. | Means of Verification | Self-reported on survey of female YCO members. | Disaggregation: Sex Age | Collection: before training, at project mid and end points. Analysis: immediately after training, mid and end of term. | Focal Points
|  | Outcome Indicator 1c | Reported increase in knowledge among project beneficiaries of neutral, non-biased observation methodology and key, interlinked political and peacemaking/building issues in the transition. |  |  | pre-training survey | 30% percent increase of individuals reporting an increase in knowledge | Delays in the contracting process with partners have resulted in delayed further training. |  | Self-reported – measured using March-April 2021 survey as pre-test compared to post-training tests. | Disaggregation: 1. Gender 2. Age 3. Geographic locations (region) •Data will also be compared against data set from March-April 2021 survey (e.g., familiarity with transitional bodies, timeline). | Collection: March-April 2021, before training, immediately after training, four months after training. Analysis: Immediately after training and four months after training.
| Output 1.1 Youth-led partner organizations participate actively in national observer network; and state advisory bodies coordinate and represent youth perspective at state and national level. | Output Indicator 1.1.1 | Number of sub-grant recipients that implement project activities and number of youth-led partner organizations and Resistance Committees that participate in advisory bodies on state level. |  |  | 0 | 8-10 partner youth-led partner organizations, 1750 advisory body participants | Selected partners were informed of corresponding Focal Points and have begun researching Advisory Bodies in the states they represent. |  | Memoranda of understanding with youth-led partner organizations; # of observers deployed; attendance lists at sessions of advisory bodies. | Disaggregation: 1. Geography (state and/or region) | Collection: quarterly Analysis: immediately after collection
Output Indicator 1.1.2
Output Indicator 1.1.3
| Output 1.2 Youth-led partner organizations and YCO are trained to conduct non-partisan observation related to key, inter-connected political and peacemaking/building milestones in the transition, and apply their skills collect data and report on transition milestones and key events. | Output Indicator 1.2.1 | Using a training of trainer’s model, number of YCO recruited, trained and deployed through youth-led partner organizations. |  |  | 0 | 216 YCO, including 36 state-level observers and 180 local-level observers. 108 women observers trained in local observation and actively engaged in peacebuilding efforts in their local communities. | Partners organizations have been selected and contracted (see above). |  | number of youth deployed as observers | Disaggregation: 1. Gender 2. Geography (region) 3. Age 4. Persons with disabilities (PWD) | Collection: Observer reports submitted. Analysis: Monthly
|  | Output Indicator 1.2.2 | Increase in TOCA measurements in media and communications outreach. |  |  | Survey of representatives of youth-led partner organizations and secretariat in first quarter 2022. | 25% increase of TOCA measurements |  |  | TOCA assessment | Disaggregation: 1. Gender 2. Age 3. Training focus | Collection: Interview with secretariat staff, TOCA tool Analysis: Biannual
Output Indicator 1.2.3
| Output 1.3 YCO Network, managed by national secretariat and youth-led partner organizations, produces public reports based on observer data regarding key political and peacemaking/building developments in the transition. | Output indicator 1.3.1 | Total number of press releases and public reports published by the YCO Network. |  |  | 0 | 2 | N/A as of November 2022. |  | Press releases and reports will be saved within TCC and YCO Network database. Final versions will be scanned and logged. | Disaggregation: 1. Publication Date 2.Thematic or Geographic Focus | Collection: Quarterly Analysis: Quarterly
|  | Output Indicator 1.3.2 | Total number of press conferences |  |  | 0 | 2 | N/A as of November 2022
Output Indicator 1.3.3
| Output 1.4 Facilitate establishment of the YCO Network components – the secretariat, the linkages between youth-led partner organizations, and the advisory bodies in order to create sustainable observer network capable of increasing scale of observation activities. | Output indicator 1.4.1 | 1 Network formed. | Registration is being reconsidered in light of the current context. Discusisons are on-going as to best option to facilitate the functioning of the secretariat and network.. |  | 0 | 1 Network formed and functioning secretariat established. |  |  | self-reported |  | Collection: Midpoint and end of project. Analysis: mid-point, end of project term
|  | Output indicator 1.4.2 | Increase in TOCA (technical and operational capacity assessment) measurements on reporting, advocacy, and monitoring and evaluation among partner youth-led partner organizations. |  |  | TOCA | Percentage of increase of TOCA measurements (TBD with partners) |  |  | Self-assessments, Center TOCA assessment of sub-grant youth-led partner organizations, Interview with secretariat staff, TOCA tool | Disaggregation: 1. Gender 2. Age 3. Training focus Tool and percentage targets to be defined in co-design phase with partner organizations, based on baseline assessment during last quarter of 2022. | Collection: Biannual Analysis: Biannual
| Outcome 2: Through coordinated YCO Network efforts, civic space for young women and men promoted and expanded. | Outcome Indicator 2a | Percent increase of youth-led subgrantee organization leaders and observers participating in the initiative that feel their perspectives are heard in the interlinked political and peacemaking/building processes during the transition. |  |  | pre-project survey with sub-grant partner orgs leaders and observers | 10% improvement | The contracting and orientation actions undertaken in this reporting period laid the foundation for future activities. |  | surveys | Data Disaggregated: Size of youth-led partner organization Geographic location Comparisons will also be drawn against March/April 2021 Center survey data among youth orgs to measure targeted partners against findings from larger youth-led partner organization community. | Collection: last quarter of 2022, mid-point of the project, end-point. Analysis: Immediately after surveys conducted (includes comparative analysis over time.)
|  | Outcome Indicator 2b | Percent change of sub-grant partners and youth-led partner organization activists who participate in observer training who feel there is a sufficient platform within the transition/peace process that reflects their needs and requirements |  |  | pre-training survey of sub-grant partners and youth-led partner organization activists who participate in observer training | 10% improvement |  |  | surveys | Data Disaggregated: Age Gender Persons with Disabilities Comparisons will be drawn against March/April 2021 Center survey data among youth orgs to measure targeted partners against findings from larger youth-led partner organization community. | Collection: last quarter 2022, mid-point of the project, end-point. Analysis: Immediately after surveys conducted (includes comparative analysis over time.)
Outcome Indicator 2c
| Output 2.1 Improved confidence and ability among YCO partner organizations and youth to conduct effective outreach and public communications. | Output Indicator 2.1.1 | Youth participants in project implementation express increased confidence in ability to meet and dialogue with stakeholders. |  |  | Established by pre-training survey of representatives of youth-led partner organizations and observers in third quarter 2022. | 25% increase in confidence levels among trained participants. |  |  | Pre-training responses, re-testing at the mid- and end-points of the project. |  | Collection: Initial phase, mid-point, and end-points. Analysis: Immediately after responses provided, including comparatively over time.
|  | Output Indicator 2.1.2 | Increase in TOCA measurements in media and communications outreach. |  |  | Survey of representatives of youth-led partner organizations and secretariat in third quarter of 2022 | 25% increase of TOCA measurements |  |  | TOCA assessment | Disaggregation: 1. Gender 2. Age 3. Training focus | Collection: Interview with secretariat staff, TOCA tool Analysis: Biannual
Output Indicator 2.1.3
| Output 2.2 YCO Network engages with stakeholders and policy makers on process, key findings and recommendations for political reforms and peacemaking/building processes. | Output Indicator 2.2.1 | Number of advocacy meetings held with stakeholders. | Individual stakeholder meetings, public forums and/or public online discussions including government officials or other stakeholders on issues related to YCO findings and recommendations regarding political and peace processes during the transition. |  | 0 | 10 advocacy meetings and/or public discussions, with minimum 600 participants in total. |  |  | weekly reports | Disaggregation: 1. Number of attendees 2. Organization or institution represented | Collection: Weekly Analysis: Quarterly
Output Indicator 2.2.2
Output Indicator 2.2.3
| Output 2.3 | Output indicator 2.3.1
Output Indicator 2.3.2
Output Indicator 2.3.3
| Outcome 3: Improved capacity of YCO and the representatives of youth-led partner organizations, particularly young women, to identify and mitigate conflict at a local and national level. | Outcome Indicator 3a | Situations of violence or potential violence are mitigated directly or indirectly by the YCO Network. |  |  | 0 | 2 incidents/flashpoints are identified with follow-on engagement. |  |  | Reports by YCO and youth-led partner organizations; reports of meetings. | Disaggregation: 1. Location. | Collection: Weekly Analysis: Monthly
|  | Outcome Indicator 3b | Misinformation/disinformation awareness strengthened through training and observer advocacy. | 216 trained individuals on misinformation/disinformation. Misinformation/disinformation included in checklists for observation and reporting. |  | 0 | Key findings released in public reports and statements. Recommendations formed to counter misinformation/disinformation among Sudanese stakeholders. |  |  | Reports and observations | Disaggregation: 1. Location. 2. Gender. | Collection: Weekly Analysis: Monthly
Outcome Indicator 3c
| Output 3.1 Observers are trained in conflict mitigation which they share with YCO; together, these young people put their conflict mitigation training into practice by, for example, conducting outreach to government officials regarding early warning signs of potential violence. | Output Indicator 3.1.1 | (a) Percentage of YCO and representatives of youth-led partner organizations trained on conflict mitigation who report improved understanding of conflict mitigation best practices. (b) Number of meetings held with stakeholders to inform interlocutors, discuss potential flashpoints, and offer recommendations. |  |  | 0 | (a) 90% of YCO and representatives of youth-led partner organizations; 30% of members of advisory bodies (representatives); (b) 5 meetings. |  |  | (a) Source: Feedback information sheets (self-reporting). (b) Weekly, monthly and/or quarterly reports. | Disaggregation: 1. Gender 2. Age 3. Location | Collection: Before training, immediately after training, four months after training. Analysis: Immediately after training and four months after training.
Output Indicator 3.1.2
Output Indicator 3.1.3
| Output 3.2 | Output Indicator 3.2.1
Output Indicator 3.2.2
Output Indicator 3.2.3
| Output 3.3 | Output indicator 3.3.1
Output Indicator 3.3.2
Output Indicator 3.3.3
| Outcome 4: | Outcome Indicator 4a
Outcome Indicator 4b
Outcome Indicator 4c
| Output 4.1 | Output Indicator 4.1.1
Output Indicator 4.1.2
Output Indicator 4.1.3
| Output 4.2 | Output Indicator 4.2.1
Output Indicator 4.2.2
Output Indicator 4.2.3
| Output 4.3 | Output indicator 4.3.1
Output Indicator 4.3.2
Output Indicator 4.3.3
++
Note on Q6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please include names and email addresses.