UN Energy Multi-Partner Trust Fund

Final naRRTive report

MAY 2023

# Purpose

The 2030 Agenda for Sustainable Development, with its 17 Sustainable Development Goals (SDGs), and the Paris Agreement on climate change provide a pathway for a more prosperous, equitable and sustainable future for people and the planet. Despite considerable initial efforts however, the world is at risk of falling short of achieving many SDGs by 2030. At the same time, while COVID-19 is the most urgent threat facing humanity today, climate change remains the biggest threat over the long term and progress towards dealing with it remains grossly inadequate. We must dramatically step up the pace of implementation during the first years of the Decade of Action to deliver the 2030 Agenda as well as the objectives of the Paris Agreement. Energy lies at the heart of both the 2030 Agenda and the Paris Agreement. Sustainable Development Goal 7 (SDG7) represents a first-ever universal goal on energy, with five targets to be achieved by 2030.

Energy is inextricably linked to climate change and many other SDGs, including poverty eradication, food security, health, education, prosperity, gender equality, jobs, transport, ocean, water and sanitation, and the empowerment of women and youth. The Global Sustainable Development Report (GSDR) 2019 identified “energy decarbonization with universal access” as one of the entry points that offer the most promise for achieving the transformations towards sustainable development at the necessary scale and speed. Without urgent action, however, the world will fall short of SDG7 achievement.

Concerted efforts in many countries are expanding electricity access, including through off-grid energy systems. Yet, 759 million people still lack access to electricity at present. 2.6 billion people remain without clean cooking solutions, causing millions of premature deaths annually, disproportionally affecting women. An energy revolution based on renewables and energy efficiency is urgently needed not just to accelerate economic progress and development, but also to slash greenhouse gas (GHG) emissions that are rapidly warming our planet. The energy sector today, dominated by fossil fuels, accounts for almost three quarters of human-caused GHG emissions. Clearly, energy is the decisive factor in cutting in half global CO2 emissions by 2030, thereby helping to avoid an increasing frequency and severity of dangerous and unprecedented weather extremes. These include heatwaves, devastating floods and droughts, which can cause dramatically increased risks to food, water and energy security, population displacement, and loss of lives and livelihoods. Effectively linking energy and climate action will be key to the success of the UNFCCC COP process, including the upcoming COP27 in Egypt and COP28 in the United Arab Emirates.

UN-Energy is the principal interagency mechanism within the United Nations system related to energy, under the auspices of the Chief Executive Board of the United Nations. The need for UN inter-agency collaboration continues to be relevant as 2030 approaches and achieving SDG7— affordable, reliable, sustainable and modern energy for all — is not on track without coordinated effort and attention.

The purpose of the UN-Energy MPTF was to support UN-Energy activities aimed at accelerating progress towards SDG7 achievement in support of the 2030 Agenda and the Paris Agreement, in line with UN-Energy Work Plan priorities for the biennial period of 2021/2022. The UN-Energy MPTF support edUN-Energy activities under the overall direction of the UN Energy Co-Chairs, namely, the Special Representative of the Secretary-General (SRSG) for Sustainable Energy for All and the Administrator of the United Nations Development Programme (UNDP), with the support of the UN-Energy MPTF Fund Secretariat.

# Results

This report presents the final narrative report on activities undertaken and results delivered between January 2021 and December 2022. It supplements the final report of the previous programmatic phase of the fund.

- Narrative reporting on results:

The UN-Energy MPTF has been instrumental in strengthening global political commitment, mobilizing partnerships for action, enhancing capacities and coordinating a coherent approach by UN-Energy. It is also helping steer international efforts by member states and all stakeholders to sharpen their action for SDG7 and enhance interlinkages between SDG 7 and other SDGs, including climate change, poverty, gender equality, food, education, health, water and jobs.

Objective One: Strengthen UN-Energy Secretariat in coordination of day-to-day functions of UN-Energy, including the launch of UN-Energy Action plan and relevant technical support activities related to the preparation of SDG7 Action Forum as a follow up from the High-Level Dialogue.

Outcome 1: Overall planning and coordination

On 24 September 2021, more than 130 global leaders, including Heads of State and Government, Ministers, executive heads of UN entities and international organizations, CEOs and other multi-stakeholder representatives, joined the High-level Dialogue on Energy, announcing ambitious targets, transformational actions and bold investments towards achieving universal energy access and net-zero emissions. One of the main outcomes of the Dialogue is the first-ever Global Roadmap for accelerated SDG 7 action which presents a clear strategy for the achievement of universal energy access and energy transition by 2030, including a set of concrete and practical milestones.

A comprehensive preparatory process consisting of over 30 advocacy events and activities at technical and ministerial level helped identify the priorities and areas where these actions and commitments are most needed. The start of this substantive preparatory process was marked by a Virtual Global Launch, which took place on 10 March 2021. This kick-off event featured video messages by over twenty ministerial level “Global Champions” from UN Member States calling for urgent action to achieve affordable, clean energy for all by 2030.

In the lead-up to the Dialogue, Ministerial-level Champions also co-hosted a series of Ministerial Forums on the 5 themes of the High-Level Dialogue during the week of 21 to 25 June 2021. A summary of the Ministerial Thematic Forums was produced and is available on the High-Level Dialogue on Energy website.

Building on the momentum from the 2021 High-level Dialogue on Energy, the UN took a major step to catalyze the large-scale action by Transforming Commitments into Action: Delivering on the outcomes of the High-level Dialogue on Energy - https://un-energy.org/pre-un-energy-plan-of-action-and-energy-compact-action-network/ launching two major initiatives, on 4 May 2022, that aim to deliver on the commitments outlined in the Global Roadmap for Accelerated SDG 7 Action.

- Plan of Action Towards 2025: put forward by some thirty leading organizations comprising “UN-Energy”, it delineates how they will help mobilize the much-needed transformational and inclusive energy transition.

- Energy Compact Action Network: established to match those governments seeking support for their clean energy goals with those governments and businesses that have pledged over $600 billion to support these commitments, through their Energy Compact.

Outcome 2: Stakeholders’ engagement

In support of the objectives of the High-Level Dialogue on Energy, more than US$400 billion in new finance and investment was committed by governments and the private sector in the form of Energy Compacts announced during the Dialogue and multi-stakeholder Energy Action pre-events on 22 and 23 September. The commitments made aim to provide hundreds of millions of people with clean energy access and speed-up energy transition while creating green jobs to leave no one behind. While the commitments announced were a significant step forward, it was also acknowledged by participants that far more is needed to address energy poverty and decarbonization of energy systems.

The Global Roadmap for accelerated SDG7 action emphasizes that the “United Nations system, supported by UN-Energy, should significantly scale up its efforts towards attaining SDG 7 and net-zero emissions. UN-Energy should be strengthened to support UN entities and other partners, including by facilitating coordination and monitoring progress of Energy Compacts, towards implementation of the global roadmap.”

In response to this call for the UN system to significantly scale up action, UN-Energy presented its commitment in the UN-Energy Pledge as part of its Energy Compact, aiming to accelerate action, catalyse multi-stakeholder action, grow the momentum, inform the global agenda, and track and share results.

In addition, EnergyNow SDG7 Action Forum - https://www.un.org/en/energynow-sdg7-action-forum. The Forum took place on 23 September 2022, on the sidelines of the opening of the 77th session of the UN General Assembly (UNGA) with the aim of catalyzing the achievement of Sustainable Development Goal (SDG) 7 (affordable and clean energy) by 2030 and net-zero emissions by 2050. One year after the UN High-level Dialogue on Energy that resulted in the Global Roadmap, the forum presented:

- UN-Energy Highlights

- Energy Compacts Annual Progress Report

UN-Energy was present at the Climate COP27 - https://mailchi.mp/un/save-the-date-launch-of-the-un-energy-plan-of-action-and-the-energy-compact-action-network-8687323 An official COP27 side event on “Implementing the UN-Energy Plan of Action to catalyze the Global Roadmap for Accelerated SDG7 Action” took place on Saturday, 12 November, bringing together representatives from various UN agencies to discuss their energy activities in support of sustainable development and net-zero emissions. Additionally, UN-Energy member organizations hosted more than 80 events at the SDG Pavilion at the UN Climate Conference (COP27) in Sharm El-Sheikh, Egypt.

Outcome 3 – Communications and Outreach

Efforts during this reporting period focused on enhancing communications and outreach activities around SDG7 in line with the Agenda 2030, working with many partners. As a follow up from the HLDE, A newsletter was sent out regularly to main constituencies and the UN-Energy Twitter account, featuring SDG7 content, grew from 500 to 10.4K+ followers.

The UN-Energy website is been redesigned and expanded to feature regular content on SDG7 themes, including articles on the SDG7 Policy Briefs, the SDG7 Tracking Report, Technical Working Group Reports, the call to action on clean cooking, and a series of “Energy Voices” interviews including with several practitioners working on energy access and clean cooking. Media outreach – including media advisories, a number of press releases and press briefings – was conducted for the launch of the UN energy plan of Action and the Energy Compact Action Network, the launch of the SDG7 policy Briefs and SDG7 Tracking report and the SDG7 Action Forum in September.

Outcome 4: Knowledge sharing, codification of lessons learned and best practices

Following up with the High-Level Dialogue on Energy, and in response to the Global Roadmap for accelerated SDG7 action, UN-Energy has committed to step up its efforts in support of achieving SDG 7 and net-zero emissions. A UN-Energy Action Plan, to be launched on 4 May 2022, will set out a framework for collective action to be taken by UN-Energy in order to achieve the massive pledge they made at the time of the High-level Dialogue. This first comprehensive plan of action by UN-Energy intends to raise ambition and strengthen coordinated action towards the SDG 7 targets.

Global Launch Tracking SDG7: The Energy Progress Report 2021 and 2022 as well as SDG7 Policy Briefs 2021 and 2022​. Launch events were held at UN Headquarters in New York, in June 2021 and 2022, to present the critically important findings of Tracking SDG7 as well as the SDG7 Policy Briefs on interlinkages of energy with other SDGs. The launchs were co-hosted by the Co-Chairs of the Group of Friends of Sustainable Energy (Denmark, Ethiopia, Norway, Pakistan) as an input to the High-level Political Forum for both years, as well as a moment to take stock on the road to implementing the Global Roadmap for Accelerated SDG7 Action coming out of the 2021 High-level Dialogue on Energy.

Objective Two:  Supporting UN-Energy’s engagement in developing and mobilizing voluntary contributions in the form of Energy Compacts, with support of the Sustainable Energy for All in collaboration with UNOPS.

Outcome 5: Successful mobilization and delivery of Energy Compacts and monitoring.

Important efforts have been paid during the reporting period to undertake diagnostics and assess needs for knowledge sharing in priority countries. To do so, several workshops have been organized with Member States to deep dive on specific needs and opportunities for energy sector action at country level, and to provide support for scaling up action through Member State-led Energy Compacts. Examples of these workshops are:

- Deep dive workshop on Energy Action: Brazil (7 June 2021)

- Deep dive workshop on Energy Action: Panama (9 June 2021)

- Deep dive workshop on Energy Action: Honduras (1 June 2021)

- Deep dive workshop on Energy Action: Nigeria (16 June 2021)

Outcomes of these discussions and diagnostics will help lay the ground for the design of joint programmes by UN-Energy organizations to support the provision of access to electricity and clean cooking solutions to priority countries, to be included in the upcoming UN-Energy Action plan (see outcome 4).

Preparations are also under way to establish an Energy Compact Action Network, to be launched in May 2022. Through this network, UN-Energy will create a framework to further strengthen the momentum brought about by the Energy Compacts, bring new stakeholders aboard, foster coalition-building, and drive a continuous increase in ambition and accelerated action, while catalysing the finance and investment required.

Advancing Energy Compacts: In May 2022, a new network (the Energy Compact Action Network or ECAN) was launched to connect the over 170 Energy Compacts or bold voluntary action commitments made submitted around the HLDE. The Secretary-General opened this high-level event marking this launch, which included participation by a large number of governments and UN agencies. This critical follow-up action is intended to activate the US$600 billion in finance and investment by governments and the private sector towards ending energy poverty and decarbonizing energy systems. At the SEforALL Forum in Kigali in May the UN-Energy team held three high-level workshops focused on Energy Compact countries (Nigeria, India and Rwanda) and their progress to date and what partnerships may be needed to move these Compacts forward. In addition, a session was held specifically focused on advancing Energy Compacts. Several countries made new commitments to their Compacts at the Forum, meaning there have now been over a dozen additional Energy Compacts announced in the period being assessed. There have also been significant advancements on the membership and modalities of the 24/7 Carbon Free Energy Compact with over 100 members joining, including Scotland with Prime Minister Sturgeon announcing the nation’s membership at COP27. The SDG7 pavilion at COP27 also included daily Energy Compact showcases featuring over 20 Energy Compacts proponents. Finally, the Energy Compacts progress report was launched at COP27 and shared with the Secretary-General by the SRSG, serving to highlight and track progress on Energy Compacts to date.

These outcomes described above were built on the strong results and collaborative activities undertaken during the earlier phase of this Multi-Partner Trust Fund (MPTF), under then SG’s SEforAll initiative. More information on these results during the earlier phase can be found on the documentation section of the UN-Energy MPTF website https://mptf.undp.org/fund/sea00

- Lessons learned and recommendations:

Key recommendations and lessons learned during the implementation of the project include:

- Energy is central to both achieving the 2030 Agenda for Sustainable Development and the Paris Agreement on climate change. Achieving SDG 7 will catalyze action to combat climate change and attain the other SDGs on poverty eradication, gender equality, mitigation of and adaptation to climate change, food security, health, education, sustainable cities and communities, clean water and sanitation, jobs, innovation, transport, and refugees and other situations of displacement.

- Results have emphasized the value of partnerships. All stakeholders have a role to play and must step up action. Member States and other stakeholders need to drive the global energy transformation forward by forming transformational partnerships. UN entities, international organizations and multilateral development banks, as well as businesses, civil society, science, cities and regional governments and other stakeholders, must step up and strengthen their efforts to support the implementation of SDG 7 and other SDGs.

- Energy Compacts are the vehicle to translate the global roadmap and key recommended actions into concrete plans with clear milestones and targets. Energy Compacts offer a global, inclusive umbrella for Member States and other key stakeholders from the business sector, sub-national governments and civil society to bring together voluntary commitments to achieve all SDG 7 targets and net zero emissions in support of the goals of the 2030 Agenda and the Paris Agreement. The Energy Compact Action Network was also formed to maximize synergies, learn lessons, track progress and mobilize further action.

- A pooled funding platform, such as this Multi-Partner Trust Fund, can play an important role to facilitate collaboration among UN entities, catalyzing synergies across their respective strengths and scale up partnerships with governments and many other stakeholders as exemplified by Energy Compacts that mobilized hundreds of billions of dollars.

- Conclusion

At the mid-point of 2030 Agenda, achieving SDG7 remains central to the attainment of all the SDGs and net zero needed to realize the objectives of the Paris Agreement on Climate Change. The UN system must step up to strengthen support and forge partnerships to scale up action.  Multi Partner Trust Fund mechanisms will continue to play a central role to galvanize such joint action to leave no one behind.  Only working together can make a progress to achieve the SDGs for a just equitable and sustainable future for people and planet.

|  | Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification |
| --- | --- | --- | --- |
| Outcome 1: Overall planning and day-to-day coordination of all aspects related to the preparatory process |  |  |  |
| Output 1.1: Successful High-level Dialogue on Energy undertaken in 2021 Indicator 1.1.1: Number of Global Leaders that participate at the High-Level Dialogue on Energy, with technical support from UN-Energy. Baseline: 0 Planned Target: 100 | 1.1.1 achieved | Exceeded the set target (130) | https://www.un.org/en/conferences/energy2021 |
| Output 1.2: Preparatory events and activities Indicator 1.2.1: Number of advocacy and preparatory events in preparation for the High-Level Dialogue on Energy, supported by UN-Energy. Baseline:0 Planned Target: 15 | 1.2.1 achieved | Exceeded the target (30 engagements at technical and high levels) | https://www.un.org/en/conferences/energy2021/Preparatory_Process |
| Outcome 2: Stakeholder engagement |  |  |  |
| Output 2.1: Global multi-stakeholder engagements conducted to establish the way forward on the achievement of the SDG 7 in line with the 2030 Agenda for Sustainable Development and the Paris Agreement Indicator 2.1.1: Number of global stakeholder consultations, in partnership with UN-Energy. Baseline: 0 Planned Target: 2 | 2.1.1 achieved | Fully delivered | https://www.un.org/en/energy-2021/page/stakeholders-participation |
| Output 2.2: Joint ambition pledges made by UN-Energy Indicator 2.2.1: Establishment of UN-Energy Pledge Baseline: 0 Planned Target: 1 (new UN-Energy Pledge) | 2.2.1 achieved | Fully delivered | https://un-energy.org/wp-content/uploads/2022/01/UN-Energy-Pledge.pdf |
| Outcome 3: Communication and Outreach |  |  |  |
| Output 3.1: Global coverages of HLDE and preparatory processes Indicator 3.1.1: Number of media coverages Baseline: 0 Planned Target: 50 | 3.1.1 achieved | Exceeded the target (100) |  |
| Output 3.2: Fully functional and updated UN-Energy Website Indicator 3.2.1: Number of viewers accessing UN-Energy website. Baseline: 1,000 Planned Target: 5,000 | 3.2.1 Achieved | Exceeded the target. | https://un-energy.org |
| Outcome 4: Knowledge sharing, codification of lessons learned and best practices |  |  |  |
| Output 4.1: Authoritative Theme Reports supported by UN-Energy compiled in support of the HLDE discussions Indicator 4.1.1: Number of Theme reports Baseline: 0 Planned Target: 5 | 4.1.1 achieved | Fully achieved | https://www.un.org/en/hlde-2021/page/theme-reports |
| Outcome 5: Successful mobilization and delivery of Energy Compacts. |  |  |  |
| Output 5.1: Energy Compact Workshops to disseminate basic information about Energy Compacts. Indicator 5.1.1 - Number of introductory Energy Compact workshops organized Baseline: 0 Planned Target: 10 | 5.1.1Achieved | Exceeded the target (over 40) |  |
| Output 5.2: Deep-dive sessions organized for theme-specific audience for Energy Compacts. Indicator 5.2.1 - Number of deep-dive Energy Compact workshops organized Baseline: 0 Planned Target: 4 | 5.2.1Achieved | Fully achieved |  |
| Output 5.3: Energy Compacts agreed and in place in countries, with clear plans, milestones and targets that chart a pathway to achieving SDG7 goals and targets Indicator 5.3.1: Number of Energy Compacts Announced Baseline: 0 Planned Target: 100 Indicator 5.3.2: New Finance/Investments for Energy Compacts announced in support of SDG7 Baseline:0 Planned Target: $200 Billion | 5.3.1 achieved 5.3.2. achieved | 5.3.1 target exceeded (150) 5.3.2 target exceeded ($600 billion) | https://www.un.org/en/hlde-2021/page/new-commitments-un-energy-summit |
| Output 5.4: Energy Compacts data base established Indicator 5.4.1: Dashboard established Baseline: 0 Planned Target: 1 | 5.4.1 achieved | Delivered. | https://www.un.org/en/energycompacts |

# Footnotes

https://www.un.org/sites/un2.un.org/files/launch_hlde_release_final-english.pdf

https://www.un.org/en/conferences/energy2021/Preparatory_Process

https://www.un.org/sites/un2.un.org/files/summary_-_ministerial_thematic_forums_for_hld_energy_of_june2021_advanced_copy.pdf

https://un-energy.org/wp-content/uploads/2022/01/UN-Energy-Pledge.pdf

https://www.un.org/en/conferences/energy2021/media

Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

# Text boxes

ii) Indicator Based Performance Assessment: