## Financial report_By activity
Annex C - project budget
Table 1 - project budget by Outcome, output and activity
Outcome/ Output number | Outcome/ output/ activity formulation: | Budget - UNWomen | Level of expenditure in USD (to provide at time of project progress reporting): UNWomen | Commitments/PO in USD - UNWomen | Level of expenditure/PO in % to date | Budget - UNDP | Level of expenditure in USD (to provide at time of project progress reporting): UNDP | Commitments/PO in USD - UNDP | Level of expenditure/PO in % to date | Percent of budget for each output reserved for direct action on gender equality (if any): | Any remarks (e.g. on types of inputs provided or budget justification, for example if high TA or travel costs)
OUTCOME 1: Open and safe spaces for inclusive participation of women in elections, politics, public life, and peacebuilding mechanisms are enhanced
Output 1.1: | Attitudes and behavioral changes towards greater women’s participation promoted through safe environments, group discussions, political party, and community engagements | 438000 | 481043.49 |  | 109.8% | 0 |  |  | 0%
Activity 1.1.1: | Conduct a regular quarterly dialogue through the IPCC structure on the prevention of VAWIE/P, peaceful political engagement, tolerance, and inclusive participation of women and vulnerable groups. | 16000 | 16000 |  | 100% | 0 |  |  | 0% | 100%
Activity 1.1.2: | Work with political parties including the women’s league for gender responsive parties that enable women to participate more meaningfully following up on collaborations with NDI and their support to political parties. Media engagement on broadcasting the work of gender responsive political parties will be an incentive to other parties | 36000 | 29200 |  | 81.11% | 0 |  |  | 0% | 100%
Activity 1.1.3: | Leadership engagement for increased tolerance to political pluralism, women’s participation, accountability, and peace in communities. Work with community leaders and Ministry of Internal Affairs (MIA) on the constitutional leadership mandate of traditional and community leaders to safeguard/protect the rights and lives of all citizens, including vulnerable groups, especially women and girls without partisan biases | 32000 | 32000 |  | 100% | 0 |  |  | 0% | 80%
Activity 1.1.4 | Engaging the Youth in peacebuilding processes- Working with CSOs, the Ministry of Youth and Sports (MoYS), particularly on capacity strengthening of young women for political leadership. This will include their engagement with political parties youth wings and institutions of governance at all levels through CSOs and the young women political leadership mentees to raise awareness on the rights of and incentives for women, including specifically young women, to participate in politics, and public life towards peaceful and equitable societies | 90000 | 117386.05 |  | 130.4% | 0 |  |  | 0% | 80% | As per the note to the file shared with PBO office , this activity will be topped up with 20k.
Activtiy 1.1.5 | Media engagement with CSOs for gender responsive reportage in dissemination of key messages on the human rights of women and profiling the work of women in Leadership at all levels. | 70000 | 68125 |  | 97.32% | 0 |  |  | 0% | 80% |  | 0 | 117386.05
Activity 1.1.6 | Conducting district and county-level gender dialogues on VAWiE/P and promoting women’s increased leadership with collaboration between the Ministries of Gender, Internal Affairs and Youth. The Caravan strategy will be leveraged. 15 dialogues are envisaged per year, once for each county bringing to 30 dialogues over 2 years. The Ministry of Gender will take lead as the gender coordination entity with support of UN Women | 90000 | 90000 |  | 100% | 0 |  |  | 0% | 100%
Activity 1.1.7 | Support CSOs to build the women’s leadership culture and participation in peacebuilding from grassroots upstream focusing integration of women in clan governance and peace-building committees and meetings to town, district, county and to national governance and peace-building discourse and architecture (from village councils to parliament Rwanda Model | 104000 | 128332.44 |  | 123.4% | 0 |  |  | 0% | 100% | As per the note to the file shared with PBO office , this activity will be topped up with 20k.
Output 1.2: | Violence against women in elections, politics and public spheres is reduced through enhanced engagement with political and electoral stakeholders and community leaders | 279000 | 277241.6 |  | 99.37% | 0 |  |  | 0% | 80% | 0
Activity 1.2.1: | Support national convention/dialogue to renew commitment to 30 percent women’s participation as stipulated in 2017 Farmington Declaration on peaceful elections, and Code of Conduct. The lack of monitoring of the implementation of the 30 percent participation of each gender has impeded progress | 19000 | 19000 |  | 100% | 0 |  |  | 0% | 80%
Activity 1.2.2: | Support political parties to implement the existing legal and policy provisions within their internal structures and externally – including codes of conduct, Memorandums of Understanding (MoU), and the developed Protocol on prevention and response to VAWiE – to inculcate intolerance to VAWiE/P in politics. Printing, dissemination, and education of VAWIE/P Protocol at national and community level | 30000 | 30000 |  | 100% | 0 |  |  | 0% | 90%
Activity 1.2.3: | 3 Printing, dissemination, and education of VAWIE/P Protocol at national and community level | 14000 |  |  |  | 0 |  |  | 0% | 80%
Activity 1.2.4: | Strengthen capacity of domestic elections observation groups to monitor and report electoral violence against women. This should include the EWRC with PBO and NCCRM (National Centre for Coordination of Response mechanisms following the development of gender responsive indicators and broader work on EWRC done under the WPS | 50000 | 51640 |  | 103.3% | 0 |  |  | 0% | 80%
Activity 1.2.5 | Reform of legal, policy, and institutional frameworks that facilitate prevention and response to VAWiE/P. Such policies will include having mandatory 30% gender quota in the elections law, facilitating for voluntary political party gender quota policies, incentives to political parties with gender quotas and alignment of the local government act (LGA) and Article 54 of the Constitution of Liberia to enable implementation of the law | 56000 | 60711.6 |  | 108.4% | 0 |  |  | 0% | 80%
Activity 1.2.6 | Support to legal clinics dealing with survivors of VAWIE/P including awareness raising to communities and women on legal aid options to survivors of electoral violence building on the UN Women’s peace and security project with Association of Female Lawyers in Liberia (AFeLL) will be leveraged | 60000 | 60000 |  | 100% | 0 |  |  | 0% | 80%
Activity 1.2.7 | Support to legal response to instances of VAWiE., This activity targets key institutions responsible for responding to VAWiE/P perpetrators in particular, the Judiciary and police as well as the political parties who should be vocal in condemning it. | 50000 | 55890 |  | 111.8% | 0 |  |  | 0% | 80%
Output 1.3: | The governing laws, policies and practices of peacebuilding and electoral institutions are strengthened | 0 | 0 |  | 0% | 325000 | 217880.8224 | 5448.6729 | 68.72% |  | 0
Activity 1.3.1 | Integrating VAWiE/P and relevant institutions / mechanisms into PBO EWRM platform |  |  |  | 0% | 35000 | 23464.0886 | 5448.6729 | 82.61% | 35%
Activity 1.3.2 | Capacity strengthening of NEC staff, the security sector, and the judiciary on VAWiE/P to ensure that all electoral processes, including training of temporary staff, includes risk assessment considerations regarding VAWiE/P (setting up continuous trainings for specific groups of stakeholders organized by LIPA in collaboration with NEC & PBO) |  |  |  | 0% | 50000 | 33520.1265 |  | 67.04% | 79%
Activity 1.3.3 | Under the EWRM, support drawing up a national roadmap on electoral violence and VAWiE/P |  |  |  |  | 40000 | 26816.1012 |  | 67.04% | 0%
Activity 1.3.4 | Support to the Legislature for the deployment of the platform and conduct of information campaigns, and train stakeholder on CFM |  |  |  |  | 80000 | 53632.2024 |  | 67.04% | 5%
Activity 1.3.5 | Collection of gender disaggregated electoral data and development of repository and databases |  |  |  |  | 30000 | 20112.0759 |  | 67.04% | 0%
Activity 1.3.6 | Development of a dialogue platform between the NEC, CSOs and political parties |  |  |  |  | 20000 | 13408.0506 |  | 67.04% | 0%
Activity 1.3.7 | Development of advocacy-mechanism with clear benchmarks for enforcement of temporary special measures for women’s participation in electoral processes |  |  |  |  | 20000 | 13408.0506 |  | 67.04% | 44%
Activity 1.3.8 | Develop & disseminate gender-sensitive civic and voter education; and set up gender sensitive election resource center for all electoral stakeholders, including marginalized groups |  |  |  |  | 50000 | 33520.1265 |  | 67.04% | 89%
Output 1.4. | Strengthened strategies of national institutions and county structures to promote inclusive participation in electoral, political, and peacebuilding processes |  | 0 | 0 | 0% | 230000 | 270085.8692 | 116717.7076 | 168.2%
activity 1.4.1 | Develop and implement Liberia-specific Gender and Elections Module |  |  |  |  | 50000 | 58714.3194 |  | 117.4% | 45%
Activity 1.4.2 | Risk assessment considerations regarding VAWiE/P is developed for all institutions engaged in elections |  | 0 | 0 | 0% | 40000 | 46971.4555 |  | 117.4% | 59%
Activity 1.4.3 | Strengthen research and analytical capacity of the Secretariat in the Legislature to provide information to decision-makers on the impact of the lack of women’s participation on democracy, peace, and stability in Liberia |  | 0 | 0 | 0% | 20000 | 23485.7278 |  | 117.4% | 4%
Activity 1.4.4 | Support Secretariat in developing an induction package for new representatives on women participation in elections, politics, and peacebuilding. |  |  |  |  | 10000 | 11742.8639 |  | 117.4% | 32%
Activity 1.4.5 | 5 Liberia Law Enforcement institutions, media, and women organizations / groups to develop joint SOPs on support to women in peacebuilding, elections, and politics |  | 0 |  | 0% | 60000 | 70457.1833 |  | 117.4% | 1.3%
Activity 1.4.6 | Conduct a mediation training for women and women organizations involved in EWRM nationally and at the county / rural level |  | 0 |  | 0% | 50000 | 58714.3194 | 116717.7076 | 350.9% | 0%
PERSONNEL, OPERATIONAL, M&E COSTS |  | 357766.36 | 265732.65 |  | 74.28% | 239392.53 | 184259.4579 | 0 | 76.97%
Project personnel costs |  | 221044 | 224514.52 |  | 101.6% | 140000 | 159062.5794 |  | 113.6%
Project operation costs |  | 40000 | 12982.44 |  | 32.46% | 60000 | 18691.5888 |  | 31.15%
Project M&E budget |  | 46000 | 28235.69 |  | 61.38% | 39392.53 | 6505.2897 |  | 16.51%
Project Audit |  | 50000 | 0 |  | 0% | 0
|  | 0 | 0 | 0 |  | 0
SUB-TOTAL PROJECT BUDGET: |  | 1074766.36 | 1024017.74 |  | 95.28% | 794392.53 | 672226.1495 | 122166.3805 | 100%
Indirect support costs (7%): |  | 75233.6452 | 52663.55 | 22570.0952 | 100% | 55607.4771 | 47055.8305 | 8551.6466 | 100%
TOTAL PROJECT BUDGET: |  | 1150000.0052 | 1076681.29 | 22570.0952 | 95.59% | 850000.0071 | 719281.98 | 130718.0271 | 100% | 97.79%

## Financial report_by Category
Table 2 - Project budget by UN cost category
Note: If this is a budget revision, insert extra columns to show budget changes.
CATEGORIES | UNWOMEN | [5 empty] | UNDP | [5 empty] | Total tranche 1 (70%) | Total tranche 2 (30%) | PROJECT TOTAL | Overall Expenses |  | Overall PO | Overall Delivry of the Total budget (%)
| Tranche 1 (70%) | Tranche 2 (30%) | Total | Expenses | PO | Del (%) | Tranche 1 (70%) | Tranche 2 (30%) | Total | Expenses | PO | Del (%) |  |  |  |  | Description of UNDG budget categories
1. Staff and other personnel | 154730.8 | 66313.2 | 221044 | 224514.52 | 0 | 101.6% | 98000 | 42000 | 140000 | 159062.5794 |  | 162.3% | 252730.8 | 108313.2 | 361044 | 383577.0994 | Staff and other personnel costs: Includes all related staff and temporayr staff costs including base salary, post adjustment and all staff entitlements | 0 | 106.2%
2. Supplies, Commodities, Materials | 30800 | 13200 | 44000 | 1200 | 0 | 2.727% | 35000 | 15000 | 50000 | 19697.3925 | 5448.6729 | 71.85% | 65800 | 28200 | 94000 | 20897.3925 | Supplies, Commodities, Materials: Includes all direct and indirect costs (e.g. freight, transport, delivery, distribution) associated with procurement of supplies, commodities and materials. Office supplies should be reported as "General Operating". | 5448.6729 | 28.03%
3. Equipment, Vehicles, and Furniture (including Depreciation) | 28000 | 12000 | 40000 | 4516.12 |  | 11.29% | 0 | 0 | 0 | 10377.1495 |  | #DIV/0! | 28000 | 12000 | 40000 | 14893.2695 | Equipment, Vehicles and Furniture including Depreciation: For those reporting assets on UNSAS or modified UNSAS basis (i.e. expense up front) this would relate to all costs to put asset into service. For those who do donor reports accdording to IPSAS this would equal depreciation for period. | 0 | 37.23%
4. Contractual services | 158200.007 | 67800 | 226000.01 | 33688.54 |  | 14.91% | 167574.771 | 71817.759 | 239392.53 | 128145.4766 |  | 76.47% | 325774.778 | 139617.759 | 465392.537 | 161834.0166 | Contractual Services: Services contracted by an organization which follow the normal procurement processes. In IPSAS terminology this would be similar to exchange transactions. This could include contracts given to NGOs if they are more similar to procurement of services than a grant transfer | 0 | 34.77%
5.Travel | 83805.64 | 35916.66 | 119722.35 | 43010.8 | 0 | 35.93% | 24500 | 10500 | 35000 | 99601.5888 |  | 406.5% | 108305.64 | 46416.66 | 154722.3 | 142612.3888 | Travel: Includes staff and non-staff travel paid for by the organization directly related to a project | 0 | 92.17%
6. Transfers and Grants to Counterparts | 282800 | 121200 | 404000 | 703198 | 0 | 174.1% | 189000 | 81000 | 270000 | 0 |  | 0% | 471800 | 202200 | 674000 | 703198 | Transfers and Grants to Counterparts: Includes transfers to national counterparts and any other transfers given to an Ips (e.g. NGO) which is not similar to a commercial service contract as per above. In IPSA terms this would be more similar to non-exchange transactions. | 0 | 104.3%
7. General Operating and other Direct Costs | 14000 | 6000 | 20000 | 13889.76 |  | 69.45% | 42000 | 18000 | 60000 | 255342.1869 | 116717.7076 | 620.1% | 56000 | 24000 | 80000 | 269231.9469 | General Operating and Other Direct Costs: Includes all general operating costs for running an office. Examples include telecommunication, rent, finance charges and other costs which cannot be mapped to other expense categories. | 116717.7076 | 482.4%
Sub-Total Project Costs | 752336.447 | 322429.86 | 1074766.36 | 1024017.74 | 0 | 95.28% | 556074.771 | 238317.759 | 794392.53 | 672226.3738 | 122166.3805 | 142.9% | 1308411.218 | 560747.619 | 1869158.837 | 1696244.1138 | Indirect Support Costs: (No definition provided) | 122166.3805 | 97.28%
8. Indirect Support Costs (must be 7%) | 52663.5516 | 22570.0936 | 75233.6452 | 52663.55 | 22570 | 100% | 38925.234 | 16682.2431 | 55607.4771 | 47055.8462 | 8551.6466 | 142.9% | 91588.7853 | 39252.3333 | 130841.1186 | 99719.3962 |  | 31121.6466 | 100%
TOTAL | 804999.9986 | 344999.9536 | 1150000.0052 | 1076681.29 | 22570 | 95.59% | 595000.005 | 255000.0021 | 850000.0071 | 719282.22 | 130718.0271 | 142.9% | 1400000.0033 | 599999.9523 | 1999999.9556 | 1795963.51 |  | 153288.0271 | 97.46%
|  |  | #REF! |  |  | #DIV/0! |  |  | 1043557.732 |  | 383602.4347
0

## Detailed budget (hidden)
Outputs/Activities | UNDG Budget category | 2020 | 2021 | 2022 | 2020 | 2021 | 2022 | 2020 | 2021 | 2022 |  |  |  |  | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women | UN Women
| Total per output and Outcome | UN Women |  |  | UNDP |  |  | WFP |  |  | 1449705
Outcome 1. Land disputes are prevented by government actors in more effective and gender responsive manner | 1613670 | 388405 | 240520 | 138480 | 344580 | 172705 | 67680 | 87100 | 87100 | 87100 | 36.76% | 56.05% | 10.07%
Output 1.1. Communities and customary governance authorities, women, and youth in targeted counties are aware of the LRA and women’s and youth’s rights to land and participation in land administration and management structures and have further information to access land disputes resolution mechanisms | 305490 | 114980 | 107810 | 72950 | 9750 | 0 | 0 | 0 | 0 | 0 | 14.17% | 0.9343% | 0%
1. Conduct a perception survey about communities’ perception about women’s right to land and participation in Semi-formal and informal dispute resolution mechanisms, and customary land management structures | Contractual Service-International consultant | 45000 | [8 empty] | 2.155% | 0% | 0%
| Travel (tickets) | 2000 | [8 empty] | 0.0958% | 0% | 0%
| Travel DSA | 15150 | [8 empty] | 0.7257% | 0% | 0%
| 2 workshops (Catering, venue) | 2000 | [8 empty] | 0.0958% | 0% | 0%
| DSA data collection | 1800 | [8 empty] | 0.08622% | 0% | 0%
| Travel | 10000 | [8 empty] | 0.479% | 0% | 0%
2. Design a communication campaign based on the findings of the survey and roll-out a communications strategy in piloted counties (community radios, town committees, local media, etc.) to change perceptions and encourage women and youth participation in semi-formal dispute resolution mechanisms | Contractual Service-International consultant | 14000 | [8 empty] | 0.6706% | 0% | 0%
| Travel (tickets) | 2000 | [8 empty] | 0.0958% | 0% | 0%
| Travel DSA | 3030 | [8 empty] | 0.1451% | 0% | 0%
| Transfer Grants for implementation of communication campaign | 15000 | 10000 | [7 empty] | 1.197% | 0% | 0%
3. Simplify, print and disseminate the LRA and LGA | Contractual Service-National Consultant-simplification |  |  |  | 6250 | [5 empty] | 0.2994% | 0.5989% | 0%
| Contractual services-Graphic Designer |  |  |  | 3500 | [5 empty] | 0.1676% | 0.3354% | 0%
| Contactual Services-Printing company | 5000 | [8 empty] | 0.2395% | 0% | 0%
5. Develop knowledge products about available disputes mechanism for communities clearly stating advantages and disadvantages of each | National Consultant |  | 16500 | [7 empty] | 0.7903% | 0% | 0%
| Contractual services-Graphic Designer |  | 3750 | [7 empty] | 0.1796% | 0% | 0%
| Contactual Services-Printing company |  | 5000 | [7 empty] | 0.2395% | 0% | 0%
| Contractual Services Editor |  | 2000 | [7 empty] | 0.0958% | 0% | 0%
6. Roll out trainings on gender, masculinities and women’s rights in targeted counties | Contractual Service-International consultant |  | 38000 | [7 empty] | 1.82% | 0% | 0%
| Travel (tickets) |  | 4000 | [7 empty] | 0.1916% | 0% | 0%
| Travel DSA |  | 6060 | [7 empty] | 0.2903% | 0% | 0%
| Contractual Services TOT , venue, catering |  | 2500 | [7 empty] | 0.1197% | 0% | 0%
| Transfer Grants roll out the training at county level |  | 20000 | 15000 | [6 empty] | 1.676% | 0% | 0%
7. Conduct an end of intervention perception survey | Contractual Service-International consultant |  |  | 27000 | [6 empty] | 1.293% | 0% | 0%
| Travel (tickets) |  |  | 2000 | [6 empty] | 0.0958% | 0% | 0%
| Travel DSA |  |  | 15150 | [6 empty] | 0.7257% | 0% | 0%
| 2 workshops (Catering, venue) |  |  | 2000 | [6 empty] | 0.0958% | 0% | 0%
| DSA data collection |  |  | 1800 | [6 empty] | 0.08622% | 0% | 0%
| Transfer Grants for Data collection |  |  | 10000 | [6 empty] | 0.479% | 0% | 0%
Output 1.2. County land offices and county land boards in pilot Counties have the capacity, procedures and systems in place to formalize customary land | 495890 | 0 | 42060 | 0 | 243445 | 142705 | 67680 | 0 | 0 | 0 | 2.015% | 43.49% | 0%
1. Roo out the need assessment | Workshop |  |  |  |  | 22500 |  |  |  |  | 0% | 2.156% | 0%
| national consultant |  |  |  |  | 13500 |  |  |  |  | 0% | 1.294% | 0%
| Transportation |  |  |  |  | 2625
| OPERATIONAL COSTS |  |  |  |  | 250 | [5 empty] | 0.02396% | 0%
| DSA for workshop |  |  |  |  | 14700 | [5 empty] | 1.409% | 0%
| transport fee |  |  |  |  | 2250 |  |  |  |  | 0% | 0.2156% | 0%
3. Rehabilitee and provide equipment and logistical support ensure the functioning of the CLO and Board Committees (UNDP) | OPERATIONAL COSTS | [9 empty] | 0% | 0% | 0%
| Equipment-Motorbikes |  |  |  | 18000 | [6 empty] | 1.725% | 0%
| Equipment |  |  |  | 71000 | [6 empty] | 6.804% | 0%
4. Capacity building of LLA staff in different areas as per capacity needs assessment including on Gender and Human Rights, Gender responsive land dispute resolution (UN Women/ UNDP) | National Consultant |  |  |  |  | 16000 |  |  |  |  | 0% | #REF! | 0%
| Workshops- contractual services |  |  |  |  | 2500 | [5 empty] | #REF! | 0%
| DSA Consultant |  |  |  |  | 700 | [5 empty] | #REF! | 0%
| Contractual Service-International consultant |  | 32000 | [7 empty] | #REF! | 0% | 0%
| Travel (tickets) |  | 4000 | [7 empty] | #REF! | 0% | 0%
| Travel DSA |  | 6060 | [7 empty] | #REF! | 0% | 0%
| Coordinaton meeting | [9 empty] | 0% | 0% | 0%
5. Support communities to carryout self-identification, establish governance structures, conduct confirmatory surveys, develop land use plans, request registration and obtain land deeds and other necessary documents (UNDP) | Grants to partners |  |  |  | 30000 | 20000 | 20000 |  |  |  | 0% | 6.708% | 0%
6. Provide technical support to LLA and PBO to conduct research and produce boundary maps in project counties using GPS (UNDP) | Consultancy-International/Local |  |  |  | 40000 | [5 empty] | 0% | 3.833% | 0%
| Travel |  |  |  | 7115 | [6 empty] | 0.6818% | 0%
| workshops 1 per district |  |  |  |  | 5000 | 5000
| National Consultant |  |  |  | 25000 | [6 empty] | 2.396% | 0%
7. Support LLA and PBO to organize dialogues to resolve all identified boundary disputes/conflicts (UNDP)- 9 meetings per year | Consultancy Local | [9 empty] | 0% | 0% | 0%
| DSA |  |  |  | 18900 | 18900 | 18900 |  |  |  |  | 5.433% | 0%
| Vehicle rental |  |  |  | 2100 | 2100 | 2100 |  |  |  |  | 0.6037% | 0%
| Catering services - workshops conferences |  |  |  | 3000 | 3000 | 3000 |  |  |  |  | 0.8624% | 0%
8. Support the erection of boundary bill-boards where boundary conflicts are resolved (UNDP)- 20 billboard | DSA- travel |  |  |  | 1680 | 1680 | 1680 |  |  |  | 0% | 0.483% | 0%
| transportation- travel |  |  |  | 1000 | 1000 | 1000 |  |  |  |  | 0.2875% | 0%
| Graphic designer -contractual services |  |  |  | 900 | [6 empty] | 0.08624% | 0%
| contruction (erection of mark of identification) |  |  |  | 10000 | 10000 | 10000 |  |  |  |  | 2.875% | 0%
| Printing -contractual services |  |  |  | 8750 | [6 empty] | 0.8385% | 0%
9. Support LLA/PBO to Print, notarized all Resolutions and distribute to key stakeholders involved in boundary land disputes (UNDP) | Contractual Services- legal support |  |  |  | 5000 | 5000 | 5000 |  |  |  | 0% | 1.437% | 0%
| Printing |  |  |  | 1000 | 1000 | 1000 |  |  |  |  | 0.2875% | 0%
Output 1.3. CLMCs are established in targeted counties and have the capacity to undertake the formalization and recognition of their land rights | 153495 | 57435 | 0 | 0 | 66060 | 30000 | 0 | 0 | 0 | 0 | 2.751% | 9.205% | 0%
1. Develop gender responsive guidelines and training materials on formalization of customary land and Conduct a ToT for LLA staff at county level (UN Women) | Contractual Service-International consultant | 40000 | [8 empty] | 1.916% | 0% | 0%
| Travel (tickets) | 4000 | [8 empty] | 0.1916% | 0% | 0%
| Travel DSA | 6060 | [8 empty] | 0.2903% | 0% | 0%
| Contractual Services TOT | 6250 | [8 empty] | 0.2994% | 0% | 0%
| DSA -roll out in 3 counties | 1125 | [8 empty] | 0.05389% | 0% | 0%
2. Training of communities in targeted counties on the various steps to familiarize communities with various steps leading to formalization (UNDP) | Transfer Grants |  |  |  | 30000 | 25000 |  |  |  |  | 0% | 5.27% | 0%
3. Support the drafting and adoption of the various by-laws to operationalize the CLMCs (UNDP) | [10 empty] | 0% | 0% | 0%
| travel |  |  |  | 8560 | [6 empty] | 0.8203% | 0%
| Consultancy-Local |  |  |  | 22500 | [5 empty] | 0% | 2.156% | 0%
5. Support the leadership election of the CLMCs (/UNDP) | Transfer Grants |  |  |  | 5000 | 5000 |  |  |  |  | 0% | 0.9583% | 0%
Output 1.4. The PBO/LLA/NBC have the capacity to systematically integrate land disputes related data into the existing early warning and response mechanism (UNDP/UN Women) | 397495 | 215990 | 90650 | 65530 | 25325 | 0 | 0 | 0 | 0 | 0 | 17.83% | 2.427% | 0%
1. Conduct a gender and HR assessment of the early warning mechanisms at county and district levels (UN Women) | Contractual Service-International consultant | 36000 | [8 empty] | 1.724% | 0% | 0%
| Travel (tickets) | 4000 | [8 empty] | 0.1916% | 0% | 0%
| Travel DSA | 15150 | [8 empty] | 0.7257% | 0% | 0%
| Travel DSA Communities | 1350 | [8 empty] | 0.06466% | 0% | 0%
| Contractual Services-Worshops 3 | 3750 | [8 empty] | 0.1796% | 0% | 0%
2. Develop indicators, procedures and guidelines, review and modify data collection tools for land conflict (UN Women) | Contractual Service-International consultant- same consultant as in activity 1.4.1 | 56000 | 10000 | 10000 | [6 empty] | 3.64% | 0% | 0%
| Contractual Services- workshop | 10000 | 5000 | 5000 | [6 empty] | 0.958% | 0% | 0%
| Travel DSA | 9090 | 5530 | 5530 | [6 empty] | 0.9652% | 0% | 0%
3. Strengthen the capacity of women pace huts in targeted counties and link them up with the LERN platform (UN Women) | Transfer Grants PBO | 25000 | [8 empty] | 1.197% | 0% | 0%
4. Strengthen capacity of 272 conflict early warning monitors through training on land related issues, provision of communication cards to send incident reports to LERN platform, minimum amount for transportation to collect data. | Contractual Service-International consultant | 36000 | [8 empty] | 1.724% | 0% | 0%
| Travel (tickets) | 2000 | [8 empty] | 0.0958% | 0% | 0%
| Travel DSA | 15150 | [8 empty] | 0.7257% | 0% | 0%
| TOT - Contractual Services | 2500 | [8 empty] | 0.1197% | 0% | 0%
| Transfer Grants PBO |  | 20000 | 15000 | [6 empty] | 1.676% | 0% | 0%
5. Technical support to produce periodic policy briefs based on incident reports on land related disputes, resolution and management | Contractual Service-International consultant |  |  |  | 15750 | [5 empty] | 0.7544% | #REF! | 0%
| Travel (tickets) |  |  |  | 2000 | [5 empty] | 0.0958% | #REF! | 0%
| Travel DSA |  |  |  | 7575 | [5 empty] | 0.3628% | #REF! | 0%
| Transfer Grants PBO |  | 10000 | 5000 | [6 empty] | 0.7185% | 0% | 0%
6. Strengthen capacity of the PBO staff on LERN Platform for increased monitoring, data collection, analysis and transmission (situation room) -computers | Contractual Service-International consultant |  | 22500 | 22500 | [6 empty] | 2.155% | 0% | 0%
| Travel (tickets) |  | 2500 | 2500 | [6 empty] | 0.2395% | 0% | 0%
| Equipment- computer |  | 3000 | [7 empty] | 0.1437% | 0% | 0%
| Travel DSA |  | 12120 | [7 empty] | 0.5805% | 0% | 0%
Output 1.5. Small scale farmers have the capacity to address and support adaptation activities and mitigate risk of conflict (WFP) | 261300 | 0 | 0 | 0 | 0 | 0 | 0 | 87100 | 87100 | 87100 | 0% | 0% | 10.07%
1. Conduct baseline study to identify current problems and potentials of vulnerable farmers in concessions affected communities, considering the key gender issues. (under UN Women budget) | Enumerators honorarium- Travel | [10 empty] | 0% | 0%
| Vehicle rental for baseline data collection | [10 empty] | 0% | 0%
| Data collection training | [10 empty] | 0% | 0%
| Stationery (assortred stationeries) | [10 empty] | 0% | 0%
2. Hold consultative meetings with stakeholders/communities and concessionaries to verify the scope of assistance received by smallholder farmers, ensuring gender sensitivity- community engagement | Trasportation fee- travel | [6 empty] | 2400 | 2400 | 2400 |  | 0% | 0.2774%
| Contactual services-Catering | [6 empty] | 1200 | 1200 | 1200 |  | 0% | 0.1387%
3. Support smallholder farmers’ associations/cooperatives (focusing on women and youth cooperatives) to intensify productivity and value chain and reduce conflict probabilities. | Development/rehabilitation of lowland for rice and vegetable production -Grants to counterpart | [6 empty] | 9000 | 9000 | 9000 |  | 0% | 1.04%
| Assorted vegetable seeds -supplies and commodities- 300 households - Grants to counterpart | [6 empty] | 5000 | 5000 | 5000 |  | 0% | 0.5779%
| Assorted fertilizers and chemicals -supplies and commodities - Grants to counterpart | [6 empty] | 10000 | 10000 | 10000 |  | 0% | 1.156%
| Assorted farming tools --supplies and commodities - Grants to counterpart | [6 empty] | 10000 | 10000 | 10000 |  | 0% | 1.156%
| Training of Women and youth groups in basic post harvest technologies - Contractual Services | [6 empty] | 4000 | 4000 | 4000 |  | 0% | 0.4623%
4. Strengthen provision of, and linkages to, value addition, marketing and market information, using ICT and sustainable and environmentally-sound tools and technologies. | Market information using ICT technologies - Contractual Services | [6 empty] | 2000 | 2000 | 2000 |  | 0% | 0.2312%
| Rice mills/haulers - Grants to counterpart | [6 empty] | 3000 | 3000 | 3000 |  | 0% | 0.3467%
| Rice threshers - Grants to counterpart | [6 empty] | 2000 | 2000 | 2000 |  | 0% | 0.2312%
| Rice winnowers - Grants to counterpart | [6 empty] | 2000 | 2000 | 2000 |  | 0% | 0.2312%
| Rice de-stoners - Grants to counterpart | [6 empty] | 2000 | 2000 | 2000 |  | 0% | 0.2312%
| Rice seed sorters - Grants to counterpart | [6 empty] | 2000 | 2000 | 2000 |  | 0% | 0.2312%
| Integrated cassava processors - Grants to counterpart | [6 empty] | 2500 | 2500 | 2500 |  | 0% | 0.2889%
| 75MT storage facility construction - Grants to counterpart | [6 empty] | 30000 | 30000 | 30000 |  | 0% | 3.467%
Outcome 2. Existing semi-formal and informal land dispute resolution mechanisms are strengthened, more sustainable and are able to reduce conflict in a more effective and gender responsive manner | 1248535 | 358010 | 277815 | 46475 | 103060 | 58720 | 18720 | 223050 | 85085 | 77600 | 32.68% | 17.3% | 8.969%
Output 2.1. Existing Semi-formal land dispute resolution bodies (CPC,CLDMC, peace huts, multi-stakeholders’ platform) have the capacity to resolve disputes in a gender and youth responsive manner and are more sustainable | 765460 | 358010 | 246235 | 36875 | 84340 | 40000 | 0 | 0 | 0 | 0 | 30.71% | 11.92% | 0%
1. Conduct a comprehensive mapping and assessment of ADR mechanism and the gender sensitives of semi-formal land and informal dispute resolutions bodies in targeted counties including MSP, Peace Committees, peace huts, palava huts and Show case how land related disputes are handled. (UNDP/UN Women) | International Consultant |  |  |  | 26000 | [5 empty] | 0% | 2.491% | 0%
| Travel |  |  |  | 11590 | [6 empty] | 1.111% | 0%
| Graphic designer |  |  |  | 6750 | [6 empty] | 0.6468% | 0%
| Printing |  |  |  | 5000 | [6 empty] | 0.4791% | 0%
2. Development of gender and conflict sensitive SOPs, guidelines, regulation for semi-formal dispute resolution bodies (UN Women) | Consultancy-international |  |  |  | 25000 | [5 empty] | 0% | 2.396% | 0%
3. Strengthen the support of semi-formal land disputes resolutions on monitoring parties adherence to the terms of signed agreement (UNDP) | Grants to partners |  |  |  | 10000 | 20000 |  |  |  |  | 0% | 2.875% | 0%
4. Develop a toolkit on gender sensitive land dispute resolution mechanisms and roll out a TOT (such as litigation, arbitration, conciliation and mediation) (UN Women) | Contractual Service-International consultant | 24000 | [8 empty] | 1.15% | 0% | 0%
| Travel (tickets) | 2000 | [8 empty] | 0.0958% | 0% | 0%
| Travel DSA | 15150 | [8 empty] | 0.7257% | 0% | 0%
| Transfer of Grants |  | 15000 | 15000 | [6 empty] | 1.437% | 0% | 0%
5. Roll out trainings on gender, masculinities, and land rights gender responsive conflict resolution and peacebuilding, LRA, for staff from LLA, NBC and members of the CLDMC, County land Offices, Peace huts, MSP, palava huts (UN Women) | Transfer of Grants |  | 5000 | 10000 | [6 empty] | 0.7185% | 0% | 0%
6. Conduct a gender audit at the NBC and develop a gender policy (UN Women/ UNDP) and gender responsive procurement strategy and roll out the strategy | Contractual Service-International consultant-gender responsive procurement | 38000 | 11875 | 11875 | [6 empty] | 2.958% | 0% | 0%
| Travel (tickets) | 8000 | 2000 | [7 empty] | 0.479% | 0% | 0%
| Travel DSA | 18180 | 6060 | [7 empty] | 1.161% | 0% | 0%
| Contractual service-validation workshop | 3125 | [8 empty] | 0.1497% | 0% | 0%
| Consultancy-Local | [9 empty] | 0% | 0% | 0%
Provide technical support to the inter-ministerial concession committee, NBC to engender concession contracting process and agreement negotiations and implementation (UN Women) | Contractual Services local- gender advisor |  | 37800 | [7 empty] | 1.811% | 0% | 0%
[11 empty] | 2.155% | 0% | 0%
| National and International Consultants | 144000 | 72000
8. Strengthen the capacity of PBO staff, NBC on gender. (UN Women) | Equipment-vehicle | 45000
| contractual service-same as activity 6 | 4750 | 61500 | [7 empty] | 3.173% | 0% | 0%
9. implement sustainability plans for women peace huts , MSP in targeted counties to increase income generation (UN Women) | National consultant- Bussiness plans | 16000 | [8 empty] | 0.7664% | 0% | 0%
| Travel DSA | 3500 | [8 empty] | 0.1676% | 0% | 0%
| Workshops 4- Contractual services | 8125 | [8 empty] | 0.3892% | 0% | 0%
| Grants to partners | 28180 | 35000 |  |  | 20000 |  |  |  |  | 3.026% | 1.917% | 0%
Output 2.2: Women and youth in targeted counties have the capacity and skills to participate in formal and informal land disputes | 41180 | 0 | 31580 | 9600 | 0 | 0 | 0 | 0 | 0 | 0 | 1.972% | 0% | 0%
1. Conduct an assessment of the set of skills needed to participate in informal and semi informal land disputes (UN Women) | Consultancy-International same as in ouput 1.1. | [9 empty] | 0% | 0% | 0%
| Travel | [9 empty] | 0% | 0% | 0%
2. Roll out Awareness activities with women and youth on their rights to participate in these structures and strengthen their set of skills (UNDP/ UN Women) | Grants to partners |  | 8794 | 9600 | [6 empty] | 0.8811% | 0% | 0%
3. Raise awareness within local and traditional leaders for women and youth participation in informal and semi- informal land disputes resolution structures (UNDP/ UN Women) | [10 empty] | 0% | 0% | 0%
|  |  | 22786 | [7 empty] | 1.091% | 0% | 0%
Output 2.3. Coordination between existing semi-formal and formal land disputes mechanisms is strengthened. (UNDP) | 56160 | 0 | 0 | 0 | 18720 | 18720 | 18720 | 0 | 0 | 0 | 0% | 5.382% | 0%
1. Line Ministries and Government institutions/ CSOs involve in the implementation of the LRA and LGA regularly meet, share information and put systems in place to coordinate the implementation at national and sub county level (UNDP) | meetining (refreshment) |  |  |  | 4500 | 4500 | 4500 |  |  |  | 0% | 1.294% | 0%
| Transportation fee |  |  |  | 5400 | 5400 | 5400 |  |  |  | 0% | 1.552% | 0%
2. Technical support to clarify roles and responsibilities of various institutions, and dispute resolution mechanisms (UNDP) | DSA |  |  |  | 8820 | 8820 | 8820 |  |  |  | 0% | 2.536% | 0%
Output 2.4. Environmental hazards (deforestation, land degradation, over-exploitation of soil and use of chemicals, water pollution) in targeted counties are effectively managed by EPA in coordination with LLA/NBC | 385735 | 0 | 0 | 0 | 0 | 0 | 0 | 223050 | 85085 | 77600 | 0% | 0% | 8.969%
1. Procure of onsite water testing kits and provide onsite training, regular monitoring of water sources for domestic use. | On-site water testing kits - Grants to counterpart | [6 empty] | 9885 | 9885 |  | 0% |  | 0%
| Training on the use of water quality testing kits - Contractual Services | [6 empty] | 2100 | 2100 | 2100 |  |  | 0.2427%
| Travel (activity monitoring and supervision) - Travel | [6 empty] | 5700 | 5700 | 5700 |  |  | 0.6588%
2. Rejuvenation of traditional water bodies / water source cleaning and provision of alternative water sources | Rehabilitate/provide 12 water point (2 in each district) - Contractual Services | [6 empty] | 12000 | 12000 |  |  |  | 0%
| 12 sets of water point cleaning tools/materials - Grant to Counterpart | [6 empty] | 600 | 600 |  |  |  | 0%
| Incentive for community volunteers for sensitization on peace building issues - Grant to counterparts | [6 empty] | 14400 | 14400 | 14400 |  |  | 1.664%
3. Flood control and drainage work through food for asset | Food or cash incentive for asset creation - Grant to counterparts | [6 empty] | 18000 | 18000 | 18000 |  |  | 2.08%
4. Support land closing for alternative use (poultry, garden etc.) by providing perimeter restriction and Training on improving land quality for improved agricultural production. | Land closing and perimeter restriction - Contractual services | [6 empty] | 6000 | 6000 | 6000 |  |  | 0.6935%
| Training of community members - Contractual Services | [6 empty] | 4000 | 4000 | 4000 |  |  | 0.4623%
5. Provide technical and financial support to conduct socio-economic-technical and environment assessment of the innovative charcoal production technology | International Consultancy - Staff and other cost | [6 empty] | 0 | 0 | 15000 |  |  | 1.734%
6. Technical support to set up of Yoshimura charcoal kiln to produce wood vinegar and sustainable charcoal production facility with storage and work area shed | International Technical consultant - Contractual Services | [6 empty] | 28500 |  |  |  |  | 0%
| Local Technical Assistant - Contractual Services | [6 empty] | 6000 |  |  |  |  | 0%
| Yoshimura kiln | [6 empty] | 24000 |  |  |  |  | 0%
| Themometer drums, jar, etc | [6 empty] | 6000 |  |  |  |  | 0%
| Field work for installing each Yoshimura kiln including local hired - Contractual Services | [6 empty] | 6000 |  |  |  |  | 0%
| Acommodation and DSA (Technical consultant) - Contractual Services | [6 empty] | 9000 |  |  |  |  | 0%
| Technical Assistant cost | [6 empty] | 3000 |  |  |  |  | 0%
| Air fare and local transportation - Contractual services | [6 empty] | 9000 |  |  |  |  | 0%
| Visa processing for technical consultant - Contractual Services | [6 empty] | 200 |  |  |  |  | 0%
| Contingency (5%) - Contractual Services | [6 empty] | 4585 |  |  |  |  | 0%
7. Introduce vinegar (condensed liquid smoke) best known as pest repellent treatment of vegetables, fruits and cash crops to boost high agricultural yield. | Training on use of condensed liquid smoke as pest repellent | [6 empty] | 8000 | 8000 | 8000 |  |  | 0.9246%
8. Support a social and media marketing campaign for the products derived from this innovative charcoal production | Community awareness | [6 empty] | 0 | 2000 | 2000 |  |  | 0.2312%
9. Provision of technical Solutions and Pilot a Support Program to Install Fuel-efficient Cookstove involving youth and women | Local Technical consultant - Contractual Services | [6 empty] | 12000 |  |  |  |  | 0%
| Local Technical Assistant - Contractual Services | [6 empty] | 6000 |  |  |  |  | 0%
| Institutional stove including labor, molds & materials - Grants for counterparts | [6 empty] | 9000 |  |  |  |  | 0%
| Accommodation & DSA (Technical Consultant) - Contractual Services | [6 empty] | 6000 |  |  |  |  | 0%
| Accommodation & DSA (Technical Assistant) - Contractual Services | [6 empty] | 1000 |  |  |  |  | 0%
| Air fare and local transportTransport - Contractual Services | [6 empty] | 7400 |  |  |  |  | 0%
| Visa processing for technical consultant - Contractual Services | [6 empty] | 200 |  |  |  |  | 0%
| Contingency (5%) - Contractual Services | [6 empty] | 2080 |  |  |  |  | 0%
10. Support the identification of youth and women (brick mason) to produce improved stoves as income-generating activities, train them as future contractor | Training of youth and women to produce improved cookstoves | [6 empty] | 2400 | 2400 | 2400 |  |  | 0.2774%
0%
Total per year |  | 746415 | 518335 | 184955 | 447640 | 231425 | 86400 | 310150 | 172185 | 164700 | 69.44% |  | 19.04%
Total Programming | 2862205 | 1449705 |  |  | 765465 |  |  | 647035 |  |  | 69.44% | 73.35% | 0%
Salaries |  | 164000 | 123000 | 82000 | 56500 | 56500 | 46750 | 44004.0125 | 35695.0125 | 35695.0125
International Staff- | Staff | 164000 | 123000 | 82000 |  |  |  | 13839 | 13839 | 13839 | 13.75% | 15.31%
National Staff | Service Contract | [6 empty] | 30165.0125 | 21856.0125 | 21856.0125
Project Assistant | Service Contract |  |  |  | 24000 | 24000 | 24000
FTA |  |  |  |  | 32500 | 32500 | 22750
Monitoring |  | 44605 | 2000 | 61830 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5.194% | 1.437% |  | 3.461%
Monitoring | DSA | 2000 | 2000 | 1830 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 0.958% | 1.437%
Baseline study | Contractual Service-International consultant | 20000 | [9 empty] | 0%
| Travel (tickets) | 2000 | [8 empty] | 0.0958% | 0%
| Travel counties | 10000 | [8 empty] | 0.479% | 0%
| Travel DSA | 10605 | [8 empty] | 0.508% | 0%
Evaluation | Service Contract |  |  | 40000 | [6 empty] | 1.916% | 0%
| DSA |  |  | 5000 | [6 empty] | 0.2395% | 0%
| Travel |  |  | 15000 | [6 empty] | 0.7185% | 0%
Endline
Operational Costs |  | 8007.5 | 8000 | 8000 | 19072.6 | 8000 | 8000 | 15000 | 10000 | 10000 | 94080.1 | 3.361%
Total per Year |  | 963027.5 | 651335 | 336785 | 528212.6 | 300925 | 146150 | 374154.0125 | 222880.0125 | 215395.0125 | 93.46% | 93.46%
|  | 67411.925 | 45593.45 | 23574.95 | 36974.882 | 21064.75 | 10230.5 | 24320.0108 | 14487.2008 | 14000.6758 | 6.542% | 6.542%
Total Per agency |  | 2087727.825 |  |  | 1043557.732 |  |  | 865236.9249
Total | 3996522.4819 |  | Categories UN Women |  | 975287.6 | Categories UNDP
| -3477.5181 | 1951147.5 | Service Contract | 953300 |  | Service Contract | 392400 | 812429.0375
|  |  | travel | 262480 |  | travel | 186065
|  |  | staff | 369000 |  | staff | 87750
|  |  | grants | 294360 |  | grants | 185000
|  |  | Equipment | 48000 |  | Equipment | 89000
|  |  | Operating costs | 24007.5 |  | Operating costs | 35072.6
|  |  |  | 1951147.5 |  |  | 975287.6
|  |  |  | 0 |  |  | 0
Note on D142: user: Kofi