2019 -2023

2019 -2023

UN Joint Programme to Build and Strengthen Urban and Rural Resilience and the Conditions for Recovery in Syria

Damascus, 30 APRIL 2024

UN Joint Programme to Build and Strengthen Urban and Rural Resilience and the Conditions for Recovery in Syria

Damascus, 30 APRIL 2024

IMPLEMENTATION PERIOD: 15 JANUARY 2019–31 DECEMBER 2023

IMPLEMENTATION PERIOD: 15 JANUARY 2019–31 DECEMBER 2023

FINAL PROGRAMME NARRATIVE REPORT

FINAL PROGRAMME NARRATIVE REPORT

UN Joint Programme to Build and Strengthen Urban and Rural Resilience and the Conditions for Recovery in Syria

FINAL PROGRAMME NARRATIVE REPORT

IMPLEMENTATION PERIOD: 15 JANUARY 2019–31 DECEMBER 2024

| Programme Title & Project Number |  | Country, Locality(s), Priority Area(s) / Strategic Results |
| --- | --- | --- |
| - Programme Title: UN Joint Programme to Build and Strengthen Urban and Rural Resilience and the Conditions for Recovery in Syria - MPTF Office Project Reference Number: 00116116 (EU) 00118029 (non-EU) |  | Outcome 1: Urban Area-based Recovery and Neighbourhood Plans that are responsive to community’s needs, particularly the most vulnerable groups, are developed, delivered and monitored in an inclusive, participatory and conflict-sensitive manner at local level. Outcome 2: Basic and social services are restored, improved and sustained to enhance community resilience and social cohesion. Outcome 3: Households and communities benefit from sustainable livelihood opportunities, including economic recovery and enhancing social cohesion and community security. |
| Participating Organization(s) |  | Implementing Partners |
| FAO, UNDP, UNFPA, UN-Habitat, UNICEF and WFP |  | Please refer to the activity matrixes. |
| Programme/Project Cost (US$) |  | Programme Duration |
| Total estimated budget as per project document is $70,766,349 |  | Overall Duration (months): 59.5 Start Date: 15 January 2019 Original End Date: (14 January 2021) Current End date: (31 December 2023) |
| Total amounts of resources already disbursed by the two donors |  |  |
| Total: $ 21,080,289 (00116116) EU $ 6,859,338 (00118029) NORWAY |  |  |
| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| Mid-Term Evaluation conducted March–April 2022. |  | o Name: Mohammad Taani o Title: Joint Programme Manager o Participating Organization (Lead): RCO o Email address: Mohammad.Taani@undp.org |

TABLE OF CONTENTS

Abbreviations	5

Executive summary	6

I. Purpose	19

II. Planning, coordination, and implementation highlights	19

III. Results	20

A.	Communication and visibility results	20

B.	Narrative reporting on results	20

C.	Implementation overview	21

Outcome 1: Urban Area-based Recovery and Neighbourhood Plans developed, delivered and monitored in an inclusive, participatory and conflict-sensitive manner at local level	22

Output 1.1. Plans and resilience programmes formulated in a participatory manner and responsive to people’s needs, particularly the most vulnerable groups.	22

Outcome 2: Basic and social services restored, improved and sustained	27

Dara’a:	28

Output 2.1 Educational, recreational and PSS spaces rehabilitated, and nutrition-sensitive agriculture education sessions provided	28

Output 2.2: Social cohesion is enhanced through neighbourhood-based rehabilitation of community assets including housing, WASH, basic social and productive infrastructure, and services	30

Deir ez-Zor:	33

Output 2.1 Educational, recreational and PSS spaces rehabilitated, and nutrition-sensitive agriculture education sessions provided	33

Output 2.2: Social cohesion is enhanced through neighbourhood-based rehabilitation of community assets including housing, WASH, basic social and productive infrastructure, and services	34

Outcome 3: Households and communities benefit from sustainable livelihood opportunities, including economic recovery and enhancing social cohesion and community security	38

Dara’a:	39

Output 3.1: Income, sustainable livelihoods opportunities and inclusive local economic development are restored and maintained in both urban and rural catchment areas to increase household incomes, boost food production and enhance local markets	39

Output 3.2: Social and economic needs of the most vulnerable groups are identified and addressed	45

Deir ez-Zor:	50

Output 3.1: Income, sustainable livelihoods opportunities and inclusive local economic development are restored and maintained in both urban and rural catchment areas to increase household incomes, boost food production and enhance local markets	50

Output 3.2: Social and economic needs of the most vulnerable groups are identified and addressed	54

D.	The JP current location identification and selection	58

E.	The JP prospective locations identification and selection	59

F.	Cross-cutting issues	59

IV. Key challenges and mitigation approaches	60

V. Lessons learned	63

VI. Opportunities	65

VII. Annexes	66

Annex A: JP Syria Dara'a Phase 1 Activity Matrix Update 31 December 2023 (Also attached separately on A3-size PDF for print)	66

Annex B: JP Syria Dara'a Phase 2 Activity Matrix Update 31 December 2023 (Also attached separately on A3-size PDF for print)	70

Annex C: JP Syria DEIR EZ-ZOR Activity Matrix Update 31 December 2023 (Also attached separately on A3-size PDF for print)	73

Annex D: JP Syria Activity Status Analysis at Outcomes Outputs levels 31 December 2023 (Also attached separately on A3-size PDF for print)	77

Annex E: JP Syria M&E framework Dara’a 1 Target vs. Reach Sheets End of 2023 (Also attached separately on A3-size PDF for print)	78

Annex F: JP Syria M&E framework Deir ez-Zor Target vs. Reach Sheets End of 2023 (Also attached separately on A3-size PDF for print)	80

Annex G: JP Syria M&E framework Dara’a 2 Target vs. Reach Sheets End of 2023 (Also attached separately on A3-size PDF for print)	84

Annex H: UNJP 2.0 Programme Document (attached Separately as PDF)	88

Annex I: FAO’s Assessment report for rehabilitation of small-scale irrigation structures in Dara’a	89

# Abbreviations

CSO		Civil Society Organization

CWC		community well-being centre

CwD		children with disabilities

DEIR EZ-ZOR		Deir ez-Zor

ECE		early childhood education

FAO		Food and Agriculture Organization of the United Nations

GBV		gender-based violence

GOPA		Greek Orthodox Patriarchate of Antioch and All the East

HH		household

IECD	Institute Européen de Coopération et de Dévelopement (European Institute for        Cooperation and Development)

IP		implementing partner

JP		The Joint Programme to Build and Strengthen Urban and Rural Resilience

JSC		Joint Steering Committee

M&E		monitoring and evaluation

LFFS		Livestock Farmer Field School

NFE 		non-formal education

NGO 		non-governmental organization

OCHA 		Office for the Coordination of Humanitarian Affairs

OoSC		out-of-school children

PBWGs	Pregnant and Breastfeeding Women and Girls

PLWG		pregnant and lactating women and girls

PMU		Programme Management Unit

PSS		psychosocial support session

PUNO		Participating United Nations Organization

PWD		people with disabilities

RC		Resident Coordinator

RH		reproductive health

SLP		self-learning programme

SME		small and medium enterprise

SP		satellite point

SSSD		Syrian Society for Social Development

SWM		solid waste management

TWG		Technical Working Group

UNDP		United Nations Development Programme

UNDSS	United Nations Department of Safety and Security

UNFPA	United Nations Population Fund

UN-Habitat	United Nations Human Settlements Programme

WFP		World Food Programme of the United Nations

# Executive summary

To date, the Syrian context has largely invoked the provision of humanitarian assistance with less emphasis on resilience efforts. The UN Joint Programme (JP) in Syria between 15 January 2019 and 31 December 2023 brought together six UN implementing agencies, namely FAO, UNDP, UNFPA, UN-Habitat, UNICEF, and WFP, who delivered coordinated resilience and recovery-oriented interventions, through a unique multi-donor, multi-year, multi-agency pooled funding mechanism to communities who witnessed and are still witnessing massive damage to every aspect of life and livelihoods.

The JP on Urban and Rural Resilience is underpinned by a commitment to collective programming towards resilience solutions, applying a nuanced, area-based, and conflict-sensitive approach, which facilitated an optimisation of community participation inclusive of targeted efforts for the inclusion of conflict affected/traditionally marginalised groups including but not-limited-to women, youth, people with disabilities and the elderly. Adherence to the application of area-based approach practices created an appropriate space for participatory and bottom-up-led processes with a focus on the rural-urban linkages, while ensuring gender-responsive/gender-transformative and inclusive planning. The complexity of the environments within which the JP is operating warranted particular effort towards ensuring interventions are identified, prioritized, designed, and implemented in a manner that accommodates effective community engagement.

The JP programming decisions are informed by a carefully designed process based on effectual community engagement through multiple consultations and workshops aiming to both build the communities’ capacities to ensure meaningful engagement in participatory processes and also implemented transparent processes to agree upon priority interventions. The priorities that emerged through the participatory workshop processes, were then analysed by the JP participating UN Organizations (PUNOs) who consider the balance of interventions in the target area, conflict sensitivity and risk, relationships/interdependence between interventions, opportunities for gender-transformative programming, and wider spatial and intersectoral consideration before finalizing proposed interventions.

The Joint Steering Committee (JSC) selected Deir ez-Zor (DEIR EZ-ZOR) city and Dara’a city and their rural catchment areas as the intervention locations for the JP, based on extensive technical assessments and on ground consultations with local community and stakeholders.

The JP, through joint and complementary interventions carefully designed by the PUNOs, contributed to improving the Syrian people’s resilience in both locations, Dara’a and Deir ez-Zor, which aimed to maximise their impact in urban and rural areas.

The sense of social cohesion and inclusion in the social fabric was improved as a result of availing safe access to various rehabilitated public green spaces, facilities and markets. The involvement of various stakeholders from community representatives in various steps of JP consultations, planning and implementation presented a value-added factor that contributed to strengthening the buy-in and advocacy.

The economic and financial capacity of targeted population increased as a result of revival and availing of diversified urban and rural livelihoods and sources of income. People became more self-sufficient and less dependent on aid. As a result of improved livelihoods of families, many drop-out of school children – who were informally working to support their families - re-enrolled in formal and non-formal education leading to a significant amelioration of education level amongst school-age children. The overall health status of population in targeted location was enhanced as a result of multiple urban-rural interventions through which, water was availed for drinking and irrigation, sewage networks and drainages were rehabilitated and cleaned, health centres were rehabilitated and bolstered, and more convenient access to reproductive health and other services was enabled for women, girls, and men.

ON OUTCOME1: The JP’s bottom-up, demand driven, and participatory approach engulfed within Outcome 1 of the JP proved utility and effectiveness in ensuring the targeted communities’ active involvement in various stages of the JP planning, design and implementation. This was apparent in the improved ability of village committees in in formulating their development action plans at the community level, which was a result of the provision of trainings and supporting the village committees which was provided by FAO. Better usage of water resources was also detected as local communities were provided with, through a participatory approach by establishing water users’ groups, water resources management trainings which equipped them with the necessary operational skills within this field. As a result of improved access to water resources and improved irrigation schemes, targeted farmers were able to yield improved results at the end of the harvest season.

This involvement of various community stakeholders including with neighbourhoods and village committees, elected representatives (i.e., Mukhtars), individuals of various backgrounds, and front-line civil workers (municipal staff, teachers, health workers, ...etc.) contributed largely to re-instating community ties, strengthening the social fabric and creating mutual understanding amongst them with the overarching objective of having their community’s essential resilience needs addressed by successful implementation of the JP. The JP mainstreamed gender under Outcome 1 by ensuring the equal participation of men, women, and other marginalized groups including youth, people with disabilities and female households.

ON OUTCOME 2: Restoring, availing and enabling access to various basic services to the community in both targeted locations was the main essence of the JP Outcome 2. Schools were rehabilitated, furnished and WASH facilities designed with gender segregation in mind to re-enable equitable access to education for boys, girls and children with disabilities. The street rehabilitation and solar lighting reflected positively on the sense of safety of people, and enhanced mobility, safer access to various locations (inc. schools, health centres, ...etc), reduced road accidents and criminal activities at night, and extended economic activities in the markets thus contributing to the overall wellbeing of people.

Sewage and water networks rehabilitation supported the amelioration of the overall health situation in both locations and reduced the likelihood of water-borne diseases, while the interventions of debris and waste removal, and cleaning of main drainage down-streams reduced pollution and environmental hazards. Against this backdrop, one major health centre was rehabilitated, while another one was equipped with solar energy to increase operational hours, which improved the access of the targeted population the facilities, and also enabled health workers to treat emergency cases in a timely manner. Additionally, the installation of multiple points for provision of reproductive health services and GBV advisory in urban and rural areas enabled a convenient, safe and discrete access for women and girls to receive such services.

Furthermore, public spaces (i.e., public gardens, parks, and main attraction squares) were rehabilitated to become a point of social gathering and community interaction in an approach to rebuild social cohesion amongst residents in many neighbourhoods, while availing a safe space for children to play.

ON OUTCOME 3: Supporting decent and resilient urban and rural livelihoods is at the heart of the JP and embedded in most of the Outcome 3 activities, while approaching the youth with various social inclusion, training and skills development interventions and provision of safety nets to the most vulnerable.

The targeted segment of population in both locations have experienced a notable change with regards to economic revenues rendered from practicing their daily work activities. Workshops in urban industrial areas were rehabilitated to avail a suitable and convenient place for craftsmen and small/micro industrialist to jump start their businesses.

Other smaller livelihoods opportunities were availed to young people graduating from skill development and vocational training through linking them to markets and employment opportunities, while other youth benefitted from provision of tools sets, mini-production tools (i.e., coffee grinders and juice machines, etc.) and small grants. Gender equality was significantly approached under such interventions due to the willingness of young men and women to enrol and high influx of participants, where females constituted a large segment. Social cohesion amongst various groups of youth from different backgrounds and education levels was approached by means of special skills training on leadership and design of innovative social initiatives to further support the fabric of their community (i.e., sport events, reading sessions, cleaning and repair of bus stops, cleaning gardens, etc.)

Both locations Dara’a and Deir ez-Zor are considered agricultural governorates, where agriculture and livestock keeping represent the main source of income for farmers and rural dwellers.

The JP addressed rural livelihoods through tailored set of interventions focused on: (A) rehabilitation of agricultural irrigation assets (Canals, water pumps and wells, grazing pastures) besides provision of key agricultural equipment (Seeding machines, maize dryers and drip irrigation nets), and agricultural inputs (i.e., seeds, fertilizers and pesticides). As a result, and due to the availability of water, agriculture was revamped in the targeted areas and the yield of the harvest increased especially for smallholder farmers (i.e., those who own small land and/or little cattle), and household needs within the targeted areas. (B) Agricultural entrepreneurship training was provided to small and vulnerable farmers, to enable them to start small business and generate income. Many of the recipients of this training were females responsible for income of their households. The JP distributed mini production toolkits (dairy production kits and food processing kits) to successful graduates and enabled them access to market their produce. (C) Livestock breeding training was administered to small-holder sheep keepers to enable them care for their small cattle and increase the number of heads through administering advanced feeding and breeding techniques.

These interventions have changed the way these small farmers look at their lives and ignited their hope to grow and generate further income for their families to fulfil their human needs. It induced their social cohesion spirit by nature through their sharing of knowledge, experience and some of the yields with their neighbours who were less fortunate. Meanwhile safety nets were administered by the JP in terms of nutrition/hygiene vouchers for pregnant and lactating women and girls and cash for children with disabilities to relief some financial burden on their families.

Throughout its implementation the JP maintained a focused approach to mainstream gender across its activities. The JP managed to target a significant number of women and girls under its joint interventions, where they represented more than half the number of the overall beneficiaries.

The following table shows the total reached beneficiaries and the proration of the JP implementation budget in both locations. The summary also includes the breakdown of beneficiaries between women and girls, and men and boys, where women and girls represent 55% of the overall beneficiaries. Persons with Disabilities (PWDs) were also targeted, representing approximately 1% of the overall number of beneficiaries.

| Grand Total REACH | W&G | M&B | OVERALL | PWDs (both W&G and M&B that are included in the overall total) |
| --- | --- | --- | --- | --- |
|  | 405,932 | 336,679 | 742,611 | 7,027 |
| Ratio | 55% | 45% |  | 1% |
| TOTAL US$ Spent | W&G | M&B |  | PWDs |
| $24,619,301.00 | $13,457,600.4 | $11,161,700.6 |  | $232,961.57 |

During its implementation period from 15 January 2019 till 31 December 2023, the JP, through joint and complementary interventions by the PUNOs, continued to support people’s resilience in both locations, Dara’a and DEIR EZ-ZOR, through multiple interventions carefully designed to achieve complementarity in action and maximum impact in urban and rural areas. Additionally, the JP maintained current and future donor involvement through high-level meetings and joint field visits, while following up, monitoring and reporting on activities and making efforts in communication and advocacy. To this end, the following key highlights were produced under the JP:

1) PUNOs’ programmatic achievements overview

- Dara’a

At rural level

During the implementation of Dara’a I and Dara’a II workplans, FAO supported food supply, access to irrigation and agricultural entrepreneurship. FAO provided entrepreneurial agricultural training to a group of beneficiaries where some of whom received grants to start their microprojects (e.g., bee keeping, poultry, dairy production, dry food products, herbal product, etc.). UNFPA complemented the FAO approach by providing few additional grants to some women who graduated from FAO training.

To support irrigation in Dara’a, FAO completed the rehabilitation of Ghadeer Al-Bustan main canal and irrigation network, where this intervention enabled farmers and livestock keepers to access water needed for irrigation and drinking for their cattle. Additionally, FAO rehabilitated five collective wells in the Green Belt area in south and east Dara’a to support irrigation of fruit trees in these areas and in complementarity to this intervention FAO supported fruit-trees’ farmers with tools and technical advice to enhance services for fruit trees. Additional four wells in the steppe (Al Badia) area south and east of Dara’a were rehabilitated to enhance access to drinking water for sheep, and benefit villagers from water for house use.

Jointly, FAO and WFP collaborated to revive livelihoods in rural Dara’a. FAO provided green fodder seeds, veterinary inputs, and skills training to cattle herders in west Dara’a, enabling them to produce an alternative to expensive concentrated fodder. WFP complemented this activity by providing ready-to-use fodder during the period when green fodder is growing. In addition, WFP provided fertilizers to support the growth of green fodder seeds.

At another dimension to support cattle keepers and breeders, WFP rehabilitated 70 hectares of Al Jalad reserve area by planting grazing plants and installing a protective fence. Additionally, WFP extended additional support to five women owners of simple dairy and cheese processing units to upgrade their businesses by providing technical training and equipment. This intervention enables them to cope with increased production demands effectively. It's worth mentioning that these women are breadwinners for their families.

Furthermore, FAO and WFP supported smallholder and vulnerable farmers together through the provision of summer vegetable seeds, drip-irrigation networks, and fertilizers. Vulnerable farmer families were supported with live poultry and agricultural inputs to support backyard farming, along with technical advice and supportive food assistance. It's worth mentioning that the targeted farmers were selected based on Categories B and C of the WFP Beneficiary Selection Tool (BST), in addition to technical criteria.

At urban level

UNDP has provided critical support to revive small and medium enterprises (SMEs), whose owners lost some or all of their work assets, where many MSMEs in different professions were revived.to support livelihoods and improve their coping capacities and resilience with focus on women-led small businesses.

UNICEF completed the rehabilitation of four schools in Dara’a Al Balad neighbourhood of Dara’a city, thus, availing learning spaces for students, besides preparation of early-childhood education spaces in two of the four schools to accommodate young pupils. School furniture has also been provided. UNICEF provided non-formal education (NFE) services and self-learning sessions to students, in addition to youth empowerment in Dara’a city through technical and vocational training.

UN-Habitat and UNDP collaborated on the rehabilitation of urban infrastructure, installation of solar lighting units in various neighbourhoods, rehabilitation of key market streets and public parks, and removal of solid waste and debris, thus, reinstating safer access and enhancing the sense of safety and security for children and women, while supporting back-to-normal life in Dara’a city. In this regard, solar units were installed, public parks rehabilitated, safer access enabled for school children through street rehabilitation, lighting and railing, and many cubic meters of solid waste were removed from 12 neighbourhoods through which, multiple temporary job opportunities were availed, in addition to cleaning the main path of Al Zaidi River valley.

Additional infrastructure services were provided to enhance the people’s resilience in Dara’a Al Balad, where the UN-Habitat and UNDP collaborated on needed WASH interventions. The UN-Habitat rehabilitated the home connections to main sewage lines in two neighbourhoods (namely Al Abbassiyeh, and Al Bihar), while UNDP worked on maintaining the water network in Dara’a Al Balad to prevent leakages, and contamination of drinking water and reduce the financial burdens and health risks related to purchasing drinking water from unknown sources. A main market street in Al Balad was rehabilitated and solar lit, and additional two parks for women were rehabilitated in collaboration with UNFPA.

In an effort to resolve many local issues in Dara’a relevant to people’s access to real-estate documentation, which continue to be a reason for HLP disputes, the UN-Habitat supported the real-estate department in Dara’a with an electronic archiving system, along with some light rehabilitation and provision of solar lighting. In Parallel, to enhance the provision of public health services, the UNDP supported the central public clinic in Dara’a with solar energy equipment dedicated for the kidney dialysis section to ensure continuity of services and extend the working hours of this critical clinic. While, for improving the broader health and hygiene level of the city the UNDP provided maintenance services to municipal vehicles and provided fog-sprayers (fumigators) to exterminate insects. Furthermore, to enhance the veterinarian services provided to cattle and farm animals, the UNDP provided newly graduated veterinarians with technical training and distributed toolkits to support the veterinarian work in the field and ensure timeliness and effectiveness of veterinary services.

Under the vocational training and life-skills development program, UNDP supported young people and adolescents in Dara’a through a tailored three-prone training programme; the first focused on economic awareness to raise the youth understanding of sustainable economic aspects, the second focused on life skills development to deal with different daily-life challenges, solve problems and make right decisions; and third provided overall awareness on gender aspects and gender health. Additionally, the organization provided qualitative training on the concepts of gender to a wide group of male and female trainees that included community leaders, members of rural development units, and community members. This training emphasized the principles of equality and impartiality in responding to the different needs of women and men with strategic views to mitigate challenges and remove obstacles in the path of achieving social justice. Other topics covered economic literacy, gender health, life skills, effective communication, problem solving, and decision making. These sessions were side supported with specialized remote psychological health sessions in as step towards achieving local social and familial peace.

UNFPA through the JP continued to support the established facilities including the women and girls safe space (WGSS) referred to as the Vision Centre, to create a space for women and girls to feel physically and emotionally safe so they are comfortable and able to freely express themselves without the fear of judgement or harm in addition to the empower them economically; and the Youth Friendly Space (YFS) to create a space for youth to support them in developing their skills and knowledge and raise their awareness of youth in GBV, RH, Mine Risk Education and PSS, and moreover to support them economically

UNFPA continued their per-mandate activities at urban and rural levels in Dara’a targeting vulnerable women with reproductive health (RH) and gender-based violence (GBV) services and advisory and psychosocial support sessions (PSSs) and advisory, provided through the ‘Vision centre.’ UNFPA continued their coordination with UNICEF by providing awareness sessions on GBV, RH, and Mine Risk education to the beneficiaries who are targeted by UNICEF  at urban and rural levels in Dara’a.

Social protection interventions saw UNDP, UNFPA and WFP targeting the most vulnerable and people with disabilities (PwD). UNDP provided mobility support (wheelchairs, crutches, and prosthetics) In addition to psychological support session and post-rehabilitation sessions; WFP provided out-of-school children (OoSC), students registered in curriculum B  and in Non-formal Education, and Pregnant and Breastfeeding Women and Girls (PBWGs) with cash-based transfers in the form of food vouchers to cover their nutritional needs (beneficiaries redeemed their vouchers for food items), while UNFPA provided PBWGs with vouchers for hygiene items. WFP provided electronic vouchers to students enrolled in non-formal education and in formal accelerated education program B in coordination with UNCIEF, while pregnant and lactating women and girls received electronic vouchers for food and hygiene items in coordination between UNFPA and WFP.

Social cohesion is a cross-cutting approach mainstreamed across all JP activities, by all PUNOs. UNDP approached social cohesion as a standalone component focusing on community empowerment; enhancing participation; building bridges among communities of diverging political, religious, ethnic, and socioeconomic backgrounds; and creating an atmosphere of social solidarity across urban and rural areas.

- Deir ez-Zor

At rural level

Jointly, WFP and FAO supported vulnerable farmers with agricultural inputs of winter/summer vegetable seeds and fertilizers, while FAO trained smallholder sheep farmers on advanced methods to expand their herds. WFP supported them by providing mobile fencing for their small cattle. To enhance rural livelihoods, FAO provided entrepreneurial agricultural training to men and women and grants for start-up projects (e.g., beekeeping, dairy production, dry food production, fodder production, etc.).

In terms of agricultural infrastructure and assets, WFP completed the rehabilitation of a wholesale farmers' market in Al Shmeitieh village, enabling farmers to have safe access and a convenient location for selling their products. FAO also distributed seeding machines to support wheat and barley farmers, enhancing their produce and achieving higher yields.

WFP completed the rehabilitation of farmers' associations' pumping stations along the Euphrates River to improve access to water for farmers, allowing them to expand cultivated areas and boost production. The technical specifications for this endeavor were developed in coordination with FAO. Additionally, to prevent agricultural product losses among maize farmers, WFP provided the local community with a maize dryer. Moreover, to support the agricultural production cycle, WFP assisted the local community in setting up food processing units.

Village committee members were trained by FAO’s experts on needs analysis and prioritization as well as drafting development plans and setting requirements to support bottom-up planning of interventions by international organizations.

At urban level

The interventions relevant to community assets and infrastructure rehabilitation through collaboration between UNDP and UN-Habitat progressed in 2023 towards completion by the end of 2023, where UNDP completed rehabilitation of water and sewage networks in in addition to five Km of electricity network. UN-Habitat complemented work in the industrial zone through internal streets rehabilitation and provision of solar lighting. Additionally, UN-Habitat completed the rehabilitation of Al-Ashaari main street and installed solar lighting units on Bor-Saiid Street, while UNDP removed solid waste and debris from eight neighbourhoods in the city including the old Souk.

To enhance the environmental and health situation at the city’s suburban southern edge, UN-Habitat completed the cleaning and rehabilitation of the main sewage drain channel of Deir ez-Zor city, where the channel bed was cleared of all weeds and wild plants and tilted to enable faster water flow. The water flow power was also strengthened by rehabilitating a water intake opening from the main river to wash away sewage water.

Within their environmental interventions, UN-Habitat removed 25,000 m3 of solid waste from the temporary landfill on Bor Saeidd street at the main wholesale market.

To revive the central archaeological city center, UN-Habitat has worked on the rehabilitation of the central square within the archaeological area, by this the important road that connects the southern and northern areas to the old bridge to the north and to Bor Saeed street to the south, where the bus station that connects DEIR EZ-ZOR with othr governorates.

In coordination with UNICEF, three parks were rehabilitated along with providing safer access to the schools students within the neighborhing perimeter of nine schools, some of which were rehabilitated by UNICEF under the JP interventions in complementarity with UN-Habitat interventions.

In cooperation with UN-HabitatUNDP, is working on the popular market rehabilitation along with a bakyard park attached to it in the neighbourhood of the rural bus stattion that connects the villages with the city. This intervention helps urban and rural dwellers especially women to access the market and conduct minor econmoic exchanges of their home made products. The activity was not completed by the designated end of the programme on 31 December 2023, and needed additional time until end of Q1 2024, therefore, and due to its importance in supporting small and seasonal livelihoods and to avoid doing harm to the communities who were anticipating it, the relevant agencies completed it using other sources of funds.

In order to support stability in the return areas and to enable people to find livelihood opprtunities, UN-Habitat has worked on the rehabilitatinon of the connections of residential sewege networks in some areas of Al Jbeileh addition to rehabilitation of Al Jbeileh market especifically the sidewalk and the main street.

In the same context, and to support the health sector, UNDP has completed the rehabilitation of Alhamidieh health center second floor.

SMEs play an essential role in the Deir ez-Zor economy, hence, availing a steady source of income and supporting urban livelihoods to different segments of workers, trainees, and professionals. UNDP worked on the revival of SMEs in the industrial zone and other areas that have seen a return movement in Deir ez-Zor to enable craftsmen and small business owners (like blacksmiths, carpentry, car maintenance, etc.) to recommence and/or resume their business activities. In this regard, UNDP has completed the revival of workshops in the industrial zone in addition to other small businesses outside the industrial zone where ten of them belong to women and five belong to people with disabilities. This intervention has contributed to creating temporary job opportunities and permanent job opportunities.

On the vocational training aspect, UNDP has conducted activities related to job fairs and trainings on different skills to beneficiaries from the youth in DEIR EZ-ZOR, who were enrolled in the UN intervention of reviving SMEs, where beneficiaries received job placement support, vocational training, and entrepreneurial skills training, and some beneficiaries received grants to start their businesses. This intervention has helped in providing 43 temporary job opportunity and 70 permanent ones.

On the life skills and youth training on active participation in the society development, UNDP has trained youth from the local community in Deir ez-Zor city and surroundings on designing activities and social initiatives, in addition to training on leading and managing the volunteering youth groups. On the other side, UNDP has designed youth initiatives like bus stations maintenance and cleaning, parks cleaning, sports activities to support people with disabilities, etc.

Based on the UNDP vision of supporting women empowerment and gender equality, the programme worked on enhancing the women economic empowerment in Deir ez-Zor through supporting women groups who are interested in entering the labour market and through enabling their economic roles outside their homes. In order to ensure the sustainability of the intervention within a supporting environment, UNDP has provided specialized services that includes training and consultation opportunities to develop knowledge skills, economic illiteracy, household budget management, and business administration and marketing and accounting to those who are interested, in addition to providing financial support to start-up businesses that are managed by women in a collective manner in order to enhance women participation in activating their roles in the community.

It is worth mentioning the services package that supports the beneficiaries in providing socio-psychological specialized support, discussions around rights concepts, company types, initiatives on legal awareness and initiatives that support youth and men participation to fill the gap of inequality not only between women and men but also between youth and men from different age groups, and also between rural and urban areas.

To support education, UNICEF completed the rehabilitation and furnishing of seven schools in Deir ez-Zor city. Adherence to gender aspect was applied especially in the WASH facilities in the schools. These rehabilitated schools have capacity to accommodate about 4,000 students UNICEF has also conducted back to schools’ campaigns and the non-formal education initiatives targeting students who are under the risk of dropping out of school, where UNICEF has implemented the remedial classes programme, the supporting learning programme (SLP), and the early childhood education programme (ECE).

Women and youth empowerment is of great importance, therefore UNDP, UNICEF and UNFPA joined efforts and collaborated with the implementing partner (IP) European Institute for Cooperation and Development (IECD) to design plans for establishing a comprehensive community centre in which the implementation of joint major multi-sectoral activity will take place supporting the social cohesion aspect.

Accordingly, each agency has implemented activities as per its mandate and expertise targeting youth, enhancing their role and participation in labour market and support the local socio-economy through   providing various VT, soft skills and capacity-building on community-based engagement and leadership to trainees.

UNFPA conducted awareness sessions on reproductive health (RH) and gender-based violence (GBV) besides supporting vocational training activities along with the other UN agencies focusing on mobile phone maintenance, solar systems maintenance in addition to foreign language and computer literacy (ICDL) courses and supported the distribution of toolkits to graduates of vocational training to help them enter the job market. Additional entertaining courses (i.e., sports, interactive theatre, painting, peer training …etc.) were also provided to support social ties and enhance collaborative social initiatives. UNFPA formulated and trained the “Orange team” to communicate messages and raise awareness in their respective societies on RH/GBV issues, who managed to reach people in Deir ez-Zor city and rural suburbs. In this regard the UNFPA formulated a committee of women from the local community and trained them to attract and enrol women in cash-for-work programs (i.e., cleaning gardens and public facilities like gardens and schools…etc.), where women and men benefitted from this program. It is worth mentioning that UNFPA implementation methodology of profession related activities that support in behaviour changing through raising awareness towards the professions that helps in abolition of the stereotyping against women and girls in Deir ez-Zor city, where UNFPA in coordination with UNDP has utilized the VTC to provide vocational training to beneficiaries in the domains of electrical maintenance, plumbing, food making, dairy production, and sweets production in all targeted areas in rural and urban Deir ez-Zor.

UNFPA continued its per-mandate interventions providing most vulnerable women and girls in Deir ez-Zor city and its rural areas with RH/GBV sessions besides psychosocial support sessions and case management through a main community centre and three satellite points in nearby suburbs and affected a referral mechanism between the points and the centre and with healthcare providers (i.e., hospitals and laboratories…) as well as with other agencies interventions to ensure maximum reach of beneficiaries to services provided by JP PUNOs reaching a total of around 71,000 beneficiaries.

UNICEF, UNDP, UNFPA and WFP implemented their social protection interventions targeting the most vulnerable and people with disabilities (PWD). UNDP provided mobility support (wheelchairs, crutches, and prosthetics) and hearing aids to 45 people with different disabilities. In this regard, UNICEF also targeted 500 children with disabilities (CwD) with cash assistance and case management services, while WFP provided food vouchers to Pregnant and Breastfeeding Women and Girls (PBWGs) and to Out-of-School Children (OoSC). UNFPA topped up the voucher for PBWGs with hygiene items between 2022 and 2023.

.

2) JP Secretariat deliverables overview

Donor involvement and high-level meetings

- The Joint Steering Committee (JSC) did not conduct meetings in physical presence, rather the JSC provided its virtual endorsements, upon offline communique for the JP relevant matters:

  - Virtual endorsement of the JP PMU budget

  - Virtual endorsement of the UN JP Phase II, workplan

- Two field mission for JP current and prospective donors’ representatives were conducted in:

  - Dara’a on 16 May 2023 with Norway and Italy.

  - Deir ez-Zor between 20 June and 22 June 2023, to support The Austrian Ambassador visit covering the UN interventions relevant to the JP and other non-JP interventions by the UN.

- One donor dialogue was held in Damascus in August 2024, at the UNDP conference room in Damascus, where the Joint Programme Manager, along with representatives from the JP participating UN agencies lead by the Resident and Humanitarian Coordinator, presented the UNJP 2.0 road map for the next implementation phase in Aleppo. The duration of the UNJP 2.0 is set between 1 January 2024 and 31 December 2026.

- The UNJP 2.0 roadmap was developed, and finetuned into a proposal submitted to Denmark and Italy, who approved their new contributions to the UNJP 2.0 in December 2023. Denmark approved contribution of 50 million Danish Kroner (DKK) and Italy approved the contribution of 4 million Euros.

- Italy contribution of 2,000,000 Euros, whose SAA was signed in late 2022, was received in March 2023. It will be utilized for sustaining key resilience interventions in the current JP locations. In this regard the Italian donor provided comments and cleared the sustainability workplan towards end of 2023.

- Contribution agreement (Standard Administrative Agreement [SAA]) was signed between Denmark and the Multi Partner Trust Fund Office (MPTFO) to contribute 50 million Danish Kroner (DKK) on four instalments.

- The SAA with Italy for a contribution of 4 million Euros on two instalments was reviewed and prepared to be signed in early 2024.

- The relevant UNJP 2.0 MoU between MPTFO and the Heads of the JP participating UN agencies was signed.

- One Heads of Agencies meeting was convened in Damascus on 26 March 2023 to discuss progress and delivery of the JP during 2022.

Planning, monitoring, and reporting

- Detailed workplan and budgeted activity matrix for the UNJP phase II [Also known as the sustainability phase], to utilize Italy’s first contribution of 2,000,000 Euros for sustaining the results and achievements made in Dara’a and Deir ez-Zor under the first phase of the JP were developed, reviewed, optimized and endorsed by the Joint Steering Committee. Funds were prepared and funds were disbursed to the JP participating UN agencies in late December 2023. Activities are designed to be implemented, between 1 January 2024 and 31 December 2024.

- All annual progress narrative and financial reports for prior years  were timely submitted to MPTFO.

- JP Programme Management Unit (PMU) monitoring staff with support from the focal points of the participating UN agencies in the field conducted a total of 3 technically detailed field monitoring missions to Deir ez-Zor. The obtention of approval for planned missions to Dara’a was faced with some obstacles relevant to security situation. The field monitoring was substituted with detailed desk reviews with the technical focal points.

- JP PMU team and the focal points of the JP participating UN agencies, conducted a scoping mission to Aleppo between 22and 25 August 2023 to support the development of the UNJP 2.0 roadmap and proposal. An earlier scoping mission was conducted by the PMU monitoring staff to Homs in January 2023 to attend a community consultation workshop organized by UN-Habitat, as pre-step for identifying possible locations for the UNJP 2.0.

Communications and advocacy

- A joint communication annual workplan was developed and shared with PUNOs comms focal points for action as agreed.

- A Joint Programme flyer that speaks to the key messages of the JP and the key results achieved in Dara’a and Deir ez-Zor was developed in coordination with PUNOs Communications Officers.

- A Joint Programme video to highlight the gains made in Deir ez-Zor, was developed by the JP Communication Officer in coordination with PUNOs Communications Officers.

- A one-pager key messages document for donors’ community outreach, was developed by the JP Communication Officer.

- A social media campaign led by the JP Communication Officer in cooperation with agencies’ Communications focal points, was done upon the significant Donors’ visit to Dara’a in May 2023, highlighting the role of the UN and JP interventions in Dara’a rural and urban catchments supporting the resilience of people, and the complementarities between UN agencies on ground.

- 15 impact stories, highlighting the complementarities/value-added of the JP in Dara’a and Deir ez-Zor were developed in coordination between the JP Communication Officer and the agencies communication focal points.

# I. Purpose

The JP has been developed to enable participating UN agencies to address critical resilience needs within targeted communities while also strengthening the resilience of displaced populations and hosting communities, promoting social and economic recovery, strengthening rural-urban linkages, supporting local planning and community participation, and contributing to overall social cohesion within communities. The JP adopts a flexible multi-year, multi-partner, and multi-sector programming approach, at district, subdistrict, city and/or village, and neighbourhood levels with strong emphasis on community consultations and decision-making to prioritize needs and activities and select areas of intervention. Under the JP, the following three outcomes will be realized:

1. Outcome 1: Urban Area-based Recovery and Neighbourhood Plans that are responsive to community’s needs, particularly the most vulnerable groups, are developed, delivered, and monitored in an inclusive, participatory, and conflict-sensitive manner at local level.

2. Outcome 2: Basic and social services are restored, improved, and sustained to enhance community resilience and social cohesion.

3. Outcome 3: Households and communities benefit from sustainable livelihood opportunities, including economic recovery and enhancing social cohesion and community security.

# II. Planning, coordination, and implementation highlights

During the implementation period of the JP, the PMU coordinated efforts with the participating UN agencies through the Technical Working Group (TWG) bi-weekly meetings and held area-based TWG meetings with technical field staff and IP representatives during field missions, while maintaining the structure of outcome-lead per each JP outcome as responsible for ensuring that all interventions under the assigned outcome are coordinated and planned coherently by the agencies participating in the outcome. Consequently, UN-Habitat was maintained as leader of Outcome 1, UNICEF as leader of Outcome 2, while FAO and UNDP co-lead Outcome 3 since it is the largest outcome, and it incorporates activities by all six agencies.

The PMU utilized the outcome-lead structure to conduct technical discussions with the participating agencies to jointly design and finalize the workplans monitoring and evaluation frameworks and set indicator values. PMU also conducted on-site coordination meetings with technical field staff to probe discussions to further enhance complementarities and joint action.

To the extent possible, the participating UN agencies utilized the inclusive municipal and neighbourhood planning and implementation approach to jointly implement interventions that are responsive to the local context and to people’s needs in the targeted urban locations and their rural catchment areas, while monitoring the context sensitivity. The joint planning approach supported the building and development of sustainable local participatory planning and implementation capacity of local community members at the neighbourhood and municipal levels.

The Joint Programme has developed a common platform to promote a coordinated multi-sector, multi-partner planning and implementation approach in the selected locations with a strong focus on:

- The development and upgrade of the capacity of civil society organizations (CSOs), neighbourhood committees, community members and representatives in addition to institutional technical service providers for responsiveness to the highest priority needs. The objective is to enable them to collectively develop, implement and monitor evidence-based policies, strategies, plans and resilience programmes.

- The delivery of essential resilience interventions to the targeted population, with particular emphasis on displaced people, returnees, host communities and people facing deprivation and different forms of vulnerability.

- The provision of sustainable livelihood opportunities to foster a more resilient society, expedite economic recovery, enhance social inclusion, and support access to social care services for the most marginalized households and communities, including a comprehensive response to GBV.

The Joint Programme’s area-based planning approach is meant to build upon and maximize the synergies between the existing programme activities in a way that is locally owned and can overcome the challenges facing resilience. Strengthening local participation in planning, implementation and monitoring proved to be essential in this regard.

The JP stakeholder engagement and consultation mechanisms include technical staff from local technical directorates, community members and community representatives, among other stakeholders.

# III. Results

## Communication and visibility results

The full year 2023 joint communication annual plan was developed in coordination with PUNOs comms focal points accumulating their feedback and comments and shared with them for their action.

An updated Joint Programme flyer that speaks to the key JP messages and the key results achieved in Dara’a and Deir ez-Zor was developed in coordination with PUNO Communications Officers in May 2023.

A Joint Programme video highlighting the JP gains in Deir ez-Zor was finalized in September 2023 by the JP Communication Officer.

A one-pager key messages document for donors’ community outreach was developed by the JP Communication Officer and shared with PUNOs for their use and reference.

A social media campaign led by the JP Communication Officer in cooperation with agencies’ Communications focal points, was done upon the significant Donors’ visit to Dara’a in May 2023, highlighting the role of the UN and JP interventions in Dara’a rural and urban catchments supporting the resilience of people, and the complementarities between UN agencies on ground.

15 impact stories, highlighting the complementarities/value-added of the JP in Dara’a and Deir ez-Zor were developed in coordination between the JP Communication Officer and the agencies communication focal points.

## Narrative reporting on results

Under the JP, collaboration between six UN implementing agencies (FAO, UNDP, UNFPA, UN-Habitat, UNICEF, and WFP) serves to build upon and maximize synergies between existing UN programming tools, activities and resources to reinforce the benefits of joint interventions.

During the last year of the JP implementation, from 1 January 2023 to 31 December 2023, activities undertaken by the JP participating UN agencies primarily built and continued on the results achieved in 2022 with regards to the implementation of the first phase of interventions in Dara’a and Deir ez-Zor, in addition to the progress on implementation of the Dara’a second phase workplan. The Deir ez-Zor activities continued throughout 2023, and most of them were completed by the end of 2023 except for a couple that faced challenges relevant to procurement delays and vetting results of selected contractors. The Dara’a second phase workplan’s activities continued throughout 2023 and all activities were completed by end of 2023, except for one activity that also faced procurement and vetting challenges. All activities prescribed under the Dara’a phase I workplan were completed during Q1 in 2023. By the end of 2023, all activities’ results are related to the achievements on the ground made through the implementation of the approved Dara’a phase I interventions, Deir ez-Zor interventions, and the Dara phase II workplan.

## Implementation overview

During the reporting period, the six participating UN agencies have been applying innovative joint programming and implementation approaches in the two selected locations, Dara’a and Deir ez-Zor.

In Dara’a, the UN agencies implemented the interventions approved under the Dara’a phase I and Dara’a phase II workplans in a complementary manner to ensure response effectiveness, while also ensuring participation and active involvement of local community members in some aspects of implementation and monitoring of the works and services under implementation. The six participating UN agencies synergized the efforts of their technical field staff in Dara’a and at the central offices in Damascus to conduct bi-lateral and joint consultations with local counterparts, including representatives of the local authorities and community, to layout implementation plans and produce project proposals for the intended activities, then to commence procurement procedures, while building on lessons learned and realistic experience accumulated throughout implementation

In Deir ez-Zor, the participating UN agencies jointly implemented the workplan activities at urban and rural levels while maintaining synergies and complementarities and avoiding overlaps and duplication. UNDP, UNICEF and UNFPA coordinated efforts on soft interventions relevant to capacity building, development and economic empowerment of women and youth under Outcome 3, for which they collaborated with one IP, hence ensuring a harmonized and cost-effective approach. At rural level, the WFP and FAO worked jointly to ensure a complementary approach to sustain agricultural livelihoods of farmers in the western and eastern rural areas of DEIR EZ-ZOR through distribution of agricultural inputs (i.e., seeds and fertilizers), provision of training and coaching, provision of agricultural machinery, and rehabilitation of agricultural and irrigation assets. In parallel, UNDP and UN-Habitat coordinated efforts on infrastructure-relevant works in some key streets, as well as in the industrial zone of Deir ez-Zor city. UNFPA implemented their key per-mandate activities relevant to RH/GBV and women’s economic empowerment, while applying a solid referral mechanism designed to ensure that eligible beneficiaries are referred to other agencies to benefit from interventions (e.g., VT by UNDP or learning by UNICEF). The same applied for UNICEF, which implemented their per-mandate back-to-learning campaigns, non-formal education (NFE) and early childhood education (ECE) interventions, while conducting light rehabilitation of schools in complementarity with UN-Habitat’s safer-access and public spaces rehabilitation interventions.

The presence of the UN hub in DEIR EZ-ZOR city staffed with well-versed technical staff who are familiar with the context and needs and have a wider and diversified view of needed responses in the area, facilitated the technical collaboration at field level and enabled better coordination between the participating agencies due to having all UN offices housed under one roof with continual ability to hold as many coordination meetings and technical discussions as needed.

Such collaboration between the six participating UN agencies in the JP highlights the added value of joint programming and reaffirms the yield of coherent and more impactful results on people’s resilience in Dara’a and Deir ez-Zor.

### Outcome 1: Urban Area-based Recovery and Neighbourhood Plans developed, delivered and monitored in an inclusive, participatory and conflict-sensitive manner at local level

The active participation and involvement of local community stakeholders in all stages of the JP represented a key factor in achieving the JP objective in strengthening urban and rural population’s resilience in the targeted locations. To this end, the JP through the PUNOs’ interventions tackled this aspect and built the capacity of local community stakeholders including community representatives and members of neighbourhood committees and Mukhtars from the urban and rural areas through various training sessions and workshops, while addressing vulnerabilities and involving marginalized groups including PwD, women and youth.

#### Output 1.1. Plans and resilience programmes formulated in a participatory manner and responsive to people’s needs, particularly the most vulnerable groups.

Dara’a:

During the implementation period, UN agencies completed the implementation of Dara’a phase I and Dara’a phase II planned interventions, while building on results achieved in 2022, lessons learned and capitalizing on the experience of conducting consultations through various technical workshops and meetings with the local community representatives.

UNDP and UN-Habitat facilitated the active involvement of 450 community participants, including neighborhood committee members, volunteers, and other stakeholders, including vulnerable individuals and persons with disabilities (PWDs). Together, they collaborated in formulating area-based resilience plans tailored to address the pressing needs of the people. This inclusive approach ensured that the voices of all segments of the community were heard and accounted for in the development of strategies to enhance resilience and promote sustainable development.

UNDP organized 10 enlightening training workshops, delving deep into the realms of civic participation, community problem-solving, and the essential essence of community engagement. These workshops aimed to enhance and support participatory planning capacities at the local level. Firstly, the project worked to enhance capacity and foster development within the local community. This involved developing collaborative plans tailored to meet community needs, with active involvement from the local community, ensuring the inclusion of key persons such as Mukhtars, religious leaders, neighbourhood committees in addition to different groups from the local community. Special attention was given to ensure the inclusion of women and youth to support their involvement in public affairs.

Through the provision of safe dialogue spaces facilitated by interactive workshops at the local level, the project ensured comprehensive participation of all active parties in targeted areas. Additionally, it worked to activate coordination mechanisms between neighbourhood committees and the broader community to influence decision-making processes and enable them to play their societal roles in a way that reflects the priorities and needs of their communities.

In Daraa, 16 workshops were conducted, including 10 workshops and trainings on civic participation and community problem-solving, benefiting 200 community members who received capacity building on resilience analysis and planning. Among them were 40 females, including 36 female-headed households, 40 internally displaced persons (IDPs), 30 youth, and 5 people with disabilities (PWDs). Additionally, six focus group discussions were held to develop five local community plans with the involvement of 237 community members, including neighbourhood committee members, volunteers, mukhtars, religious leaders, and other stakeholders. Among them were 47 women, including 37 female-headed households, 60 IDPs, 38 youth, and five PWDs.

Parallel to these workshops, UNDP conducted two pivotal sessions on Protection from Sexual Exploitation and Abuse (PSEA), benefiting 125 recipients. These awareness sessions served as crucial pillars in fortifying the community's understanding and commitment to safeguarding the well-being and dignity of its members.

The JP contributed to the sustainability of efforts, by applying a multidimensional capacity-building approach between individuals and organizations, reflected by UNDP’s intervention to enhance the capacity of NGOs. This was achieved by conducting a gaps analysis followed by a two-day strategic planning workshop where lead roles were assigned to the well-functioning and more experienced NGOs to work with newly established ones in a twinning approach. Through this intervention, UNDP was able to enhance the capacities of nearly 13 NGOs operating in Dara’a at local and national levels. The ultimate goal of this activity is developing an online platform that brings together local NGOs and individuals interested in making a positive impact in their communities and showcases the effective CSO contributions beyond relief into recovery and Sustainable Development Goal (SDG) active partners. The platform provides online training modules and resources, practical guidelines, and toolkits. It also provides a conducive and enabling space for networking and knowledge sharing among NGOs, CSOs and various youth initiatives in addition to interested experts and practitioners. The establishment of the platform’s interface for the Dara’a governorate has been completed and is currently operating live online. It is worth mentioning that all NGOs in Dara’a will have access to the platform.

UNFPA under the Dara’a phase I work plan undertook data collection activities to support the JP’s Outcome 1, through joint consultations with the local community members focusing on women’s needs and priorities, and through a gendered market analysis that – in addition to various field mission findings – informed the design of potential interventions that addressed the needs. Under the Dara’a phase II work plan and based on the results of the resilience analysis conducted in 2021, which identified climate change as an essential trigger for vulnerability in Dara’a, UNFPA developed a concept note for in-depth research on the Impact of Climate Change in GBV and Gender Dynamics to help communities anticipate the climate-associated risks and encourage different stakeholders to factor these risks in their strategies and plans. UNFPA had conducted the research on the " Impact of Climate Change in the Women and Girls in Dara'a Governorate"

UNFPA formulated its activities to be in harmony with participating UN agencies’ efforts in order to cover current resilience needs and to maximize benefits for the targeted communities. Furthermore, UNFPA worked on linking the market and community needs and identifying the urban and rural linkage areas, jointly with FAO and UNDP.

To empower communities to drive resilience building interventions in their areas, FAO applied its rural community action plans approach in Dara’a. This activity included the identification of 10 villages in Dara’a based on their record of willingness of community to cooperate and the role women play in the social and economic. The trainings’ main objectives were to build the knowledge of existing village development committees on resilience building and development concepts compared with the humanitarian ones that prevailed along the long years of the crisis, then working with them to develop their villages development action plans. The importance of these plans is to move from list of desired activities into identifications of actual needs; prioritization of these needs, then identification of what each community can participate to.

The training topics covered were: humanitarian assistance vs. resilience and development; village and local community resources; forms of community participation; problem and solution trees; identification of priorities; and developing a village development multisectoral action plan.

1The Development plan of Jmarin village

The participants were about six individuals from each village – three to four from the existing officially assigned village development committee, in addition to two selected active and influential persons from the village (i.e., facilitators) with a good educational level, and at least one female who played a critical role to support the existing assigned by the governor office village committee in developing their plans and in improving village representation. The total number of trainees was 51. The main training was preceded with advanced training to these influential persons (facilitators) in the targeted villages to support and strengthen the current development committees with skilled members who can help in the planning, formulation and implementation of village plans.

After concluding the training, and through remote follow up and support by FAO, each village’s committee members continued their meetings to improve, refine and finalize their village actions plans.

During Dara’a phase I, UN-Habitat undertook a number of capacity-building workshops in collaboration with other PUNOs to support the capacities of targeted communities, including neighbourhood committees and local leaders, to ensure their full and meaningful engagement in consultative and participatory processes. The workshops briefed participants on the expectations from their engagement in consultative processes, and equipped them with knowledge of the ambitions, scope, and objectives of the JP.

During Dara’a phase II UN-Habitat continued the work initiated in the first phase regarding strengthening local community capacity, undertake in collaboration of other PUNOs agencies number of participatory workshops and training sessions for wider segments of targeted communities covering rural and urban areas where environmental challenges along Al Zaydi valley and urban -rural linkages were discussed and addressed in depth.

These workshops were followed with a monitoring and evaluation dialogue to ensure the sustainability of the projects, beyond the end-date of JP, through polishing the knowledge and capacities of local communities and ensuring their ability to continue oversight of interventions.

It is worth highlighting that due to the volatility of the security situation in Dara’a Al Balad during various periods of the JP implementation (i.e., summer 2021, and intermittent through 2022 and 2023) various interventions relevant to holding capacity building workshops were postponed.

Yet, Despite the security obstacles that caused several workshops’ postponements, UN-Habitat successfully conducted participatory community- based workshop through which the first draft of the design for two open spaces in Dara’a Al-Balad was developed and designed. All challenges and priorities to secure safer access for students to schools and public spaces were defined in collaboration with community representatives, including students, parents, and teachers. Students also participated in traffic safety awareness sessions to complement tangible impact of safer access activities in the targeted neighbourhoods, some of 120 students from five schools participated in these sessions.

The JP activities under Outcome 1 strengthened the social cohesion between people through multiple sessions of participatory planning, community dialogue and outreach to high-risk groups like unemployed youth and female-headed households, allowing for smaller-scale and discrete discussions, where confidence and trust is built within a small group setting, prior to undertaking wider consultative processes.

Deir ez-Zor:

UN-Habitat in coordination with UNFPA, among other UN agencies, implemented their capacity-building sessions for local neighbourhood committees and community members. The training objective was to nurture local ownership of JP activities by building the capacities of local community and neighbourhood committee representatives to manage and monitor JP interventions. Participants were trained to be able to meaningfully participate in detailed planning of communal activities such as restoration of public spaces and enhancing rural-urban linkages and value chains. The training ensured participants’ readiness for continued engagement on JP activities going forward and ensured enhanced engagement from women in related dialogues through bespoke consultative and capacity-building processes with support from UNFPA. The training targeted neighbourhood committee members and community representatives of 12 neighbourhoods from the urban and adjacent rural areas.

UNDP carried out a total of 25 FGDs were conducted to develop local community plans with the involvement of 237 community members, including neighbourhood committee members, volunteers, mukhtars, religious leaders, and other stakeholders. Involving 250 community members, including 93 women, 74 of whom were female-headed households, 83 youth, and three PWDs. Furthermore, four workshops and trainings on civic participation and community problem-solving were conducted, benefiting 51 community members, including seven females, four female-headed households, 10 youth, and 39 returnees.

Over the course of four participatory sessions, including workshops, focus discussion groups, and capacity development sessions, these dedicated individuals worked hand in hand to develop comprehensive strategies aimed at addressing the pressing challenges faced by their communities. With each collaborative session, the resilience plans took shape, guided by shared experiences of those most intimately connected to the issues at hand. Together, they forged a path forward, grounded in unity, inclusivity, and a steadfast commitment to building a brighter, more resilient future for all

UNDP commenced its first interventions to assess and enhance local NGOs’ capacities in Deir ez-Zor in November 2017, where an expert was contracted and commissioned to DEIR EZ-ZOR to conduct a CSO capacity assessment. The expert convened three focus groups with local CSO representatives, local authorities, and representatives from academia. Through interviews with the only six NGOs that have been operating in DEIR EZ-ZOR, a capacity needs assessment was convened, based on which, the said NGOs’ management, staff and volunteers were enrolled in a UNDP civic empowerment platform (CEP) training programme, each in accordance with their position and type of specialty.

In late 2021, UNDP carried out a follow-up capacity needs assessment and organized a collaborative workshop for CSOs operating in DEIR EZ-ZOR. The outcomes of this assessment informed the development and implementation of a personalized capacity development intervention. This initiative comprises various training sessions, on-the-job coaching, and mentoring, concurrent with the establishment of the DEIR EZ-ZOR CSO

Figure 2Participants during the exchange visits

Figure 2Participants during the exchange visits

platform. These activities are aligned with the Program’s strategy for enhancing NGO capacities in Syria, focusing on three levels:

1- Individual Level: Enhancing the skills and knowledge of staff and management.

2- Institutional Level: Strengthening organizational capacity.

3- Supportive Environment Level: Fostering an enabling civic environment.

In 2023, building on UNDP's continuous commitment to supporting the most vulnerable areas, the Civic Empowerment Program organized Exchange Visits for seven NGOs from Deir ez-Zor to interact with four NGOs in Damascus. This initiative is part of ongoing efforts to bolster NGOs, the frontline entities aiding communities and individuals in need through collaborative exchanges. These exchange visits primarily aimed to support associations in Deir ez-Zor by providing them insights into the operational mechanisms of some of successful associations in Damascus. The objective was to broaden knowledge, exchange experiences, and foster networking among civil organizations in Syria.

The Development plan of Hatla village

UNDP developed online platform that brings together local NGOs which provide online training modules and resources, practical guidelines, and toolkits. It also provides a conducive and enabling space for networking and knowledge sharing among NGOs.

Similar to Dara’a, FAO delivered training to village development committees.  The total number of trainees was 58. Likewise, Dara’a, the training was preceded with advanced training to a number of well-known and influential persons in the targeted villages to support and strengthen the current development committees with skilled members who can help in the planning and formulation of village plans. After concluding the training, FAO worked with the trainees to improve and sharpen their development plans. This activity was concluded with a plenary workshop where the development plans were presented before representatives of UN agencies and the relevant governorate technical entities in Deir ez-Zor to inform future interventions in their villages. Some elements of these plans were proposed under the exit strategy aimed at sustaining the gains achieved through this phase of the Deir ez-Zor workplan and strengthening the positioning of these committees as representatives of their villages and as entry points that humanitarian, development and peace actors need to go through and work with. Resilience analysis conducted by UNFPA revealed that the area is at risk of waterborne diseases due to the low level and low flow of water in the Euphrates River compounded by unhealthy drinking and irrigation techniques. In Q3 of 2022, Deir ez-Zor started witnessing a cholera outbreak. During that period, UNFPA worked with PUNOs to adjust some activities (especially awareness-raising and expanding the existing referral pathways to link infected people with the specialized health facilities) to support the communities facing the disease. In this regard, UNFPA conducted nine awareness sessions on cholera prevention in the JP-supported facilities in rural and urban communities.

### Outcome 2: Basic and social services restored, improved and sustained

The population’s resilience cannot be sustained without having reliable and functional infrastructure facilities in place, in addition to the restoration of the community’s fixed common assets, including but not limited to schools, health centres and public green spaces. To this end, the JP PUNOs collaborated on implementing a complementary set of interventions aimed at rehabilitating schools, streets, public green spaces, public heritage squares and health facilities, as well as provision of street lighting, while in parallel reinstating the local community’s confidence through a group of soft interventions relevant to education and training and supporting the most vulnerable children with cash-based-assistance.

### Dara’a:

#### Output 2.1 Educational, recreational and PSS spaces rehabilitated, and nutrition-sensitive agriculture education sessions provided

Nearly all the JP activities planned under Outcome 2 in the Dara’a phase I and Dara’a phase II workplans have been completed. Since the start of the activity in late 2020, UNICEF, through its IPs, was able to support 10,667 children in addition to their caregivers. The activities included:

- Support students at risk of dropping out through engaging them in remedial education.

- Engaging Out-of-School children in Self Learning Program, including non-standard students applying for the national exam’s grades 9 and 12.

- Targeting children with severe disabilities with tailored education activities.

- Supporting children aged 3-5 with early childhood development and supplies distributions.

UNICEF with its IP managed to continue delivering these critical educational activities (especially national exams support) to the children in need almost without interruption despite the tense/critical security situation in Dara’a city during the first half of November 2022.The table below shows achievements against targets

|  |  | Planned Target |  |  |  |  | Actual Target |  |  |  |  | Justification of Over / Under Achievement |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Indicators |  | Women | Men | Girls | Boys | PWDs | Women | Men | Girls | Boys | PWDs |  |
| Number of people reported to have been accessed by (BTL) Back-to-Learning campaigns | 9,000 |  | 8,000 | 5,070 | 4,930 | 1,000 | 10,788 | 10,948 | 3,441 | 3,902 | 486 | the over achievement is due to the good impact of the BTL campaign targeting children and caregivers, along with the activities and services provided (i.e. schools' rehabilitation, distribution of school supply, and provision of remedial classes, as well as exams' support) which allowed to offer services to more children including some IDP children who moved into the area due to security issues in the governorate. |
| Number of out-of-school children (including children with disabilities) enrolled in remedial classes and self-learning programme (SLP) |  |  |  | 3,150 | 3,350 | 600 |  |  | 5,969 | 4,698 | 1,784 | Upon roll-out of NFE activities such as remedial education, SLPs and support classes for national exams, the exchange rate fluctuation was a big factor. The Syrian pound (SYP) depreciation led to accumulated savings, enabling UNICEF IPs to reach more children. A better value for money was achieved as more children could be reached for a lower child-unit cost since the IP’s budget is disbursed in the SYP. |

Additionally, UNICEF and its partners concluded the planned back-to-learning campaign reaching about 29,500 children and caregivers with advisory on the importance of re-enrolment in formal education.

Preparatory work for the expansion in rural areas was completed towards the end of 2022, and the most deprived locations were identified based on local consultations with the local communities, while ensuring partners’ access, given the instability of the security situation, as well as the joint targeting with other agencies’ programmes. In response to the identified needs in these rural areas, UNICEF established two centres for children with disabilities (CwD) in addition to the one established under Dara’a I workplan. The three centres met the special educational needs of CwD who had severe types of disabilities, yet still had the ability to learn and develop. Similarly, five early childhood education (ECE) centres were established to provide children aged 3-5 years old with the needed skills and knowledge to excel in their upper educational levels. The capacity of the back-to-learning team in rural areas was built to ensure sufficient and qualitative access to the targeted 15,079 (7,850 females and 7,229 males) children and caregivers through door-to-door visits, where community awareness was raised towards the importance of education, and the available educational pathways and education service providers within the targeted locations. During these visits, 2,413 out of school children (OoSC) were identified and provided with the needed information that would enable them to re-join the educational system.

It’s worth mentioning that 26,920 children and adults benefitted from seven community initiatives conceived by the joint efforts of the local community in Dara’a City and its rural, Directorate of Education, and some local NGOs and UN agencies. These initiatives contributed to increasing community social cohesion and community sense of belonging, discovering sport talents amongst children, raising children’s awareness towards climate change risks and many other vital social themes.

In parallel, WFP has delivered cash-based assistance via food vouchers to about 525 Curriculum B students (252 girls and 273 boys) and 215 children (103 girls and 112 boys) enrolled in non-formal education (NFE) in 2022, and to 1,183 Curriculum B students (568 girls and 615 boys) and 847 children (407 girls and 440 boys) enrolled in NFE in 2023. The pilot to support children enrolled in NFE with vouchers was launched under the umbrella of the Joint Programme and targets mainly Children with Disabilities and adolescent boys and girls enrolled in self-learning programs. Feedback from families of children enrolled in NFE reflected that the voucher has contributed positively to their children’s regular class attendance and supported their cost of living.

The voucher value is equivalent to 36 USD at maximum (the voucher value is changed based on MEB, and market price analysis done by the VAM unit in WFP) paid in Syrian pounds and is transferred to the families of the targeted children upon children achieving 80 percent of monthly school attendance. Thus, the voucher system supports children’s education by encouraging regular attendance and simultaneously supports households’ resilience by offering food inputs that reduce the need to resort to negative coping mechanisms.

Additionally, protection support for girls is provided by UNFPA, while UN-Habitat provided awareness training sessions on traffic safety and safer access to about 120 children selected from six schools.

#### Output 2.2: Social cohesion is enhanced through neighbourhood-based rehabilitation of community assets including housing, WASH, basic social and productive infrastructure, and services

Under Output 2.2 in Dara’a, UNICEF completed the rehabilitation of three schools planned under phase I, thus, availing educational space for about 1,450 students (850 girls and 600 boys).

Two of these schools were provided with two early childhood education (ECE) rooms, which will be serving a total of 60 children in two different neighbourhoods deprived of such services, while one of these schools will function as a lower secondary school for girls.

This will help reduce the percentage of out-of-school girls in the community where especially early marriage is a common practice and part of the norms. As a consequence of these practices and norms, some parents used to prevent their female children from walking long distances to reach the nearest school after completing 6th grade.

Rehabilitation works in the three schools was completed in August 2022. The furniture started to be delivered gradually to these schools starting from late December 2022, enabling the two primary schools to gradually enrol a total of 550 children in the second semester that started in January 2023. Those children used to attend overcrowded schools farther away; more have joined in the academic year 2023–2024.

It was not possible to open the female lower secondary school in the second semester without changing the learning environment for the girls already attending in an alternative school, especially since a good portion of the girls are sitting for the lower secondary national exams, and they needed to keep the same pace with their specialized teachers.

Meanwhile, the Directorate of Education is working to secure a supportive cadre of specialized teachers for the newly opened school before the onset of the new academic year 2023–2024.

Due to the economic crisis in the country and budget cuts, it is expected that the budget allocated to Ministry of Education can hardly cover the school’s basic running costs (i.e., paper, classroom supplies, photocopying, etc.). During 2023, the fourth school has been completed, allowing 750 children to regularly attend classes.

Linkages between UNICEF’s education and youth programs and WFP’s programs implemented in Dara’a phase 2 were established, while maintaining referrals of Out-of-School Children (OoSC) ultimately to formal education. During phase 2, WFP supported families of children in Curriculum B and out-of-school children and adolescents enrolled in UNICEF’s non-formal programs with vouchers in an effort to encourage them to pursue education and to offset the need for child labour. Through the provision of vouchers, WFP is actively encouraging the enrolment of out-of-school children and adolescents in education programs. This benefits the individuals by providing them with educational opportunities as part of a broader social safety net.

The large amounts of accumulated debris and solid waste pose health risks to communities and hinder access to schools, hospitals, and parks. UNDP’s programme package was designed to provide an immediate recovery response through its debris management and solid waste management (SWM). The intervention provided a valuable source of income and green jobs for vulnerable communities, establish safer and cleaner access, contribute to enhancing hygiene conditions in Dara’a and, lastly, aim to change local communities’ behaviours and attitudes to improve how waste is managed.

In Dara’a, UNDP conducted awareness sessions, and cleaned 12 neighbourhoods in both Dara’a Al Balad and Dara’a Al Mahatta by removing 10,096 m3 of solid waste. This was achieved by availing 884 temporary job opportunities over a period of six months to solid waste workers, and providing them with work tools (including shovels, carts, sweepers, and protection gear).

The key elements focused on are inclusion and commitment to leave no one behind even in activities that might generate stigma for women. When planning the intervention, UNDP considered the local culture and local practices in Dara’a; hence, it fosters women’s involvement as supervisors to avoid any harm and to support women in creating livelihood opportunities. UNDP continued its intervention in solid waste and debris removal under Dara’a II workplan, extending its efforts to clean an additional 10 neighbourhoods where 500 tons of solid waste and 12,000 m3 of debris were collected. Additionally, two pieces of equipment were maintained, and 551 temporary job opportunities were created. Furthermore, 116 tools and necessary equipment were provided to local actors.

In conclusion, the waste removal intervention that offered practical solutions to everyday problems faced in Dara’a, also represented an essential tool that promoted social cohesion and dialogue.

The rehabilitation of public gardens and the enabling of safer access to schools for students through improved pathways and street solar lighting represent some of the JP’s interventions that were completed by achieving complementarity between both UN-Habitat and UNDP interventions. UN-Habitat collaborated with UNDP on the installation of around 50 solar lights and on rehabilitating a major park in Dara’a, along with three additional parks that were rehabilitated solely by UN-Habitat.

This provided more than 5,000 students with safer access and connectivity to schools and parks. Additionally UN-Habitat completed restoration of targeted cultural heritage and the city’s main market area, through rehabilitation of the central medians, paved areas, and footpaths along the main access routes to these localities, which was also supported with solar lighting.

The wider installation of solar lighting in various targeted areas of the city have provided significant benefits including enabling a return to economic activity in hours of darkness and contributing to safer movement of people, especially women, children, the elderly, and people with disabilities.

Installation of solar street lighting is one of these JP activities that has the best multiplier effects since it brought life back to some areas, increased the sense of security, enhanced social cohesion and revitalized economic activity during the evening hours. In Dara’a, shop owners used to close their shops by sunset, then, after installation of street solar lights some shop owners decided to continue working in the evening to boost their business. Moreover, this activity brought about unintended positive effects since some students were noticed studying for their final exams under the solar-powered street lighting in early summer evenings.

In 2023, UN-Habitat in cooperation with UNICEF, implemented an integrated intervention in order  to provide safe and secure access for the students of five schools in Dara’a Al-Balad, some of which were rehabilitated by UNICEF , in parallel with restoration of two open public spaces in the vicinity of the targeted schools, this intervention was carried out with intensive participation of the community members , students in particular, in the design phase, and they were also involved in some initiatives during the implementation phase.

In the same regard and in order to promote the resilience and stability of residents and returnees in Dara’a Al-Balad UN-Habitat implemented multiple service projects, where the household connections were repaired in Al Abassiyeh an Al Bhar neighbourhoods, and the main street “ with a 1,100 length” including Swedan Market Street was rehabilitated and supported by 26 street lighting units, this work was a continuation of our joint cooperation with UNDP to support security by providing solar street lighting where needed in Dara’a city.

Another important community-demanded project was the community environmental centre that was completed supplied and equipped with basic supplies and materials in order to provide space and sustainable support for environmental assessment, community participation and environmental initiatives. Moreover, and from the same aspect of environmental protection, Wadi Al-Zaidi and its banks were cleaned of waste causing air and land pollution in complementarity with UNDP intervention in removing solid waste and rubble from the streets of Dara’a al-Balad. The main damaged pipelines within the valley area were also rehabilitated in order to protect the soil and groundwater from pollution

Regarding the strengthening and promoting social cohesion amongst women and families UN-Habitat restored ‘Sobeh wa Masa’ park that locates among multiple service and trade centres, the work took a participatory method where women and youth participated in some initiatives during the design and finishing works.

Supporting residents to improve their access to cadastral services and maintain security of tenure was one of UN-Habitat’s interventions in the second phase of Daraa by equipping the workspace with the necessary equipment.

Under the JP Dara’a Phase II, UNDP significantly improved the capacity of the primary health centre in Daraa by installing solar power systems. This strategic initiative aims to enhance outreach to a larger number of patients by ensuring a sustainable and reliable source of electricity.

UNDP also carried out maintenance and rehabilitation of 10 points on the water network – that suffered damage during the conflict – in Dara’a to restore water supply capacity, reduce leakage, wastage, and contamination of sewage water, and alleviate the economic, environmental, and health pressures associated with water supply from unsafe sources. In the realm of specialized training, the United Nations Development Programme provided a comprehensive training course on modern methods in veterinary medicine in the field for 57 newly graduated veterinarians in coordination with the Directorate of Agriculture, aiming to enhance and improve healthcare for livestock and alleviate burdens on livestock breeders. Additionally, 30 kits equipped with necessary equipment and tools were distributed to facilitate the work of field veterinary teams and enable them to provide medical services effectively.

### Deir ez-Zor:

Like in Dara’a, under Outcome 2, the JP PUNOs prepared their interventions guided by the processes to jointly identify resilience needs and priorities. Projects were designed, planned for, and supported by individual and joint agency missions, leveraging the presence of the UN Hub colleagues and collective in-house discussions and meetings. The PUNOs laid plans to conduct their interventions addressing light rehabilitation of infrastructure (water, sewage, and electricity networks) in the vicinity of schools and industrial areas, roads and green spaces rehabilitation alongside other supportive activities such as the provision of solar lighting, SWM, etc.

#### Output 2.1 Educational, recreational and PSS spaces rehabilitated, and nutrition-sensitive agriculture education sessions provided

As for the soft activities implemented by UNICEF including back-to-learning campaigns, NFE, SLPs, ECE and education for CwD, an agreement with the IP was signed, preparations for implementation were finalized, and implementation started as planned in February 2023. The table below shows the actual targets against the planned ones.

WFP’s cash-based assistance to Out-of-School Children (OoSC) in coordination with UNICEF, as well as their similar-in-nature intervention to support the nutrition of Pregnant and Breastfeeding Women and Girls (PBWGs) in coordination with UNFPA, was both delayed due to extended discussions with donors regarding collaboration with their selected implementing partner (namely, ASSLS). However, the issue was resolved in September 2022, and implementation was completed by Q1 2023, reaching 3,154 PBWGs. Malnutrition is a significant concern for pregnant and breastfeeding women and their infants. WFP's intervention helps prevent malnutrition by providing essential nutrition support during critical stages of pregnancy and the first 6 months of an infant's life. This leads to healthier outcomes and breaks the intergenerational cycle of malnutrition for both mothers and children.

The delivery of vouchers to children in Curriculum B in Deir ez-Zor started in October 2022 and has reached (3,500 children in 2022 and 5,800 in 2023 children in both Deir ez-Zor city and Mayadeen city, where the highest concentration of OoSC registered in Curriculum B exists.

The following table shows the achievements against planned targets:

|  | Planned Target |  |  |  |  | Actual Target |  |  |  |  |  | Justification of Over / Under Achievement |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Indicators |  | Women | Men | Girls | Boys | PWDs | Women | Men | Girls | Boys | PWDs |  |
| Number of people reported to have been accessed by (BTL) Back-to-Learning campaigns |  | 3650 | 3350 | 3550 | 3450 | 0 | 7444 | 6747 | 8172 | 8972 | 262 | the over achievement is due to the good impact of the BTL campaign targeting children and caregivers, along with the activities and services provided (i.e. schools' rehabilitation, distribution of school supply, and provision of remedial classes, as well as exams' support) which allowed to offer services to more children including some IDP children who moved into the area due to security issues in the governorate. |
| Number of children at risk of dropping out or /and out-of-school children (including children with disabilities) enrolled in remedial classes and self-learning Programme (SLP), and Early Childhood Education (ECE) |  | 0 | 0 | 765 | 735 | 0 | 0 | 0 | 8253 | 6109 | 0 | the under-achievement on CWD is mainly since there no such a number of CWD as per target. |

UN-Habitat designed its safer-access interventions to support safer routes for school children, rehabilitate open spaces within the rehabilitated schools’ catchment area and conduct awareness sessions for the children on traffic safety. The intervention targeted three locations; 160 students participated in the workshops, and about 7,000 students benefitted from this intervention. The intervention was completed by April 2023, and it complemented UNICEF’s school rehabilitation activities.

#### Output 2.2: Social cohesion is enhanced through neighbourhood-based rehabilitation of community assets including housing, WASH, basic social and productive infrastructure, and services

UNICEF finalized the rehabilitation of the planned six schools in Deir ez-Zor city and managed to rehabilitate an additional school, which was handed over to the DoE in July 2023. All schools were equipped with gender-segregated WASH facilities and special WASH facilities for CwD. School furniture including desks, tables, chairs, white boards, and other similar supplies were also provided. 1,081 children already benefited from the rehabilitation of Jameel Alwan School, while approximately another 2,900 children (1,700 girls and 1,200 boys) benefitted from the rehabilitation of the remaining six schools as these schools will be activated by September 2024. Despite the huge need for putting the rehabilitated schools into service, the DoE faced tremendous challenges which forced them to re-schedule the utilization of the schools; the challenges included lack of qualified teaching personnel which is already on its way to be resolved in DEIR EZ-ZOR city as the graduates of the Teacher Qualification Institute will have a mandatory assignment to DEIR EZ-ZOR schools.

The JP interventions relevant to community assets and infrastructure rehabilitation through collaboration between UNDP and UN-Habitat progressed as planned. UNDP completed rehabilitation of water and sewage networks, where 1,15 kilometres of sewage network and 4,000 metres of water network have been rehabilitated in the industrial area of Deir ez-Zor. Additionally, UNDP restored five kilometres of electricity network in the same location. UN-Habitat complemented the work through street rehabilitation and provision of solar lighting; to this end, UN-Habitat has finalized tender documents that have been sent to procurement. The industrial area is already experiencing a significant return of those who left their workshops due to the damage caused during the crisis.

About 80 beneficiaries were supported to revive their workshops. They relocated back to the industrial area, benefiting from trainees and apprentices who received VT under the UNDP programme to support the rehabilitation of workshops and encourage the return of other craftsmen and small industrialists to the area.

Under the SWM intervention, UNDP has conducted three awareness-raising sessions to effectively encourage waste prevention behaviour within the waste-collection catchment area. UNDP has removed 13,000 m3 of solid waste and 10,000 m3 of debris from eight neighbourhoods including the industrial area and the heritage site of Al Souq Al Maqbi. To pave the way for future rehabilitation works within Al Souq Al Maqbi, UN-Habitat worked on rehabilitating the square at the centre of the archaeological site. UNDP deployed 262 temporary workers and distributed 230 units of solid waste removal tools (shovels, sweepers, carts, protective gear etc.), and necessary equipment was provided to workers. Beyond the achieved target, UNDP worked on removing additional quantities of solid waste mainly in Al-Jbeileh neighbourhood

Collaboration between the two agencies (UNDP, UN-Habitat) extends to street rehabilitation and solar lighting, wherein UNDP is started installing solar light poles on Al-Ashaari street, and UN-Habitat rehabilitated a 1,100-metre stretch of the street’s sidewalks and central median and provided new curb tiles and rainwater drainage facilities. Asphalting of the road was completed in April 2023 due to the seasonality nature of asphalting works that require special weather conditions. The provision of street solar lighting will illuminate areas suffering from power shortages, upgrade access, improve the community infrastructure, enable safer movement for the population and facilitate commercial activities. In this regard UN-Habitat has completed the installation of 70 solar lighting units in Bor Saiid street, which forms a major axis stretching along the southern edge of the city connecting the eastern and western neighbourhoods.

Furthermore, to enhance the health and environmental situation in Deir ez-Zor, UN-Habitat has finished cleaning and decontaminating the main sewage down-stream canal of Deir ez-Zor and rehabilitating its damaged parts. This work was completed by early December, when about 15,000 m3 of polluted accumulated waste was excavated, scrapped, and removed. Also, a 32-metre-length of reinforced concrete main pipes has been replaced.

The technical studies for restoration of domestic connections to the sewage and water networks in targeted vulnerable neighbourhoods have been completed, and tendering is ongoing. The transfer of the accumulated waste from the informal dumps to the official landfill was completed by the beginning of June 2023, where 25,000 m3 of waste were transferred to the permanent dump outside the city.

In parallel, UNDP boosted the capacity of Al Hamediyeh health centre by rehabilitating the second floor. This will avail additional space for more outpatient clinics to receive more patients. This work has been completed, and 30 temporary jobs were also created.

To enhance the connectivity between Deir ez-Zor and other governorates along with nearby cities and towns, UN-Habitat rehabilitated the main Pullman terminal (i.e., inter-governorate coach-bus station) of Deir ez-Zor.

Works were completed by June 2023, and it contributed to enhancing the connectivity of Deir ez-Zor to other governorates in Syria, as more coach-bus companies re-established their lines to Deir ez-Zor now that a reliable station is in operation.

This in turn contributed to creating multiple micro job opportunities for workers in the station and availed space for mini-livelihoods opportunities (i.e., small sandwich, snacks and soft drinks shops).

Simultaneously, UN-Habitat and UNDP jointly collaborated to design and set up an open area intended for use as a public farmers’ market..

Additionally, during 2023, and in cooperation with UNICEF, UN-Habitat implemented a project to inhance safer access to students in 9 schools in deir Ez Zor city , some of which UNICEF rehabilitated, along with the revival of three public park that were rehabilitated in parallel, within the catchment area of ​​these schools.

And in order to revive the city centre, the central square within the archaeological heritage area has been rehabilitated. Thus, the main south -north axis reopened and rehabilitated, linking the old bridge in the north with Bor Saiid Road in the south, where the main Pullman terminal (i.e., inter-governorate coach-bus station) was rehabilitated by UN-Habitat under the JP as well.

Moreover, to enhance the stability of the population in the return areas and support livelihood opportunities, UN-Habitat undertook an intervention to rehabilitate household connections to some parts of Al Jbeileh neighborhood, in addition to the rehabilitating the main Jbeileh market street especially the sidewalks near the rehabilitated shops., in integration with UNDP interventions in the same area.

### Outcome 3: Households and communities benefit from sustainable livelihood opportunities, including economic recovery and enhancing social cohesion and community security

Job creation and better access to jobs have the potential to increase incomes and contribute to more cohesive and equitable societies. Conversely, unemployment and poverty can trigger alienation that contributes to instability. Similarly, social cohesion and resilience in Dara’a and Deir ez-Zor require full and meaningful engagement of adolescents, youth, women, and marginalized vulnerable groups to ensure that they develop skills and reach their potentials and grasp opportunities to positively contribute to the well-being of their society. A focus on resilience can bolster the self-reliance of communities exposed to recurring or compounded disasters, such as epidemics or extreme events like drought hits, and also strengthen institutions reliant on short-term interventions to break the cycle of crisis towards recovery.

The JP under Outcome 3, through joint interventions by the six participating agencies, is effectively addressing the population’s needs for different urban and rural livelihoods opportunities, while working on rehabilitation of assets that contribute to economic recovery of SMEs and professions in addition to agricultural assets. In parallel, the agencies building on their expertise in social interventions that enhance social cohesion, build bridges, and strengthen ties between communities of diverging political, religious, ethnic and socioeconomic (including rural/urban) backgrounds, create an atmosphere of social solidarity and strengthen social cohesion at the local level. The JP participating UN agencies have implemented various community initiatives through youth engagement and empowerment, while availing specialized GBV/RH services for women and adolescent girls to support their sense of health and social safety and stability. Additionally, the JP participating agencies applied social protection schemes to respond to the needs of the most vulnerable including PBWGs and PwD in Dara’a and Deir ez-Zor, by providing prosthetics services and cash-based assistance. Additionally, since the health system and equal access to health facilities are essential for sustaining livelihoods because they contribute to maintaining the health and well-being of the people (labour force), the JP has contributed to improving the health system in rural and urban communities in DEIR EZ-ZOR. In the reporting period, UNFPA has provided hygiene assistance to 1,020 PBWGs in Deir ez-Zor using an electronic voucher modality..

### Dara’a:

#### Output 3.1: Income, sustainable livelihoods opportunities and inclusive local economic development are restored and maintained in both urban and rural catchment areas to increase household incomes, boost food production and enhance local markets

FAO, UNDP, and WFP have each developed an integrated assessment methodology, which was jointly discussed to inform and support the planning of resilience-based interventions relating to agriculture and livelihoods in support of the local economy and food security in urban and rural areas.

During the crisis, many irrigation structures were impacted and became out of service leaving large agricultural lands unserved and farmers with no source of income. Naturally, the first focus is to restore access to water which is critical for food supply and livelihoods support particularly under the challenging situation in Syria.

After conducting a technical requirements assessment of the irrigation infrastructure in the Dara’a district and consulting with local stakeholders, the Ghadeer Al Bustan irrigation scheme was identified as the top priority. This irrigation system is one of few schemes in the Dara’a that serves a large number of farmers. Furthermore, the decision to prioritize this scheme is supported by the results of the natural resource assessment conducted by the FAO, which shows that there is sufficient water available to support extensive irrigation once again. There were two stages involved in rehabilitating this scheme:

1. The main open canal flow, which was 25 km in length and had rectangular and trapezoidal portions, needed light rehabilitation to allow water to flow through and reach the branching field irrigation canals.

2. The field irrigation canals downstream of Nawa town had to be repaired to supply irrigation water to 600 hectares of land.

As a result, a total of 16,000 farmers were able to access additional water for irrigation. They could use this water to directly irrigate their fields through the canal and pipes, or recharge groundwater aquifers through surface or flood field irrigation.

It is important to add, that all FAO interventions related to access to water are designed based on natural resources assessment to ensure suitability to the current situation of natural resource and to not harm these resources for the future generations. It is also combined with social factor through establishment of Water users associations to engage local communities in managing and operating the irrigation system.

On the other hand, FAO restored nine community wells in the southern and southeast regions of Dara’a to provide farmers with supplementary irrigation for fruit trees and enable sheep herders to provide water for their animals.

Five of these wells were in the Green Belt zone, a nationwide initiative started in the 1980s in the marginal areas which receive only 200–250 mm of precipitation on average annually. These wells supplied supplementary irrigation for fruit plants prior to the crisis. The wells were not working, though, because most of the buildings and equipment were damaged or stolen during the crisis.

the remaining rehabilitated four wells are located in the steppe areas (Al-Badia) in eastern Dara’a. These wells were drilled and equipped by the government to provide drinking water for the sheep herds who usually move with the nomads in Al-Badia area.

To enable good governance, collective and sustainable use of the rehabilitated water resources, FAO established eight Water Users Associations (WUAs), whose board members were selected from the local community and received training from FAO on best practices in water resources management. Upon completion, the intervention is expected to improve the livelihoods of more than 4000 farmers and livestock keepers, through provision of a water source, and to do no harm to natural resources.

Prior to commencing the rehabilitation of irrigation structures FAO conducted an assessment (see Annex A) on the natural resources in the watershed of Dara’a. The assessment included desk studies, remote sensing, and a socioeconomic assessment. To identify priority areas for the proposed interventions in a way that ensures sustainable use of water resources, sites were selected based on this study’s outcome.

One of FAO pillars is supporting women and youth access to sustainable agricultural livelihood opportunities through building their entrepreneurship skills and enhancing their business management capacity for agriculture-related livelihood opportunities (FAO Agri-entrepreneurship programme called NABTA). This included greater focus on market-oriented production in order to increase their revenues, improve their livelihoods and eventually contribute to improved food and nutrition security. To maximise the impact of this programme, FAO combined this programme with grants scheme to support a number of graduates who propose feasible business plans. FAO has developed a grants manual tailored to Syrian conditions that articulates all stages, starting from the announcement of the activity to receiving applications as well as information on the selection criteria for each phase, the selection committee and the disbursement of grants and their mentorship and monitoring.

In Dara’a, FAO provided training to 378 youth and women between 2021 and 2023 through a series of training workshops and provided seed funding to 36 graduates to start-up agricultural businesses and coached and mentored them throughout the inception phase of their projects. UNFPA complemented the FAO activity by providing grants to seven entrepreneurial projects, submitted mainly by women, to help respond to and address the multiple needs of local communities. The average grant amount is between 2,000 and 3,000 USD. In the same context, WFP is dedicated to achieving the goal of economically empowering those who have graduated from FAO training. WFP has provided seed funding for five projects proposed by the activity graduates, with 3 females and 2 males as beneficiaries. This intervention aims to decrease vulnerability and enhance their resilience.

These projects cover a wide range of topics, including beekeeping for the production of honey and by-products, food and dairy processing, producing chemical fertilizer alternatives (like composting and vermicomposting) and fodder alternatives (like silage and barely sprouts), aromatic and medicinal plants, mobile ultrasound devices, and medicinal and aromatic plants and etc).

In order to provide vulnerable farmer households with stable sources of income and livelihood, two major value chains were chosen for support. Communities in Deir ez-Zor and Dara’a recognized vegetables and livestock (sheep) as their primary sources of income and as suited for the Agri-ecological zone in which they were targeted.

WFP and FAO supported the small-scale farmers in western Dara’a – an area known for its skilled farmers and high productivity of summer vegetables, particularly tomatoes but seriously impacted by the crisis. With view to enable farmers produce early summer vegetable FAO distributed high quality seeds to 450 farmers (140 females and 310 males) who established their small-scale nurseries to have the seedlings ready to be cultivated early enough. WFP complemented this activity by providing these farmers with fertilizers and drip irrigation nets. This was supported with technical follow-up by a team of agronomists to help them sustain food security and increase their profits by selling their early products in the market.

Since most of the fruit trees orchards in the Green blet area in Dara’a were abandoned and were not served during the crisis due to the inaccessibility to water for irrigation and the lack of security in these areas,  FAO supported 500 farmers whose lands are located in the vicinity of the Green Belt wells, with some basic tools such as pruning shears and saws and technical follow-up in their fields through a team of 15 agronomists  in early 2023 to improve their skills on the seasonal services provided to their trees such as pruning, fertilizing and pest control

WFP and FAO focus on enabling cow herders to produce a substitute for the expensive fodder concentrates and improve the health conditions of their cows.  FAO provided green fodder seeds and veterinary inputs to 450 cattle herders (99 females and 351 males) in west Dara’a. In order to increase the efficiency of this activity, a team of 19 agronomists and veterinarians were hired to provide technical follow-up and advices to the beneficiaries through regular field visits and remotely through WhatsApp groups. WFP complemented this activity by providing ready-to-use fodder and fertilizers during the lean season to improve the growth of green fodder. WFP and FAO's intervention supports community resilience by addressing the needs of both livestock and vegetable farmers. By strengthening agricultural practices, providing essential inputs, and offering technical support, the intervention helps communities better withstand challenges such as climate variability and market fluctuations.

Youth and adolescents represent a critical cohort that warrants particular attention and investment as they are the future that will bring positive change, build economies, mend the torn social fabric, and encourage peacebuilding and social cohesion. Most of those adolescents in Dara’a, particularly girls, lack support and skills-building programmes due to being pressured to stay indoors for safety reasons. Therefore, offering opportunities for youth and adolescents to learn and participate will leave a positive sustainable impact. The JP through UNICEF focused on strengthening and improving access to skills-development programming. It also promoted alternative pathways and learning beyond schools while implementing skills-development programming. UNICEF supported the development of foundational, transferrable, and technical programming such as entrepreneurship to prepare adolescents for a better future. UNICEF supported the employability of female and male adolescents and youth and provided them with opportunities for economic self-empowerment. These include creating fora for adolescents to generate economic or social value for themselves as individuals or for their peer groups and communities.

In Dara’a city and its rural areas, UNICEF reached 10,083 young people, of whom 6,810 were female beneficiaries, with technical and vocational training relevant to market demands, and skills related to work readiness, entrepreneurship, and employability (i.e., entrepreneurship skills training, apprenticeships and internships, job matching, employment coordination, mentoring and job shadowing). Adolescent girls were further provided with gender-sensitive skill-building. The table below shows the achievement against the planned targets.

| Indicator | Planned Target |  |  | Actual Target |  |  | Justification of Over Achievement |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Female | Male | total | Female | Male | total |  |
| # of individuals supported with vocational and skills training (gender, disability & age disaggregated) | 1,800 | 1,200 | 3,000 | 6,810 | 3,273 | 10,083 | UNICEF has used its existing spaces to deliver the training, additionally, UNICEF has deployed mobile teams and engaged youth in executing diverse activities across multiple regions to cover vulnerable people in rural communities especially in light of extreme transportation difficulties. The outreach modality was very productive and cost efficient, as it enabled UNICEF to access higher number of beneficiaries at moderate cost. |
| Number of youth who received training on life skills, citizenship and capacity building to enhance their social and civic engagement | 2,000 | 2,000 | 4,000 | 10,684 | 8,439 | 19,123 |  |
| Number of youth leaders trained on response planning, dialogue facilitation, dispute mediation and negotiation skills to be community-based peace-agents | 1,000 | 1,000 | 2,000 | 5,217 | 6,256 | 11,473 |  |

Under this activity, UNICEF managed to surpass the target because mobile teams were implemented. The mobile teams reached additional beneficiaries over greater geographic area with less expense. The JP PMU with JP PUNO focal points conducted multiple field visits to Dara’a during the implementation period to monitor the implementation of different activities by the JP PUNOs and visited implementation sites, met beneficiaries, and took note of positive testimonies. Furthermore, the PUNO field staff in Dara’a conducted regular follow-up with beneficiaries of livelihoods to ensure their connection to the local business/employment market and to help address any concerns such people may face as they progress in improving their lives. UNICEF approached evaluating the impact of this activity through some follow-up figures provided by the IP. The IP has sampled 77 youths, of whom 30 are girls, who participated in the VT, entrepreneurship and skill building trainings and found that most of them became self-employed. Those include trainees learning household electricity, mobile phone maintenance, sewing, resin art, painting, and office management. Six youths (including two girls) who had attended courses in Dara’a Centre became employees in the centre itself to support other youth.

The UNFPA under the JP in 2023 continued to support the established facilities, through their implementing partner  including:

1- Women and girls Safe Space (WGSS):

The implemented activities in the WGSS in 2023 aimed to:

- develop the women's and girls’ soft skills by conducting several training in (Arabic language literacy courses, English and French language courses, sign language courses, and Braille alphabet learning courses.

- Raise awareness of women's and girls’ in GBV, RH and MHM, in addition to the legal issue by coordinating with the LNGO who provided this service

- Providing support in GBV and PSS case management.

- Economic empowerment activities by conducting several types of Vocational Training (VT), which was conducted for the first time in Dara’a, in addition to distributing startup tool kits.

- In collaboration with WFP, supporting Pregnant and Breastfeeding Women and Girls (PBWGs)  to obtain the needed hygiene items through E- Voucher project.

The Vocational training was conducted through the private sector who possessed the need experience and ability to provide accredited certificates to help trainees start working.

The achievements during 2023 covered

- 138 women and girls benefited from Vocational Training on ICDL, Confectionery industry, home electronics maintenance, Beekeeping, Mushroom and conservatory cultivation, and Mobile phone maintenance and management (advanced project management).

- 122 women and girls - who had trained on VT- received start-up kits.

- 3300 women and girls benefited from GBV and RH services and developing soft skills training services.

2- Youth Friendly Space (YFS): The implemented activities in 2023 in the YFS aimed to:

- Developing Youth skills to support them in entering the labour market by conducting Life skills training, language training (English, German, French), in addition to Arabic language literacy courses,

- Economic empowerment activities by conducting several types of Vocational Training (VT) distributing startup tool kits to trainees after finishing VT and providing grant activities.

- Developing youth skills to participate in their communities to raise awareness of Mine Risk, GBV, and RH, by establishing a Youth Volunteering team.

- Raise awareness of youth in GBV, RH, and PSS by conducting awareness sessions and recreational activities, PSS case management,

The achievements during 2023 covered

- 560 beneficiaries benefited from the Vocational training, and life skills training in the following topics (advanced Excel, electronics maintenance, ICDL, graphic design, mobile phone maintenance, small projects - training, accounting laptop, maintenance automotive electricity, Life skills, and languages courses

- 78 beneficiaries - who had trained on VT- received start-up kits.

- 8 beneficiaries benefited from a grant to establish their projects

- 1134 beneficiaries received awareness sessions in Mine Risk Education some sessions were conducted in coordination with UNICEF to children who were targeted by UNICEF

- Conducted a training for 25 young people to increase the number of the Orange Team to raise Peers' awareness in their communities on GBV and RH, and 1492 Yonge people received awareness sessions on RH and GBV by the Orange Team,

- Developing OT skills through conducting training in interactive theatre. To use this approach during conducting awareness sessions

- 1800 beneficiaries received the PSS, and GBV services.

- Implementing two CBIs (Installing lighting in Al-Naima village, installing curtains for the windows of the women’s department in the National Hospital in Dara’a.

Ensuring no one is left behind, the Vision Centre is accessible to PwD, with both physical and sensory disabilities, through:

- Facilitating access to people with mobility issues by ensuring no physical barrier at the entrance

- Installing wide doors allowing wheelchair passage

- Providing all communications in braille, as well as audio (sound system) and written format

- Installing rubber carpets on the floor to guide people with sensory disabilities

- Providing awareness videos with sign language and subtitles

- Ensuring WASH facilities are accessible for people with physical issues

#### Output 3.2: Social and economic needs of the most vulnerable groups are identified and addressed

Building on the Youth-Lead Market Assessment (YLMA) conducted jointly by UNFPA and UNDP in 2021, the JP, through UNFPA under the Dara’a phase I workplan, supported the capacity development of over 3,000 young Syrians to enhance their access to livelihoods opportunities and their integration into the economy. The idea was to support them with self-reliance and the ability to generate income through skills and vocational training. UNFPA and UN-Habitat have carried out a consultation session with women from Dara’a city and the catchment rural areas to address, identify and prioritize women’s needs regarding safer access to daily activities and family communal spaces. The relevant interventions were completed within the course of 2022 and 2023.

Additionally, within the scope of its livelihoods activities through UNDP, the JP has provided critical support to revive 95 local businesses and small and medium enterprises (SMEs) who lost some or all of their livelihoods’ assets during the crisis through provision of start-up grants to reactivate their businesses aiming to re-establish their income generating and entrepreneurial endeavours. UNDP field staff periodically followed up on the status of those beneficiaries. Most of them are still doing business and even were able to provide few micro employment opportunities for workers and apprentices. However, those beneficiaries are still facing challenges regarding the availability of electricity, which interrupts operation hours. Additionally, UNDP provided VT to 50 beneficiaries to enhance their skills and equip them with new ones, to help them engage in economic activities, access employment, and improve their coping capacities and resilience. UNDP focuses on supporting women-led micro, small and medium enterprises and helps match women to possible employment opportunities that will in turn alleviate frictions over rising inequality.

During the implementation of the Dara'a Phase I workplan, UNDP received over 800 applications, from which only 50 were initially selected. Subsequently, an additional 45 were accepted due to budget availability. Under Dara'a Phase II, UNDP successfully targeted another 66 beneficiaries for the rehabilitation of their SMEs, in addition to 70 for job training. This initiative aims to further contribute to building the resilience of targeted beneficiaries by enhancing both their human assets (skills) and physical assets (market access). Also, under Outcome 3, the JP through UNDP provided 45 prosthetic services along with psychosocial support and around 180 post-treatment rehab sessions to PwD.

In addition, UNDP provided high-quality training in Dara'a. The initiative began by disseminating concepts of gender equality among various segments of society, especially community leaders from both genders across different sectors, particularly rural development units. These trainings served as a cornerstone for subsequent interventions as a tool to address key issues affecting equality in rights and justice in meeting needs with a strategic outlook aimed at removing barriers hindering social justice. According to locally identified needs, the training focused initially on economic literacy and household management to serve as an effective gateway for positive dialogue within families, shedding light on various familial, economic, and social roles, and optimal investment strategies to overcome the current crisis. Additionally, sessions were conducted to raise awareness about sexual health, providing information to enhance awareness in this aspect. Life skills development was also emphasized, providing knowledge and skills aimed at empowering individuals to effectively deal with daily challenges and develop their personal and social capacities. These skills include time management, problem-solving, decision-making, effective communication, among others, enabling individuals to achieve success in their personal, professional, and social lives. Furthermore, all these services were supported by remote specialized mental health services. Collectively, these trainings and activities worked towards building trust among women and men in the targeted area of Dara'a as an initial step towards family and local peace.

Under the Dara’a phase II workplan and in addition to the social support, UNFPA focused on provision of sustainable economic empowerment support. Furthermore, in cooperation with relevant national and international stakeholders, UNFPA supported conducting research to enable communities (with special focus on women) to tackle climate change risks.

The JP through WFP and UNFPA has provided nutrition and hygiene assistance to 3,581 Pregnant and Breastfeeding Women and Girls (PBWGs) in Dara’a to prevent chronic and acute malnutrition and to improve their dietary diversity and hygiene conditions, which is a growing concern in Syria. Through WFP's cash-based transfers (value vouchers), the JP helped ensure that poor households, often female-headed households, are able to save and spend money on things related to livelihoods. Through the multipurpose electronic voucher (e-voucher), supported by both agencies targeting PBWGs, recipients gain access to a wide range of fresh food and hygiene items from contracted retailers on a monthly basis.

This dignified assistance modality put the beneficiaries and their needs at the centre of humanitarian programming, enabling them to make informed decisions on the assistance they receive. Women participating in the programme not only receive a monthly value voucher for fresh food and selected hygiene items but also benefit from a variety of other services that accompany their pregnancy and breastfeeding period. These include sensitization and assistance on healthy nutrition, RH, GBV and antenatal/postnatal services in UNFPA-affiliated clinics as well as access to UNFPA-supported WGSSs for integrated reproductive health and GBV-related services. The value of the e-voucher is regularly adjusted based on the market price trends to preserve beneficiaries’ purchasing power. The minimum expenditure basket (MEB) is used as a reference for both food and hygiene transfer value. The voucher value ranged during the reported period, with 41–45 USD for Dara’a and 34–39 USD for DEZ (WFP’s contribution was 32–36 USD for Dara’a and 25–30 USD in DEZ; UNFPA’s contribution was 8.7 USD). The assistance was provided for four months, from September until December 2022.

Like many other cities within Syria, Dara’a is suffering from a high unemployment rate. In the emergency employment creation, predominantly unskilled labour is employed to conduct public works schemes or other short-term activities prioritized by affected communities such as SWM. The objective of emergency employment is to support immediate livelihood stabilization for vulnerable communities through rapid injection of cash into the local economy and to mobilize activities that benefit the entire community, in a step that will further support the community’s resilience. UNDP supported emergency employment through its SWM, and other infrastructure works that were described under Outcome 2.

Since social cohesion plays an essential role in achieving the JP main objectives, four social cohesion  initiatives took place in Dara’a aiming to foster community trust and cohesion. Overall, 247 people participated, and 212 youth were trained on community organization and dialogue facilitation to enhance the decision-making process and provide opportunities and mechanisms for participants to voice their opinions in influencing decision-making and enhance their community participation, motivating them to be change agents themselves rather than targets for change.

The completed activities are as follows:

- ‘Space of Peace.’ This included organizing a number of social activities and events in the park such as (1) cleaning and beautifying the park, (2) holding dialogue and awareness sessions for neighbourhood residents and youth to address the issues facing youth and enhance their knowledge about their rights/duties, (3) hosting a drawing exhibition and (4) establishing a charitable activity to collect and offer money and children’s games to affected families.

- ‘Take A Breath.’ This initiative was developed by a group of young people, local leaders, and volunteers in Dara’a who received training within the youth capacity-building programme. The Al Matar neighbourhood was selected to implement the initiative as one of the densely populated areas. The initiative aimed to promote community cohesion among different social groups and engage them in various community activities to break the ice, remove barriers between them, and achieve integration. The activities under this initiative include revival of the Al Matar park by cleaning and beatifying the garden and equipping an outdoor theatre that will bring together many people from the different neighbourhoods of Dara’a city through the establishment of interactive social activities and seminars dealing with different community problems. Moreover, cultural events were organized to promote positive behaviour in addition to showcasing theatre, storytellers and book sharing within the effectiveness of the “my book and your book” social initiative.

- ‘Sports Pulse.’ This initiative included (1) reactivating safe spaces for football and basketball, (2) conducting an afforestation campaign for the courtyard where the sports league will be held, (3) establishing a football league and (4) hosting an honorary friendly match for the elderly.

- ‘Tune.’ This initiative involved young people in organizing and implementing various musical, heritage, social and cultural events; it included an introductory session where all participants met and opened various discussions on the different types of folk art, formation of singing and dancing bands, organizing voluntary theatrical event for the public, etc., in an effort to re-establish social cohesion and strengthen community ties.

During Dara’a phase I, WFP supported the livelihoods of vulnerable households with poultry, fertilizers, and sprayers. This type of intervention was timely since the prices of both fertilizers and eggs saw unexpected increases. WFP supported 500 households with poultry and another 500 households with fertilizers and sprayers, with 30% of the supported households headed by females.

Most of the phase-II activities were implemented in coordination with FAO, where FAO provided green fodder seeds, veterinary inputs, and technical training to 450 cattle breeders in western Dara’a, enabling them to produce cost-effective alternatives to concentrated feed and improve the health of their cattle. WFP complemented this activity by providing ready-to-consume fodder quantities (250 kg per breeder) during periods when green fodder is unavailable. To encourage the growth of the distributed green fodder seeds by FAO, WFP also provided fertilizers (25 kg per breeder) to support the growth of the distributed green fodder seeds provided by FAO. This comprehensive support ensures that breeders have access to the necessary resources for successful green fodder production, enhancing their ability to feed their livestock and maintain their livelihoods.

FAO also supported another 450 small-scale farmers by providing summer vegetable seeds and technical support. WFP complemented this effort by providing drip irrigation systems along with agricultural fertilizers. The drip irrigation system increased the efficiency of cultivation and water-saving.

WFP's support extended to graduates from FAO's Agri-entrepreneurship training program. Five graduates (3 females and 2 males) received financial grants to start their entrepreneurial projects. This initiative not only empowered individuals to become self-reliant but also stimulated economic growth within the community. By fostering entrepreneurship and providing the necessary resources, WFP contributes to enhancing their resilience.

WFP rehabilitated Al Jalad pastoral reserve. The reserve covers an area of 70 hectares that was cultivated with pastoral shrubs. 60,500 seedlings were planted, and the area was supported with fencing, solar lighting, and a guard room. This intervention supports 100 sheep holders who own 3,000 heads of sheep. WFP rehabilitated the pastoral reserve in collaboration with the local community. This collaboration is essential for ensuring the sustainability and success of the intervention, through engaging 81 workers (45% males and 55% females) from the local community in the cultivation process, paid under the cash-for-work modality. This intervention helps not only by providing employment opportunities but also by fostering a sense of ownership and responsibility among community members toward the restored area. The rehabilitation of the pastoral reserve contributes to sustainable land management practices, preventing soil erosion, protecting the rehabilitated area, and increasing access to pasture in lean seasons.

Adolescents and young people between 10 and 24 years old in Syria have missed opportunities to develop and learn. They have limited access to skills development opportunities and basic services, including supporting their safe transition from school to work. Syrian girls are vulnerable to child and forced marriages and early pregnancy and have limited or no access to services and learning opportunities. Syrian youth are struggling with a high unemployment rate, lack of matching between youth skills and labour market needs due to dramatic changes in the economy and poor skills-development programmes, lack of access to formal education and poor quality of education including technical and vocational education and training, difficult transition from school to work and lack of alternative and flexible learning pathways and educational opportunities, especially for the most marginalized youth (such as youth who dropped out of school). In response to these multiple challenges, UNICEF reached 17,454 (of whom 9,538 are females) of the most vulnerable adolescents and youth, especially those who are deprived of education, training, or employment. They have been supported through an integrated package of skills-building services and opportunities, including the development of life skills (communication skills, problem solving, dealing with stressful and challenging situations, teamwork, etc.).

Additionally, UNICEF provided 9,931 adolescents and youth (of whom 4,324 are female) with coordinated initiatives to support the development of their social, economic, and civic skills and opportunities through volunteerism and social cohesion activities. UNICEF managed to exceed the target because mobile teams were able to reach additional beneficiaries with fewer expenses.

### Deir ez-Zor:

#### Output 3.1: Income, sustainable livelihoods opportunities and inclusive local economic development are restored and maintained in both urban and rural catchment areas to increase household incomes, boost food production and enhance local markets

Adhering to the JP’s overall objective to enhance people’s resilience by supporting and availing sustainable livelihoods opportunities, FAO and WFP joined efforts to support vulnerable farmers in the eastern and western rural areas of Deir ez-Zor city through synergized and complementary interventions.

To support local food production, WFP and FAO distributed inputs for vegetable production to 1,000 vulnerable farmers, of which 30% are females, in rural Deir-ez-Zor governorate and the rural suburbs of Deir-ez-Zor city to enhance their food security and sources of income, as well as to boost local food production. Farmers have the opportunity to sell surplus produce in local markets, generating additional income for their households. This economic diversification helps improve financial stability and resilience against economic shocks. Increased vegetable production benefits not only the individual farmers but also contributes to the overall availability of fresh and nutritious produce in the community. The distribution of winter vegetable seeds, fertilizers and fertilizer spraying toolkits was conducted late 2021 to 500 vulnerable farmers’ households. Later in spring 2022, the targeted farmers harvested the yield of this intervention, while also in late spring 2022, FAO and WFP continued this intervention by targeting additional 500 farmers with distribution of summer vegetable seeds and fertilization toolkits, reaching a total target of 1,000 vulnerable farmers. Those farmers continued benefitting from the harvests of winter and summer vegetables as they brought new seeds with the yield of the first crops and re-planted them thus ensuring the sustainability of the benefit.

The selection of vegetable packages was influenced by various factors such as market preferences, farmers' demands, the climatic conditions of the targeted areas, and the nutritional content. Throughout the cultivation season, technical instruction and follow-up are provided, both on-site and virtually (via WhatsApp groups). A group of technical experts in vegetable cultivation carried out the training and follow-up. WFP supplemented this activity at the same time. Here, complementarity made it possible to fulfil the various needs that farmers have to sustain their output. WFP supplied nutrients and equipment for applying fertilizers to the same recipients, while FAO supplied high-quality seeds and training.

To support smallholder sheep keepers and improve their technical skills on best livestock management practices, FAO established ten livestock Farmer Field Schools (FFSs) to aid small-scale sheep keepers in improving their animal management skills. These schools served as educational hubs for 200 sheep keepers who might be vulnerable to poverty, offering them a platform for exchanging information and skills, as well as testing and validating approaches to more profitable, efficient, productive, and market-driven sheep farming. Over an eight-month period between late-2021 and mid-2022, a team of veterinary professionals and agronomists held frequent meetings and provided technical follow-up both in the field and virtually (via WhatsApp groups)

WFP supported 200 sheep keepers (104 females and 96 males) (from enrolled and non-enrolled in LFFS) in rural Deir ez-Zor with livestock fences, crucial for improving the conditions of sheep keeping. Livestock fences help protect the sheep from harsh weather conditions and wild animals, reducing the risk of loss or injury. This intervention enhances the welfare of the sheep, which are valuable assets for the livelihoods of the keepers.

WFP's provision of a maize dryer to the local community to support 4,000 farmers in the targeted area was essential for reducing post-harvest losses and improving maize quality. Post-harvest losses can significantly impact farmers' income and food security. The maize dryer allows farmers to properly dry and store their maize, preserving its quality and ensuring a higher market value. This intervention directly supports farmers' incomes and food availability.

WFP empowered the collective work of 20 women by establishing four income-generating dairy processing units and providing technical training, a critical step towards gender equality and women's economic empowerment. By supporting women in rural areas, WFP not only improves their livelihoods but also promotes their active participation in decision-making processes and community development. Empowered women contribute to the overall resilience and prosperity of their communities.

Congruent with the interventions in Dara’a, and to support young people to start their own business through the FAO’s NABTA programme, FAO concluded agricultural entrepreneurial training for 100 young men and women (35 males and 65 females) to lay the ground for small income-generating start-up agricultural projects, and provided seed funding, coaching and mentorship throughout the inception phase for 10 agricultural projects.

Water availability is a key factor for sustaining agricultural livelihoods. Despite being located on the banks of the Euphrates River, Deir-ez-Zor rural areas still suffer from limited capacities to pump and streamline water from the river to farming lands. With the aim of enhancing irrigation infrastructure, expanding cultivated areas, and increasing production, WFP rehabilitated seven pumping sets along the Euphrates River to enhance and expand irrigated land. This resulted in an increase in the irrigated area by 210 hectares and improved irrigation for another 1,300 hectares. Technical specifications were developed in collaboration with FAO. GOPA was selected by WFP as a cooperating partner to implement all the mentioned activities in Deir-ez-Zor. The field-level agreement was signed in January 2023.

The Euphrates basin is one of the main wheat producers’ areas in Syria, which is the core crop to sustain food security, nutrition, and livelihoods. Since most of the agricultural machinery was destroyed or looted during the conflict in Deir ez-Zor, FAO has filled some gaps by supplying 12 seeding machines that were used for the current wheat/barley season. In a similar approach to support the Water Users’ Associations, FAO established Agriculture Machinery Users Groups to oversee and govern the use of these seeding machines. The machinery will help reduce the cost of seed for farmers by optimizing the sowing rate.

To sustain the economy of rural areas, farmers need to have a reliable solid outlet to be able to sell their final agricultural produce. WFP rehabilitated a wholesale farmers market in Al-Shmeitieh village in north-western rural Deir ez-Zor, which will avail farmers and cattle herders with a spacious commercial area to conduct sales transactions, hence, reviving agricultural produce business and enhancing the food system in the area. The market was always open to the public but operating at minimal capacity, and its overall condition was not convenient when considering the laborious movements of wholesalers, farmers, and livestock keepers, including a sizable number of women, given the peak of operation during the early dawn hours. Therefore, the rehabilitation works included steel canopies for the existing vegetable sales outlets, levelling, paving, asphalting works for the vegetable yard, fencing works, solar light street poles, new gender segregated lavatory units, and external drinking water points. This has helped to ensure that the market is easily accessible and safe and that it provides convenient facilities to strengthen commercial transactions involving agricultural/livestock products. The rehabilitation works contributed to bringing back more wholesalers and retailers from farther areas to conduct economic transactions. The market was handed over in November 2022 accordingly to the municipality of Al-Shmeitieh village. The intervention enhanced and sustained the economic transactions between farmers and traders and contributed to an increase in micro job opportunities for daily workers and availed more opportunities for truckers and haulers.

At the urban level, UNDP worked on reviving SMEs in the industrial zone and other areas in Deir ez-Zor that have seen a return to enable craftsmen (including car mechanics, blacksmiths, metal workers, carpenters, and many others) to recommence and/or resume their business activities in their proper locations. SMEs have an essential role in the Deir ez-Zor economy since they avail numerous work opportunities for various levels of workers from professionals to apprentices, hence, providing a steady source of income and supporting urban livelihoods. Simultaneously, UNDP finalized the revival of 80 workshops in the industrial area and another 45 outside the industrial area. Out of these 45, 10 are women-owned and five are owned by PwD. This activity contributed to the creation of 12 temporary job opportunities and 125 permanent jobs.

#### Output 3.2: Social and economic needs of the most vulnerable groups are identified and addressed

Through their multiple VT initiatives, UNDP prepared young people in Deir ez-Zor to enter the job market by conducting employment events and training beneficiaries on various professions, then launching them as apprentices in UNDP’s SME rehab activities. Some 154 beneficiaries received employment support services, 253 beneficiaries received VT and 62 beneficiaries received entrepreneurship skills training. In addition, nine beneficiaries received start-up grants that led to the establishment of seven local start-up businesses. This activity contributed to the creation of 43 emergency job opportunities and the realization of 70 actual employment opportunities. Youth development and economic empowerment is a key factor for recovery and sustainable resilience. In this regard, UNDP, UNFPA and UNICEF established a fully-fledged community centre under agreement with the selected IP, namely IECD, to implement one major joint multipronged activity in the domain of social cohesion. Each agency as per its mandate and area of expertise shall implement a set of integrated interventions targeting young people to enhance their role and engagement in socioeconomic recovery and resilience, through developing initiatives to solve the problems that impede recovery, including with provision of VT, specialized training, case management and awareness sessions along with provision of productive toolkits and seed funding. IECD established a youth-friendly space (YFS) to deliver youth-supported activities funded by the three agencies. IECD also put in place efficient pathways to link beneficiaries with services delivered by other agencies. To ensure sustainable income-generating opportunities, IECD is conducting a rapid market assessment to gather information on the livelihood support activities. Through this assessment, IECD identified market opportunities suitable for women and PwD. For youth-led initiatives, IECD also ran a community consultative process to identify the initiatives that will contribute to building the resilience of the targeted communities with special focus on women and PwD. The training centre location was selected in an accessible area in Deir ez-Zor city, and then prepared, furnished, and equipped. It was put into operation by mid-second quarter 2022 and continued through 2023. During the implementation period UNICEF was able to provide employability skills including life skills, VT, and entrepreneurship skills to 2,481 adolescents and youth (1,489 girls and 992 boys). The trainings included mobile phone and computer maintenance, sewing, electrical skills, solar system installation, etc. Among them, 47 participants (30 girls and 17 boys) were capacitated as trainers of trainees, especially to deliver sessions to their peers on solar system installation and English language. Furthermore, 40 participants (23 girls and 17 boys) benefited from community-based civic engagement and social cohesion activities. After completing their entrepreneurial training, six young people gained seed funding for their successful projects. The table below shows the achievements against planned targets:

| Indicator | Planned Target |  |  | Actual Target |  |  | Justification of Over Achievement |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Female | Male | total | Female | Male | total |  |
| Number of youths who benefitted from the three participating agencies services -per mandate - in terms life skills, citizenship and capacity building on planning for recovery, besides vocational training to enhance their livelihoods and social and civic engagement | 2,200 | 2,100 | 4,300 | 5,680 | 3,916 | 9,596 | UNICEF has used its existing spaces to deliver the training, additionally, UNICEF has deployed mobile teams and engaged youth in executing diverse activities across multiple regions to cover vulnerable people in rural communities especially in light of extreme transportation difficulties. The outreach modality was very productive and cost efficient, as it enabled UNICEF to access higher number of beneficiaries at moderate cost. |

UNDP completed the training stage where 125 project volunteers and community leaders were engaged to support in the designing of community initiatives. The initiative proposals have been developed and were launched and initiatives were implemented accordingly.

According to the strategic vision of UNDP for gender issues and gender equality, the program has economically empowered women in Deir ez-Zor by supporting women's groups interested in entering the workforce and activating their economic roles outside the home. To ensure sustainable outcomes within a supportive environment, specialized services were implemented, including training and counselling to develop cognitive and non-cognitive skills, economic literacy, household budget management, with an additional focus on business management, marketing, and finance for those in need. Additionally, financial support and financing for women-led grassroots projects were provided as a means of enhancing women's participation in activating their roles. It's worth noting the range of supportive services provided to beneficiaries and their surroundings, including specialized psychosocial support, dialogues on rights concepts and partnership forms, legal awareness, and the implementation of initiatives supporting the involvement of men and youth to bridge the gap of inequality and injustice not only between women and men of different age groups and physical abilities but also between rural and urban areas.

UNFPA assessed the capacities of IECD to implement specialty programmes in the domains of GBV and RH and noticed that IECD has some limitations in these domains, therefore, UNFPA in coordination with UNICEF and UNDP decided to limit the partnership with IECD to youth support and empowerment-related activities only, while engaging another IP to deliver GBV, RH and cash-for-work activities under Outcome 3. UNFPA identified Greek Orthodox Patriarchate of Antioch and All East (GOPA) as a potential IP and discussed project modalities and risks with them and agreed on the supported mitigation measures, then finalized the workplan for Q1 of 2022, which was put into implementation as of Q2 2022, and continued until the end of the programme by 31 December 2023.

During the 2023 the IECD was continually engaging in a community consultative process, specifically targeting youth-led initiatives. This process seeks to identify projects that will enhance the resilience of the community with particular focus on empowering women and people with disabilities.

Also, UNFPA partners were focusing on diverse Skill Training. The training programs encompassed a wide range of skills, including mobile phone and computer maintenance, sewing, home electrical maintenance skills, and solar system installation, besides other skills.

In partnership with GOPA, UNFPA established one community well-being centre (CWC) in the city of DEIR EZ-ZOR, connected to three SPs in the surrounding rural communities to deliver case management, psychosocial, family planning, RH, and economic-support activities. All of the supported facilities are accessible and adapted to accommodate the needs of PwD. Additionally, given the electricity and fuel shortage in DEIR EZ-ZOR, the facilities are solar operated.

Since the establishment of the CWC and SPs in Q2 of 2022, every month, about 2,000 women, men, girls, boys and PwD report to them to receive health services from the established family clinics. Besides improved access to health services, the facilities also provide GBV response and prevention support to vulnerable men and women. Beneficiaries receive case management, PSS, RH and GBV awareness and economic empowerment services. Given the transportation difficulties, the facilities offer transportation services for women coming from remote and hard-to-reach areas and for referral cases. As part of the GBV prevention, UNFPA provides economic support to women through skills development and productive assets, and through linking women with suitable livelihood support delivered by other JP partners (business counselling services). Economic-support activities are informed by a gender-focused market analysis. UNFPA is also coordinating with other health agencies to increase medicine supply in DEIR EZ-ZOR and is working on evidence-based advocacy on this regard.

The below table shows the cumulative number of beneficiaries served under the GBV/RH component during 2023 through the community well-being centre (CWC) and the youth friendly space (YFS)

| Facility | Girls | Women | Boys | Men | total |
| --- | --- | --- | --- | --- | --- |
| GOPA-Deir ez-Zor-(CWC) | 77 | 1271 | 8 | 154 | 1510 |
| IECD-Deir ez-Zor-(YFS) | 102 | 559 | 41 | 185 | 887 |

For the implementation of the cash-for-work activities, UNFPA adopted a strict community-based approach, including the establishment of community women’s committees to support in the planning, targeting, and monitoring of the JP activities in DEIR EZ-ZOR. The committee also supported the identification of the most vulnerable women and men based on specific criteria.

Social cohesion is not separate from support to livelihoods and economic empowerment and the social protection schemes under the JP contributes to the resilience and social inclusion of families who have children with disabilities (CwDs) as well as families who have PBWGs, who are considered among the most vulnerable people in Deir ez-Zor.

WFP is collaborated with UNFPA to support PBWGs with hygiene and nutrition cash-based assistance in an approach to contribute to their families’ resilience, while to support the social inclusion of people with disabilities (PwDs), UNDP under the Joint Programme delivered five hearing aids and two air mattresses and distributed mobility aid including six electric wheelchairs, two manual wheelchairs and 12 blind sticks.

In the same regard, UNICEF’s Integrated Social Protection Programme provided children living with severe disabilities with regular cash transfers (USD 40 per month/USD 120 per quarter), implemented by a vetted money transfer company, and case management services for a 24-month period. Children with disabilities are considered among the most vulnerable and disadvantaged children in Syria. Through an integrated social protection approach that combines cash transfers and case management services, the contribution addressed both economic and social vulnerabilities of CwD and their families.

UNICEF identified a qualified partner that implemented the integrated programme to reach the target of 500 CwD, of whom 40 percent are girls, with regular cash assistance. The selected partner was responsible for the identification, registration and verification of beneficiaries and the provision of case management services. There is a clear division of roles whereby UNICEF utilized the services of a third-party financial service provider to transfer the cash grants to families, while relying on a national IP to implement the case management component. While the cash helped families meet the basic needs of children and households, the case management component facilitates the referral of CwD to available social services, increased their social inclusion and responded to their specific protection concerns.

The JP fund contribution to UNICEF was instrumental to reaching the targeted 500 CwD (208 girls and 292 boys) with one quarterly payment of USD 120 for each child and delivery of case management services in Deir ez-Zor governorate from November 2022 till February 2023. Using the JP fund along with its other resources, UNICEF will continue the support to all identified enrolled children providing cash assistance and case management services till the end of their two-year programme cycle in Deir ez-Zor governorate.

Based on evidence generated from post distribution monitoring (PDM) survey conducted in Deir ez-Zor in July 2023, the way the cash is used reflects the needs of the beneficiary families. Most of the families are using the cash to cover their nutritional needs, with 40 percent of the cash received was used to buy food. Spending on health, clothes and WASH are occupying almost the rest of the cash there (46 percent). The PDM confirmed that most of the beneficiary families declared that their financial resources of the family are insufficient to meet the basic needs of the children in the family, as defined and prioritized by the family. The PDM also showed a high percentage of the beneficiaries’ satisfaction with the Programme.

On a different dimension of social cohesion, UN-Habitat coordinated with UNICEF to bring parents, children, school principals and teachers together to draft designs of public greenspaces and safer access to venues that are used by school children and women in the city. This act represented a step that further enhanced social interaction and strengthened community buy-in of the JP interventions. Moreover, UN-Habitat, UNDP and UNFPA have carried out a consultation session with women from Deir ez-Zor city and surrounding rural areas to identify and prioritize women’s needs regarding safer access to basic services/public spaces, where the participants identified a small garden next to the local market that would give them a safe space to rest after finishing their micro economic exchanges and before travelling back to their villages.

## The JP current location identification and selection

Based on a 2019 comprehensive inception report that offered detailed local contextual analysis, area needs, risks, potential interventions, and partner mapping, Deir ez-Zor city/district and Dara’a city/Dara’a district and subdistrict were eventually selected as the final locations for interventions under the JP and were approved by the JSC. Following the selection of locations, the participating UN agencies commenced planning for their preliminary assessments to be conducted in these two locations. The participating UN agencies adhered to the location and activity selection criteria as stipulated in the description of action.

From UN-Habitat’s point of view, Dara’a and Deir ez-Zor scored high levels of population vulnerability and resilience needs. Added value could be gained in terms of confidence-building and bridging differences to enhance social cohesion. Dara’a city is considered a key hub in the southern area, close to the border with Jordan and a food basket source for Damascus and the southern areas, especially for vegetables and grain. Any amelioration in the situation of the city and its population shall entail a positive impact on the whole southern area. Likewise, Deir ez-Zor city is considered a main pole on the Euphrates River in the eastern area and the source of many strategic agricultural products and livestock. Any progress of the city will have a positive impact for the whole region and the eastern area.

UNFPA identified the targeted locations in Dara’a following joint consultations and assessments with UNICEF, FAO and UNDP, along with the nature and type of resilience and livelihood activities set out in the Description of Action document (i.e., ProDoc). Activities and services are aligned with criteria set out in the ProDoc. Activities are implemented at the city level with a focus on the most critical areas, including the city centre and nearby rural areas, and on vulnerable groups such as women, youth and PwD. In Deir ez-Zor, UNFPA identified the locations based on the availability of other UNFPA facilities in each district, needs, geographical reach and accessibility, security, and the possibility of referrals, if needed. Five locations inside the governorate were selected to implement the activities and services based on the approved workplan as follows: the YFS that is established jointly with UNICEF and UNDP as well as the CWC in the city centre, and the SPs in Al Shmeitieh, Harabish and Marat neighbourhoods.

Also, the identified locations for the FAO intervention considered the vulnerability of people and the levels of current and potential urban-rural linkages. Interventions were designed to respond to the identified needs and to contribute to the project objective to strengthen urban-rural linkages and recover agricultural livelihood activities.

UNICEF identified the following locations in Dara’a and Deir ez-Zor urban, suburban and rural areas:

- There are several communities that have witnessed extensive damage during the crisis in Dara’a and are currently witnessing a gradual flow of returnees. These communities include the following: Ataman, Kherbet Ghazala, Mokhayam Dara’a and Naeimeh in Dara’a subdistrict; Deir Adas in As-Sanamyn subdistrict; Sheikh Meskin, Namer, Bosr Al Harir and Hrak in Izra subdistrict; Nahta and Al Kark in Bosra subdistrict; and the Al Shajara area. Under the Dara phase I and phase II workplans, UNICEF focused on Dara’a city including Dara’a Al Balad neighbourhoods and Tafas, Nassib, Naeimeh, and other villages in Dara’a subdistrict.

- For locations in Deir ez-Zor, UNICEF’s planned interventions focused on Al Hamedieh, Baajen, Jbeileh, Sheikh Yaseen and the old airport neighbourhoods.

## The JP prospective locations identification and selection

In light of the possibility of receiving additional funding and in the lead-up to the next phase of the JP and building on the results of the location selection workshop of August 2022, upon which four prospective locations (namely: Aleppo, Hama, Homs, and Rural Damascus governorates) were identified, Aleppo Governorate with focus on East Aleppo City was selected to be the targeted location for JP’s next phase. Against this back drop the PMU along with the focal points of the participating UN agencies and with the support of context analysis experts and other technical experts from the agencies, elaborated an in-depth context analysis of East Aleppo City and its surroundings to identify connectors and dividers across different socio-economic themes analysed the associated risks and opportunities around them.

DENMARK and ITLAY expressed willingness to fund the second phase of the JP in Aleppo, and the JP PMU collaborated with the context sensitivity team and technical focal points at the JP PUNOs to produce a roadmap for the second phase of the JP, which was called the UNJP 2.0.

## Cross-cutting issues

The JP is the multi-agency programme, which builds on the experience and comparative advantages of six participating UN agencies, to provide a harmonized and integrated response to the complex challenges and essential population needs in two targeted areas: Dara’a and Deir ez-Zor. It is a rational response to addressing the communities’ vulnerabilities in a coordinated, streamlined, and cost-effective way while maximizing synergies among IPs and drawing on UN agencies’ expertise and presence in the field.

According to the 2023 Humanitarian Needs Overview (HNO) document, the Deir ez-Zor subdistrict population is estimated at 275,894 people among whom around 59,201 people are internally displaced persons (IDPs), while there are 422 spontaneous IDP-returnee. According to the HNO 2023, there are 179,944 people in need in Deir-e-Zor subdistrict.

In Dara’a, women represent more than 51 percent of the entire population. There are critical shortages in the provision of RH services – from family planning to antenatal and postpartum care – and new-born care. Yet early or forced marriage is a human rights violation, and it often leads to early pregnancy, which exposes girls to significant health risks. The most recent available data show that early marriage was most prevalent in Dara’a, where 26 percent of women aged 20–49 were married before the age of 18. Early marriage has occurred in both rural and urban areas of Syria as of 2006. Regarding PwD, it is estimated that 45 percent of the injured population are expected to sustain a permanent impairment, exceeding the global average rate of PwD of 15–30 percent. This requires further attention and specialized services.

In coordination with the participating UN agencies and the JP PMU, UNFPA focuses its efforts on leveraging gender equality, enhancing the quality of interventions and engagement of beneficiaries, empowering women, and supporting youth participation through adaptation and fine-tuning of JP activities to streamline gender and protection issues into them. This will help in addressing different types of vulnerabilities whether related to gender, youth, disabilities, etc., through tailored activities to support the vulnerable groups’ access to UNFPA services in particular and to other UN agencies’ services provided through the JP, with the long-term objective of changing social norms and preventing negative coping mechanisms. Furthermore, UNFPA stretches out its capacities to support women’s empowerment and access to markets by means of provision of VT, toolkits, and seed funding in collaboration with FAO and other UN agencies.

The Whole School Approach and Skill-Building Opportunities by UNICEF implies that schools are an entry point for local communities, NGOs, and the UN to invest in and leverage resources to maximize collective efforts and results. More specifically, schools can serve as a common platform where children access protective and inclusive environments and quality learning; teachers benefit from professional development; and communities access awareness-raising activities, social protection services, as well as essential education supplies.

As part of its resilience development agenda and drawing on the experience of the ‘No Lost Generation Initiative’ promoted in the region, UNICEF focuses on addressing the social needs of children, adolescents, and youth by promoting an integrated package of services. Starting from the school as a place for positive social exchanges in the community – as well as a safe learning environment – UNICEF promotes programmes aimed at increasing access to quality education for children and, at the same time, supporting families with basic income to address the needs of their children. Winterization, NFE activities, community based ECE, self-learning initiatives as well as seed funding for social entrepreneurship promoted among young people involved in vocational and life skills training will contribute to the injection of resources in the selected communities addressed at increasing social inclusion and social cohesion.

Skills-building, entrepreneurship, employment, and livelihoods are addressed in an integrated manner. The JP supports meaningful adolescent participation and social/civic engagement of girls and boys in local communities, giving them equitable access to safe spaces to be seen and heard, where they practice acquired life skills through either social entrepreneurship initiatives, or wider citizenship and social mobilization. The ultimate objective is for adolescents and youth to improve their capacities to contribute to enhancing resilience and social cohesion in their communities and hence transition to adulthood with purpose.

Within the ‘Whole School Approach’ model, the school-feeding programme offers the opportunity to achieve multiple objectives ranging from education, social protection, increasing food production and revitalizing the local economy. Local sourcing of ingredients and food commodities along with support provided to local manufacturers in food processing for use in education and social protection programming by WFP-UNICEF-FAO is at the heart of the approach to support the most vulnerable school-aged children in Syria. For example, the use of fortified date bars in the school-feeding programme promotes the local sourcing of raw ingredients from local suppliers and producers, who benefit from FAO’s agriculture inputs and technical support at production stage. This leads to positively impacting livelihood opportunities across the supply chain.

# IV. Key challenges and mitigation approaches

Security and accessibility

The security situation in Syria in general and particularly in Dara’a rural areas continues to present a challenge and may temporarily hinder access to implementation. The sporadic tensions and conflicts in Dara’a governorate during 2022 and 2023, especially in the eastern and western rural areas of Dara’a city, have caused some temporary delays in the activities of the participating UN agencies under the JP Dara phase I workplan. While the UN has established a hub in Deir ez-Zor, and the situation in Deir ez-Zor city and its nearby rural suburbs is considered somewhat stable for the JP implementation, yet the difficulties and lack of security on some sections of the highway leading to Deir ez-Zor pose a challenge, especially for private contractors who need to transport raw materials to execute their contracts with the UN agencies.

UN field missions to implementation sites require approval from the Ministry of Foreign Affairs and Expatriates (MoFAE), where the purpose, location, and participants, whether national or international staff, should be defined. Similarly, private contractors apply for their own permits and coordinate with relevant governmental authorities to transport goods, supplies and equipment and to deploy workers and implement contracts.

Although security incidents are usually unpredictable, the UN Department of Safety and Security (UNDSS) maintains coordination with the relevant security parties in the country and stays abreast of developments. Any significant information regarding road-related and/or location-related risks are immediately shared with UN agencies, enabling the UN agencies to take necessary measures.

Humanitarian situation

The scale, severity and complexity of humanitarian needs suffered further worsening in 2023 due to the economic downturn resulting in some of the most challenging humanitarian conditions experienced in the past twelve years of the crisis: topped by the aftermath of the earthquake that hid the northern parts of Syria in February 2023, besides the rising cost of commodities and sharp devaluation of the local currency, especially as of the second half of 2023; scarcity of fuel and shortening of electricity connection hours, all in addition to various protracted socioeconomic impacts of COVID-19; the collapse of the Lebanese economy; sanctions; and climate change-induced events such as droughts.

As a result, risks of GBV; the likelihood of de-prioritization of women’s health, antenatal and postnatal care; de-prioritizing children’s education in return for sending them to child labour; hostility; and criminal actions all had severely increased, along with disrupted and deteriorated access to life-saving sexual and reproductive health services, as well as essential GBV services. Additionally, the severe increase in financial burdens on families to maintain their access to basic needs on top of the increased costs of agricultural inputs and other livelihood sources may disrupt the gains made to sustaining livelihoods that were achieved through the JP interventions.

Integration and coordination

Each of the participating UN agencies has its own mandate, expertise, and specific programmes, and some of the agencies’ programmes share similar aspects and technical characteristics. This fact presented a key challenge to finding synergies, where interventions are streamlined to tackle the most opportunities for complementarities to maximize effectiveness and impact, as the JP is intended by nature to be conducted jointly. The PMU utilized the bi-weekly TWG meetings approach to share updates on the progress of UN agencies’ implementation of the JP activities, discuss challenges and present common solutions for better coordination and more harmonized activities on the ground. This helped to a large extent in overcoming coordination challenges. Additionally, the PMU created a communication working group (CWG) and also held area based TWG meetings with technical field staff during field missions, hence extending and enhancing the coordination efforts at the technical field level.

Financial

Exchange rate related: The gap between the official exchange rate of the US dollar to the Syrian pound and the unofficial market rate remained a key financial challenge in 2023 and is still negatively impacting the UN operations in general, since the UN agencies have to apply the official rate in transactions with local IPs, while when they procure services, supplies and/or materials for projects, they are challenged with prices inflated according to the unofficial rate. The UN agencies, especially WFP, are closely monitoring the changes in market prices of many commodities and supplies and circulate frequent updates. The UN agencies are required to use the official rate in transactions with IPs and contractors, which inevitably imposes some burden on execution of required works and provision of services. The flexibility of the JP to absorb further interested donor funds might provide a solution to cover the gap should additional donor funding become available.

Operational

Operational challenges are usually relevant to UN agencies’ internal procedures with regards to procurement and financial transfers to implementing partners. In some cases, when the procurement value exceeds a certain threshold, the case needs to be referred to the regional office of a given agency for review and clearance. Recognizing that procurement planning plays a critical role in expediting implementation, the JP PMU with the TWG members explored various opportunities to enhance joint procurement, where two or more agencies would collaborate to implement a joint intervention or to complement each other work by means of sharing the technical studies and/or assign the procurement task to one of the agencies, hence saving time and cost dedicated for administrative processes.

Implementing partners related

Generally, agencies face the issue of a limited number of qualified IPs who can implement activities with expected quality and reach, and, in some cases, agencies have to directly deliver their interventions, which inevitably adds additional burden and time. In cases where the IPs’ performance and capacities are not up to the standards of UN agencies as evaluated through the framework of a Harmonized Approach to Cash Transfers, agencies may suspend or put on hold contracts with IPs and share such information with other UN agencies.

The lack of qualified IPs at local level in the targeted locations remained a challenge for all JP PUNOs. To mitigate this challenge, agencies exerted good efforts in building the capacity of their current and prospective IPs, whether through JP interventions or through their own mandates.

Other challenges

The absence of a UN Hub in Dara’a governorate, along with intermittent access challenges in some parts of western and eastern rural Dara’a, continued to pose a challenge to regular follow-up, coherent planning, and joined-up coordination with external partners.

Furthermore, in both currently targeted locations Dara’a and Deir ez-Zor, the seasonality nature of agriculture production and the timeline to implement relevant activities were hampered by internal procurement delays as well as cumulative delays related to vetting processes and discussions with the JP donors, where in some cases, FAO, for example, had to amend timelines of relevant agricultural activities, consequently delaying the intended response until the following season.

In other cases, under education sector’s interventions, it was noticed that OoSC tend to be absent from their programmes due to other family responsibilities, which hindered their access to the NFE programmes and remedial classes for OoSC offered by UNICEF and its implementing partners. This challenge was mitigated by piloting the WFP cash-based assistance to children enrolled in NFE programmes in addition to those enrolled in the formal expedited Curriculum B.

The negative vetting results of some initially selected bidders, along with the UN internal procurement rules that prevent them from moving the selection to the second-best bidder without legal basis for the disqualification of first bidder, played a role in delaying implementation as the concerned agencies resorted to cancelling the bid and reannouncement, thus consuming additional time. Some of the red-lighting vetting feedback resulted in cancellation of some activities that were already approved. The relevant PUNOs who cancelled activities as per vetting results amended the activity matrix and diverted funds to support and/or expand on other activities in the same location or in the other location.

Some adopted mitigation measures

Some of the mitigation measures taken include but are not limited to: The JP Manager with support from the Resident Coordinator Office and PMU staff continued a dialogue and liaison with relevant national and local governmental entities and adopted an effective approach, embodied through the establishment of the JP task force that includes representatives from key relevant government entities to facilitate discussions and implementation on the ground.

Also, the last extension of the JP until 31 December 2023 helped the JP UN agencies that have seasonal interventions (FAO and WFP) to implement their activities on schedule while helping all other PUNOs to cover up for earlier procurement-related and vetting delays and other limitations due to internal and/or external factors, besides delays caused indirectly by the aftermath of the earthquake of February 2023, which caused the UN agencies to shift their activities and resources to focus on quick humanitarian response in the devastated areas. . UNICEF, along with its IPs, frequently discussed alternative approaches to enable better access to their programmes for OoSC (i.e., offering support classes during weekends). FAO and WFP continued to apply flexibility and prepare alternative plans to counter the effects of procurement and/or vetting delays, where for example, a given delay in procuring winter agricultural inputs can be flexibly switched to procuring summer inputs.

To cover for time and costs related to procurement processes, UNDP and UN-Habitat applied flexibility in terms of joining efforts to conduct planned civil works in the same geographic area. Both agencies adopted a one-design for a technical study to rehabilitate a public farmers market in Deir ez-Zor and applied a one-procurement process to increase efficiency and reduce the lead time and costs associated with the relevant administrative procedures.

# V. Lessons learned

Being continually appraised of external factors

- Sharing updated assessment findings on humanitarian status as well as on security and accessibility to projects’ locations enabled agencies to apply any needed changes in their workplans to respond to population resilience needs under the fluid and complex Syrian context. This could be achieved through analysis and consolidation of feedback collected through regular field monitoring visits by staff as well as feedback from local coordinators, IPs, and third-party monitors.

- Continuous monitoring of local markets status with regards to availability of workforce, work tools, supplies, and materials, in parallel with monitoring inflation and the exchange rate fluctuations and its trends, helped to better estimate costs and lead to more efficient budgeting.

- There was a keen need to continually monitor and address the climate change effects on people’s resilience in the targeted locations, especially since rural livelihoods depend mainly on the availability of water resources, which are hampered by several drought-like conditions.

Continual engagement with donors

- Continual engagement with donors and extended discussions regarding vetting results proved effective; while it may have consumed considerable time, yet it helped in bridging gaps of understanding at both PUNOs and donor ends and supported reaching common ground.

- Conducting, whenever possible, field visits to JP implementation sites for current and prospective donors’ representatives significantly helped donors to better appraise the situation on the ground, get a better view of JP achievements and have a more in-depth understanding of challenges.

Enhancing aspects of planning, coordination of implementation, and operations

- Joint planning, coordination and discussion among the participating UN agencies and the formulation of joint activities and services along with substantive consultations with local stakeholders lead to a more integrated design and planning of activities and more efficient allocation of resources.

- Applying joint procurement where possible could minimize the lead time for procurement and capitalized on UN agencies’ strengths and core competencies.

- Periodical discussions with stakeholders at national level represented by the JP taskforce and at subnational levels with local technical staff and local community laid the ground for a more effective participatory approach in area-based planning and implementation, while simultaneously facilitated access and mitigated any emerging challenges and risks facing implementation on the ground.

- Continual coordination between the JP PUNOs’ technical field staff in Dara’a and Deir ez-Zor and the JP PUNO focal points in central offices lead to achieving more solid complementarities and triggered innovative ideas to further enhance planning efforts at PUNO central offices. Furthermore, it fostered closer monitoring and sharing of findings to troubleshoot and resolve any emerging technical issues or obstacles in implementation in a timely manner. Additionally, field staff obtained better comprehension of access and security aspects and were able to provide timely information to central offices to manoeuvre implementation and field missions.

- Having a dedicated gender specialist to focus on gender equality and gender mainstreaming was key to helping agencies better design interventions that address gender, protection, and other cross-cutting issues.

- Context sensitivity monitoring needed to be further enhanced at planning and implementation levels. Having experts to provide knowledge and expertise to the JP PUNOs key focal points proved useful.

- Involving vulnerable segments of society (i.e., young people, women and PwD) in assessments such as the Youth-Led Market Assessment and introducing new topics for discussion such as the impact of climate change on resilience along with combining the consultations with natural resources assessment studies and reports proved a good approach to help add new dimensions to the conducted assessments. It provided the JP PUNOs with additional knowledge to design interventions that effectively address resilience needs and ensure that interventions are environment-friendly and do not create any harm on the sustainability of natural resources.

- Continual and periodic awareness-raising campaigns and sessions with caregivers and families of OoSC helped to a large extent in highlighting the critical need for education and the importance of keeping children in school.

- Online sessions and distance learning modalities need to be identified for the next project phase in response to the challenges and lessons learned from COVID-19 lockdowns, and in light of the emergence of other medical conditions that may require quarantine and/or natural disasters that render learning spaces unusable. Using these new modalities will improve the impact of education programmes. More investments are needed in delivering a blended approach for remote learning, which requires teachers and parents of children, who play a critical role in distance learning and learning recovery, mental health, and psychosocial support, to promote children’s well-being.

- There is a need to strengthen digital and remote access, which also includes the need to improve tools and guidance on remote monitoring and follow-up with the implementing partners.

- There is a need to address some of the barriers to education among CwD. UNICEF (with other funding sources) aims to provide training to education staff on best practices in CwD inclusion, which also comprises the provision of specialized supplies for trained personnel to ensure that children with symptoms are supported according to their specific needs.

# VI. Opportunities

Collaboration between UN Agencies creates synergies that reinforce the benefits of the interventions. The six UN implementing agencies have a wealth of experience from implementing activities within Syria and in similar contexts globally. The central aspect of the Joint Programme and neighbourhood planning approach is to build upon and maximize the synergies between the existing programming tools and activities of the UN agencies in a way that is locally owned and able to overcome the challenges facing sustainable resilience-building activities. Ongoing interventions have highlighted the importance of promoting social cohesion among population groups in targeted areas, particularly those hosting a high number of displaced people.

As the JP progressed effectively on the ground, agencies have capitalized on their hands-on experience under the JP in jointly harmonizing the implementation of Deir ez-Zor and Dara’a phase II workplans, while overcoming many drawbacks of the Dara’a phase I workplan. Additionally, the local stakeholders in both locations, based on their involvement in the bottom-up planning process, became more enthusiastic about supporting implementation and providing feedback.

Italy has joined the cohort of JP donors’ with a contribution of 2 million euros, that were signed in late 2022 and paid in early 2023 to fund the JP Phase II, where the initial contributions of 2 million euros will enable the JP to sustain some of the gains made in both current locations, Dara’a and Deir ez-Zor, by maintaining some key activities supporting people’s resilience.

Furthermore, in 2023 Denmark has also joined the cohort of the JP donors with a contribution of 50 million Danish Kroner (DKK) to support the JP expansion to the new location (ALEPPO governorate) based on the UNJP 2.0 programme document, while an additional contribution of 4 million euros from Italy will support the UNJP 2.0 in Aleppo.

# VII. Annexes

## Annex A: JP Syria Dara'a Phase 1 Activity Matrix Update 31 December 2023 (Also attached separately on A3-size PDF for print)

## Annex B: JP Syria Dara'a Phase 2 Activity Matrix Update 31 December 2023 (Also attached separately on A3-size PDF for print)

## Annex C: JP Syria DEIR EZ-ZOR Activity Matrix Update 31 December 2023 (Also attached separately on A3-size PDF for print)

## Annex D: JP Syria Activity Status Analysis at Outcomes Outputs levels 31 December 2023 (Also attached separately on A3-size PDF for print)

## Annex E: JP Syria M&E framework Dara’a 1 Target vs. Reach Sheets End of 2023 (Also attached separately on A3-size PDF for print)

## Annex F: JP Syria M&E framework Deir ez-Zor Target vs. Reach Sheets End of 2023 (Also attached separately on A3-size PDF for print)

## Annex G: JP Syria M&E framework Dara’a 2 Target vs. Reach Sheets End of 2023 (Also attached separately on A3-size PDF for print)

## Annex H: UNJP 2.0 Programme Document (attached Separately as PDF)

The UNJP 2.0 Programme Document was shared with Denmark, Italy, Switzerland, Sweden and Norway. It was endorsed and based on which, Denmark contributed 50 million Danish Kroner and Italy committed to contributed 4 million euros. Denmark already signed the contribution agreement and paid 25% of the contribution, while the signature of contribution agreement with Italy is being followed up by the time of drafting this report.

## Annex I: FAO’s Assessment report for rehabilitation of small-scale irrigation structures in Dara’a

Rehabilitation of small-scale irrigation systems in Dara’a, Syria

Under

UN Joint Programme to Strengthen Urban and Rural Resilience and the Conditions for Recovery in Syria

Abstract about the Natural Resource Assessment report

More than ten years of the Syrian crisis has caused serious damages to the key socio-economic infrastructure deteriorating people livelihood and stability. This crisis, combined with frequent drought events, has resulted in negative impacts on all sectors especially the irrigation and agriculture sectors. Rehabilitation of these sectors is a resilient action to regain agricultural production, improve livelihoods and prevent further deterioration of the country’s natural resources. Since natural resources assessment can give a detailed picture needed for suggesting sustainable resilient interventions, FAO-Syria has recently played a pioneering role in assessing natural resources in different areas of Syria. An analysis of the state of natural resources in two severely damaged areas of Syria, Dara’a and Deir ez-Zor were produced in order to determine the feasibility of interventions for sustainable agricultural production and rural livelihood support.

This NRA report covers the natural resources assessment in Dara’a district. Great reliance was placed on remote sensing techniques and hydrological modelling in carrying out this work. While remote sensing offers a large opportunity to monitor and manage natural resources at multi-temporal and multi-spatial resolution, hydrologic modelling helps in understanding, predicting, and managing natural resources at watershed and sub-watershed scales. The integrated use of remotely sensed data and the hydrologic modelling, especially the use of physically based models, helps in prioritizing and characterizing the appropriate interventions, developing plans for effective and sustainable management of natural resources, and predicting the long-term impacts of the proposed interventions as well as the impacts of climate change on natural resources. The methodology used in this project adopted the concept of the integrated use of remote sensing and hydrologic modelling. It can be summarized in making use of all available ground data, remotely sensed-derived data, and hydrological modelling outcomes to prioritize interventions regarding their potential impact on increasing agricultural production on the one hand and sustaining existing natural resources on the other.

A set of well-defined criteria was selected to assess the feasibility of each potential intervention, the optimal sites for implementation, estimated cost-benefits, and potential social and environmental impacts. Among the most important criteria that have been relied upon in selecting the most priority interventions are: i) the sustainability of water resources, particularly ensuring that groundwater is not depleted; ii) promoting sustainable environmental utilization of seasonal surface water resources through rainwater harvesting structures; iii) and sustainable use of land resources through promoting best land management practices.

The Soil and Water Assessment Tool (SWAT) was used in this study to simulate the different hydrological processes and quantify the impact of land management practices at watershed/sub-watershed scales. SWAT relies on physical equations to describe the relationship between input and output variables; therefore, it can legitimately be proposed for modelling watershed with little monitoring data. SWAT was successfully run on a daily time step covering the time period 1991-2019 (29 years). The required land use map for running the model was derived from high-resolution satellite imageries, whereas the required soil type map was produced using 94 soil profiles in combination with landform units and slope. Monthly measurements of storage volume from about 20 reservoirs were used to assess the simulated surface water balance in Dara’a district. Comparing the measured values with the simulated ones showed good agreement. Besides, groundwater model was also developed to represent the groundwater system and develop future predictive scenarios that reflect the impact of human activities and climate change on the available water resources.

In addition, FAO’ databases and portals were also widely used in this project, for example, Gross Biomass Water Productivity (GBWP) and Total Biomass Production (TBP) were taken from the FAO Water Productivity Portal (WaPOR), whereas valuable remote sensing derived indices for monitoring the drought and agricultural heath, such as Agricultural Stress Index (ASI) and Mean Vegetation Health Index (VHI), were obtained from the FAO-GIEWS (Global Information and Early Warning System). The FAO CropWat software was also used for calculating water and irrigation requirements of the crops cultivated in the study area based on soil, climate, and crop data. On the other hand, the results of the chemical analyses of groundwater in the study area showed values that are within the permissible limits (standards) for most of the collected samples, and it can thus be used for drinking, agricultural, industrial, and household uses. Information about the socio-economic conditions and humanitarian needs were collected and analysed at the community and sub-district levels.

A group of interventions have been proposed based on the analysis of the results of the natural resources assessment in consultation with farmers as well as specialists from the relevant entities. As examples of the proposed interventions, we mention the rehabilitation of wells (in areas that do not suffer from groundwater depletion), rainwater harvesting structures, pumping stations, and irrigation canals.

Finally, the optimal sites and characteristics for the proposed interventions were chosen using the suitability analysis (overlay analysis) that relies on integrating the normalized weights of the parameters affecting the selection of each intervention. For example, the groundwater depletion was supposed to be the most affecting parameter in producing the suitability map for rehabilitating groundwater wells, whereas the potential runoff was considered the most affecting parameter in producing the suitability map for building/or rehabilitating rainwater harvesting structures.

In conclusion, the integrated use of remotely sensed data and the hydrological modelling implemented in Dara’a district has assisted in identifying appropriate interventions for increasing agricultural production through sustainable use of natural resources. Application of this approach has resulted in identifying locations for sustainable use of surface and groundwater resources for agricultural investment. This encourages further development and application of this approach in other areas of the country.

Project summary

| Intervention/subproject title | Rehabilitation of small-scale irrigation systems in Daraa, Syria |
| --- | --- |
| Project title | UN Joint Programme to Strengthen Urban and Rural Resilience and The Conditions for Recovery in Syria |
| Project symbol | UNJP/SYR/022/EC |
| Implementing agencies | FAO |
| Budget | 425,000 USD |
| Implementation period | 3 months |
| Targeted Areas | - The following 5 locations: Al Kokliah, El-Taebah Jizah, Mktal albint, Nassib alfayiz and Umahat Al Yadudah for the rehabilitating 5 groundwater wells within the green belt area - Gadeer Al Bustan for the main/branch canals and Nawa for the field irrigation canals |
| Direct beneficiaries Indirect beneficiaries | Direct: 18,500 HH |
| Activities | Activity A: Rehabilitation of farmers’ field irrigation system in Gadeer Al Bustan - Light rehabilitation for the main open channel flow (1.5 m3/s, length 25 km, flume structure, rectangular, and trapezoidal sections), and the water intakes on the main canal in order to let water flow through and reach branched field irrigation canals. - Rehabilitation of field irrigation canals downstream Nawa Activity B: Rehabilitation of 5 groundwater wells for farmers of small-scale agricultural activities in the Green Belt areas: Al Kokliah, El-Taebah Jizeh, Mktal albint, Nassib alfayiz, and Umahat Al Yadudah groundwater wells. |
| Linkage to FAO’s Strategic Framework: | The project is in line with the two regional Initiatives on Water Scarcity (WSI) and on Small-Scale Family Farming (RI SSFF) |

Rehabilitation of small-scale irrigation systems in Daraa, Syria

Background:

Priority areas for sustainable interventions were identified within Dara’a district based on desk studies and remote sensing assessment for Dara’a watershed. Small-scale irrigation structures that require rehabilitation works were listed based on the field survey findings and analysis of the assessment in consultation with local stakeholders. Two types of activities were proposed: Rehabilitation of groundwater wells and rehabilitation of surface irrigation canals. Figure 1 shows the proposed activities in the targeted area.

Figure 1. Proposed activities in the targeted area

Assigned activities:

FAO studies the stakeholders proposed activities for vulnerable farmers and advised of rehabilitation of the groundwater wells located in suitable areas in terms of the needs, soil and sustainable use and the surface field irrigation system in the target district.

Further discussion with the donor (EU) resulted in the agreement to implement two the following activities:

Activity A:

Rehabilitation of farmers’ field irrigation system in Gadeer Al Bustan

The targeted area is within the irrigation scheme of Ghadeer Al Boustan Dam (10.8 MM3). The work includes:

- Light rehabilitation for the main open channel flow (1.5 m3/s, length 25 km, flume structure, rectangular, and trapezoidal sections), and the water intakes on the main canal in order to let water flow through and reach branched field irrigation canals

- Rehabilitation of field irrigation canals downstream Nawa

Activity B:

Rehabilitation of 5 groundwater wells for farmers of small-scale agricultural activities in green belt areas: Al Kokliah, El-Taebah, Jizeh, Mktal albint, Nassib alfayiz, and Umahat Al Yadudah groundwater wells.

The Green belt wells were drilled and equipped by the local Directorate of Agricultural in the 1980s in order to provide water through tankers to farmers and householders for supplementary irrigation and to herders for livestock drinking use. The wells and green belt area (olive trees mostly) are located within farmers’ lands.

Table 1 below gives some details regarding the proposed activities. They will be supported through establishing water users’ associations and running a number of trainings to manage irrigation in targeted areas, fairly distribute water among beneficiaries, operate and maintain the water distribution systems.

| Proposed Activity (Figure 2) | General information |
| --- | --- |
| - Rehabilitation of farmers’ field irrigation network: Ghadeer Al Boustan irrigation network | The canal requires light rehabilitation works to be refunctioned. The work includes: - Light rehabilitation of the main open channel, 25 KM, 1.5 m3/s, mainly the first part (5kM) and the flume structure that supply water to the downstream irrigation networks. - Rehabilitation of the field irrigation network downstream Nawa. The work includes rehabilitation of the pipeline system and its field water intakes. With this work, the surplus water can flow down to Shaikh Maskeen dam, downstream the canal Rehabilitation works would: - Allow groundwater recharge through surface/flood field irrigation - Prevent evaporation from the dam lake (10.8 MM3) and allow farmers to use it for irrigating their crops This would in turn reduce amount of pumped groundwater and sustain aquifers from depletion. Water flow with earthen canals will also allow shallow groundwater recharge (Wells in the surrounding area will indirectly be recharged) - Improve farmers’ livelihoods and reduce agricultural input costs (costs of pumping ground water) |
| - Rehabilitation of groundwater wells: green belt wells | - The wells were drilled and equipped by the local directorate of agricultural in the 1980s. They used to provide water through tankers to small-scale farmers, householders and herders for supplementary irrigation and livestock drinking use. - Activity will be supported through establishing water users’ associations and training to fairly distribute water among beneficiaries, operate and maintain the rehabilitated wells - Sustainability is ensured through selecting wells within groundwater promising aquifers - Solar powered pumping system will be implemented - Farmers’ cooperation will be encouraged through establishing WUAs for operating and maintaining the system - Herders and local farmers’ livelihoods are expected to be improved - Improving agricultural production and increasing number of opportunities for labour works is expected |

Estimated costs, beneficiaries, and target area:

| Proposed Activity | No. of proposed wells to be targeted | Area proposed to be irrigated/or supplementary irrigated, ha | Beneficiaries, HH | Estimated cost, USD | Remarks |
| --- | --- | --- | --- | --- | --- |
| - Rehabilitation of farmers’ field irrigation network: Ghadeer Al Boustan irrigation network |  |  |  |  |  |
| 1. Rehabilitation of main open channel | - | 3700 ha | 15,000 HH (direct) including livestock keepers 10,000 HH (indirect) | 105,000 |  |
| 2. Rehabilitation of field irrigation canals | - | 600 ha | At least 1,500 HH (direct) including livestock keepers 4,000 HH (indirect) | 120,000 | This work cannot be implemented without rehabilitating the main canal |
| B. Rehabilitation of groundwater wells: Green Belt wells |  |  |  |  |  |
| For 5 wells | 5 | 350 ha | Expected No of beneficiaries for each well: 400 HH (direct) including livestock keepers 500 HH (indirect) Total: 2000 (direct) 2500 (indirect) | 200,000 | Beneficiaries include herders and householders |

Table 1 details regarding the proposed activities in Darra

Figure 2 Location of the assigned two activities in Daraa

Sub-activities for the activities A and B:

Activity A:

Rehabilitation of farmers’ field irrigation network: Ghadeer Al Boustan irrigation network

The targeted area is within the irrigation scheme of Ghadeer Al Boustan Dam. The work includes rehabilitation for the main open channel, the water intakes on the main canal for the field irrigation network in Nawa. District: Darra, Sub-district: Nawa; Figures 3 and 4. Figure 5 shows example o of the damaged pipelines.

Figure 3: Map of the field irrigation system and main open channel flow

Figure 4: Targeted field irrigation network in Nawa

| Activity | Sub-activity |
| --- | --- |
| - Supply and install reinforcement concrete works. - Supply and install concrete works. - Supply, install and carry-on hydraulic tests for all (GRP, P.V.C) pipes, joints, reducer, flange, and assemblies - Metal/steel works. | - Rehabilitation of the main open channel flow (Length 25 km, flume structure, rectangular, and trapezoidal sections) - Earth work - Reinforcement concrete work - Plain concrete work - Metal works for the vertical control gates |
|  | - Rehabilitation of the field irrigation system - Earth work (excavation and backfill): 13810 M.L - Supply, install and hydraulic tests for all GRP pipes, joints, reducer, flange, and assemblies: 385 M.L - Supply, install and hydraulic tests for all P.V.C pipes, joints, reducer, flange, and assemblies: 13005 M.L - Metal works (gates, fittings): 1600 kg |

Figure 5: Damages in the main open channel flow within the field irrigation system

Activity B:

Rehabilitation of groundwater wells: Green Belt wells

B.1. Main criteria for selecting the groundwater wells

- The well shall be located in a promising area for sustainable use of groundwater for agriculture based on the produced map of suitable areas for the rehabilitation of groundwater wells in Dara’a, Figure 6

- Farmers shall agree to establish a water users’ association/group to operate and maintain the rehabilitated system. The management board shall be elected to be responsible for fair and efficient distribution of water. A signed and stamped declaration that the implemented system shall be managed by the members of the WUA that will be established.

- Farmer who owns the groundwater well shall agree to share the water resource with neighbouring farmers and herders.

- Farmers should belong to vulnerable groups (low income, family member with special need…)

Figure 6: Locations of the 5 green belt wells on the map of the suitable areas for the rehabilitation of

groundwater wells in Dara’a,

B.2. Coordination of selected groundwater wells for rehabilitation activities and establishing WUAs:

|  | Name of the selected groundwater well (green built well) | Geographic coordination |  |  |
| --- | --- | --- | --- | --- |
|  |  | N | E | Main activities |
|  | Al Kokliah Well | 32°39'5.73" | 36° 1'44.77" | - Rehabilitation of the groundwater well including the mechanical and electrical equipment - Civil work: Service room and the water tank - Solar power energy for pumping the water - Establishing of Water Users Associations and training |
|  | El-Taebah geezah well | 32°33'48.69" | 36°16'43.46" |  |
|  | Mktal albint well -Al Badia | 32°32'51.47" | 36° 8'35.84" |  |
|  | Nassib alfayiz well | 32°33'1.72" | 36° 9'35.85" |  |
|  | Umahat Al Yadudah well | 32°41'19.84" | 36° 3'46.98" |  |

B.3. Beneficiaries:

The area to be served by irrigation is in total 350 ha, Table 2 presents details for every well.

|  | Name of the selected groundwater well | Beneficiaries | Area to be irrigated/supplementary irrigated | Volume of water to be made available M3/day |
| --- | --- | --- | --- | --- |
|  | Al Kokliah Well | Direct 2000 HHs Indirect 2500 HHs | 350 Ha | 216 m3/day |
|  | El-Taebah geezah well |  |  | 480 m3/day |
|  | Mktal albint well -Al Badia |  |  | 240 m3/day |
|  | Nassib alfayiz well |  |  | 240 m3/day |
|  | Umahat Al Yadudah well |  |  | 240 m3/day |

Table 2 Details for targeted wells

B.4. Sub-activities for every selected groundwater well:

- Kokliah groundwater well.

Location: District: Darra, Sub-district: Mzeireb

| Activity | Sub-activity |
| --- | --- |
| - Rehabilitation and installation of submersible pump with electric motor and related fittings and accessories - Solar power system for pumping ground water | - Conduct well-cleaning and development (405m) - Supply, install and test the discharge pipe (18 bar -170m) - Supply, install and test a submersible pumping unit: Q=18 m3/hr., H=200 m with all needed fittings and accessories - Supply a solar pumping system for the submersible pumping unit - Repair, fix and rehabilitation all required civil works for the service room |

Figure7: Kokliah groundwater well

- El-Taebah geezah groundwater well.

Location: District: Dara’a, Sub-district: Jizeh

| Activity | Sub-activity |
| --- | --- |
| - Rehabilitation and installation of submersible pump with electric motor and all related fittings and accessories - Solar power system for pumping water | - Conduct well cleaning and development (300m) - Supply, install and test the discharge pipe (20 bar -230m) - Supply, install and test a submersible pumping unit: Q=40 m3/hr., H=190 m with all needed fittings and accessories - Supply a solar pumping system for the submersible pumping unit. - Repair, fix and rehabilitation the civil work of service room |

Figure 8: El-Taebah Geezah groundwater well

- Mktal albint groundwater well -Al Badia.

Location: District: Darra, Sub-district: Dara’a

| Activity | Sub-activity |
| --- | --- |
| - Rehabilitation and installation of submersible pump with electric motor and all related fittings and accessories - Solar power system for pumping water | - Conduct well cleaning and development (288m) - Supply, install and test discharge pipe (20 bar -225m) - Supply, install and test a submersible pumping unit: Q=20 m3/hr., H=225 m with all needed fittings and accessories - Supply a solar pumping system for the submersible pumping unit. - Repair, fix and rehabilitation the civil work of service room |

Figure 9: Mktal albint groundwater well -Al Badia

- Nassib alfayiz groundwater well.

Location: District: Dara’a, Sub-district: Dara’a

| Activity | Sub-activity |
| --- | --- |
| - Rehabilitation and installation of submersible pump with electric motor and all related fittings and accessories - Solar power system for pumping water | - Conduct well cleaning and development (285m) - Supply, install and test discharge pipe (20 bar -185m) - Supply, install and test a submersible pumping unit: Q=20 m3/hr., H=210 m with all needed fittings and accessories - Supply a solar pumping system for the submersible pumping unit. - Repair, fix and rehabilitation the civil work of service room |

Figure 10: Nassib Alfayiz groundwater well

- Umahat Al Yadudah groundwater well.

Location: District: Darra, Sub-district: Mzeireb

| Activity | Sub-activity |
| --- | --- |
| - Rehabilitation and installation of submersible pump with electric motor and all related fittings and accessories - Solar power system for pumping water | - Conduct well cleaning and development (380m) - Supply, install and test discharge pipe (20 bar -190m) - Supply, install and test a submersible pumping unit: Q=20 m3/hr., H=200 m with all needed fittings and accessories - Supply a solar pumping system for the submersible pumping unit. - Repair, fix and rehabilitation the civil work of service room |

Figure 11: Umahat Al Yadudah groundwater well

The term ‘programme’ is used for programmes, Joint Programmes, and projects.

Strategic Results, as formulated in the Strategic UN Planning Framework (e.g., UNDAF) or project document.

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as ‘Project ID’ on the project’s factsheet page, the MPTF Office GATEWAY.

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date, which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

The public market area was completed, by the date of submitting the report,

https://drive.google.com/file/d/1DmcsULbw5B5yckpzvCxj-cvmFcCEpWIW/view?usp=sharing

Mukhtars are locally elected members of the community to represent a given neighbourhood located in an urban or rural location.

Out of the supported 1,784 CwD, 578 were children with severe disabilities targeted with tailored educational activities. The remaining 1,206 were children with moderate disabilities targeted along with their peers with inclusive educational activities.

When the partnership was signed with the local NGO in late 2020, the USD value was 700 SYP. The USD value has fluctuated throughout the years to 1,250 SYP, then to 2,500 SYP. We have been amending the budget periodically, and with the savings (getting more Syrian pounds for the same dollars) we conducted no-cost extensions to the partnership, enabling the partner to reach more children using the same budget.

UNDP defines solid waste management in Dara’a as the collection and removal of municipal waste generated from household and commercial activities and defines debris collection and removal as the removal of debris from main streets in the city, including residential, commercial and industrial neighbourhoods. Emergency jobs are created for workers from the local community in both subsectors (debris and waste removal). Management entails a three-month awareness campaign aimed at behaviour change of communities regarding solid waste.

Mayadeen city south of Deir ez-Zor city was approved as an additional location to implement the WFP’s voucher activity for children enrolled in Curriculum B due to high concentration

Upon the kickstart of the JP in DEIR EZ-ZOR there were very few workshops (mechanics…etc.) operating in the industrial area. By late 2022 80 workshops were rehabilitated through the JP, and this attracted and expedited voluntary return of other workshops owners. By June 2023 there were about 400 workshops opened and operating. According to the Deir-e-Zor chamber of industry records

The DEIR EZ-ZOR awareness campaign initiated targeting 20 female-headed households to introduce and train the female on sorting and recycling activities (two participants initiated a small business from recycling).

The installation of solar lights by UNDP was not completed by the end date of the programme on 31-12-2023, due to various challenges related to procurement and vetting, which caused delays

Temporary jobs refer to the workers and labourers who worked on rehabilitating the Al Hamediyeh health centre under the supervision of the contractor. Such jobs include plumbers, electricity workers, glass and aluminium workers, painters, etc. The Al Hamedieh health centre suffered some minor damage due to the explosion of an unexploded ordinance in neighbouring abandoned building, then followed by the earthquake of February2023

The activity was not completed by the designated end of the programme on 31 December 2023, and needed additional time until end of Q1 2024, therefore, and due to its importance in supporting small and seasonal livelihoods and to avoid doing harm to the communities who were anticipating it, the relevant agencies completed it using other sources of funds. The public market area was completed, towards end of March 2024 – by time of preparation of this report.

Four rounds of transfers have been processed, and the value of each transfer is 8.7 USD

The IP (Syrian Society for Social Development; SSSD) is implementing the majority of activities in Dara’a. Under this activity SSSD has engaged 10 young people in UNMAS certified training on Basic Learning on Mines and UXOs; then the trained individuals will conduct awareness sessions in several rural and urban communities in Dara’a. Because mines and UXOs are sensitive topics in the Dara’a context, the government counterpart informed SSSD that they need to get a specific approval for these activities before they implement.

SMEs refer to small craftsmen shops (carpentry, blacksmithing, automobile repair, little bakeries for deserts, tailors, aluminium workers, painters, etc.).

The first one is positioned in the nearby Harabish suburban neighbourhood of Deir ez-Zor city, while the other two are in the western and eastern rural areas (Al Shemitieh village and Marat village).

For more information on the CWC and SP functions, please visit the link: https://drive.google.com/drive/folders/1yWhFCp0tI843_5i-It8sixvjc0biKkV_?usp=share_link.

The total figures of beneficiaries during the implementation period are reflected in the reach figures in DEIR EZ-ZOR monitoring framework annexed to this report

Paid in Syrian pounds according to the official exchange rate.

By the end of 2023, DENMARK approved a 50 million DKK and ITALY approved a 2 million EUROs contribution to the UNJP 2.0. DENMARK already paid 25% of their contribution.

By end of July 2023 the official exchange rate against the USD was set at 3000 SYP, then at the beginning of August it was increased to 8,500 SYP, then increased to 11,500 SYP by the beginning of October 2023, then towards the beginning of December 2023, it was increased to 12,500 SYP and maintained until the writing of this report, where it accounts for about 87% of the unofficial rate.

Curriculum B is an expedited formal education programme, managed by the Department of Education, to help children who lost years of education due to the crisis catch up with their peers. WFP is supporting vulnerable children enrolled in this programme with vouchers, conditional to attendance.

Updated activity matrices are attached to the report separately in A3-size PDF format.

FAO carried out a natural resource assessment for the entire watershed that contains Dara’a district.