Partnership for Action on Green Economy (PAGE)

MPTF OFfice GENERIC finalprogramme NARRATIVE report

REPORTING PERIOD: from July 2017 To December 2022

| Programme Title & Project Number |  |  | Country, Locality(s), Priority Area(s) / Strategic Results |  |
| --- | --- | --- | --- | --- |
| - Programme Title: UNEP/GGKP – PAGE Workplan (Global Activities) - Programme Number (if applicable) - MPTF Office Project Reference Number: 106751 |  |  | (if applicable) Country/Region |  |
|  |  |  | Priority area/ strategic results |  |
| Participating Organization(s) |  |  | Implementing Partners |  |
| - Organizations that have received direct funding from the MPTF Office under this programme UN Environment Programme / Green Growth Knowledge Partnership |  |  | - National counterparts (government, private, NGOs & others) and other International Organizations |  |
| Programme/Project Cost (US$) |  |  | Programme Duration |  |
| Total approved budget as per project document: USD 2,192,430 MPTF /JP Contribution: - by Agency (if applicable) UNEP: USD 2,192,430 |  |  | Overall Duration 66 months Start Date 1.07.2017 |  |
| Agency Contribution - by Agency (if applicable) |  |  | Original End Date 30.06.2020 |  |
| Government Contribution (if applicable) |  |  | Actual End date 31.12.2022 Have agency(ies) operationally closed the Programme in its(their) system? | Yes No |
| Other Contributions (donors) (if applicable) |  |  | Expected Financial Closure date: 20.11.2023 |  |
| TOTAL: |  |  |  |  |
| Programme Assessment/Review/Mid-Term Eval. |  |  | Report Submitted By |  |
| Evaluation Completed Yes No Date: 04.2023 (Evaluation of the implementation of PAGE, operational strategy 2016-2020) Yes No Date: 03.2021 (GGKP Terminal Review) Evaluation Report - Attached Yes No Date: 04.2023 |  |  | - Name: Adriana Zacarias Farah - Title: OiC, GGKP - Participating Organization (Lead): UNEP - Email address: adriana.zacarias@un.org |  |

# FINAL PROGRAMME REPORT FORMAT

# EXECUTIVE SUMMARY

The Green Growth Knowledge Partnership (GGKP) plays a pivotal role in promoting the transition to an inclusive green economy, supported by its extensive network of over 90 international organizations, research institutes, and think tanks. In collaboration with the Partnership for Action on Green Economy (PAGE), GGKP has made significant strides in global capacity development and knowledge sharing. Key achievements include:

- Online Platforms: Developed and launched the Green Industry Platform and Green Finance Platform, offering over 3,168 and 3,387 knowledge products, respectively, to support evidence-based greening decisions for policymakers, SMEs, and financial institutions.

- Green Growth Expert Connect Solution: launched in 2017, provides tailored guidance on green economy topics, notably aiding the Mongolian Ministry of Construction and Urban Development in drafting a National Green Construction Policy.

- SME Support Centre and I-GO Assistant: Shared over 600 knowledge products and conducted over 1,100 self-assessments to improve resource efficiency among SMEs and industry stakeholders.

- Green Finance Measures Database: Features over 800 policy and regulatory measures from more than 110 countries, monitoring national green finance efforts.

- Green Forum: Since its launch in February 2021, has grown to over 4,500 members, facilitating global discussions on green growth and sustainable finance with over 7,100 posts and 38 groups.

- Events and outreach: Organized major events like the “Fast, Fair and Green” side event at the 2019 UN High-level Political Forum and a series of webinars under the “Green Economy Transformation” project.

- Global Initiatives Collaboration: Launched in 2021 the Natural Capital for African Development Finance initiative, together with the African Development Bank, GIZ and World Wide Fund for Nature. Additionally in 2021, GGKP launched a Gender Expert Group co-chaired by the Global Green Growth Institute and the International Institute for Environment and Development to aid evidence-based policy development processes.

GGKP's efforts highlight its dedication to driving a global shift towards a sustainable and inclusive green economy through comprehensive knowledge sharing, expert collaboration, and community engagement.

# Purpose

The Green Growth Knowledge Partnership (GGKP) is a global network of experts and organizations dedicated to providing the policy, business and finance communities with knowledge, guidance, data and tools to transition to an inclusive green economy (IGE). The GGKP’s three knowledge platforms – Green Policy Platform, Green Industry Platform and Green Finance Platform – offer direct access to the latest research, learning opportunities and thought leadership to empower government decision makers, small and medium-sized enterprises (SMEs) and financial institutions to make evidence-based decisions about how to green their operations. A leading engine for inter-institutional collaboration, the GGKP establishes and facilitates expert groups to assess the state of knowledge on specific green economy themes, identify gaps and catalyse coordinated responses. To achieve impact, the GGKP engages in three workstreams: generating knowledge, managing knowledge and sharing knowledge.

As of 2023, the GGKP has a global partnership of over 90 international organizations, research institutes and think tanks.

GGKP collaborates with the Partnership for Action on Green Economy (PAGE) on PAGE’s global and regional services package that follows a systematic and institutionalized approach to capacity development and knowledge sharing. A key element of the global effort is to provide platforms and forums for countries and learning institutions to come together, exchange successful approaches in their green economy transformation and gain immediate insights from peer-to-peer learning. The following objectives and outputs describe how GGKP contributes to the results framework of PAGE.

Outcome 4: National and regional stakeholders, including green economy champions, decision-makers, practitioners, and youth representatives, access and apply knowledge for advancing IGE

Output 4.1 - IGE knowledge products and platforms generated/leveraged and shared

- Expert Connect Service

- GGKP to establish a new section of the existing platform for policymakers named Expert Connect Service, to submit questions and interact with experts (engaging with a minimum of 12 subject-matter experts) with a rough estimation of 240 hours of expert services per year, or 720 hours of expert services over the course of the project.

- Green Industry Platform and Green Finance Platform Development and Delivery

- GGKP to collaborate with PAGE and scale the sharing of North-South-South collaboration through the expansion of the GGKP collaborative “platform” approach to the industry and finance communities.

- These parallel platforms to provide the industry and finance communities with the latest knowledge, information, best practices, and data in an effort to catalyse a much larger impact and strengthen PAGE delivery by supporting global efforts to address critical knowledge and data gaps and stimulate collaborative project delivery.

- The work to include scoping and use needs study, defining scope of work and web development, partner outreach and engagement, content sourcing and uploading, launch of green industry and green finance platform, in addition to the service delivery, content update, outreach and monitoring over 2.5 years.

- Expert Exchange Development and Delivery

- To provide an online forum where PAGE country partners can share information and provide peer support after the PAGE country project has formally closed, thereby increasing the opportunities for sustainability of the PAGE outcomes and impacts.

- The work to include scoping and user needs analysis, defining scope of work and web development, expert outreach and engagement, launch of expert exchange, in addition to the network facilitation expansion and outreach.

# Assessment of Programme Results

- Development and launching of online platforms

During the period of 2017 to 2022, GGKP successfully developed four key products. These include two knowledge platforms, namely the Green Industry Platform and Green Finance Platform, which offer quick and easy access to the latest research, case studies, toolkits and learning products to

empower policymakers and advisers, small and medium-sized enterprises (SMEs), banks, insurance and investment firms to make evidence-based decisions about how to green their operations.

Additionally, the project introduced the Green Growth Expert Connect Solution, offering policymakers direct access to leading technical and policy experts for tailored guidance on various green economy topics. Furthermore, the Green Forum was improved and officially launched as an online interactive community space for professionals to exchange and discuss insights in support of a sustainable economic transition.

  - Launching of the Green Growth Expert Connect Solution

The Green Growth Expert Connect Solution was launched in 2017 to link up existing virtual green economy consultation services and to expand the scope of expert advice available. The solution provides policymakers direct access to leading technical and policy experts for quick and tailored guidance on a range of green economy topics. In addition, GGKP has developed an online roster of experts and led outreach to promote the usage of the Expert Connect service. For each engagement, an expert works with the policymaker to provide tailored support, including reviewing draft strategies, analysing policy options, sharing experiences and best practices from other countries, and facilitating networking with peers. In 2018, the Expert Connect service provided expert assistance to support the Mongolian Ministry of Construction and Urban Development in drafting a National Green Construction Policy, which was adopted by the parliament in February 2019. Additionally, the Expert Connect service provided expertise for reviewing and proofreading the Mongolian Green Economy Assessment Report prior to its publication in Mongolia.

Although the GGKP Expert Connect project officially ended in mid-2020, the GGKP continued to host the service until 2021.

  - Launching of Green Industry Platform and Green Finance Platform

PAGE and the GGKP launched the Green Industry Platform (GIP) and the Green Finance Platform (GFP) at the High-Level Political Forum in July 2019, addressing the importance of the two sectors’ contribution to the green economy transition. The two platforms provide easy access to the latest research, data, guidance, and tools through 193 country pages specified by region, sector or cross-cutting themes for both the financial and private sector.

Green Industry Platform

The GIP helps support SMEs become more competitive in their green transition by promoting more sustainable and profitable businesses. As of December 2023, the Green Industry Platform featured over 3,168 knowledge products, including research, case studies, guidance, tools and platforms, insights, courses and multimedia across 20 sectors and 31 themes. The platform also operates the SME Support Centre, which is an online repository of knowledge and support services on the topic of resource efficiency. Its main users are businesses, SMEs and relevant industry stakeholders.

The support centre curates resources across six main topical areas – energy, water, waste, materials, chemicals and general resource efficiency strategy. Since 2019, the Green Industry Platform has uploaded and shared over 600 knowledge products (research, case studies, technical

guidance) and support services (training, financing solutions) in the SME Support Centre. Knowledge and support services are shared through the I-GO Assistant, a resource efficiency self-assessment and navigation tool developed by the Green Industry Platform for SMEs and industry stakeholders. Since its launch in March 2022, more than 1100 assessments have been carried out.

Green Finance Platform

The GFP provides a library of market, policy and regulatory innovations driving the green transformation. The GFP further focuses on sustainable finance principles, practices and protocols for banking, investment, and insurance institutions.

As of December 2023, the Green Finance Measures Database (GFMD) within GFP comprises 800+ policy and regulatory measures across over 110 developed and developing countries. The GFMD serves as a tool for monitoring national green finance efforts while also allowing financial actors to monitor sustainable finance interventions across jurisdictions and align sustainable finance measures with global standards and best practices. As of December 2023, the total number of knowledge products featured on the Green Finance Platform is 3,387.

The platform also assumed executing responsibility for the Global Environment Facility project named ‘Aligning Finance Policies’, which focuses on the development of national Sustainable Finance Roadmaps in six countries – China, India, Kazakhstan, Mexico, Mongolia and Nigeria – and building international consensus on best practices – from policies and regulations to standards and norms – to green the financial system. As part of this effort, the Nigeria Green Banking Tagging Review was successfully launched in mid-February 2022.

  - Official Launching of the Green Forum

The Green Forum provides an online community space for professionals to share and discuss insights in the pursuit of a sustainable economic transition. It was officially launched to the public in February 2021 at the Fifth Session of the UN Environment Assembly.

The forum includes discussions on global topics and the ability for users to create dedicated groups focused on specific themes, initiatives, projects and communities of practice. It enables community members to enhance collaboration and exchange learnings to address similar challenges and identify new connections or partnerships.

Along with design and user experience enhancements, the forum improvements included a user interface redesigned community discussion and group pages, integrated community widget across all GGKP’s platforms for cross-promotion and linkages, enhanced group functionality as well as improved group management.

The Green Forum membership has reached over 4500 since its launch consisting of various stakeholders from policymakers, academics, and finance actors to the private sector. Over 7,100 posts have been published ranging from opinions, events, opportunities, knowledge, and blogs. There are currently 38 Groups that include such topics as trade, water security and green growth, and sustainable finance policy, and 16 Community Discussions, ranging from climate change and agriculture to the circular economy and blue economy. While Discussions allow users to join freely, the Groups offer a unique space for certain clusters to collaborate on specific challenges or projects while maintaining a degree of confidentiality.

  - Redesign of the Green Policy Platform

The Green Growth Knowledge Platform was renamed the Green Policy Platform to have alignment between the now three GGKP platforms, the Green Finance Platform, Green Industry Platform and Green Policy Platform. The Green Policy Platform  underwent a redesign of the initiatives pages as stand-alone websites, renamed “+Platforms” (replicated also across the Green Finance and Green Industry Platforms), and development of a Learning Hub as part of the Green Learning Network. A new landing page was also developed which links to a new “Green Learning Network” +Platform, and a new content type for Academic Programmes was added. By the end of 2023, the Green Policy Platform featured more than 10,189 green growth knowledge products, across 37 sector and thematic pages. Of these, 286 knowledge products included a gender focus.

- Events, Advocacy and Outreach

In addition to developing platforms, GGKP’s communications activities – both in person and online – facilitate connecting a dynamic global green growth community to the most up-to-date and relevant knowledge, guidance, data and tools for greening policy and practice. During the project implementation, GGKP organized three major events and webinars.

- HLPF side Event - Fast, Fair and Green

The GGKP, PAGE, and a group of institutions leading the transition to a green economy jointly organised “Fast, Fair and Green”, the official UNEP side event at the 2019 UN High-level Political Forum for Sustainable Development (HLPF). The event explored the question “How can we create an economic transition fast, fair, and green enough to achieve the SDGs and NDCs?”. The event also marked the launch of the Five Principles of Green Economy, which provide a valuable compass in the transition to sustainability, and the launch of the Green Industry Platform and the Green Finance Platform, which equip businesses and financial institutions with the knowledge guidance, data, and tools they need to equitably green their operations.

- Webinar series under the IKI project Green Economy Transformation

In 2018-2021, the GGKP convened a series of five webinars under the IKI project, “Green Economy Transformation (GET)”, in cooperation with PAGE. In 2019, the GGKP held two webinars under the GET project:

- Measuring What Matters: A new methodology for collecting and reporting data on fossil fuel subsidies (2 October 2019), which introduced a new methodology for collecting and reporting data on fossil fuel subsidies developed jointly by UNEP, OECD, and the IISD’s Global Subsidies Initiative in the context of SDGs.

- We're Here to Help: Free policy advisory services for a greener economy (29 May 2019), which presented a number of advisory services that are available free of charge to policy makers, policy advisors, and supporting institute from international organizations and development institutes to support the transition to an inclusive green economy, including how they can be accessed and utilised.

The GET project is funded by the German Federal Ministry of Environment, Nature Conservation and Nuclear Safety (BMU) through its International Climate Initiative (IKI) and is implemented by the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH and UNEP.

- High-Level Media Debate at the 2019 PAGE Ministerial Conference: “What is Wealth?”

In conjunction with the 2019 PAGE Ministerial Conference on “Inclusive and Sustainable Economies”, PAGE, GGKP and partner organisations convened thought leaders from government, business, academia and civil society for a High-level Media Debate to address the question, "What makes your country wealthy?". The panel called for new approaches to national wealth accounting that quantify natural and social capital in addition to productivity. The debate was broadcasted live on CNBC Africa. The discussion concluded with an agreement on the inherent value of nature for economies and societies, and an emphasis on the opportunities that lie ahead and the urgent need to move things forward.

- Cooperation with other initiatives

GGKP’s interactive fora enables community members to enhance collaboration and exchange learnings to address similar challenges and identify new connections and partnerships. So far, GGKP succeeded in setting up a global partnership of over 90 international organizations, research institutes and think tanks. A few examples of cooperation with other initiatives are presented below, which were established over the duration of the project.

- Under the Natural Capital for the SDGs (NC4-SDGs) initiative, GGKP in partnership with the Basque Centre for Climate Change (BC3) expanded the expert group’s natural capital gap methodology to assess the financial investment needs for filling the gap and applied it to 20 countries, including 12 in Africa. In collaboration with the GIZ Economics of Land Degradation (ELD) initiative and in-country partners, the expert group also completed three pilot tests of the methodology focusing on terrestrial natural capital restoration in India, Kyrgyzstan and Rwanda.

- In September 2021, in addition to organizing a number of online meetings and knowledge-sharing events, the GGKP together with the African Development Bank (AfDB), GIZ and World Wide Fund for Nature (WWF) launched the Natural Capital for African Development Finance (NC4-ADF) initiative. There, in partnership with the International Institute for Sustainable Development (IISD), NC4-ADF launched its first natural capital analysis of an AfDB development finance project, the Tanzania Kakono Hydropower Plant study, using the IISD Sustainable Asset Valuation (SAVi) methodology.

- Under NC4-ADF, the expert group also seeded a new Working Group on Development Finance under the Africa Natural Capital Accounting Community of Practice to support natural capital applications in financing infrastructure 30 development, focusing on an AfDB case study in Mozambique which was be completed in 2023.

- In November 2021, the GGKP also launched a new Gender Expert Group to catalyse collective action towards gender equality and women’s empowerment in the transitions to green, low-emission economies. The Gender Expert Group is co-chaired by the Global Green Growth Institute (GGGI) and the International Institute for Environment and Development (IIED) and provides research, capacity building and knowledge sharing to aid evidence-based policy development processes. The working group has to date produced three reports addressing knowledge gaps in gender equality and women’s empowerment in green growth approaches.

ii) Indicator Based Performance Assessment:

|  | Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification |
| --- | --- | --- | --- |
| Outcome 4: National and regional stakeholders, including green economy champions, decision-makers, practitioners, and youth representatives, access and apply knowledge for advancing IGE Indicator: Baseline: Planned Target: |  |  |  |
| Output 4.1: IGE knowledge products and platforms generated/leveraged and shared Indicator 4.1.1: Number of IGE knowledge products generated and made available on PAGE website for national level application Baseline: Planned Target: Indicator 4.1.2: Number of platforms established or leveraged to advance IGE knowledge-sharing and dialogue, including for and by youth and green economy champions Baseline: Planned Target: | - Green Growth Learning Network - Green Finance Platform - Green Industry Platform - Green Growth Knowledge Platform - Green Growth Learning Network - Green Finance Platform - Green Industry Platform - The Green Forum - Green Growth Expert Connect Solution |  | Online link to knowledge products and platform PAGE annual reports |
| Output 4.2: IGE South-South and Triangular events and dialogues organised to promote knowledge-sharing and debate on IGE Indicator 4.2.1: Number of IGE South-South and Triangular events, peer learning and dialogues, including scaling of good practices, held in cooperation with other partners Baseline: Planned Target: | - HLPF side Event - Fast, Fair and Green in 2019 - Webinar series under the IKI project Green Economy Transformation in 2018-2021 - High-Level Media Debate at the 2019 PAGE Ministerial Conference: “What is Wealth?” in 2019 |  |  |

iii) Evaluation, Best Practices and Lessons Learned

GGKP continuously monitored its online activities, including the use of the web platforms, social media, and newsletter and produced regular analytics reports. GGKP web platform analytics were captured using Google Analytics. Social media analytics were captured using Twitter Adds analytics, LinkedIn analytics were captured using LinkedIn’s built-in analytics platform, and newsletter analytics were captured using Constant Contact’s built-in analytics platform. To report on these analytics and the GGKP’s key activities and successes, the GGKP developed a full Annual Report every two years, along with an Impact Report in the years that an Annual Report was not published. In addition, the GGKP used a mix of surveys with more detailed in-person interviews when feasible to garner feedback from the audience and obtain qualitative data that explores the strengths, successes, challenges and areas for improvement. This regular monitoring approach has enabled GGKP to react quickly to changing circumstance. For example, in 2020, the GGKP noticed a spike in its webinar registration and participation due to COVID-19, and accordingly increased the frequency and profile of the webinars to maximise results in area of knowledge sharing.

A terminal review of GGKP’s programme period 01/2018 – 12/2021 was completed in May 2021 and provided detailed recommendations and corresponding implications for the design of the current programme period (2022-2025). Some of the key recommendation and corresponding actions are as follows:

- Recommendation: the GGKP should strengthen its knowledge generation workstream by systematizing knowledge. The already existing work to identify knowledge gaps, trends, interests and needs, not only through the Expert Working Groups but also by regularly surveying partners could be strengthened through knowledge systematization, including tacit knowledge exchanged in the webinars, published in the platforms, or discussed in the Green Forum.

- The GGKP aims to utilise its knowledge generation workstream in efforts to increase collaboration with partners as well as knowledge sharing activities in webinars, workshops, the Green Forum and other exchange and outreach opportunities.

- Recommendation: the GGKP should strengthen its strategy and delivery mechanisms to enhance knowledge use. Identifying entry points and incentives for increased engagement of project partners would likely contribute to strengthen the learning loop.

- In addition to continuing its webinar series to raise awareness on the platforms and among Knowledge Partner and Steering Committee organisations, the GGKP plans to further mainstream and institutionalise the GGKP within its partners, including by enhancing the role of Coordinators to promote GGKP products and services within their organisations. This includes the use of GGKP tools (e.g. I-GO solution, Green Financial Measures database) to support existing projects and programmes.

- Recommendation: the GGKP should strengthen its resource mobilization strategy. It should aim to secure sufficient funds to cover both operational costs (e.g. by establishing a non-earmarked trust fund) and ad-hoc activities (e.g. to respond to arising needs and priorities or to seize opportunities).

- The GGKP will continue to leverage its recent expansion and the added menu of services to engage in bilateral funding discussions as well as opportunities to engage in resource mobilisation and project participation with its partners. This includes new services, such as the +Platforms and Green Forum.

- Recommendation: the GGKP should strengthen the mandate of the Expert Working Groups, ensuring that they are able to respond to arising needs. This should include efforts to raise additional resources, develop detailed workplans and establish concrete targets, including concrete linkages with knowledge sharing and use (see above the recommendations to strengthen the TOC).

- The GGKP established a new Expert Working Group on Gender. The GGKP also reviewed with UNEP and UNIDO how the initiative might support circular economy initiatives that could possibly open an entry point for collaborating with crucial stakeholders, such as the European Union. This has led to targeted funding from the EU to enhance circular economy knowledge management and sharing.

The term “programme” is used for programmes, joint programmes and projects.

Strategic Results, as formulated in the Strategic UN Planning Framework (e.g. UNDAF) or project document;

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as  “Project ID” on the project’s factsheet page on the MPTF Office GATEWAY.

The MPTF/JP Contribution is the amount transferred to the Participating UN Organizations – see MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities. Please see MPTF Office Closure Guidelines.

Financial Closure requires the return of unspent balances and submission of the Certified Final Financial Statement and Report.

Note: Outcome statements are shortened versions of those in the PAGE Strategy 2021-2030. The full description of Outcome 4 reads National and regional stakeholders, including green economy champions, decision makers, practitioners, and youth representatives have access to cutting-edge knowledge for advancing IGE approaches and global best practices, analytical tools and platforms and events for sharing their insights and innovations with peer groups within and across countries and communities.