Internal Displacement Monitoring Centre (IDMC)

Global harmonized data on internal displacement to inform prevention, response and solutions

ANNUAL NARRATIVE PROJECT REPORT

01 January - 31 December 2025

TABLE OF CONTENTS

1. PROJECT INFORMATION	1

2. PROJECT SELF-ASSESSMENT SURVEY	2

2.1. Data quality	2

2.2. Ecosystem and collaboration	3

2.3. Data update and use	5

2.4 Contribution of CRAF’d funding	7

3. KEY ACHIEVEMENTS AND RESULTS	8

3.1 Key achievements	8

3.2. Ecosystem partnership and outcomes	10

3.3. Results from data uptake and use	13

4. LESSONS LEARNED	16

5. VISIBILITY AND EXTERNAL ENGAGEMENT	18

5.1 External coverage and engagement	18

5.2 Leadership testimonial	21

5.3  Partner testimonial	21

# 1. PROJECT INFORMATION

| Project title | Global harmonized data on internal displacement to inform prevention, response and solutions |
| --- | --- |
| MPTFO project number | 00140773 |
| Organization name | Norwegian Refugee Council (NRC)/Internal Displacement Monitoring Centre (IDMC) |
| Organization website | https://www.internal-displacement.org/ |
| Project duration [months] | 24 |
| Grant size [USD] | $1,500,000 |
| Implementing partners | N/A |
| Report submission date | 23 Feb 2026 |
| Authorization | - We grant the Complex Risk Analytics Fund (CRAF’d) a non-exclusive, worldwide, royalty-free, perpetual license to use, reproduce, adapt, distribute, and publicly display the submitted quotes, photographs, videos, and other communication materials solely for communications, outreach, advocacy, and reporting purposes. We confirm that we hold all necessary rights and have obtained required consents from any individuals or third parties featured, in line with applicable laws and ethical standards. Ownership remains with the originating party. Where feasible, CRAF’d will provide attribution as specified, except where impracticable or inconsistent with the format or purpose of use. Materials shall not be used in a misleading or defamatory manner. |

# 2. PROJECT SELF-ASSESSMENT SURVEY

Use this section to self-assess your project’s performance across four areas: data quality, ecosystem and collaboration, data uptake and use, and the contribution of pooled funding. For each question, select a rating and explain your choice clearly and concisely, using evidence from the reporting period. Keep responses short (2-3 sentences) and focused on what changed, improved, or was enabled. Avoid lengthy narrative or descriptions of activities alone.

## 2.1. Data quality

| #I | Question | Rating | Justification (evidence-based) |
| --- | --- | --- | --- |
| a. | To what extent has the project ensured transparency and public accessibility of its data, insights, and methodologies? | 4 - Great extent | IDMC’s data is publicly accessible via its platforms, as well as through APIs and HDX. Over the reporting period, IDMC’s data has been downloaded more than 25,000 times through its website, more than 78,000 times through HDX. |
| b. | To what extent has the project applied open standards, machine-readable formats, and interoperable approaches (e.g. APIs)? | 3 - Moderate extent | The project has applied interoperable, machine-readable approaches by expanding structured outputs and strengthening alignment with open reference standards. As of the latest internal release, 98% of records are prepared with publishable location information aligned with OCHA’s Common Operational Datasets (CODs), enabling consistent geographic referencing across products and APIs. Progress has also been made in adding unique disaster identifiers and hazard attributes to historical disaster datasets, improving cross-dataset linking and reuse. These enhancements will be made publicly accessible through updated APIs and data products as part of the project’s scheduled releases. |
| c. | To what extent has the project ensured the accuracy, completeness, and reliability of its data or insights through validation or peer-review processes? | 5 - Very great extent | IDMC strengthens the accuracy, completeness, and reliability of its data through systematic validation with national authorities, reconciling discrepancies and regular data-sharing. This is complemented by peer exchange and cross-checking with UN partners (UNHCR, IOM, UNICEF, OCHA), including technical reviews of figures, methods, and diagnostics to ensure consistency and robustness across data products. |
| d. | To what extent has the project implemented responsible data practices, including informed consent, privacy, confidentiality, fairness, and risk mitigation? | 5 - Very great extent | In the implementation of this project, IDMC uses secondary sources, with no personal data collection. Access controls protect confidentiality, and do-no-harm checks, aggregation/redaction, and provenance tracking are implemented to mitigate risks and support fairness through multilingual monitoring. |
| e. | To what extent has gender expertise or inclusive analysis (e.g. sex, age, disability) been incorporated into the design, collection, or validation of the data or insights? | 4 - Great extent | Considering the scope and purpose of the project, a specific gender expertise or inclusive analysis cannot be included in the implementation of the activities. However, where possible, IDMC’s data is disaggregated by sex, age and disability. |

## 2.2. Ecosystem and collaboration

| #II | Question | Rating | Justification (evidence-based) |
| --- | --- | --- | --- |
| f. | To what extent has the project strengthened data- or insights-sharing and collaboration among ecosystem partners? | 4 - Great extent | Enhanced APIs, dashboards and structured outputs have strengthened data sharing and downstream applications, while also enabling new partner-generated datasets and analysis from actors such as IOM, OCHA and UNHCR. |
| g. | To what extent has the project strengthened sustained partnerships with organizations operating in fragile and crisis-affected settings? | 4 - Great extent | In the implementation of the project, IDMC has sustained partnerships through the operational use of its data and APIs in crisis contexts by actors such as OCHA/HDX Signals, WFP, INFORM), as well as its ongoing technical collaboration with UNHCR, UNICEF and IOM on disaggregation and integration. |
| h. | To what extent have local and national actors been meaningfully involved in the design, collection, validation, or use of the project’s data or insights? | 5 - Very great extent | Local, national and regional actors were engaged through design consultations (e.g. CONRED/SIRED Guatemala) and methodological alignment and validation with authorities for the inclusion of displacement metrics into their monitoring and subsequent publishing of the data through IDMC’s GIDD and IDUs, including Colombia’s UARIV and Sierra Leone’s NDMA. |
| i. | To what extent has the project built or strengthened partnerships with women-led or feminist organizations that influenced the analysis or use of data or insights? | 1 - Not at all | Considering the scope and purpose of the project, no specific partnerships have been built with women-led or feminist organizations. |

## 2.3. Data update and use

| #III | Question | Rating | Justification (evidence-based) |
| --- | --- | --- | --- |
| j. | To what extent have the project’s data or insights informed funding or resource allocation decisions that improved the timing, targeting, or dignity of crisis action in fragile and crisis-affected settings? | 4 - Great extent | Through the implementation of this project, IDMC has been able to accelerate the timeliness and consistency of internal displacement data updates, strengthening situational awareness for ecosystem partners and supporting more informed decision-making. Rising requests for GIDD/IDU API access and downloads also show growing partner uptake and integration into analytical workflows. The most measurable effects on partners’ ability to allocate resources more rapidly and in a more targeted and dignified way are expected once all deliverables are operationalised and disseminated. |
| k. | To what extent have the project’s data or insights strengthened anticipatory action or early warning / early action capabilities of partners? | 4 - Great extent | GIDD/IDU enable monitoring and near-real-time alerts, feed forecasting and risk models (OCHA/HDX, INFORM, ICPAC, UNHCR), and strengthen anticipatory action and allocation decision (WFP, UNDP, FFO, Sida). |
| l. | To what extent have the project’s data or insights contributed to earlier, faster, or more targeted assistance to affected populations? | 4 - Great extent | IDMC’s IDU and GIDD datasets enable earlier, more targeted assistance by improving early warning and anticipatory-action decisions. They inform EU ECHO analysis, World Bank FCV/GTFS2 operational support, and UNDSS protocol triggers. IGAD uses them to forecast weather-related displacement; WFP integrates them for risk projections; INFORM and OCHA refine severity analysis and prioritisation across partners. |
| m. | To what extent have the project’s data or insights enabled partners to analyze and address the gendered impacts of crises? | 3 - Moderate extent | Improved workflows support sex- and age-disaggregated analysis, including coordination with UNHCR and UNICEF. IOM’s GPID uses IDMC IDUs for disaggregation, and UNHCR includes it in global reporting. |

## 2.4 Contribution of CRAF’d funding

| #IV | Question | Rating | Justification (evidence-based) |
| --- | --- | --- | --- |
| n. | To what extent has CRAF’d funding enabled your organization to pursue new or expanded areas of work that would otherwise not have been possible? | 5 - Very great extent | CRAF’d funding expanded IDMC’s responsible AI work, enabling AI-assisted tools that improve timeliness, disaggregation, and event analysis. It also catalysed partnerships on conflict forecasting and climate-change impacts on displacement. This would not have been possible without this funding. |
| o. | To what extent has CRAF’d funding strengthened your organization’s data, analytical, or technical capabilities and the overall quality of your work? | 5 - Very great extent | CRAF’d funding is enabling IDMC to expand its time series coverage back to 2008, improving temporal and spatial completeness for early warning and anticipatory action. It is also strengthening quality via automation, validation/error detection, 42-language monitoring, and surge support. This strongly contributes to improving the quality of IDMC’s work and provides instrumental contribution to internal displacement data. |

# 3. KEY ACHIEVEMENTS AND RESULTS

Use this section to highlight your project’s key achievements and results from the reporting period. Focus on key milestones, decision-linked use of data or insights, and partnership outcomes. For each entry, clearly explain what was achieved, why it mattered, and what changed as a result. Emphasise results and decisions enabled, not activities alone, and keep responses concise and evidence-based.

## 3.1 Key achievements

Use this sub-section to present the top three key achievements from the reporting period. Focus on major milestones or breakthroughs that led to clear results for the project. For each achievement, explain why it was significant, how it contributed to the project’s objectives, and what changed as a result. Emphasise results and decisions enabled, not activities alone. Keep descriptions concise, factual, and evidence-based. The achievements reported in this section will be highlighted on your project page in the upcoming CRAF’d Annual Report.

| #V | Key achievement | Significance | Links / materials |
| --- | --- | --- | --- |
|  | Briefly describe a major result or milestone achieved while implementing the project during this reporting period. For example: The project developed a cloud system that now delivers up-to-date weather and impact feeds. | Explain why this achievement matters, how it contributed to project objectives, and what changed as a result. For example: The cloud system enables drought outlooks from 2 to 4 months in advance and flood alerts up to 16 days ahead. Using this data, local NGOs started targeted seasonal funding allocations ahead of the hazard impact. | Provide direct links to reports, tools, dashboards, articles, or other materials that demonstrate or document the achievement. |
| a. | IDMC has built and benchmarked an operational automation stack replicating IDMC monitoring: NLP extraction supports data review in 42 languages processed across 120 countries/territories, with ~92% geolocation accuracy, plus event/source matching and alerting foundations. | This achievement accelerates monitoring and standardises outputs, reducing manual effort and enabling analysts to focus on validation and interpretation. It also improves spatial granularity so partners can better assess displacement concentration and localised impacts. | NLP Pipeline Pilot (Closed code). The public-facing results will be released with the project outputs, including updated APIs and dashboards. |
| b. | IDMC has reviewed external sources for 177/199 countries (for structured and non-structured data) as part of the historical data revision. This is expected to add 5,000+ historical events to IDMC’s GIDD once validated. | This achievement strengthens completeness and comparability of historical time series used by partner tools (e.g. INFORM, donors), improving confidence in trend analysis, risk scoring and early warning baselines. | https://www.internal-displacement.org/database/displacement-data/ |
| c. | IDMC has increased production via automation: in 2025, IDMC published 11,110 internal displacement updates, with ~50% generated through project automation. Semi-automated ingestion was also implemented, including 21 structured datasets (20 countries) and 10,814 records entered automatically (HULK uploads). | This achievement enables more frequent, scalable updates and reduces manual data-entry bottlenecks. Faster availability of validated updates improves usability for operational partners integrating IDMC data into planning and response workflows. | https://www.internal-displacement.org/database/api-documentation/ |
| d. | Expanded external uptake of IDMC data products: 150+ organisations made 35,711 API requests in 2025 (+92.6%). IDMC datasets saw 31,797 unique HDX downloads (78,341 total), plus 25,542 downloads from the IDMC website. IDMC data contributed to 46 HDX Signals alerts. | These figures show IDMC’s displacement dataset is increasingly used as a shared, harmonised reference feeding multiple platforms and applications. Partners integrate IDU/GIDD into early warning and modelling workflows, combining displacement signals with conflict, hazard and food-security indicators. Examples include JRC INFORM integrating displacement into severity metrics (and exploring IDU for warning), WFP linking displacement trends with food insecurity for forecasting and preparedness, eEARTH/Crisis Group incorporating displacement indicators to contextualise climate–conflict pathways, UNDSS using data for internal early warning, and Action Against Hunger (GIS4tech) integrating displacement into flood monitoring tools. HDX Signals alerts further demonstrate operational use for rapid situational awareness. | https://idmc-labs.github.io/ https://matemies.github.io/ https://data.humdata.org/signals https://drmkc.jrc.ec.europa.eu/inform-index/ https://www.wfp.org/ https://eearth.io/ https://crafd.io/projects/icpac-climatemodeling https://www.unhcr.org/refugee-statistics |
| e. | IDMC has developed and deployed a web bot (HULK) to automate uploads into HELIX: 3,442 figures take ~130 hours manually vs ~8.2 hours with HULK. In 2025, HULK entered 18,000+ data points for the reporting year. | Removes data-entry bottlenecks, reduces transcription errors, and enables faster publication as soon as new data are identified—improving timeliness, reliability, and scalability of production workflows. |  |

## 3.2. Ecosystem partnership and outcomes

Use this sub-section to describe partnerships that contributed to the implementation of the project and/or to strengthening the data and reporting ecosystem during the reporting period. Partnerships may include organizations that acted as implementing or counterpart partners, contributing directly to data collection, coordination, validation, or analysis of project outputs, as well as organizations that contributed to system-level outcomes, such as improved data sharing, interoperability, standardization, or reuse of data by multiple stakeholders.

For each partnership, describe the concrete results achieved through collaboration and what changed as a result. Focus on outcomes and added value generated by the partnership rather than coordination activities or processes.

| #VI | Partner organization | Result of the partnership | Links / materials |
| --- | --- | --- | --- |
|  | List the organization that contributed as an implementing, counterpart, or ecosystem partner to the project. | Briefly describe what improved or changed because of the partnership, including concrete outputs or outcomes (e.g. better data, wider access, shared standards). For example: The organization collaborated with two additional data partners to deliver multi-sectoral needs assessments; during the 2026 humanitarian planning cycle, the partners aligned their data collection approaches and developed a standardized implementation package that will be integrated into their API in future iterations, improving consistency and reuse of data | Provide direct links to reports, datasets, dashboards, tools, or publications that demonstrate the results of the partnership. |
| a. | UNHCR (Global Data Service) | Improved comparability across flagship reporting by aligning end-of-year displacement figures and agreeing follow-ups to reduce discrepancies between organisations’ published statistics. | Internal meeting notes; agreed follow-ups; next alignment meetings programmed in 2026. https://www.unhcr.org/refugee-statistics/download |
| b. | IOM (Global) | Strengthened coherence of global displacement reporting through joint data alignment discussions with IDMC and UNHCR, with follow-up actions to harmonise year-end figures and methods where feasible. | Internal meeting notes; follow-up conversations and coordination meetings planned for 2026. |
| c. | EGRISS | Contributed to standardisation by providing technical input on the IDP exit measure methodology and sharing IDMC’s revised stock methodology and capacity strengthening work, supporting improved statistical guidance and comparability. | EGRISS SC notes; agenda/participants. |
| d. | CONRED (Guatemala) | Enabled integration of internal displacement indicators into the SIRED damage-assessment platform, improving feasibility of routine, georeferenced displacement reporting and strengthening national ownership of displacement data. | https://www.linkedin.com/posts/ivana-hajzmanova-4b8ba389_internaldisplacement-guatemala-disaster-activity-7307497034083692545-D28S?utm_source=share&utm_medium=member_desktop&rcm=ACoAAA4cymEBQOXqQPSv9n831LC1wkzEFSzXTmY |
| e. | UARIV (Colombia) | Improved prospects for harmonised national IDP stock figures by establishing a series of technical meetings with IDMC and UNHCR to address discrepancies and agree on closer collaboration for the 2025 stock estimate. | Internal IDMC methodology document; technical meeting notes; data request follow-ups. |
| f. | 3iS (Ecuador) | Increased data quality and comparability by incorporating IDMC review into the annual displacement survey design (coverage period, sampling, questionnaire revision), strengthening the reliability of outputs used to fill data gaps. | Questionnaire drafts; review comments; survey plan/timeline. |
| g. | NRC (Honduras) | Improved publication readiness and policy relevance of survey results by planning joint discussion on dissemination approach (stocks vs. new displacement) in light of upcoming government stock releases and consistency with GRID figures. | Survey results brief; dissemination note; planned NRC meeting. |
| h. | NDMA (Sierra Leone) | Expanded primary data access and future capacity support through NDMA’s commitment to share qualitative and quantitative displacement data with IDMC and explore collaboration on training, methodological support, and an in-country visit. | Data-sharing commitment (email/notes); capacity-building concept note. https://www.linkedin.com/posts/idmc-geneva_sierra-leone-a-country-regularly-hit-activity-7371452502770343936--ZAV?utm_source=share&utm_medium=member_desktop&rcm=ACoAAA4cymEBQOXqQPSv9n831LC1wkzEFSzXTmY |

## 3.3. Results from data uptake and use

Use this sub-section to provide at least three examples showing how the project’s data or insights were taken up and used by partners to inform concrete decisions or actions, leading to measurable outcomes. Selected examples will be featured as “Impact Stories” on the CRAF’d website.

For each example, describe the context, how the data or insights were used to inform a decision or action, and what changed as a result. Keep descriptions concise, factual, and evidence-based.

Examples should demonstrate one or more of the following:

- Improved anticipation, prevention, or response in fragile and crisis-affected settings

- Changes in funding, prioritization, or resource allocation decisions

- Earlier, faster, more targeted, or more dignified assistance to affected populations

| #VII | Context | Data-driven decision | Resulting impact | Links / materials |
| --- | --- | --- | --- | --- |
|  | Briefly describe the problem, risk, or decision gap in a fragile or crisis-affected setting. For example: Repeated intercommunal tensions in Akobo County, South Sudan, were causing cyclical displacement, with limited early warning to prevent escalation before violence occurred. | Explain and, where possible, quantify how the project’s data or insights informed concrete decisions and actions, including their relevance for resource allocation and programming. For example: Project’s data was integrated into the displacement prediction model to forecast population movements up to 3 months ahead. In May 2024, elevated risk forecasts triggered a targeted programmatic response, including inter-community dialogues engaging over 200 local leaders, youth, and officials. | Describe the difference this made in practice, including quantitative results where available. For example: Preventive action contributed to 2,800 fewer displaced people than neighboring areas, achieved a ROI of over 6.6× emergency funding, and informed early-action models now used in 6 countries. | Provide full links to relevant reports, articles, and other materials that demonstrate the use case and impact. |
| a. | UN-OCHA (HDX “Signals”) – Enabling timely detection of displacement spikes to inform anticipatory action and evidence-based funding allocations | IDMC’s IDU is used as part of the HDX Signals to detect displacement spikes and trigger automated alerts supporting anticipatory action and response planning. | CERF used HDX “Signals” to guide over US$46m allocations in seven countries, benefiting nearly two million people; GOALPrime and IRC used alerts to secure funding faster and inform staff-safety decisions. In 2025, IDMC data contributed to 46 HDX Signals alerts that supported evidence‑based decision-making and funding allocation. | https://data.humdata.org/signals |
| b. | EU JRC (INFORM Risk Index) – Integrating displacement risk into crisis severity metrics to strengthen risk analysis and prioritisation of preparedness and funding | The EU JRC uses IDMC’s GIDD data as internal displacement indicator in INFORM severity metrics (vulnerable groups/uprooted people) to monitor risk and guide preparedness and funding prioritisation. | Improved crisis risk scoring supports evidence-based allocation decisions by donors and UN partners, strengthening early warning and targeted response in fragile contexts. | https://drmkc.jrc.ec.europa.eu/inform-index |
| c. | IOM (Global Profiles for Internal Displacement – GPID) – Providing disaggregated displacement insights to support targeted programming and evidence-based resource allocation | Combines IDMC’s IDU data with demographic and socio-economic maps to produce sex- and age-disaggregated population estimates. | Enables more targeted, equitable programme planning and resource allocation by identifying who is affected by displacement at national and subnational levels | https://dtm.iom.int/global-profiles-for-internal-displacement/gpid/index.html? |
| d. | Dynamic Early Warning & Action Model – Informing anticipatory and preventive action through forward-looking conflict risk modelling | Uses IDMC’s IDU data in machine learning-based conflict forecasts and decision models to simulate preventive interventions and country prioritisation. | Predicts emerging and overlooked conflict risks using advanced modeling to guide resource allocation. It prioritizes early prevention over accuracy, accepting false positives to avert costly crises and strengthen peacebuilding. | https://conflictforecast.org/ |
| e. | World Food Programme – VAM APP-FF – Supporting risk-informed operational planning by linking displacement trends to underlying crisis drivers | Uses IDMC’s IDU data and visualises IDP levels and trends alongside conflict and hazard indicators to support early warning, risk analysis and decision-making within WFP and partners. | Improves situational awareness and prioritisation by linking displacement trends to risk drivers, supporting earlier preparedness actions and better-targeted response planning. | https://dataviz.vam.wfp.org/conflict-and-internal-displacement-explorer/internal-displaceme |
| f. | eEARTH (International Crisis Group) – Informing anticipatory action by identifying emerging climate-related conflict risks | Early warning system identifying climate-driven conflict pathways in the Horn of Africa to support anticipatory analysis and prevention-oriented decision-making uses IDMC’s GIDD and IDU data. | Earlier identification of climate-security escalation risks, improving prioritisation for preventive engagement and resource allocation before crises intensify. | https://www.crisisgroup.org/sites/default/files/2024-06/eearth-2-pager-june-2024.pdf https://globalchallenges.org/updates/crisis-groups-early-action-and-risk-tracking-hub-eearth-is-live/ ; https://crafd.io/projects/icg-eearth |
| g. | German Federal Foreign Office (GFFO) & Swedish International Development Cooperation Agency (Sida) | Both agencies integrate IDMC’s displacement data and insights into their internal tools to inform funding allocations. This data informs anticipatory action by enabling comparability across crises, enabling more evidence-based prioritisation and resource decisions grounded in consistent, comparable displacement trends. | Evidence-based and timely resource allocation |  |
| h. | Climate‑risk forecasting and early warnings require reliable, harmonised and comparable data to understand how hazards drive displacement. | IDMC’s data, covering internal displacement due to conflict, violence and disasters across countries and over time, enables IGAD’s ICPAC to integrate population movement into hazard‑impact models with methodological consistency. | This integration strengthens regional climate‑risk forecasting and supports planning discussions, scenario-based preparedness exercises and long‑term regional decision‑making across the region. |  |

# 4. LESSONS LEARNED

Use this section to provide up to five lessons from the reporting period that are relevant to the design, implementation, use, or sustainability of the project. For each lesson, clearly state the insight gained and describe how it informed an adjustment, improvement, or future approach. Focus on learning that led to action or change, rather than general observations. Keep responses concise, practical, and evidence-based.

| #VIII | Category | Lesson learned | Adjustment informed |
| --- | --- | --- | --- |
|  | Select the category of the lessons learned.. | Briefly describe what your organization learned while implementing the project during this reporting period. For example: The project learned that data downloads alone did not provide insight into who was using the platform or how the data informed decision-making. | Explain what you changed (or will change) in project implementation or reporting as a result of this lesson. For example: An API user registration mechanism was introduced to capture user profiles and usage patterns, enabling better analysis of data uptake and use.) |
| a. | Methodology | High-quality AI classifications require sustained human oversight. Analyst capacity was insufficient to review outputs at scale, creating a validation gap. | Onboarded a dedicated team of annotators and strengthened the human-in-the-loop process to review, correct, and improve AI-generated classifications. |
| b. | Methodology | Model performance depends on high-quality labelled data and clear decision rules; without consistent annotations, accuracy and comparability degrade over time. | Standardised annotation guidelines and expanded training/QA for annotators to improve consistency, raise model performance, and protect comparability across reporting cycles. |

# 5. VISIBILITY AND EXTERNAL ENGAGEMENT

Use this section to document how the project and its results were communicated, referenced, or recognised externally during the reporting period. Focus on visibility that demonstrates reach, uptake, or influence, rather than promotional activity alone.

## 5.1 External coverage and engagement

Use this sub-section to provide at least three examples of where the project’s work was featured, discussed, or referenced externally during the reporting period, such as events, blogs, reports, peer-reviewed articles, or other platforms. For each example, briefly describe the coverage or engagement and include a quantitative indicator of reach or engagement where available.

| #IX | Type | Description | Reach / indicator | Links / materials |
| --- | --- | --- | --- | --- |
|  | Select the type of coverage and engagement. | Provide the title and a short description of the engagement or coverage, explaining what was shared or referenced and in what context. For example: Presented at an international data forum to share the project’s data collection methodology and gather feedback. | Provide a quantitative indication of reach or uptake, such as number of participants, downloads, views, citations, or mentions, where available. For example: Received feedback from over 50 workshop participants. | Include direct links to publications, recordings, dashboards, or other materials documenting the engagement or coverage. |
| a. | Events & presentations | Global Profiles for Internal Displacement (GPID) launch webinar, by IOM and IDMC. Introduces first harmonised global dataset on demographic/socio-economic profiles in displacement based on IDMC’s IDU. | 101 attendees 200+ downloads | Global Profiles for Internal Displacements ¦ Displacement Tracking Matrix IOM - Global Profiles for Internal Displacement (GPID) ¦ Humanitarian Dataset ¦ HDX |
| b. | Events & presentations | IDAC Innovation Webinar #2 on AI and geospatial tools to close data gaps on climate, displacement and children. Included IDMC contributions on disaggregated disaster displacement. (October 29, 2025) | 101 attendees | Innovation Webinar #2: Bridging data gaps on climate, displacement and children – International Data Alliance for Children on the Move (IDAC) https://www.youtube.com/watch?v=-aWM6WVfrzA |
| c. | Events & presentations | AI for Good – AI-powered Crisis Computing (Graduate Institute, Geneva) | 30 attendees | https://www.graduateinstitute.ch/communications/events/ai-powered-crisis-computing |
| d. | News media coverage | Euronews, media mention. Euronews Green: “Where conflict, poverty and climate collide”—explains IDMC data on record internal displacement and disaster movements. Published on May 15, 2025 | 10,300 views | https://www.euronews.com/green/2025/05/15/where-conflict-poverty-and-climate-collide-number-of-internally-displaced-people-tops-80-m |
| e. | News media coverage | Anadolu Agency, media mention based on AFP wire dispatch, widely syndicated internationally: Reports on IDMC/GRID figures as internal displacement surpasses 80M; compares total to Germany’s population. Published on May 13, 2025 | This media outlet does not share data on the number of views. | https://www.aa.com.tr/en/world/number-of-internally-displaced-people-worldwide-surpasses-80m-for-1st-time-report/3565921 |
| f. | News media coverage | Le Monde (English), media mention. Coverage of record IDMC/NRC figures for 2024; links conflict and disasters to unprecedented internal displacement totals. Published on May 13, 2025 | This media outlet does not share data on the number of views. | https://www.lemonde.fr/en/international/article/2025/05/13/more-than-83-million-internally-displaced-people-were-registered-in-2024-a-new-record_6741208_4.html |
| g. | News media coverage | El País (Spanish), media mention. Coverage of record internal displacement in 2024 based on IDMC/GRID figures. Published on May 14, 2025 | 26,800 views | https://elpais.com/internacional/2025-05-13/el-numero-de-desplazados-internos-en-el-mundo-vuelve-a-dispararse-en-2024-con-un-nuevo-record-de-834-millones.html |
| h. | News media coverage | The Guardian, media mention: ‘I don’t want to be here. But we can’t go home’: what life is like for people forced to flee floods and fighting. Feature on the reality of three internally displaced people (Bangladesh, Sudan and Colombia), based on IDMC/GRID figures. Published on May 23, 2025. | 81,300 views | https://www.theguardian.com/global-development/2025/may/23/floods-trauma-displaced-conflict-climate-crisis-safety-bangladesh-sudan-colombia-idp-camps |
| i. | Events & presentations | Workshop on disaster displacement in Mexico with federal and local authorities to improve disaster displacement response (October 19, 2025). Introducing IDMC’s displacement metrics and methodology for partners to implement it to produce interoperable data aligned with international standards, which can feed directly into the GIDD and IDU. | 19 August 2025 25 participants from 23 different departments of local and federal disaster response authorities and UNHCR |  |
| j. | Publications & reports | WMO Global Report. This global report on the state of climate uses IDMC data on a set of extreme weather events |  | https://wmo.int/sites/default/files/2025-11/State%20of%20the%20Climate%202025%20Update%20COP30%20%2831%20oct%29.pdf |

## 5.2 Leadership testimonial

Use this sub-section to provide one quote from your organization’s leadership reflecting on the project’s results and the contribution of CRAF’d support. Limit the quote to a maximum of 25 words. Also, submit a high-quality photo of the person quoted and label them accordingly.

| #X | Quote | Full name of person quoted | Title of person quoted |
| --- | --- | --- | --- |
| a. | CRAF’d support helped IDMC to deliver high-quality displacement data, which enables system-wide responses from early warning and funding decisions to policies and programmes. | Tracy Lucas | Director IDMC |

## 5.3  Partner testimonial

Use this sub-section to provide up to three quotes from partners or users of the project’s data or insights. Quotes should describe how partners contributed to the project or how they used the data or insights in practice, particularly for crisis anticipation, prevention, or response. Limit each quote to a maximum of 20 words. Provide properly labelled photos of the person quoted if available.

| #XII | Quote | Full name of person quoted | Title & organization of person quoted |
| --- | --- | --- | --- |
| a. | IDMC’s IDU enabled IOM’s GPID, linking 349 million displacement events to demographic profiles, bridging critical gaps in understanding local vulnerabilities. | Dr. Robert Beyer | Data and Research Analyst IOM’s Global Data Institute |
| b. | UNHCR uses IDMC’s GIDD as their primary IDP statistics source for flagship reports like Global Trends and their statistics website. | Edgar Scrase | Senior Statistics and Data Analysis Officer UNHCR’s Global Data Service |
| c. | Using IDMC data, UNICEF maps hotspots to help governments target vulnerable, high-risk communities with resources to improve disaster resilience. | Laura Linda Healy | Climate Change, Migration and Displacement expert Child Protection Section UNICEF |
| d. | IDMC data complements WFP food insecurity analysis with conflict and disaster displacement overviews. Alongside other sources, it informs internal decision-making. | Anja Palm | Conflict analyst at the World Food Programme |