UNITED NATIONS DEVELOPMENT PROGRAMME (UNDP)

INFORM WARNING

FINAL NARRATIVE PROJECT REPORT

11 July 2023 - 01 January 2026

TABLE OF CONTENTS

1. PROJECT INFORMATION	1

2. PROJECT SELF-ASSESSMENT SURVEY	2

2.1. Data quality	2

2.2. Ecosystem and collaboration	3

2.3. Data update and use	6

2.4 Contribution of CRAF’d funding	8

3. KEY ACHIEVEMENTS AND RESULTS	9

3.1 Key achievements	9

3.2. Ecosystem partnership and outcomes	10

3.3. Results from data uptake and use	13

4. LESSONS LEARNED	15

5. VISIBILITY AND EXTERNAL ENGAGEMENT	18

5.1 External coverage and engagement	18

5.2 Leadership testimonial	20

# 1. PROJECT INFORMATION

| Project title | INFORM WARNING - An open system to aggregate and present quantified multihazard information |
| --- | --- |
| MPTFO project number | 00140249 |
| Organization name | United Nations Development Programme |
| Organization website | undp.org |
| Project duration [months] | 30 |
| Grant size [USD] | $700,000 |
| Implementing partners | Data Friendly Space (DFS) |
| Report submission date | 2 Mar 2026 |
| Authorization | - We grant the Complex Risk Analytics Fund (CRAF’d) a non-exclusive, worldwide, royalty-free, perpetual license to use, reproduce, adapt, distribute, and publicly display the submitted quotes, photographs, videos, and other communication materials solely for communications, outreach, advocacy, and reporting purposes. We confirm that we hold all necessary rights and have obtained required consents from any individuals or third parties featured, in line with applicable laws and ethical standards. Ownership remains with the originating party. Where feasible, CRAF’d will provide attribution as specified, except where impracticable or inconsistent with the format or purpose of use. Materials shall not be used in a misleading or defamatory manner. |

# 2. PROJECT SELF-ASSESSMENT SURVEY

Use this section to self-assess your project’s performance across the reporting period in four areas: data quality, ecosystem and collaboration, data uptake and use, and the contribution of pooled funding. For each question, select a rating and explain your choice clearly and concisely, using evidence from the project period. Keep responses short (2-3 sentences) and focused on what changed, improved, or was enabled. Avoid lengthy narrative or descriptions of activities alone.

## 2.1. Data quality

| #I | Question | Rating | Justification (evidence-based) |
| --- | --- | --- | --- |
| a. | To what extent did the project ensure transparency and public accessibility of its data, insights, and methodologies? | 5 - Very great extent | The project applied open-by-design principles: all underlying data sources are publicly available, and methodologies for the Risk Monitor and Crisis Anticipation were documented and validated with partners during 2025. The INFORM Warning platform is being developed as an open-access system, with plans to publish methodologies and code at launch, reinforcing transparency beyond the reporting period. |
| b. | To what extent did the project apply open standards, machine-readable formats, and interoperable approaches (e.g. APIs)? | 5 - Very great extent | During 2025, the project implemented a data infrastructure designed around open standards and machine-readable formats, enabling automated ingestion, processing, and updating of multi-hazard indicators. The INFORM Warning platform is being developed with interoperable outputs and an API to support integration into partner systems, with finalisation planned ahead of launch in mid 2026. |
| c. | To what extent did the project ensure the accuracy, completeness, and reliability of its data or insights through validation or peer-review processes? | 5 - Very great extent | In 2025, the project placed strong emphasis on methodological validation, including partner review through the Technical Working Group and in-depth testing of the Risk Monitor against historical and emerging risk signals. Initial validation exercises demonstrated the system’s ability to detect real-world events, and a structured plan for ongoing validation and reliability monitoring was established prior to launch. |
| d. | To what extent did the project implement responsible data practices, including informed consent, privacy, confidentiality, fairness, and risk mitigation? | 5 - Very great extent | The project was designed to avoid personal or sensitive data entirely, relying exclusively on secondary, aggregated, and publicly available sources, which significantly reduces privacy and protection risks. In 2025, responsible data principles were embedded through alignment with established humanitarian data responsibility frameworks and through peer review of methodological choices to mitigate analytical bias and misuse risks. |
| e. | To what extent was gender expertise or inclusive analysis (e.g. sex, age, disability) incorporated into the design, collection, or validation of the data or insights? | 2 - Slight extent | Gender and inclusion considerations were acknowledged during design discussions; however, in 2025 the availability of reliable, comparable sex-, age-, and disability-disaggregated data suitable for inclusion in a global warning system remained limited. There are currently no forecasts that incorporate a gender component, however other datasets on vulnerability were included (food insecure people, displaced people). Systematic gender analysis could not yet be integrated, though the methodology is designed to accommodate such data as availability improves |

## 2.2. Ecosystem and collaboration

| #II | Question | Rating | Justification (evidence-based) |
| --- | --- | --- | --- |
| f. | To what extent did the project strengthen data- or insights-sharing and collaboration among ecosystem partners? | 5 - Very great extent | In 2025, INFORM Warning convened over 20 multilateral and technical partners through the Technical Working Group and dedicated workshops, creating a structured space for joint methodological development and validation. This process led to strengthened data-sharing arrangements, alignment of analytical approaches, and increased commitment from partners to integrate INFORM Warning outputs into system-wide processes. |
| g. | To what extent did the project strengthen sustained partnerships with organizations operating in fragile and crisis-affected settings? | 3 - Moderate extent | While INFORM Warning operates at a global level, in 2025 it strengthened engagement with organizations that have operational presence in fragile and crisis-affected settings, particularly through technical collaboration and validation processes. However, sustained country-level institutional partnerships remain limited at this stage and are expected to expand following system deployment and national-level application. |
| h. | To what extent were local and national actors meaningfully involved in the design, collection, validation, or use of the project’s data or insights? | 3 - Moderate extent | In 2025, engagement was primarily with global and multilateral entities, reflecting the system’s global scope and development phase. Limited involvement of national actors occurred through initial country-level testing and discussions (e.g. pilot applications), but structured and sustained local participation is expected to increase following deployment and country adaptation. |
| i. | To what extent did the project build or strengthen partnerships with women-led or feminist organizations that influenced the analysis or use of data or insights? | 1 - Not at all | In 2025, partnerships were primarily with multilateral and technical organisations, and engagement with women-led or feminist organisations influencing the analytical framework remained limited. While gender considerations were discussed, no dedicated partnerships with such organisations directly shaped the methodology during this reporting period. No such partnerships are planned for the future, since the scope of INFORM Warning is too broad and data providers are normally large multilateral organisations. We will consider such partnerships if there are relevant opportunities. |

## 2.3. Data update and use

| #III | Question | Rating | Justification (evidence-based) |
| --- | --- | --- | --- |
| j. | To what extent did project’s data or insights inform funding or resource allocation decisions that improved timing, targeting, or dignity of crisis action in fragile and crisis-affected settings? | 3 - Moderate extent | INFORM Warning has not yet been publicly launched; therefore, its data did not directly inform funding decisions during the reporting period. However, in 2025 the project worked closely with CERF, IFRC, IASC and other Technical Working Group members to align warning outputs with existing allocation and anticipatory financing processes, positioning INFORM Warning for structured use in resource prioritisation upon deployment. The strong, demonstrated uptake of other INFORM products in funding methodologies reinforces the likelihood of near-term integration. |
| k. | To what extent did the project’s data or insights strengthen anticipatory action or early warning / early action capabilities of partners? | 3 - Moderate extent | Although the platform is not publicly available in 2025 INFORM Warning strengthened anticipatory action frameworks by developing and validating a quantified, multi-hazard warning and crisis anticipation methodology with key partners. Engagement with IASC EWEAR, UN Regional Monthly Reviews, and IFRC Risk Watch helped ensure outputs are structured to directly support early warning and anticipatory decision-making once deployed. |
| l. | To what extent did the project’s data or insights contribute to earlier, faster, or more targeted assistance to affected populations? | 3 - Moderate extent | While the platform has not yet been publicly launched, INFORM Warning was fully developed and tested in 2025, with key operational partners directly involved in validating outputs. Members of the Technical Working Group, including actors engaged in anticipatory financing and horizon scanning processes, confirmed that the structured country warning levels and crisis alerts will enable earlier prioritisation and more targeted decision-making once integrated into their workflows. This positions INFORM Warning to contribute concretely to timelier and more evidence-based assistance. |
| m. | To what extent did the project’s data or insights enable partners to analyze and address the gendered impacts of crises? | 2 - Slight extent | In 2025, INFORM Warning incorporated structural vulnerability dimensions relevant to inequality and fragility; however, the system’s ability to analyse gendered impacts remains constrained by the limited availability of comparable, sex-disaggregated early warning data at global scale. While partners recognised the importance of this dimension during methodological discussions, dedicated gender-differentiated analytical outputs have not yet been systematically integrated. |

## 2.4 Contribution of CRAF’d funding

| #IV | Question | Rating | Justification (evidence-based) |
| --- | --- | --- | --- |
| n. | To what extent did CRAF’d funding enable your organization to pursue new or expanded areas of work that would otherwise not have been possible? | 5 - Very great extent | CRAF’d funding enabled INFORM Partners collectively to develop a scientifically advanced, system-wide early warning product that goes beyond existing tools in scope, methodological rigor, and innovation. The integration of multi-hazard risk aggregation, causal modelling, and AI-supported crisis anticipation represents a level of analytical advancement that would not have been feasible through fragmented or core funding alone. In 2025, this pooled support allowed partners to jointly design, validate, and operationalise a shared public good for the wider humanitarian system. |
| o. | To what extent did CRAF’d funding strengthen your organization’s data, analytical, or technical capabilities and the overall quality of your work? | 5 - Very great extent | CRAF’d funding significantly strengthened the collective analytical and technical capacity of INFORM Partners by enabling the development of advanced data pipelines, automated risk aggregation methods, and AI-enhanced crisis anticipation tools. In 2025, this support improved the scientific robustness, validation processes, and interoperability of INFORM products, elevating the overall quality, credibility, and strategic relevance of the analysis available to the wider humanitarian system. |

# 3. KEY ACHIEVEMENTS AND RESULTS

Use this section to highlight your project’s key achievements and results from the reporting period. Focus on key milestones, decision-linked use of data or insights, and partnership outcomes. For each entry, clearly explain what was achieved, why it mattered, and what changed as a result. Emphasise results and decisions enabled, not activities alone, and keep responses concise and evidence-based.

## 3.1 Key achievements

Use this sub-section to present the top three key achievements from the reporting period. Focus on major milestones or breakthroughs that led to clear results for the project. For each achievement, explain why it was significant, how it contributed to the project’s objectives, and what changed as a result. Emphasise results and decisions enabled, not activities alone. Keep descriptions concise, factual, and evidence-based. The achievements reported in this section will be highlighted on your project page in the upcoming CRAF’d Annual Report.

| #V | Key achievement | Significance | Links / materials |
| --- | --- | --- | --- |
|  | Briefly describe a major result or milestone achieved while implementing the project. For example: The project developed a cloud system that now delivers up-to-date weather and impact feeds. | Explain why this achievement matters, how it contributed to project objectives, and what changed as a result. For example: The cloud system enables drought outlooks from 2 to 4 months in advance and flood alerts up to 16 days ahead. Using this data, local NGOs started targeted seasonal funding allocations ahead of the hazard impact. | Provide direct links to reports, tools, dashboards, articles, or other materials that demonstrate or document the achievement. |
| a. | The INFORM Warning Risk Monitor was fully developed and validated, aggregating trusted, frequently updated multi-hazard forecast indicators into standardized country-level Warning Levels. | This establishes the first open, globally comparable system that translates complex forecast and trend data into clear, quantified early-warning signals across all crisis types. It enables decision-makers to systematically identify where risks are increasing over the next 1–12 months, strengthening prioritisation and anticipatory planning across agencies. | https://inform-warning.staging.nepware.io/ |
| b. | The Crisis Anticipation component was finalised, generating structured Crisis Alerts for countries with “Very High” warning levels, including contextual analysis, scenarios and projected humanitarian impacts. | This bridges the gap between rising risk signals and potential humanitarian consequences. By combining causal modelling, structured templates, and AI-supported contextual analysis, INFORM Warning moves beyond detection of risk trends to forward-looking projections that directly support anticipatory funding and preparedness decisions. The results of the Crisis Alert component are curated / validated by a human analyst. Testing was carried out on a preliminary data set and over a 6 month rolling period once the full database was developed. There will be ongoing testing, validation and refinement of INFORM Warning outputs. |  |
| c. | INFORM Warning was co-developed and operationally aligned with major global decision-making processes, including IASC Early Warning and Analysis, UN Regional Monthly Reviews, CERF anticipatory funding discussions, and IFRC Risk Watch. | Through structured validation and engagement with intended institutional users, the system is positioned for direct integration into funding allocation and early-action mechanisms. This ensures INFORM Warning will function as a shared evidence base for coordinated, system-wide prioritisation rather than a standalone analytical product. |  |

## 3.2. Ecosystem partnership and outcomes

Use this sub-section to describe partnerships that contributed to the implementation of the project and/or to strengthening the data and reporting ecosystem during the reporting period. Partnerships may include organizations that acted as implementing or counterpart partners, contributing directly to data collection, coordination, validation, or analysis of project outputs, as well as organizations that contributed to system-level outcomes, such as improved data sharing, interoperability, standardization, or reuse of data by multiple stakeholders.

For each partnership, describe the concrete results achieved through collaboration and what changed as a result. Focus on outcomes and added value generated by the partnership rather than coordination activities or processes.

| #VI | Partner organization | Result of the partnership | Links / materials |
| --- | --- | --- | --- |
|  | List the organization that contributed as an implementing, counterpart, or ecosystem partner to the project. | Briefly describe what improved or changed because of the partnership, including concrete outputs or outcomes (e.g. better data, wider access, shared standards). For example: The organization collaborated with two additional data partners to deliver multi-sectoral needs assessments; during the 2026 humanitarian planning cycle, the partners aligned their data collection approaches and developed a standardized implementation package that will be integrated into their API in future iterations, improving consistency and reuse of data | Provide direct links to reports, datasets, dashboards, tools, or publications that demonstrate the results of the partnership. |
| a. | Technical Working Group (UN agencies, donors, NGOs and technical partners) | Through structured co-development and validation in 2025, the Technical Working Group ensured that INFORM Warning outputs are directly aligned with institutional decision-making processes, including IASC Early Warning and Analysis, UN Regional Monthly Reviews, CERF anticipatory financing discussions, and IFRC Risk Watch. This collaboration resulted in agreed warning thresholds, validated methodologies, and structured output formats designed for integration into funding and prioritisation workflows, increasing the likelihood of systematic uptake at launch. |  |
| b. | European Commission Joint Research Centre (JRC) | The JRC provided scientific leadership in refining the causal modelling framework and validating the aggregation methodology underpinning the Risk Monitor and Crisis Anticipation components. This strengthened the methodological rigor, comparability, and statistical robustness of INFORM Warning, enhancing credibility with technical users and establishing a foundation for long-term maintenance and scientific oversight. |  |
| c. | Data Friendly Space (DFS) | DFS developed the interoperable data infrastructure, automated pipelines, and API architecture that underpin INFORM Warning. This resulted in a scalable, machine-readable, and integration-ready system capable of monthly updates and external system connectivity, significantly strengthening the technical quality, sustainability, and ecosystem interoperability of INFORM products. |  |

## 3.3. Results from data uptake and use

Use this sub-section to provide at least three examples showing how the project’s data or insights were taken up and used by partners to inform concrete decisions or actions, leading to measurable outcomes. Selected examples will be featured as “Impact Stories” on the CRAF’d website.

For each example, describe the context, how the data or insights were used to inform a decision or action, and what changed as a result. Keep descriptions concise, factual, and evidence-based.

Examples should demonstrate one or more of the following:

- Improved anticipation, prevention, or response in fragile and crisis-affected settings

- Changes in funding, prioritization, or resource allocation decisions

- Earlier, faster, more targeted, or more dignified assistance to affected populations

| #VII | Context | Data-driven decision | Resulting impact | Links / materials |
| --- | --- | --- | --- | --- |
|  | Briefly describe the problem, risk, or decision gap in a fragile or crisis-affected setting. For example: Repeated intercommunal tensions in Akobo County, South Sudan, were causing cyclical displacement, with limited early warning to prevent escalation before violence occurred. | Explain and, where possible, quantify how the project’s data or insights informed concrete decisions and actions, including their relevance for resource allocation and programming. For example: Project’s data was integrated into the displacement prediction model to forecast population movements up to 3 months ahead. In May 2024, elevated risk forecasts triggered a targeted programmatic response, including inter-community dialogues engaging over 200 local leaders, youth, and officials. | Describe the difference this made in practice, including quantitative results where available. For example: Preventive action contributed to 2,800 fewer displaced people than neighboring areas, achieved a ROI of over 6.6× emergency funding, and informed early-action models now used in 6 countries. | Provide full links to relevant reports, articles, and other materials that demonstrate the use case and impact. |
| a. | Supporting Forecast-Based Early Action (IFRC National Societies) National Red Cross and Red Crescent Societies implement Early Action Protocols (EAPs) that trigger anticipatory funding when forecast thresholds are met. However, identifying elevated multi-hazard risk trends in advance of formal trigger activation remains a challenge, particularly in fragile contexts with overlapping risks. | In 2025, IFRC engaged through the INFORM Warning Technical Working Group to assess how country-level Warning Levels and Crisis Alerts can serve as advance signals of heightened likelihood of EAP trigger activation in the coming months. INFORM Warning will provide National Societies with forward-looking, multi-hazard risk signals covering a 1–12 month horizon to complement hazard-specific forecasts. | This positions INFORM Warning to strengthen anticipatory planning by alerting National Societies to rising risk conditions before formal trigger thresholds are reached. The system will support earlier preparedness measures, more targeted readiness actions, and improved coordination ahead of potential emergency activation. |  |
| b. | Strengthening Humanitarian Allocation Methodologies (DG ECHO and CERF) Humanitarian funding instruments such as DG ECHO and CERF require transparent, comparable and forward-looking evidence to prioritise allocations for fragile and crisis-affected settings. Existing methodologies often rely primarily on structural risk and current severity metrics, with limited integration of dynamic short-term risk projections. | In 2025, DG ECHO and CERF engaged through the INFORM Warning Technical Working Group to explore incorporation of Warning Levels and Crisis Alerts into allocation methodologies. DG ECHO plans to integrate INFORM Warning into its humanitarian aid and Disaster Preparedness allocation frameworks and explore its application in anticipatory action programming. CERF is examining how INFORM Warning can support earlier allocations under the Rapid Response window and inform global analysis for the Underfunded Emergencies window. | These commitments establish a pathway for INFORM Warning to directly influence funding prioritisation decisions at global scale. By adding a quantified, forward-looking risk layer to allocation methodologies, the system is expected to strengthen timeliness, targeting, and anticipatory financing decisions across fragile contexts. | ECHO Resource Allocation using INFORM Warning |
| c. | Institutionalising Early Warning in UN System Processes (UNDP, UN RMR, IASC EWEAR) Global and regional crisis monitoring processes such as the UN Regional Monthly Reviews (RMR) and IASC Early Warning and Analysis discussions require comparable, cross-country risk signals to support leadership-level decision-making. Variability in analytical inputs can limit consistency and early prioritisation across fragile and crisis-affected settings. | In 2025, UNDP confirmed plans to integrate INFORM Warning into country, regional and global risk monitoring processes, including the next generation of the Crisis Risk Dashboard (CRD) and UN RMR discussions. Simultaneously, discussions with the IASC Early Warning Group explored how INFORM Warning Warning Levels could support structured horizon scanning presented to the Emergency Directors Group (EDG). | This institutional alignment embeds INFORM Warning within formal UN decision-making architecture. By providing a shared, quantified multi-hazard risk layer, the system is positioned to improve comparability, strengthen anticipatory dialogue at senior levels, and enable earlier system-wide prioritisation of emerging crises. |  |

# 4. LESSONS LEARNED

Use this section to provide up to five lessons from the reporting period that are relevant to the design, implementation, use, or sustainability of the project. For each lesson, clearly state the insight gained and describe how it informed an adjustment, improvement, or future approach. Focus on learning that led to action or change, rather than general observations. Keep responses concise, practical, and evidence-based.

| #VIII | Category | Lesson learned | Adjustment informed |
| --- | --- | --- | --- |
|  | Select the category of the lessons learned.. | Briefly describe what your organization learned while implementing the project. For example: The project learned that data downloads alone did not provide insight into who was using the platform or how the data informed decision-making. | Explain what you changed (or will change) in project implementation or reporting as a result of this lesson. For example: An API user registration mechanism was introduced to capture user profiles and usage patterns, enabling better analysis of data uptake and use.) |
| a. | Methodology | Calibrating warning thresholds across diverse hazards and country contexts is more complex than anticipated. Early testing showed that uniform aggregation rules risked over- or under-weighting certain hazard signals in fragile contexts. | Threshold parameters and aggregation weights were refined through iterative validation with the Technical Working Group. A structured validation and reliability monitoring plan was developed to continuously test model outputs against real-world outcomes after launch. |
| b. | Partnerships | Early and sustained engagement with intended institutional users is critical to ensure analytical outputs align with real decision-making workflows rather than remaining standalone technical products. | In 2025, structured alignment discussions were deepened with CERF, DG ECHO, IFRC, UNDP and IASC processes to tailor output formats and warning categories to existing allocation and horizon-scanning methodologies, increasing the likelihood of formal integration. |
| c. | Operational | Building a global, multi-hazard automated data pipeline requires greater flexibility than initially planned, particularly when data providers change formats, frequency, or availability. | The technical architecture was strengthened to improve modularity and redundancy, enabling substitution of alternative data sources where necessary and improving long-term resilience and sustainability of the system. |
| d. | Organizational | Developing an innovative, AI-enhanced analytical system requires balancing methodological ambition with institutional risk management and internal confidence-building. | Additional peer review, documentation, and expert validation processes were introduced to strengthen transparency and internal buy-in. Clear communication materials were developed to explain the role of AI within a human-validated analytical framework. |
| e. | Communications | Technical users require concise, decision-oriented outputs rather than detailed methodological explanations when engaging in funding or anticipatory discussions. | Warning Levels and Crisis Alerts were simplified into clearer, standardised formats designed for senior-level decision processes, while maintaining open access to full methodology and underlying data for technical users. |

# 5. VISIBILITY AND EXTERNAL ENGAGEMENT

Use this section to document how the project and its results were communicated, referenced, or recognised externally during the project reporting period. Focus on visibility that demonstrates reach, uptake, or influence, rather than promotional activity alone.

## 5.1 External coverage and engagement

Use this sub-section to provide at least three examples of where the project’s work was featured, discussed, or referenced externally during the project reporting period, such as events, blogs, reports, peer-reviewed articles, or other platforms. For each example, briefly describe the coverage or engagement and include a quantitative indicator of reach or engagement where available.

| #IX | Type | Description | Reach / indicator | Links / materials |
| --- | --- | --- | --- | --- |
|  | Select the type of coverage and engagement. | Provide the title and a short description of the engagement or coverage, explaining what was shared or referenced and in what context. For example: Presented at an international data forum to share the project’s data collection methodology and gather feedback. | Provide a quantitative indication of reach or uptake, such as number of participants, downloads, views, citations, or mentions, where available. For example: Received feedback from over 50 workshop participants. | Include direct links to publications, recordings, dashboards, or other materials documenting the engagement or coverage. |
| a. | Events & presentations | INFORM Warning Technical Working Group – Soft Launch Demonstration (Q4 2025) Presentation and live demonstration of the pre-production INFORM Warning platform to the Technical Working Group, composed of UN agencies, donors, NGOs and research institutions. The session presented finalised Risk Monitor and Crisis Alert methodologies and confirmed alignment with institutional early-warning and allocation workflows. | Approximately 25–30 participants representing over 20 multilateral and humanitarian organisations. Feedback informed final refinements and strengthened formal institutional commitment to integrate INFORM Warning into decision-making processes. | INFORM Warning Launch Deck |
| b. | Events & presentations | Bilateral Institutional Briefings with Key Decision-Makers (Q4 2025 – Q1 2026) Targeted technical and strategic briefings delivered to organisations including WFP, IFRC, IASC Early Warning and Analysis, ICRC, DG ECHO, FCDO, CERF, Save the Children and GiveDirectly. Sessions demonstrated platform functionality and explored integration into funding allocation methodologies, anticipatory financing, and horizon-scanning processes. | More than 10 briefing sessions, with 5–20 participants per session (estimated total reach: 100+ technical and strategic stakeholders). Engagement resulted in structured pathways for integration into global risk monitoring and allocation systems. |  |
| c. | Events & presentations | INFORM Warning Launch and Communications Strategy – Phased Global Rollout (2025–2026) Development of a structured, phased launch strategy including a 2025 soft launch with partners, pre-launch user briefings in early 2026, and an official high-level launch event at the Data for Peace Conference (Q2 2026), followed by continued global outreach. The strategy ensures coordinated visibility with UNDP, CRAF’d, DG ECHO and the INFORM partnership. | Launch activities target major multilateral agencies, donors, UN system actors and humanitarian networks, with anticipated engagement of several hundred technical and strategic stakeholders across 2026 events. | INFORM Warning Launch Strategy |

## 5.2 Leadership testimonial

Use this sub-section to provide one quote from your organization’s leadership reflecting on the project’s results and the contribution of CRAF’d support. Limit the quote to a maximum of 25 words. Also, submit a high-quality photo of the person quoted and label them accordingly.

| #X | Quote | Full name of person quoted | Title of person quoted |
| --- | --- | --- | --- |
| a. | INFORM Warning transforms complex risk forecasts into clear, actionable insights – helping us both anticipate where crises may emerge and understand their potential impact. This allows us to act early to prevent crises from escalating. | Shoko Noda | UN Assistant Secretary-General, UNDP Assistant Administrator and Director of the Crisis Bureau |