PBF PROJECT progress report

COUNTRY:  Solomon Islands

TYPE OF REPORT: semi-annual, annual OR FINAL:

YEAR of report: 2023

| Project Title: Gender Responsive Peacebuilding in Extractive Industries in Isabel Province, Solomon Islands Project Number from MPTF-O Gateway: 00125625 |  |
| --- | --- |
| If funding is disbursed into a national or regional trust fund: Country Trust Fund Regional Trust Fund Name of Recipient Fund: N/A | Type and name of recipient organizations: IOM (Convening Agency) UNFPA |
| Date of first transfer: 22 January 2021 Project end date: 21 January 2023 Is the current project end date within 6 months? |  |
| Check if the project falls under one or more PBF priority windows: Gender promotion initiative Youth promotion initiative Transition from UN or regional peacekeeping or special political missions Cross-border or regional project |  |
| Total PBF approved project budget (by recipient organization): Recipient Organization Amount IOM $ 1,154,925 UNFPA $ 345,075 $ $ Total: $ 1,500,000 Approximate implementation rate as percentage of total project budget: 89.31% *ATTACH PROJECT EXCEL BUDGET SHOWING CURRENT APPROXIMATE EXPENDITURE* Gender-responsive Budgeting: Indicate dollar amount from the project document to be allocated to activities focussed on gender equality or women’s empowerment: $ 1,218,590 Amount expended to date on activities focussed on gender equality or women’s empowerment: $999,148.96 |  |
| Project Gender Marker: Project Risk Marker: Project PBF focus area: |  |
| Report preparation: Project report prepared by: Nathalie Hanley, Programme Manager, IOM Solomon Islands Project report approved by: IOM Regional Office for Asia and the Pacific Did PBF Secretariat review the report: |  |

NOTES FOR COMPLETING THE REPORT:

- Avoid acronyms and UN jargon, use general /common language.

- Report on what has been achieved in the reporting period, not what the project aims to do.

- Be as concrete as possible. Avoid theoretical, vague or conceptual discourse.

- Ensure the analysis and project progress assessment is gender and age sensitive.

- Please include any COVID-19 related considerations, adjustments and results and respond to section IV.

PART 1: OVERALL PROJECT PROGRESS

Briefly outline the status of the project in terms of implementation cycle, including whether preliminary/preparatory activities have been completed (i.e. contracting of partners, staff recruitment, etc.) (1500 character limit):

The project was initiated on 22 January 2021 and concluded on 21 January 2023. All project staff were recruited in the first reporting period, and partnership agreements were put in place with four civil society organizations: Solomon Islands Planned Parenthood Association (SIPPA), Stages of Change Women’s Theatre Association (SOC), community-based organization (CBO) Sitapuna, and the Isabel Provincial Council of Women (IPCW).

While the original project duration was of 18 months, noting the impacts on implementation of civil unrest in November 2021 and of the country’s first outbreak of COVID-19 in January 2022, IOM and UNFPA sought and obtained a six-month no-cost extension in mid-2022. As domestic travel restrictions started to ease from April 2022, and limitations on in-person gatherings were lifted in June 2022, this additional time allowed for the completion of remaining project activities, as well as for a Final Evaluation to be undertaken from November 2022 until January 2023. A final monitoring visit was undertaken by the project team from 6 to 14 January 2023, and wrap-up workshops were undertaken with key stakeholders in Buala on 13 January 2023 and in Honiara on 17 January 2023.

Please indicate any significant project-related events anticipated in the next six months, i.e. national dialogues, youth congresses, film screenings, etc.  (1000 character limit):

N/A.

FOR PROJECTS WITHIN SIX MONTHS OF COMPLETION: summarize the main structural, institutional or societal level change the project has contributed to. This is not anecdotal evidence or a list of individual outputs, but a description of progress made toward the main purpose of the project. (1500 character limit):

The project has resulted in improved understandings, at the community level, of the value of including women in leadership and peacebuilding. Monitoring undertaken both before and after outreach and awareness interventions showed community awareness increasing from 15 per cent to 85 per cent among the 3,416 people reached.

The project also resulted in the creation of gender-balaced eco-peacebuilding groups across all ten target communities. Nine of these groups were women-led, offering concrete opportunities for strengthening the leadership of women at the community level. Moreover, the small grants provided to eco-peacebuilding groups supported structural or societal improvements across all ten communities through, for example, the construction of women's resource centres in some communities and inter-community reconciliation interventions in others.

Two communities (Talise and Koisisi) also committed to recommending the appointment of female chiefs during the next convention of their House of Chiefs, which could see greater consideration for the role of women in leadership and informal justice resolution being cemented at the institutional level in Isabel Province.

Additionally, the Standard Operating Procedures on informal justice resolution, developed in partnership with the Isabel Council of Chiefs, and designed to apply across all eight Houses of Chiefs in Isabel (and consequently across every community in Isabel Province), will allow for greater standardization, greater transparency and greater accountability in the application of informal justice, as well as more frequent referral to formal justic actors for criminal matters which should not be informally resolved. The Ministry of Traditional Governance, Peace and Ecclesiastical Affairs (MTGPEA) will keenly oversee progress in fully adopting and applying these SOPs, noting this could be a potential model to replicate across other provinces.

Furthermore, one of the recommendations to emerge from the peacebuilding dialogue held with communities, government and industry in November 2022, was for Isabel Provincial Government (IPG) to consider a Provincial Ordinance mandating the presence of women at timber rights hearings, and the appointment of at least one woman as a trustee, for timber rights acquisition processes to be considered valid. This is tabled for discussion and consideration at Isabel Province’s Leadership Summit set to be held in early June 2023, and could prove transformative in securing greater rights for women in matters relating to land ownership and decision-making.

Finally, the project also supported and strengthened the roll-out and establishment of the SafeNet referral network for SGBV cases at the provincial level, with programming activities leading to the commitment of provincial service providers to sign an MOU for improved coordination. The Ministry of Women, Youth, Children and Family Affairs (MWYCFA) is currently in the process of recruiting a technical advisor to support the development of this MOU.

In a few sentences, explain whether the project has had a positive human impact. May include anecdotal stories about the project’s positive effect on the people’s lives. Include direct quotes where possible or weblinks to strategic communications pieces. (2000 character limit):

The project has resulted in positive impacts for target communities in Isabel province, particularly among women and young women. Many related having an improved understanding of their rights following outreach and awareness interventions, as well as greater confidence and self-esteem. Community leadership have also demonstrated an improved understanding of the need for greater gender equality efforts, with one leader relating: "Most times we always try to put only males to lead our community. So we just realized some of the mistakes, that we should apply gender equality so that females too can be included in some leadership positions".

Mobile clinic outreach services provided by SIPPA resulted in five life-saving clinical referrals over the course of the project, with one beneficiary stating: "If it was not for SIPPA's Medical Mobile Team, I would have died already".

Additionally, the installation of toilets, handwashing basins and solar panel lighting across the two pilot communities of Talise and Bolitei has resulted not only in improved safety and security for women and young women, but also in improved sanitation for all community members, as further outlined in this article: https://medium.com/@UNmigration/where-improved-sanitation-can-offer-protection-from-gender-based-violence-and-crocodiles-72f2214425bf. Older persons and minors have particularly benefitted, noting that mangroves previously used for open defecation are far and challenging to access.

Finally, the project has also allowed for the capacity of grassroots CBO Sitapuna to be developed, particularly through the mentorship and training of Stages of Change Women's Theatre Association. This has given Sitapuna increased skills, resources and confidence to continue its engagement and advocacy, even beyond the lifetime of the project. As stated by Sitapuna: "This project is one of the biggest projects that the Sitapuna advocacy team has encountered. However, the success of this project is the resources that are being put together. As a result, it not only helps communities and people outside, but also within the group itself. This project really helps address issues that exist in many families. Though it is challenging, as advocators it is a privilege to take this project on board and help address these existing issues".

PART II: RESULT PROGRESS BY PROJECT OUTCOME

Describe overall progress under each Outcome made during the reporting period (for June reports: January-June; for November reports: January-November; for final reports: full project duration). Do not list individual activities. If the project is starting to make/has made a difference at the outcome level, provide specific evidence for the progress (quantitative and qualitative) and explain how it impacts the broader political and peacebuilding context.

- “On track” refers to the timely completion of outputs as indicated in the workplan.

- “On track with peacebuilding results” refers to higher-level changes in the conflict or peace factors that the project is meant to contribute to. These effects are more likely in mature projects than in newer ones.

If your project has more than four outcomes, contact PBSO for template modification.

Outcome 1:  An enabling environment is created to support women’s human rights and participation of women and young women in community-based peacebuilding processes.

Rate the current status of the outcome progress:

Progress summary: (3000 character limit)

A successful communication campaign held in 2021, which was further bolstered through consistent engagement with communities and key stakeholders, resulted in evident behaviour and attitude changes in target communities, as well as increased levels of knowledge about the rights of women, and their contributions to community-based peacebuilding.

The communication campaign, timed to coincide with the 16 Days of Activism against Gender-Based Violence in 2021, allowed for 3,416 people (1,773 female and 1,643 male) to be reached with messaging on women’s rights, women’s leadership and women’s inclusion in peacebuilding and conflict resolution, through community theatre performances developed specifically for the context of communities affected by extractive industries in Isabel Province, as well as through visibility materials designed in English, Pidgin, the local Maringe language, and the languages of migrant workers in Isabel Province (Chinese, Malay and Bahasa Indonesia). All ten target communities were reached, as well as three additional sites in Sigana and in the provincial capital of Buala. In tandem with these activities, an art and essay-writing competition was launched for primary and secondary school children in Isabel, on the themes of women’s rights, women’s leadership, and women’s inclusion in peacebuilding, with winning entries selected in early 2022.

A radio talk-back show was also organized on 27 August 2022, with a panel featuring Isabel’s Premier, Rhoda Sikilabu, as well as local law enforcement, and health, mental health and social service providers. The panel discussion on women’s rights and women’s leadership was broadcast live, reaching an estimated audience of 500 listeners, and was replayed by the Solomon Islands Broadcasting Company during the 16 Days of Activism against Gender-Based Violence in December 2022.

A community engagement manual on women’s rights, women’s leadership and women’s inclusion in peacebuilding and conflict resolution was also developed and finalized in 2022. This manual was used by implementing partner Stages of Change to conduct training for community-based organization Sitapuna on how to hold dialogues and engagement on these themes at the community level. Following training, Sitapuna started rolling out theatre performances and community engagement sessions across target communities, reaching 1,605 people across the ten target communities, as well as an additional 314 people in two neighbouring communities. This helped to reinforce messaging shared during the project’s communication campaign, and led to women in target communities expressing increased self-esteem, and well as increased courage to advocate for their rights. Additionally, all implementing partners supported the distribution of information, education and communication (IEC) materials across target communities, with over 10,000 IECs distributed over the project period.

A training manual on Gender, Peacebuilding and Leadership was also finalized and was delivered as a Training of Trainers (TOT) from 26 to 29 April 2022 to 18 participants (8 women and 10 men). Trainers were drawn from the provincial SafeNet network and included representatives from provincial government, law enforcement, civil society and traditional leadership. Following the TOT, trainers cascaded the training across all 10 project communities between 9 and 18 May 2022, reaching a total of 287 people. While the primary target audience for this training were women and young women (231 women and girls reached), 56 men and boys were also engaged. Trainees at the community level reported increased knowledge and skills and expressed an interest in further training.

A research piece on “Understanding peacebuilding in communities affected by extractive industries in Isabel Province” was also finalized on 14 April 2022, based on primary data collected across four communities in September 2021. The research focused on gender norms, beliefs and factors surrounding women’s participation in informal justice resolution, conflict prevention and peacebuilding mechanisms in Isabel Province. Some of the key recommendations advanced in the report include: 1) the capacity building of traditional leaders to support and include women in peacebuilding and decision-making; 2) greater accountability of logging companies to the communities in which they operate; and 3) the engagement of provincial and national government with logging companies on their environmental health and corporate social responsibility strategies. These recommendations informed the project team’s approach to implementation, and sixty copies of the report were distributed to key stakeholders at the national and provincial level, including the Solomon Islands Forestry Association.

Finally, a gender impact assessment of the logging industry in Isabel Province was finalized in January 2023, based on primary data collected across six communities in September 2021, and was supplemented by an external facing four-page brief. Findings indicate that logging companies often fail to adequately consult with women when negotiating access to land, compensation payments or benefit-sharing agreements, which can disempower and disadvantage women, and may also undermine traditional decision-making structures and matrilineal land tenure principles. The preliminary findings from this assessment served to inform dialogues held under Outcome 2.

Overall, progress under Outcome 1 resulted in demonstrable support from national and provincial government, local authorities, traditional leaders, service providers and target communities, facilitating implementation of project activities, and driving the sustainability of project interventions. Importantly, knowledge and attitude changes at the community level also created more space for women to recognize and uphold their rights, with the support of men and traditional leaders.

Indicate any additional analysis on how Gender Equality and Women’s Empowerment and/or Youth Inclusion and Responsiveness has been ensured under this Outcome: (1000 character limit)

Gender Equality and Women’s Empowerment was ensured under this outcome in the following ways: 1) The project team participating in stakeholder engagement and activities was comprised of both men and women; 2) The project team took into account the perspectives and views of both male and female stakeholders in the design and delivery of activities; 3) Research was conducted to clearly understand existing barriers to women’s empowerment, so as to more effectively address these under project interventions; 4) Women’s organizations were engaged as project partners; 5) Community engagement materials and training materials were specifically contextualized to meet the capacity-building needs of women and young women in target communities; 6) Community engagement materials and training materials clearly articulate women’s rights, the importance of gender equality, and the value of including women in leadership and peacebuilding. They also provide specific examples of women’s leadership in the Pacific and in Isabel Province; 7) While training opportunities primarily targeted women and girls, men and boys were also invited to participate, so as to strengthen their uptake and understanding of gender equality principles; and 8) Women and youth in target communities were engaged to provide catering during project activities, allowing them income-generating opportunities.

Youth Inclusion and Responsiveness was ensured by: 1) Conducting communication and advocacy activities that specifically targeted children and youth; 2) Ensuring that literacy barriers did not preclude the engagement of children and youth in the project’s communication campaign activities, which were primarily delivered through community theatre performances and dialogues; 3) Engaging children and youth aged 15 and up in training activities conducted at the community level; and 4) Engaging women and youth in target communities to provide catering during project activities, allowing them income-generating opportunities.

Outcome 2:  Women and young women are able to drive change within their communities through peacebuilding dialogues.

Rate the current status of the outcome progress:

Progress summary: (3000 character limit)

In 2022, the project team supported the establishment of eco-peacebuilding groups across all ten project communities. These groups served as a community-level coordination mechanism to collect, share and address community concerns related to safety and security, conflict resolution and environmental degradation, particularly when related to the local presence of extractive industries. All the groups were comprised of ten members (five women and five men). Across the ten communities, nine of the groups were chaired by women, and eight of the groups had a female treasurer.

Between 1 May and 9 June 2022, the project team held focus group discussions (FGDs) across all ten communities with the eco-peacebuilding groups, community leadership and interested community members, on community concerns related to the local presence of extractive industries. In total, 163 community participants (74 women and 89 men) participated in these discussions. These FGDs served to identify the key social, environmental and economic concerns that were discussed both with logging company representatives, and with national and provincial government representatives, at dialogues held on 16-17 November 2022 in Honiara, with the participation of community representatives. The primary areas of conflict within communities, between communities and logging companies, and between communities and government relate to: the unequal or unfair distribution of benefits; the lack of appropriate consultation, and the insufficient inclusion of women in consultation and decision-making; the failure to honour agreements entered into; weak monitoring, oversight and enforcement of laws and regulations by government; allegations of corruption and bribery; and the negative social and environmental impacts of logging, which are insufficiently mitigated or addressed by government or logging companies.

The FGDs on community concerns relating to the logging industry also served to inform the development of small projects, in each community, to address and respond to identified sources of conflict. The project team supported community eco-peacebuilding groups in developing detailed budgets and work plans, and in identifying two to three indicators which could be used to measure the success of selected interventions. Eco-peacebuilding groups were then provided with a cash grant of 40,000 SBD (equivalent to 5,000 USD) with which to implement their projects. While the projects varied across communities, they included: reconciliation interventions to address inter-community conflict; the construction or upgrading of multi-purpose community centres; the construction of multi-purpose women’s resource centres; the construction of a kindergarten, repairs and upgrades to water supply infrastructure damaged by logging activities; and the construction of a marketplace. In each community, discussions were held on the viability and sustainability of interventions proposed, in particular to mitigate the risk of any proposed infrastructure being under-utilized or falling into disrepair. It is important to underline that while all eco-peacebuilding groups were able to expend the grants within the project timeframe, procuring necessary materials for construction, not all communities were able to complete their infrastructure projects by 21 January 2023, due to the reliance on labour as an in-kind contribution from the community (leading to longer implementation timeframes than originally envisaged). That being said, community satisfaction with the eco-peacebuilding projects was rated highly during the project team’s final monitoring visit, with tangible benefits to communities easy to observe. Some communities have also taken the initiative to mobilize additional resources, so as to further their project ideas. IOM has continued to follow up with eco-peacebuilding groups after project end, and those that have not yet completed their infrastructure projects expect to do so by June 2023.

FGDs were also held between 1 May and 9 June 2022, in all ten communities, on informal justice resolution, in order to inform the development of clear and transparent SOPs on access to informal justice. FGDs were held with men and women separately, in order to reflect the different experiences that men and women may have when seeking access to justice. More than 361 community members (216 women and at least 145 men) were consulted across the ten communities. Issues to emerge from these FGDs were a lack of standardization (between and within communities) on: matters resolved through informal justice; penalties applied; and fees levied by traditional and community leaders for their time. Barriers to accessing formal justice also emerged, as well as a lack of female representation among the traditional leaders and chiefs who make decisions on informal justice. One of the positive developments to emerge from this consultation, however, was the recognition by community leaders that women are under-represented in decision-making. In two communities, a commitment was made to recommend the appointment of female chiefs at the next convention of their House of Chiefs.

Following the FGDs, the project team coordinated with senior traditional leadership in Isabel Province (the Isabel Council of Chiefs), as well as the Ministry of Traditional Governance, Peace and Ecclesiastical Affairs (MTGPEA) to develop SOPs on informal justice resolution that would be applicable across all eight Houses of Chiefs and therefore applicable across all communities in Isabel Province. These harmonized SOPs clearly outline what matters can be resolved through informal justice and what matters need to be referred to formal justice actors, and include specific gender-sensitive provisions as well as standardized fees and penalties.

The SOPs were introduced and discussed with traditional leaders and the Isabel Council of Chiefs during training conducted for community chiefs on conflict resolution and applying rights-based and gender-sensitive informal justice resolution. From 18-27 October 2022, two four-day trainings were conducted reaching 43 participants (5 women, 38 men), including 1 representative from Isabel Provincial Government, 1 representative from the Isabel Council of Chiefs, 1 representative from law enforcement and 40 chiefs from across 29 communities in Isabel Province. Representatives from the executive of each of the eight Houses of Chiefs were in attendance. A representative from the Ministry of Justice and Legal Affairs also provided traditional leaders with an overview of key national legislation during the training, to ensure chiefs have a better understanding of what matters can be resolved through informal dispute resolution and which must be referred to formal justice actors. This session was particularly valuable in filling critical knowledge gaps and was described by participants as ‘eye-opening’. This training gave each House of Chiefs the opportunity to review the draft harmonized SOPs and provide inputs. Based on this review and the validation of the SOPs, final edits were applied, and the SOPs were submitted to the Isabel Council of Chiefs for implementation in 2023. MTGPEA will monitor the status of their implementation, noting the significant value attributed to the SOPs, and the benefit that replicating this model across other provinces could potentially bring.

Finally, a peacebuilding dialogue on community concerns with regard to logging in Isabel Province was held on 16-17 November 2022 in Honiara. Ahead of the dialogue with industry representatives, the project team coordinated with the Solomon Islands Chamber of Commerce and Industry (SICCI) through a meeting held with SICCI’s Chief Executive Officer on 30 March 2022. While no logging companies operating in Solomon Islands are members of SICCI, the Chamber expressed interest in continued coordination and updates. The project team also met with the Vice President of the Solomon Islands Forestry Association on 4 November 2022, to confirm the Association’s participation in the upcoming dialogue.

The two-day dialogue was attended by a total of 45 participants (26 men and 19 women), and included representatives from ten communities in Isabel Province, Isabel Provincial Government (IPG), the Ministry of Forestry and Research (MOFR), the Ministry of Justice and Legal Affairs (MJLA), MTGPEA, the Ministry of Police and Correctional Services, the Public Solicitor’s Office (PSO), the Solomon Islands Forestry Association, Earth Movers Solomons Limited and Mas Pacific International Limited. Community concerns discussed included concerns about: 1) the distribution of benefits and impacts on community cohesion; 2) environmental monitoring and compliance; 3) social protection and gender rights; and 4) safety and security challenges.

The dialogue was described as “the first of its kind” by MTGPEA, for successfully bringing industry representatives to the table for constructive conversations with community representatives and government representatives. Following the dialogue, recommendations emanating from the discussions, and directed to MOFR, PSO, Ministry of Women, Youth, Children and Family Affairs (MWYCFA), MJLA, IPG, communities, logging companies and the Solomon Islands Forestry Association were circulated with key stakeholders.

One recommendation made to IPG was to consider a Provincial Ordinance mandating the presence of women at timber rights hearings, and the appointment of at least one woman as a trustee, for timber rights acquisition processes to be considered valid. This will be discussed during Isabel Province’s Leadership Summit set to be held in early June 2023. The Leadership Summit will be hosted by the Maringe House of Chiefs, and the dialogue recommendations have already been included as an agenda item for the meeting. The Summit will be attended by representatives of the Provincial Government, Chairpersons of the eight Houses of Chiefs, the Paramount Chief and Isabel Council of Chiefs Executive, three Members of Parliament for Isabel and church leaders. Outcomes of the meeting will be drafted into resolutions which will be considered for implementation by Isabel’s tripod system (churches, traditional leaders and provincial government).

The Solomon Islands Forestry Association also circulated the recommendations with its membership, and expressed interest in future engagement, and MTGPEA stated that conversations held during the dialogue, as well as the wider project, have been instrumental in informing an upcoming review of Solomon Islands’ national Peacebuilding Strategy.

Finally, following the dialogue, and to ensure that communities impacted by logging have sufficient access to key information materials, which better allow them to enact their rights, the project team printed 585 copies of the Code of Logging Practice and 540 informational leaflets on the timber rights acquisition process, which were distributed across the ten project communities, and to provincial government stakeholders, in January 2023.

Indicate any additional analysis on how Gender Equality and Women’s Empowerment and/or Youth Inclusion and Responsiveness has been ensured under this Outcome: (1000 character limit)

Gender Equality and Women’s Empowerment was ensured under this outcome in the following ways: 1) The project team participating in stakeholder engagement and project activities was comprised of both men and women; 2) The project team met with and took into account the perspectives and views of both male and female stakeholders; 3) Eco-peacebuilding groups were composed of equal numbers of men and women; 4) The appointment of women to the roles of Chair and Treasurer for the ten eco-peacebuilding groups was strongly recommended, resulting in nine female Chairs and eight female Treasurers; 5) When relevant, FGDs were conducted separately for both men and women; 6) All data collection tools developed included specific questions on gender considerations; 7) Five of the eco-peacebuilding projects developed seek to promote gender equality and women’s empowerment; 8) SOPs on informal justice resolution contain specific gender-sensitive provisions; 9) Two representatives from each community – one man and one woman – were invited to participate in the peacebuilding dialogue held in Honiara in November 2022; 10) The agenda for the peacebuilding dialogue included a session on social protection and gender rights; and 11) Recommendations to emerge from the dialogue seek to address gender inequalities, in particular the proposed Provincial Ordinance mandating the presence of women at timber rights hearings, and the appointment of at least one woman as a trustee, for timber rights acquisition processes to be considered valid.

Youth Inclusion and Responsiveness was ensured in the following ways: 1) Three of the eco-peacebuilding projects developed address the needs of children and youth; 2) The agenda for the peacebuilding dialogue included a session on social protection and gender rights; and 3) Recommendations to emerge from the dialogue include recommendations on supporting women to access child support payments in the case of spousal abandonment.

Outcome 3:  Coordinated government and CSOs have improved quality of service provision and higher beneficiary reach targeting women and young women who face violations due to conflict dynamics between community and logging companies and their workers.

Rate the current status of the outcome progress:

Progress summary: (3000 character limit)

In partnership with MWYCFA, and with co-funding from the IOM Development Fund (IDF) project “Enhancing the Response to Gender-Based Violence and Trafficking in Persons (TIP) in the Solomon Islands”, a five-day training on GBV and TIP was delivered on 22-26 November 2021 to 22 provincial SafeNet participants in Isabel Province (11 women and 11 men), reaching government counterparts, civil society representatives, law enforcement representatives, medical representatives, community leaders and religious representatives.

This was further built on from 5-7 July 2022, when a SafeNet coordination training was held in Buala for 14 provincial service providers (11 M, 3 F) to enhance their coordination and referral practices. One of the key outcomes was the commitment to work towards developing a provincial inter-agency Memorandum of Understanding (MOU) to ensure strengthened referral processes. In follow-up discussions held with MWYCFA in April 2023, the Ministry indicated that it is in the process of recruiting a technical advisor to support the development of this MOU, tentatively by mid-2023.

From 12-21 July 2022, two three-days trainings on GBV and referral were also held for police officers in Isabel. The first training, specifically targeting female police officers, reached 6 participants. The second training, targeting male police officers, reached 14 participants. These two trainings combined mean that over two-thirds of Isabel’s police force has now received dedicated training on GBV.

Additionally, from August to November 2022, implementing partner IPCW conducted trainings on applying a survivor-centred approach across all project communities, reaching 229 women and 79 men.

Between 1 May and 9 June 2022, a needs assessment to identify gaps in the existing referral system was also conducted, in form of FGDs held in each target community. More than 372 people (233 women and 139 men) were consulted on challenges in accessing SafeNet services, inclusive of medical services, counselling services, legal assistance, law enforcement support and protective services (shelters or safehouses). The primary challenges were: a lack of knowledge about services and rights to access services; a lack of availability or accessibility of services; slow response times from services providers (particularly law enforcement); financial barriers; and cultural barriers. A findings report, along with recommendations on how to address or mitigate key gaps and challenges, was shared with national and provincial SafeNet coordinators and is available online.

Following the FGDs, contact directories for referral services were also developed in poster format (for schools, clinics, community halls and churches) as well as in a foldable pocket format for individuals. 160 copies of A3 and A4 referral posters, as well as 2500 copies of the pocket referral cards, were disseminated across all target communities and shared with service providers in December 2022 and January 2023.

A mobile phone and mobile credit were also provided to each of the ten communities to enable survivors who don’t have personal communication devices to access services through a trusted community focal point. Since June 2022, IPCW reported receiving an average of 16 calls per month. Of these, a little over half related to requests for assistance or referral, while the remainder were requests for information or related to training activities in target communities.

IPCW equally supported target communities with procurement of materials to establish a community-level ‘safehouse’ for women and girls in need of protective services. While communities were not able to fully complete their safehouses by project end due to the reliance on labour as an in-kind contribution from the community (leading to longer construction timeframes than originally envisaged), all materials and furnishings were procured, and strong progress was made across the majority of communities. IOM and IPCW are continuing to monitor safehouse construction across all communities, and most are expected to be completed by mid-2023. During the final monitoring visit undertaken by the project team, community members expressed their interest in seeing the safehouses completed as soon as possible, as following the range of trainings delivered at community level, they increasingly see the value in having this easily accessible safe space. Additionally, IPCW provided case management services and referral support to 22 beneficiaries (20 female, 2 male) over the project period, in partnership with Family Support Centre.

SIPPA held two Training of Trainers on psychosocial first aid (PFA) for its 40 volunteers (19 men and 21 women from the 10 target communities) from 20-24 June 2022 in Baolo and 27 June – 1 July 2022 in Sepi. The trained volunteers then conducted three cascade trainings in Baolo, Sepi and Koisisi, training a total of 102 community leaders and community members (46 male and 56 female) on how to apply PFA knowledge and skills in their communities.

SIPPA also delivered onsite mobile outreach services, with one outreach conducted from 17 June to 4 July 2022 across all ten communities, one outreach from 15 to 30 August 2022 across five communities, and one outreach from 8 to 15 December 2022 across nine catchment areas of three communities. Family planning services, contraceptives, counselling, and tests for cervical cancer, pregnancy and sexually transmitted infections were offered at each site. In total, 530 women were provided with clinic sexual and reproductive health services (192 women below the age of 24 and 338 above the age of 24). During delivery of these services, five lifesaving clinical referrals were made. Additionally, over 5,000 male condoms were distributed.

Finally, a safety and security audit, as well as focus group discussions with women and young women, were conducted in two pilot communities, Talise and Bolitei, from 8 to 15 October 2021. Representatives from IPG and MWYCFA were invited to participate in and monitor this activity, which helped to strengthen government engagement with the programming and ensure government support for the implementation of safety and security features requested by the communities. In both Talise and Bolitei, the lack of toilets in the communities was highlighted as the primary safety and security issue to address. Community members practised open defecation in the mangrove which put women and young women at risk of potential GBV incidents, but also put community members at risk of attacks by crocodiles. In Bolitei, the community’s access to piped water was cut off when a truck from a nearby logging operation accidentally ran over and damaged piping, so support with ensuring access to water was also required. Women and young women in Talise and Bolitei also expressed strong levels of enthusiasm about forming women-led security councils in their communities. In focus group discussions they expressed the view that men do not always ensure that the safety and security needs of women and girls are addressed or raised in community-level discussions and consequently women and young women are eager to take on leadership and decision-making roles in this respect. While these women-led security councils were not established during the lifetime of the project, women continued to express the intent to establish them, and in Talise, women indicated that the eco-peacebuilding group would likely take on this function moving forward, as well as oversight of the women’s resource centre under construction.

Following the safety and security audit and FGDs undertaken in 2021, steps were then taken to meet community requests for the installation of toilets to mitigate safety and security risks. The provincial government’s Rural Water Sanitation and Hygiene (RWASH) team undertook visits to both sites, in order to assess the feasibility of the request, and to develop the list of materials to be procured. Procurement of materials for toilets, handwashing basins and solar panel lights was concluded in 2022, and materials were shipped to project sites. A two-day pre-training was conducted by the RWASH team in both Talise and Bolitei, and community members in Talise also provided miller timber as an in-kind contribution to this activity.  Across both sites, communities also provided labour for dam improvements and the installation of the toilets, as an in-kind contribution to support workers from the RWASH teams. Construction of the toilets in Talise was concluded in January 2023. While not all toilets in Bolitei were completed by project end, the RWASH team ensured a comprehensive handover with community members in Bolitei, including the community plumber and engineer, so that remaining toilets could be finalized by the community after project end. All toilets were designed to be equipped with sliding bolt locks, as well as solar panel lighting on the inside and outside. Additionally, the project supported all women and girls in Talise and Bolitei with solar powered flashlights (150 flashlights distributed in each community), and also procured an additional 240 solar powered flashlights to be distributed to the 30 most vulnerable women and girls in the eight communities that were not selected as pilot sites for this activity.

Indicate any additional analysis on how Gender Equality and Women’s Empowerment and/or Youth Inclusion and Responsiveness has been ensured under this Outcome: (1000 character limit)

Gender Equality and Women’s Empowerment was ensured under this outcome in the following ways: 1) The project team participating in stakeholder engagement and activities was comprised of both men and women; 2) The project team met with and took into account the perspectives and views of both male and female stakeholders; 3) GBV and SRH services were designed to meet the needs of women and young women; 4) Gender balance was met in the composition of SIPPA volunteers mobilized for psychosocial support activities; 5) Male participants were also included in the FGDs on barriers in accessing SafeNet services, in recognition of the fact that men and boys may also be survivors of GBV and that those who are may face significant challenges in accessing services primarily designed to cater for women and girls; and 6) Both men and women were provided with capacity building opportunities, including through organizing dedicated training for male and female police officers separately.

Youth Inclusion and Responsiveness was ensured by: 1) Extending direct assistance and case management services to young women and girls. The first survivor supported by IPCW through the project was a 12-year-old girl; and 2) Including youth in FGDs on barriers in accessing SafeNet services.

PART III: CROSS-CUTTING ISSUES

| Monitoring: Please list monitoring activities undertaken in the reporting period (1000 character limit) In order to strengthen ownership and sustainability of programming interventions, and to enhance the capacity of provincial government to support the project team with on-the-ground monitoring, representatives from IPG were included in all FGDs and capacity building activities conducted, and have provided input and advice on all activities undertaken. Representatives from MTGPEA and MWYCFA were also engaged to accompany the project team for activities undertaken, and to support implementation, both to allow central government counterparts to monitor ongoing programming, but also to ensure consistency of project activities with the Ministries’ objectives and approaches. The project team regularly travelled to Isabel during project implementation, both to support delivery of activities, and to monitor the roll-out of activities at the community level. Monitoring of activities was equally tracked through forms and surveys designed to capture accurate data on number of people engaged in project activities, as well as feedback from participants in training activities. Remote monitoring, via regular phone calls and emails with IPG, with eco-peacebuilding groups, and with implementing partners in Isabel was also undertaken. In order to strengthen remote monitoring and coordination, a laptop was procured for the project team’s focal point at IPG. Financial monitoring of implementing partners IPCW and Sitapuna was also undertaken in 2022, through a spot-check and compliance visit conducted by IOM’s Finance Assistant. A final monitoring visit was undertaken in January 2023, in order to collect endline survey data, and track the progress and impact of programming. Finally, noting that some in-kind construction activities have yet to be completed at the community level, IOM and IPCW will continue to monitor these through till completion. | Do outcome indicators have baselines? Has the project launched perception surveys or other community-based data collection? |
| --- | --- |
| Evaluation: Has an evaluation been conducted during the reporting period? | Evaluation budget (response required): USD 50,000 If project will end in next six months, describe the evaluation preparations (1500 character limit): Terms of Reference (TOR) for the evaluation were drafted, reviewed and finalized in coordination with IOM, UNFPA and UNPBF. Following this the TOR were advertised, applications were received and reviewed, and a consultant was contracted following a successful interview and reference checks. The evaluation was conducted from November 2022 to January 2023. IOM and UNFPA compiled lists of key stakeholders to engage during the evaluation and coordinated with IPG and other counterparts on arrangements for field-level data collection. Field-level data collection was undertaken from 5-16 December 2022 in Honiara, Buala, and across three of the ten target communities in Isabel - Kia, Baolo and Bolitei. Communities selected for primary data collection were chosen in coordination with the Evaluation Reference Group, comprised of IOM, UNFPA and UNPBF. Following field-level data collection, the draft Evaluation Report, as well as a draft two-page brief, were circulated with the Evaluation Reference Group for comment. Comments were taken into consideration by the evaluator, and a final version of the Evaluation Report and two-page brief were prepared and shared with the Evaluation Reference Group. The Evaluation Report generated 47 recommendations, some of which were taken into consideration in the context of project closure, and some of which will inform future programming approaches. |
| Catalytic effects (financial): Indicate name of funding agent and amount of additional non-PBF funding support that has been leveraged by the project. | Name of funder: Amount: European Union EUR 550,000 IDF USD 300,000 |
| Other: Are there any other issues concerning project implementation that you want to share, including any capacity needs of the recipient organizations? (1500 character limit) | Owing to Government of Solomon Islands COVID-19 travel restrictions, the IOM Programme Manager worked remotely from Bangkok, Thailand, until 4 March 2022. The challenges this posed to implementation were heightened by domestic travel restrictions, and restrictions on in-person gatherings, imposed following the outbreak of civil unrest in November 2021 and the country’s first outbreak of COVID-19 in January 2022. In the short-term, COVID-19 and the civil unrest also redirected the immediate priorities of government and civil society counterparts, which was mitigated to a small extent by the project team’s extremely close coordination with partners in Isabel. As a number of hardware stores were burnt down during riots in November 2021, this also posed challenges to the procurement of certain fixtures, fittings and piping materials needed for the installation of toilets and handwashing basins. In order to accelerate delivery of programming following domestic travel restrictions being eased in April 2022, and restrictions on in-person gatherings being eased in June 2022, IOM allocated additional staffing to support implementation, at no cost to the project. Despite these efforts, as well as the six-month no-cost extension granted by UNPBF, certain activities reliant on labour as an in-kind contribution for the construction of community infrastructure could not be completed within the timeframe of the project. As there is no financial cost associated with their completion, work on these will continue to progress beyond the lifetime of the project, and IOM and IPs will provide ongoing monitoring. Nonetheless, an important lesson learned is that while these infrastructure activities were requested by the communities themselves, significantly longer construction timeframes were required than those originally outlined, owing to competing priorities of community members. CSO IPs, and in particular SIPPA, also experienced challenges with regard to financial management and expenditure of funds, which resulted in a significant and unexpected under-expenditure. Another lesson learned, which is reflected in the Evaluation Report, is that dedicated capacity building of CSO IPs in financial management, monitoring and reporting should be included as specific activities in future programming. Another point to underline is that the project team placed an important emphasis on sustainability during implementation, and this has allowed for continued use of project outputs beyond the lifetime of the project. Stages of Change Women’s Theatre Association have continued to use the Community Engagement Manual developed under the project during new activities being implemented in Guadalcanal, and IOM has adapted the referral posters and referral cards developed for Isabel to four other provinces – Choiseul, Makira, Malaita and Guadalcanal. SIPPA purchased an outboard motor to conduct its mobile clinic outreaches, and has thus been able to continue service delivery beyond the lifetime of the project. The relationship established with the Solomon Islands Forestry Association will also allow IOM to continue partnering with them not only in Isabel, but also in Choiseul, Makira, Malaita and Guadalcanal. Project outputs and reports were shared with all key stakeholders via email, as well as during dedicated project closure workshops held in Buala and Honiara. All project outputs have also been uploaded onto a Sharepoint folder for continued ease of access. Finally, in addition to supporting Gender Equality and Youth Inclusion in implementation of project activities, measures were also taken to strengthen inclusion of persons with disabilities (PWD), particularly in communication and advocacy efforts and in service provision. This was written into IOM’s partnership agreements with Stages of Change Women’s Theatre Association, Sitapuna and Isabel Provincial Council of Women. To the extent possible, disaggregated data on PWD has also been included in reporting. |

PART IV: COVID-19

Please respond to these questions if the project underwent any monetary or non-monetary adjustments due to the COVID-19 pandemic.

- Monetary adjustments: Please indicate the total amount in USD of adjustments due to COVID-19:

$ 0

- Non-monetary adjustments: Please indicate any adjustments to the project which did not have any financial implications:

Noting the impacts of civil unrest and COVID-19 on programming, IOM and UNFPA sought and obtained a no-cost extension to mitigate the effect of delays in implementation primarily resulting from stringent mobility restrictions in effect from November 2021 to April 2022. This allowed for the completion of remaining project activities.

- Please select all categories which describe the adjustments made to the project (and include details in general sections of this report):

☐ Reinforce crisis management capacities and communications

☐ Ensure inclusive and equitable response and recovery

☐ Strengthen inter-community social cohesion and border management

☐ Counter hate speech and stigmatization and address trauma

☐ Support the SG’s call for a global ceasefire

☒ Other (please describe):  No-cost extension

If relevant, please share a COVID-19 success story of this project (i.e. how adjustments of this project made a difference and contributed to a positive response to the pandemic/prevented tensions or violence related to the pandemic etc.)

N/A

PART V: INDICATOR BASED PERFORMANCE ASSESSMENT

Using the Project Results Framework as per the approved project document or any amendments- provide an update on the achievement of key indicators at both the outcome and output level in the table below (if your project has more indicators than provided in the table, select the most relevant ones with most relevant progress to highlight). Where it has not been possible to collect data on indicators, state this and provide any explanation. Provide gender and age disaggregated data. (300 characters max per entry)

|  | Performance Indicators | Indicator Baseline | End of project Indicator Target | Indicator Milestone | Current indicator progress | Reasons for Variance/ Delay (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 An enabling environment is created to support human rights and participation of women and young women in community-based peacebuilding processes | Indicator 1.1 Proportion of population who believe government services are promoting human rights of women and young women | 99% | 80% |  | 96% | A survey conducted in 2021 with 231 women and young women in all ten target communities revealed that 229 believed existing government services promote the rights of women and young women. While it might have been expected that as the knowledge of women and young women about their rights increased, the percentage of respondents who still held this belief would decrease, no substantive changes were observed during an endline survey conducted in January 2023 with 200 female respondents and 100 male respondents. Interestingly, male respondents were less likely to indicate that government services promote the human rights of women and young women (92%) than female respondents were (98%). |
|  | Indicator 1.2 Number of government officials engaged in protecting the rights of women and young women through project activities | 0 | 40 |  | 71 | Under the project, 71 individual government officials were engaged in supporting programming and project activities aiming to protect the rights of women and young women in Isabel Province. |
|  | Indicator 1.3 Number of CSOs engaged in promoting women and young women’s right in communities adjacent to logging camps | 3 (Family Support Centre, Provincial Council of Women, Mothers Union) | 6 |  | 6 (Family Support Centre, Provincial Council of Women, Mothers Union, Solomon Islands Planned Parenthood Association, Stages of Change, Sitapuna) |  |
| Output 1.1 Stakeholders have sufficient knowledge and skills to mainstream women’s rights in community-based peacebuilding dialogues | Indicator 1.1.1 Number of community members engaged in community-based dialogues on women's rights and peacebuilding | 0 | 500 |  | 1,919 | 1,605 reached in ten target communities, and an additional 314 reached in two neighbouring communities. |
|  | Indicator 1.1.2 Percentage of participants engaged in community based dialogues who report improved understanding of the importance of including women in peacebuilding processes | 0% | 80% |  | 63.31% | 1,215 of the 1,919 persons engaged in community based dialogues reported improved understanding of the importance of women's rights and of including women in peacebuilding processes. |
| Output 1.2 Women, young women and target communities have improved awareness of their rights and peacebuilding and leadership skills. | Indicator 1.2.1 Number of women and young women trained on leading peacebuilding processes | 0 | 200 |  | 231 women and 56 men in project communities | Additionally, 8 women and 10 men were trained as trainers. |
|  | Indicator 1.2.2 % increase in community awareness of the role of women in peacebuilding processes | 0% | 20% |  | 70% | Monitoring undertaken both before and after outreach and awareness interventions showed community awareness increasing from 15 per cent to 85 per cent among the 3,416 people reached. Additionally, during a final monitoring visit, 95.67% of the 300 individuals surveyed by the project team reported improved awareness of the role of women in peacebuilding processes (91/100 men and 196/200 women surveyed). |
| Outcome 2 Women and young women are able to drive change within their communities through peacebuilding dialogues | Indicator 2.1 % of women in eco-peacebuilding committees | 0% | 30% |  | 50% |  |
|  | Indicator 2.2 Number of eco-peacebuilding committees led by women | 0 | 3 |  | 9 |  |
|  | Indicator 2.3 % increase in community perception of change achieved through peacebuilding dialogues | 0% | 50% |  | 79.33% | 79.33% of the 300 community respondents surveyed in the final monitoring visit indicated their belief that the dialogues held in November 2022 had or would lead to positive change (46.33% responded 'yes' and 33% responded 'partially'). |
| Output 2.1 A network of women’s eco-peacebuilding groups (including young women) are established to represent women’s rights in dialogue with private sector and government officials. | Indicator 2.1.1 Number of women led eco-peacebuilding groups established | 0 | 3 |  | 9 |  |
|  | Indicator 2.1.2 Number of community-level peacebuilding action plans formed | 0 | 10 |  | 10 |  |
|  | Indicator 2.1.3 Percentage of communities reporting that eco-peacebuilding projects implemented have resulted in positive change | 0% | 100% |  | 100% | All communities reported that eco-peacebuilding projects implemented have resulted in positive change. During the final monitoring visit, the project team also surveyed 290 individual respondents across all ten communities, and 99.31% of individual respondents indicated their belief that eco-peacebuilding projects have resulted in positive change (84.14% indicated 'yes', and 15.17% indicated 'partially'). |
| Output 2.2 Formal and Informal Dispute resolution mechanisms are readily accessible to women and young women | Indicator 2.2.1 Number of communities where women have access to SOPs on informal justice resolution processes | 0 | 10 |  | 10 | SOPs on informal justice resolution have been drafted and are in the process of being endorsed for use across all 8 Houses of Chiefs in Isabel Province, which would make them applicable across every single community of Isabel Province. As the project team opted to develop the SOPs in such a way that they would have a broader application than the 10 target communities - but would also have a more sustainable and systemic impact - the endorsement and validation of the SOPs is being coordinated with the Isabel Council of Chiefs. In the interim, the draft SOPs have been shared with all 10 target communities, who also participated in the review process. |
|  | Indicator 2.2.2 Number of communities whose chiefs have been trained on women's rights and gender-responsive dispute resolution processes | 0 | 10 |  | 10 |  |
| Output 2.3 Directors of logging companies are engaged in peacebuilding dialogues to address potential drivers of conflict | Indicator 2.3.1 Number of directors of logging camps engaging in dialogues | 0 | 5 |  | 1 | While only one director from a logging company operating in Isabel Province participated in dialogues held under the project (the director of Earth Movers Solomons Limited, who is also the Vice President of the Solomon Islands Forestry Association), two representatives from Mas Pacific International Limited attended at the request of their director, who was unable to join in person. |
|  | Indicator 2.3.2 Number of people participating in peacebuilding dialogues (disaggregated by sex) | 0 | 50 |  | 45 (26 men and 19 women) |  |
|  | Indicator 2.3.2 Number of community-level peacebuilding action plans supported by logging companies CSR resources | 0 | 1 |  | 0 | While no logging companies provided additional resources to support community-level peacebuilding initiatives during the project implementation period, following the dialogue with industry held on 17 November 2022, and based on the advice of the Solomon Islands Forestry Association, the community of Leleghia sent a formal request for financial assistance to Mas Solo Investment Ltd, with the backing of Isabel Provincial Government. |
| Outcome 3 Coordinated government and CSOs have improved quality of service provision and higher beneficiary reach targeting women and young women who face violations due to conflict dynamics between community and logging companies and their workers. | Indicator 3.1 Number of CSOs and grassroot organizations reporting being able to provide improved services to women and young women in logging adjacent communities | 0 | 5 |  | 4 (Solomon Islands Planned Parenthood Association, Family Support Centre, Isabel Provincial Council of Women, Mothers Union) |  |
|  | Indicator 3.2 Percentage of women and young women who are satisfied by the services provided by CSOs and government service providers through the project | 0% | 90% |  | 100% | 100% of the beneficiaries directly asked about their satisfaction with services provided under the project indicated that they were satisfied. However, results under this indicator should be interpreted with caution, as fewer than 5% of beneficiaries were engaged about their levels of satisfaction. Regrettably, despite multiple requests and reminders, implementing partner SIPPA consistently failed to administer anonymous beneficiary feedback forms during provision of mobile clinic outreaches, which would have provided more reliable data for this indicator. |
| Output 3.1 Reporting and referral mechanisms are available to women and young women in logging camps in Isabel province | Indicator 3.1.1 % of women who are aware of available referral mechanisms (disaggregated by age) | 53% | 90% |  | 92% | Based on an inception survey undertaken with 231 women in target communities, 53% indicated having heard of SafeNet. However, during FGDs on access to SafeNet services, levels of knowledge were estimated to be at less than 10% across target communities. During an end of project survey conducted in January 2023, 184 women out of the 200 women surveyed indicated being aware of available referral mechanisms and services. |
|  | Indicator 3.1.2 Number of CSO representatives trained on GBV and supporting referral to services | 0 | 20 |  | 61 |  |
|  | Indicator 3.1.3 Number of RSIPF officials trained on GBV and supporting referral to services | 0 | 20 |  | 23 |  |
| Output 3.2 GBV, SRH and justice services are available to women and young women in logging adjacent communities in Isabel province. | Indicator 3.2.1 Number of women and young women accessing services (disaggregated by age) | 0 | 200 |  | 530 women and girls were provided with clinical SRH services (of which 192 were below the age of 25) and 22 individuals (20 female, 2 male) were provided with SGBV counselling and referral services. |  |
|  | Indicator 3.2.2 Number of women and young women who are satisfied with the quality of service provided by CSOs and government | 0 | 200 |  | 27 beneficiaries were asked about and reported satisfaction with services provided. | More comprehensive data against this indicator is lacking due to SIPPA's failure to administer anonymous beneficiary feedback forms during their mobile clinic outreach activities. During IOM and UNFPA's final monitoring visit, 194 out of 200 women surveyed in project communities expressed some level of satisfaction with general services (not project-specific services) provided by CSOs and government (170 reported satisfaction and 24 reported partial satisfaction). |
|  | Indicator 3.2.3 Number of calls/texts made to the wellness hotline per month | 0 | 5 |  | 16 | An average of 16 calls were made per month, of which 53.6% were related to requests for assistance/referral, while others were related to requests for information. |
| Output 3.3 Women and young women in targeted communities have improved personal security addressing concerns of potential violations by migrant workers in logging camps | Indicator 3.3.1 Percentage of women provided with security devices or infrastructure improving personal safety | 0% | 80% |  | 100% | 100% of women in Talise and Bolitei are benefitting from improved personal safety following the distribution of 150 flashlights in each community (one for each woman and girl), as well as the installation of flush toilets with locks and solar panel lighting. |
|  | Indicator 3.3.2 % of women and young women who report improved personal security | 0% | 50% |  | 97.5% | 87.5% of female respondents surveyed in January 2023 indicated that their personal security had improved, and 10% reported that it had partially improved. |
|  | Indicator 3.3.3 Number of women-led security councils established | 0 | 2 |  | 0 | While women-led security councils were not established in the project timeframe, women and young women in the two pilot communities of Talise and Bolitei continued to indicate their commitment to establishing them. In Talise, women indicated their intention to leverage the eco-peacebuilding committee to play this role moving forward. |

By project end, over 95 per cent of the 300 community members surveyed during a final monitoring visit reported improved understanding of the importance of including women in peacebuilding processes.

Community members reached included 950 children under the age of 18; 1,115 youths aged 18 to 35; and 13 persons with disabilities.

Additionally, a recorded version of the theatre performance was screened for an audience in Buala on 18 December 2022, International Migrants Day.

A training on community mobilization was held on 19 – 22 September 2022 for 23 participants from Sitapuna (14 F, 9 M), and a second training on using theatre for communication and advocacy was held on 12 – 19 October 2022 for 16 participants from Sitapuna (10 F, 6 M)

Following this TOT, 94% of trainees indicated that their knowledge of gender, peacebuilding and leadership had increased; that the content and topics covered were applicable to their daily work; and that they would be able to use the knowledge gained in their workplace within the next 1 to 3 years.

Trainees reached included 71 youth aged 15 to 30 (62 F, 9 M).

For example, the project amendment and no-cost extension request coordinated with UNPBF included provisions for additional capacity-building of community leaders, as well as more robust and meaningful inclusion of provincial and national government in dialogues to be held with and about logging companies operating in Isabel Province.

Roles of the eco-peacebuilding groups, as outlined in their Terms of Reference, include: 1) Collect and share information on community concerns, including those raised by women and girls, persons with disabilities, and other vulnerable groups; 2) Participate in dialogues and discussions related to community concerns, and, if appropriate, designate representatives to participate in provincial-level or central-level discussions on community concerns; 3) Design and implement a community-level eco-peacebuilding project, ensuring efficiency and transparency in the implementation. This will include documenting and reporting on results to IOM/UNPBF, as well as to other community members, and ensuring accountability with regard to management of the small eco-peacebuilding grant (SBD 40,000); 4) Advocate for peace and conflict resolution within the community, and promote peaceful resolution to conflicts; 5) Advocate for gender equality and meaningful participation of women in leadership, peacebuilding and conflict resolution; and 6) Coordinate appropriately with existing community governance structures, to ensure alignment and synergy of activities.

Reported on further below.

To serve for one or more of the following purposes: 1) to provide vocational training as a means of securing alternative employment to logging; 2) to provide a safe space for counselling of those who have experienced a violation of rights; 3) to strengthen confidentiality and privacy for those undergoing informal justice resolution; and 4) to conduct youth awareness and empowerment activities.

To serve as a space for women’s empowerment and fostering women’s leadership and confidence to participate in decision-making, as well as for some of the purposes outlined in the footnote above.

To mitigate protection risks for pre-primary school children who currently have to walk for more than 30 minutes, along a road shared with logging trucks, to attend kindergarten in a neighbouring community.

To strengthen food security, noting that subsistence agriculture crops are often damaged by wild boars displaced from their natural habitats by logging activity.

In Leleghia, for example, the repair of water pipes damaged by a logging company, as well as the installation of 15 new standpipes and a new water tank, has restored access to running water for the entire community.

IOM will continue to follow up with eco-peacebuilding groups as needed until completion of all infrastructure projects.

In two communities, male participants did not fill in the FGD sign-in sheets for this activity. It is estimated that an additional 30 men participated, bring the total number of men engaged to an estimated 175.

Following this training, 95% of trainees indicated that their knowledge of GBV and TIP had increased; 75% that the content and topics covered were applicable to their daily work; and 90% that they would be able to use the knowledge gained in their workplace within the next 1 to 3 years.

In two communities, male participants did not fill in the FGD sign-in sheets for this activity. It is estimated that an additional 30 men participated, bring the total number of men engaged to an estimated 169.

https://roasiapacific.iom.int/sites/g/files/tmzbdl671/files/documents/2023-03/Barriers in Access to GBV Support Services in Isabel Province.pdf

In the form of a safe and private room in a women’s resource centre, community centre or health centre.

19 toilets, 19 handwashing basins and 38 solar panel lights for Talise and 14 toilets, 14 handwashing basins and 28 solar panel lights for Bolitei.

The project “Strengthening the Capacity of Civil Society Organisations in Solomon Islands to Prevent Trafficking in Persons and Gender-Based Violence and to Protect Survivors” was initiated on 15 March 2022, and will help to build on some of the achievements under this project at the national level and in the target provinces of Guadalcanal, Makira and Malaita.

The project “Enhancing the Response to Gender-Based Violence and Trafficking In Persons in the Solomon Islands” was initiated on 1 February 2021 with a focus on Isabel and Choiseul provinces. Through this project, complimentary activities and co-funding have supported the objectives of the PBF project.