
[image: ]


THE GLOBAL DISABILTY FUND (GDF) END OF PROGRAMME REPORT – 
NATIONAL PROGRAMMES

Programme information -Summary 

	Programme title: 
	Promoting the realization of the exercise of legal capacity of PwD in Argentina.

	Countries 
	Argentina – Region or provinces: National/Federal, Northwestern Region, by also leveraging on existing Programmes within the UNSDCF 2021-2025 (Humanitarian Response Plan to the socio-sanitary emergency in Salta; Spotlight Initiative; Gran Chaco Initiative)

	Overall programme duration: 
	40 months (apr 2022 - jul 2025)

	Budget: 
	Total budget: 300.000 USD
Co-funding: 90.000 USD

	Overall programme focal persons: 
	Valeria Guerra 
Human Rights Advisor - RCO 

	All PUNOs focal points: 
	UNDP
Daniela Mazzoni 
Democratic Governance Analyst 
UNFPA
Celeste Leonardi
Sexual and Reproductive Rights Officer 
PAHO/WHO
Cecilia Marzoa
Especialista en Gestión de programas y Alianzas OPS/OMS Argentina 
UNICEF
Malena Acuna
Social Policy Officer 
OHCHR/RCO
Valeria Guerra 
Human Rights Advisor 

	OPDs and Gov focal points 
	OPDs:
REDI
Marcelo Betti
President 
ASOCIACIÓN AZUL
Elena del Bo
President 

Government 
· National Secretariat of Disability (ANDIS) - National Ministry of Health 
No focal point appointed 
· National Ministry of Justice. Human Rights Secretariat (SDH)
No focal point appointed 
· Ministry of Health: 
National Directorate of Sexual Reproductive Health (DNSSR)
No focal point appointed 
· Presidency: 
National Council on Social Policies Coordination (CNCPS)
No focal point appointed 

	Reporting period (please include start and end date of the implementation phase): 
	april 2023 - july 2025

	Short description of the programme: 


	The Argentina UNPRPD Programme seeks to support the State and OPDs in advancing the CRPD through enhancing Equality and Non-discrimination, overcoming Service Delivery barriers, and ensuring PwD participation.
The problems that will be addressed by the program are barriers to the exercise of an independent life and gaps in capacity and knowledge of duty bearers in implementing and coordinating disability policy; participation of PwD and OPDs in decision-making process; mainstreaming disability in SDGs and UNSDCF will also be addressed.
The strategy will be based on supporting the implementation of national and specific regulations and adaptation of specific procedures and laws regulating legal capacity by the CRPD; the production of evidence for decision-making and knowledge products and the development of trainers´ programs to bring about attitudinal changes in procedures and service lines aiming at the independent life. The program will also address intersectional stigma and discrimination, especially against women and girls with disabilities and indigenous with disabilities, regarding their access to sexual and reproductive health and rights. It will also focus on persons with psychosocial and intellectual disabilities, in the exercise of their legal capacity.
Three priority focus areas are:
1. Support the State in the enhancement of autonomy, the exercise of the legal capacity, and the independent life of PwD, encouraging their participation in policy reforms and public policy implementation.
2. Support the UNS to ensure strengthened disability inclusion and monitoring in the UNSDCF implementation.
3. Mainstream disability in SDG planning, monitoring, and coordination mechanism.

	Target groups1   
	All persons with disabilities, with a primary focus on women and girls with disabilities, and on underrepresented groups of persons with disabilities, persons with intellectual and/or psychosocial disabilities and indigenous people with disabilities.

	Thematic focus2 :  
	Legal Capacity; Access to Justice, GBV & sexual and reproductive health; Access to Information and ICTs, OPDs capacity building.




Introduction
The purpose of this report – which is consistent with the UNDG Standard Progress Report format – is to provide information on the achievements of the project towards the realization of its stated objectives. In keeping with the UN system on-going efforts to strengthen result-orientation, the report should focus on systemic, structural transformation rather than process, highlighting how the different elements of the result chain described in the approved project document contributed to advance the rights of persons with disabilities in keeping with the Convention on the Rights of Persons with Disabilities. [footnoteRef:1] [1:  The following definitions, which are based on the UN Development Group Harmonized RBM Terminology, were used in the “Template for Programme Proposals”, utilized by UN Country teams to developed the approved project documents:
Impact: Positive and negative long-term effects on identifiable population groups produced by a development intervention, directly or indirectly, intended or unintended. These effects can be economic, socio-cultural, institutional, environmental, technological or of other types.
Outcome: The intended or achieved short-term and medium-term effects of an intervention’s outputs, usually requiring the collective effort of partners.  Outcomes represent changes in development conditions which occur between the completion of outputs and the achievement of impact.
Outputs: The products and services which result from the completion of activities within a development intervention.] 

Reporting teams are encouraged to attach annexes containing additional relevant information (including assessments, evaluations and studies undertaken or published) and share videos, photographs (high resolution image files) or other multi-media materials illustrating the work and impact of the project. It is recommended, however, that all annexes be clearly referenced, using footnotes or endnotes within the body of the narrative.
Please note the report should be accessible.[footnoteRef:2] [2:  Prior to the submission of this report, please check that the document is accessible to persons using screen readers. In a window system it is possible to do this by going to the File Menu, clicking Check for Issues and then Check Accessibility. If errors, warnings and tips show up in the report of the accessibility checker, please follow the instructions in the checker to make the necessary corrections. On a Mac, click on review and select check accessibility. When the document is accessible the checker will display a report stating “No accessibility issues found. People with disabilities should not have difficulty reading this document.” Please see Windows Accessibility Checker ; Apple Mac Accessibility Checker for more information.
 .] 


1.Progress towards impact and specific outcomes
Using the table format provided below, please provide information on the contribution towards impact and outcome indicators. Please make sure to capture, in your description, relevant shifts in addressing gaps in preconditions to CRPD implementation, capacity development as well as in the wider disability inclusion agenda and implementation of the SDGs in the country. Where it has not been possible to collect data on indicators, additional narrative information should be provided detailing why that was the case and what plans have been put in place to ensure that the relevant data will be provided. 


	Expected Impact of the programme/ Impact statement

	The expected impact of the programme is to contribute to a sustained transformation of national policies, systems, and practices towards disability inclusion in Argentina. By equipping public institutions, OPDs, and other key stakeholders with knowledge, tools, and platforms for participation, the programme aims to strengthen the enabling conditions for CRPD implementation, ensure equitable access to rights and services —including sexual and reproductive health—, and promote inclusive justice and governance systems. 
In the long term, these efforts are expected to reduce structural barriers, foster active participation of persons with disabilities in decision-making, and embed the principles of the 2030 Agenda —particularly the commitment to “leave no one behind”—across national development and humanitarian actions.

	Please provide narrative description on the contribution towards the stated impact 

	The programme contributed to the stated impact by strengthening capacities and creating tools to advance disability inclusion in policies, services, and participatory mechanisms. Through coordinated actions in the justice, health, and governance sectors, it developed training processes, policy guidelines, and knowledge products that were co-created with organizations of persons with disabilities (OPDs). These initiatives promoted rights-based approaches, addressed barriers in areas such as legal capacity and sexual and reproductive health, and supported inclusive governance practices. The programme also fostered spaces for dialogue and advocacy, enabling OPDs to engage more effectively in decision-making and monitoring processes. 
Although national‑level institutional changes faced limitations, the programme helped consolidate advances and capacities at subnational levels, laying the groundwork for sustained progress towards the realization of the CRPD and sustainable development.




Reporting on the contribution to GDF impact (please see annex 1 for indicators)
	GDF Impact Indicator (please refer to approved proposal section 5 for relevant indicators selected by the programme)
	Country baseline  
(Beginning of the project reporting period)
	Country Endline  
(End of the project reporting period)
	Means of Verification

	Coverage of essential health services/Universal Health Coverage disaggregated as a proportion of the population, by sex, age and disability (SDG indicator 3.8.1)
	Argentina’s health system has historically been split into three distinct regimes: i) the contributory social security sector (covering 57 % of the population); ii) the contributory private health insurance sector (5.1 % of the population); and (iii) the public sector, providing free health care services to all but mostly used by the uninsured (37.9 % of the population). Those not insured by contributory sector, which consist mostly of the poor and vulnerable, have access to free, non- contributory (tax-financed) health care at health facilities in the public sector. However, services received from these health facilities are often of uneven quality. In addition, the uninsured are underserved in terms of preventive care.  
According to the 2021 UNICEF’s National Survey on Children and Adolescents, 6,8% of persons who needed medical assistance or medication did not access due to lack of money or transportation. In Northwest region, it reaches up to 11%. 
When analyzing by wealth quintiles, it is observed that in the lowest quintile the deficit amounts to 12%. 
There is no updated disaggregated data on disability.  
	The Single Disability Certificate (CUD) is key to reducing inequalities, as it guarantees access to essential services. However, access to it remains limited. Of the estimated 4.3 million people with disabilities in Argentina, only 1.680.723 had a CUD in November 2023 (ANDIS, 2023).
The health system faces significant challenges in providing comprehensive care to persons with disabilities. A medical-assistance approach still predominates, hindering early detection and access to appropriate treatments. Although medical coverage is similar between children and adolescents with and without disabilities, inequalities persist, reflected in a higher incidence of illness and lower rates of seeking medical attention among the population with disabilities. (UNICEF SITAN 2025)
The project has contributed by supporting the implementation of legal frameworks and policies related to legal capacity and sexual and reproductive health with disability inclusion perspective to enable PwD be able to fulfill their rights and access inclusive health services
	“Estudio personas con discapacidad” INDEC, 2018 https://www.indec.gob.ar/ftp/cuadros/poblacion/estudio_discapacidad_12_18.pdf 
SITAN, UNICEF 2025 https://www.unicef.org/argentina/media/27206/file/Resumen%20ejecutivo%20UNICEF%2015_12.pdf.pdf 
SRH guidelines and toolkits adapted to the realities of women with disabilities and diverse gender identities

	Increase of disability data/disaggregation (including by sex) within standard data and CRPD compliant collection processes.
	By building specific indicators to monitor legal capacity restriction sentences and on institutional approaches to motherhood processes of women with psychosocial and intellectual disability (disaggregated by sex) the State will count with more information to report and comply with CRPD’s standards. 
	The availability of statistical data disaggregated by disability is one of the major gaps in the country, especially information related to the exercise of legal capacity and processes and practices regarding persons with psychosocial and intellectual disabilities.
One of the results of the project was the development of specific indicators on these issues, which could serve as baselines to measure progress.
	Methodological guides for judicial actors in legal capacity proceedings



	SDG indicator 16.7.2 Proportion of population who believe decision-making is inclusive and responsive, by sex, age and population group.
	By opening systematic/permanent channels and mechanisms for the engagement and participation of PwD and OPDs, decision-making processes will be more inclusive and responsive
	Baseline was constructed during the implementation of the project. Also, Alternative reports for the human rights mechanism such as CRPD, CRC, among others. 
	A toolbox to support inclusive governance at the local level
Digital accessibility materials aimed at justice sector portals and information systems
The methodology and measurement instrument were designed to measure to access to justice (SDG 16.3.3) based on the specific needs and perspectives of persons with disabilities
CRPD Committee’s OPDs Reports 
HLPF, Argentina’s Third Voluntary Review 




	Outcome 1

	National Stakeholders have the knowledge and practical tools to effectively contribute the development and implementation of disability inclusive policies and systems
Throughout the 2022–2024 implementation period, significant progress was made under Outcome 1 in strengthening the capacities of key national actors—particularly in the areas of health, justice, and governance—toward the effective development and implementation of disability‑inclusive policies aligned with the CRPD.

In 2022, the project focused on establishing strategic alliances and engaging multiple government sectors through the design and implementation of training programs and seminars aimed at public officials across Argentina’s 24 jurisdictions. These capacity-building efforts were complemented by knowledge production on disability inclusion, particularly in the justice sector. Key milestones included the definition of a people-centered justice strategy for persons with disabilities, the identification of stakeholders in the civil and administrative justice systems, and the promotion of inclusive justice through pilot models aligned with CRPD principles. OPDs were also supported through connections with the Pro Bono Network and law clinics. In parallel, policy and practice guidelines were developed for sexual and reproductive health (SRH) services for persons with disabilities, in collaboration with OPDs and health authorities. 

In 2023, the project deepened its work with national institutions through capacity-building activities in both health and justice sectors, emphasizing sexual and reproductive rights and legal capacity. OPDs played a central role in co-developing protocols and tools to support persons with disabilities in navigating judicial processes. Technical materials and guides were produced to promote inclusive SRH services, with specific tools addressing the needs of women and diverse gender identities with disabilities. A roundtable with OPDs from across the country was organized to define joint advocacy strategies during the electoral cycle, and OPDs were supported in analyzing Argentina’s Third Voluntary Review of the 2030 Agenda. At the same time, the UN Country Team received targeted training on mainstreaming disability in programming, while exploratory work with judicial informatics teams advanced strategies for digital accessibility in justice services.

In 2024, capacity-building initiatives continued with a strong territorial component. Workshops were delivered to health professionals in Jujuy and to judiciary and public prosecutor personnel nationwide, emphasizing rights-based approaches to legal capacity determination. Information materials were produced to improve SRH access and digital accessibility, including graphic guides and easy-to-read formats. Legal system assessments were carried out, resulting in workshops and consultations aimed at legal reform and aligned with SDG indicator 16.3.3. A toolbox for inclusive local governance was also created, along with a mapping of good practices at the provincial and municipal levels. Across all actions, OPDs and persons with disabilities were meaningfully engaged, ensuring alignment with CRPD standards and reinforcing a participatory approach.

	Please provide narrative description on the progress made to achieve outcome 1 

	The joint program strategically combined training, technical assistance, and collaborative development of tools to improve the inclusion of persons with disabilities—particularly in the justice and health sectors.

One of the central achievements was the development and institutionalization of training programs for justice and health personnel, incorporating a human rights-based approach aligned with the Convention on the Rights of Persons with Disabilities (CRPD). These training initiatives, delivered in both virtual and in-person formats, contributed to increasing awareness and skills among public officials, enabling them to address legal capacity, accessibility, and inclusive sexual and reproductive health (SRH) services.

The program actively engaged organizations of persons with disabilities (OPDs) in the co-creation of protocols, practical guides, and strategic advocacy tools. This participatory methodology ensured that the knowledge products and policy recommendations reflected the lived experiences and needs of the disability community. Notable outputs include:

· SRH guidelines and toolkits adapted to the realities of women with disabilities and diverse gender identities
· Methodological guides for judicial actors in legal capacity proceedings
· A toolbox to support inclusive governance at the local level
· Digital accessibility materials aimed at justice sector portals and information systems
· The methodology and measurement instrument were designed to measure to access to justice (SDG 16.3.3) based on the specific needs and perspectives of persons with disabilities

In terms of policy dialogue and governance, the program successfully promoted national discussions through roundtables, consultations, and participation in monitoring frameworks such as the Voluntary National Reviews of the 2030 Agenda. Legal reform needs were identified through diagnostic studies and workshops, laying the groundwork for future legislative adjustments to better protect the rights of persons with disabilities.

Furthermore, by fostering cross-sectoral engagement—particularly among justice, health, and local government actors—the program cultivated long-term institutional relationships and generated political will to sustain disability-inclusive practices. A strong emphasis was placed on sustainability, with replication mechanisms built into the training strategies and the creation of user-friendly support materials.

Ultimately, Outcome 1 has strengthened the enabling environment for the realization of rights enshrined in the CRPD and reinforced national and local capacities to ensure that persons with disabilities are not left behind in public policy formulation and implementation.




	Outcome 2

	Gaps in achievement of essential building blocks or preconditions to CPRD implementation in development and humanitarian programs are addressed.

Across its three years of implementation, Outcome 2 focused on strengthening the legal and institutional ecosystem to ensure the full exercise of legal capacity and political participation of persons with disabilities.

In 2022, the groundwork was laid for high-impact legal reforms through alliances with key national stakeholders, including ANDIS, and strategic engagement in federal-level dialogue. The project-initiated diagnoses of the national and provincial legal frameworks—particularly the Civil and Commercial Code—and facilitated interinstitutional coordination to design participatory legal reform proposals. Complementary actions, including cooperation with the Legal Aid Providers Network of Buenos Aires and the co-design of a virtual access-to-justice guide, expanded innovation and collaboration in this area.

In 2023, the programme expanded on this groundwork by codeveloping regulatory proposals with OPDs and with teams from the health and justice sectors to strengthen the implementation of Resolution 65/2015 on SRH accessibility, and to advance the application of reasonable accommodations, support systems, and safeguards. Furthermore, training was delivered to public officials to ensure alignment with the CRPD and national legislation. Experimental workshops were held to empower OPDs and support their formalization, political participation, and access to institutional funding.

In 2024, Outcome 2 emphasized regulatory proposals and community-centered solutions. It delivered a validated public policy recommendation for the legal capacity determination process under Article 37 of the Civil and Commercial Code and further developed practical tools such as the Federal Replicability Manual and an Access to Justice Guide for persons with disabilities. A special focus was given to Indigenous communities in the Gran Chaco region, through participatory diagnostics, stakeholder mapping, awareness campaigns, and community workshops, with particular attention to women and children with disabilities.

Additionally, the project produced a Guide on Assistive Technologies and Universal Design for the justice system to improve digital equity and foster accessible political participation.

These achievements demonstrate a solid progression in the implementation of inclusive legal norms and the promotion of the rights of persons with disabilities, particularly those from historically excluded groups, such as people with psychosocial and intellectual disabilities and Indigenous communities.

	Please provide narrative description on the progress made to achieve outcome 2

	Throughout the three years of implementation, the project made significant progress in achieving Outcome 2, which focused on promoting inclusive legal and policy reforms aligned with the CRPD, and strengthening the participation and legal empowerment of persons with disabilities, including those from Indigenous communities and individuals with intellectual and psychosocial disabilities.

In the first year, the groundwork was laid by initiating a strategic dialogue with key stakeholders such as ANDIS and legal institutions, opening pathways to influence national legal reforms. Diagnostic assessments of the Civil and Commercial Code and provincial regulations were conducted collaboratively with OPDs and state actors, setting the stage for the co-creation of regulatory proposals. These efforts aimed to strengthen guarantees for the exercise of legal capacity and the design of inclusive justice systems.

Building on this foundation, 2023 focused on advancing concrete proposals. Working groups and roundtables were established to revise existing regulations—such as Resolution 65/2015 of the Ministry of Health—and to address the application of CRPD principles in healthcare and justice systems. These included recommendations for accessibility measures, reasonable accommodations, and safeguards. The project also delivered a six-session training series on the social model of disability for health and justice personnel, enhancing their understanding of inclusive legal frameworks. In parallel, workshops with OPDs focused on promoting political participation, organizational strengthening, and access to institutional financing.

In 2024, these efforts matured into actionable tools and public policy proposals. A comprehensive document was produced and validated by stakeholders to reform the legal capacity determination process, aligning it with Article 37 of the Civil and Commercial Code and CRPD standards. The project developed and disseminated a Federal Replicability Manual and an Access to Justice Guide for persons with disabilities, aimed at institutionalizing inclusive practices within the judiciary. These instruments were designed to be adopted at different government levels and replicated in diverse jurisdictions.

Particularly noteworthy were the initiatives carried out in Indigenous territories. Workshops and mapping missions were conducted in the Gran Chaco region, promoting dialogue on the unique challenges faced by Indigenous persons with disabilities. 

Additionally, a technical Guide on Assistive Technologies and Universal Design was developed for the justice system, offering sector-specific recommendations to advance digital inclusion for persons with visual, auditory, intellectual, and psychosocial disabilities.

Overall, the project's strategy combined national-level legal advocacy with territorial interventions and participatory processes. This approach ensured the creation of regulatory tools, guidelines, and campaigns that are context-sensitive, rights-based, and co-designed with persons with disabilities, reinforcing the sustainability and ownership of the outcomes achieved.



	Outcome 3

	National development and humanitarian plans, budgets, programs and monitoring processes are disability inclusive

Continuous collaboration with public institutions and the UN Country Team has resulted in the mainstreaming of disability in strategic planning instruments, monitoring mechanisms, and interagency communications. Persons with disabilities and their representative organizations have been meaningfully involved in consultations, contributing to inclusive public policy planning, capacity-building efforts, and the development of accessible information and tools. These actions have fostered sustained institutional change and positioned disability inclusion as a cross-cutting priority in sustainable development frameworks.

	Please provide narrative description on the progress made to achieve outcome 3

	In 2022, the project laid the groundwork for a stronger interagency strategy, enhancing the United Nations System’s ability to influence national development agendas in line with disability inclusion. The project supported the sensitization of the UN Country Team (UNCT), promoting the incorporation of disability in the implementation of the United Nations Sustainable Development Cooperation Framework (UNSDCF 2021–2025). This year served as a key period to engage system actors and set a common foundation for action.
In 2023, the focus shifted toward strengthening the participation of Organizations of Persons with Disabilities (OPDs) in national and international monitoring mechanisms. A national consultation roundtable was held, prioritizing the inclusion of underrepresented groups such as Indigenous women, children, and adolescents with disabilities in SDG follow-up. Two in-person training sessions were conducted for the staff of UN agencies in Argentina, introducing the social model of disability and human rights-based approaches. These sessions also provided a space for agencies to share best practices and identify challenges in mainstreaming disability in their respective mandates. Additionally, the project supported dialogue with the National Council for the Coordination of Social Policies (CNCPS) and the SDG Technical Commission, advocating for the harmonization of disability indicators in national monitoring frameworks.
In 2024, the project deepened these efforts through specific actions aimed at ensuring the inclusion of persons with disabilities in strategic joint development planning and information systems. A virtual consultation workshop with the disability community was organized as part of the Common Country Analysis (CCA) process, generating inputs for the diagnosis of the situation of persons with disabilities’ rights in Argentina  that informed a practical document with tools and guidelines for integrating disability into the UN strategic programming. In parallel, lessons learned from a health-related workshop in Jujuy were systematized, highlighting key barriers and suggesting intersectoral strategies for inclusive service delivery.
Moreover, a specialized training was delivered to communication teams of all UN agencies in Argentina to improve document and content accessibility. This initiative, led in partnership with the OPD Libertate, resulted in a guideline with practical recommendations for ensuring inclusive communication practices. The materials produced allow for continued internal capacity building and institutional work in relation to disability inclusion.
Together, these efforts demonstrate a coherent and consistent approach to positioning disability as a cross-cutting issue in strategic development planning, by reinforcing institutional capacities and promoting participatory mechanisms aligned with international human rights standards.




2. Achievement of specific outputs 
Please complete by indicating what was achieved on each output and report against the output indicators. In the narrative, please describe any challenges during the output delivery. The narrative could include any qualitative results from the output activities that were completed, contextual specifics e.g. who are the beneficiaries? What are the intervention types? Any unexpected / unplanned results? 
Please complete one table per output and the relevant output indicators. Add as many tables as required. 
	Output 1.1.A 

	Governmental stakeholders strengthened their capacities to ensure the implementation of disability-sensitive regulatory frameworks, mainly Civil and Commercial Code and norms focused on sexual and reproductive rights, policies on service delivery and monitoring systems to assure the exercise of legal capacity with an intersectional approach in accordance with the implementation of the CRPD and SDG.

	Brief narrative description on completion of output 

	Throughout the implementation period, the programme fostered strong alliances with key national institutions, notably the Ministry of Health, the National Directorate of Sexual and Reproductive Health, Human rights Secretariat and the national disability authority (ANDIS), and various justice sector bodies. These collaborations were instrumental in advancing disability-inclusive regulatory frameworks and service delivery practices, particularly in the areas of legal capacity and sexual and reproductive rights.
In the health sector, technical documents, guidelines, and policy notes were developed in a participatory manner through roundtable discussions involving experts, OPDs, and national authorities and workshops. These resources strengthened the conditions for public healthcare providers across the country to guarantee the sexual and reproductive rights of persons with disabilities, especially women, girls, adolescents, and individuals with gestational capacity—using a gender, disability, and human rights-based approach.
In parallel, targeted training initiatives for health professionals in the province of Jujuy improved capacities to deliver accessible and inclusive healthcare services. Training materials, methodologies, and systematized documentation were produced to ensure replicability and institutional sustainability.
Within the justice sector, agreements were reached with multiple national and federal stakeholders to assess and improve procedures for determining legal capacity. Workshops for judicial officials and public defenders were conducted to align their practices with the CRPD, emphasizing the social model of disability and a rights-based approach. These sessions contributed to the development of a qualitative-quantitative study on legal capacity rulings nationwide, identifying challenges and good practices across jurisdictions.
Additionally, joint capacity-building initiatives between health and justice actors were implemented, creating a replicable experience that can serve as a model for future multi sectoral training efforts. Methodological frameworks and support materials were developed to facilitate the continued rollout of these sessions in different regions and institutions.
By incorporating intersectional perspectives, including gender and geographical diversity, the programme ensured that inclusive practices are integrated into both national policy development and local service delivery. These coordinated actions represent significant progress in institutionalizing disability-sensitive governance, promoting the exercise of legal capacity, and strengthening accountability mechanisms in line with CRPD commitments.



Reporting on Output 1.1 Indicators (Refer Annex 2)
	Indicator*
	Start level 
Baseline
(Beginning of the project reporting period)*
	Target*
	End level 
End line
(End of the project reporting period)*
	Means of Verification

	1.1 # of trainings (disaggregation by type of capacity building) developed and delivered in the UNPRPD programme. (Disaggregated by topics) 

	0

	
	2022
1 training program designed

	1 Trainer of trainers program on exercise of legal capacity:

(1) Training of Trainers Programme on Legal Capacity – Core Curriculum Design

(2) Training of Trainers Programme on Legal Capacity – Implementation and Methodological Tools

	
	
	
	2023

Six virtual training meetings were held for:
(1) judicial officials; 
(2) health care providers on legal capacity and informed consent in sexual and reproductive health practices for women and other persons with capacity to bear children with disabilities, focusing on psychosocial and intellectual disabilities.

	a. Training Design Proposal. Link:
https://drive.google.com/file/d/1MLkAT8AX53oZ_uFsc9KOoCMwosmbMrF5/view?usp=drive_link   
Executive Report. 
https://drive.google.com/file/d/1iXZ6pDQUyz3XWqX9HCRSjPTtbBYtG_d8/view?usp=drive_link  
Powerpoint presentations aimed specifically at health care providers and judicial officials.
https://drive.google.com/file/d/16I5aeHJtsg4utuTLP_oYZc6dG5jCdkEo/view?usp=drive_link    
https://drive.google.com/file/d/1wUQGf0IamkgX9ZuXCWbI0Pgpf3ZxOdGB/view?usp=drive_link    
https://drive.google.com/file/d/12Tb7RDw05UFH2KKw8cn1fnxf-uWf_V49/view?usp=drive_link    
https://drive.google.com/file/d/1AKyTT6OpyuSrBm-NNgaugmuWQEZiXk8u/view?usp=drive_link      
https://drive.google.com/file/d/1SvCoCyyLBc2BD34e6jCVxTvcCYXv-eLZ/view?usp=drive_link    
https://drive.google.com/file/d/1yiXtMKA6gRTETnXrRnkaWt56TSTkVudb/view?usp=drive_link  
Training recording.
https://drive.google.com/file/d/1wogUnB_-OjEz69ve0sV-VHUq_B_EfEEF/view?usp=drive_link    
https://drive.google.com/file/d/1858t9AKF1w8St_O3zV-9MR7ybOF3mK2F/view?usp=drive_link    
https://drive.google.com/file/d/1T6XsCISGOJFpziQlbnQ42k0dEAB1Rwnx/view?usp=drive_link     
https://drive.google.com/file/d/1c2a9uTu9CV3LtWZwfWyktcklMaiHvu-i/view?usp=drive_link     
https://drive.google.com/file/d/1MI436cHZyFnFe5jbJ_r6Gf84-lI7Hs5P/view?usp=drive_link    
https://drive.google.com/file/d/1_l9QP5mYBPMN4zZz5GJ0a-VtEunDp8a8/view?usp=drive_link 

	
	
	
	2024 

A two-day training was held for sexual and reproductive health teams in the province of Jujuy on accessibility to care for people with disabilities. Practical tools for care (Consultants Carolina Buceta and Constanza Leone, experts with disabilities)

	Workshop report 

	
	
	
	2024

A three sessions workshop was held for officials and employees of the Judiciary and the Public Prosecutor's Office with competence in processes of determination of legal capacity on social disability perspective 


In this activity, a validation process is carried out with DPOs, civil society and actors

	
Workshop Implementation of the CRPD in judicial processes for determining legal capacity proposal 

Materials:  PPT Taller

Workshop report

Photos/screenshots

Sample of certificates delivered 
Document of systematization of the training process.

Blog Post




	
	
	
	2024

A two-session workshop was held on the need for regulatory reform at the federal level to strengthen the legal capacity and access to justice of persons with disabilities 
	
Workshop recordings

Participation certificates

 Workshop Rapporteurship

 Report of the workshop on the need to reform provincial procedural codes in civil and commercial matters

PPT Workshop 

	
	
	
	2024

A training workshop for health services in the public sector was conducted, focusing on sexual and reproductive health teams in the Gran Chaco region. Additionally, a policy document was developed based on this experience
	
Sexual and Reproductive Health and Persons with Disabilities Program - JUJUY December 2024 

Systematization of the workshop on Sexual and Reproductive Health of Persons with Disabilities in Jujuy

	
	
	
	2024 

A systematization document of materials used in the 2023 training for health professional and justice employees together was developed to ensure the replicability of the experience. 
	
Materials for a training Health professionals and justice system employees.   


	
	
	
	2024

A methodological proposal was developed for the replication of training on the perspective of the rights of persons with disabilities aimed at health and justice teams, based on the experience of the 2023 federal workshops. 
	
Final document  

	1.2 # of participants (disaggregated by type of stakeholder3) disaggregated by sex,disability,rural/urban participating in capacity building activities funded or provided by UNP
RPD programmes
	0
	
	2023 

64 participants attended the training workshop on legal capacity of PwDs
33 health professionals and
31 justice officials.

52 self-perceived women and 8 self-perceived men.

	a. Strategy and list of participants. 
https://drive.google.com/file/d/1_57-q48GLmwIsjmO6MSm7Kpe9OZ-B-dF/view?usp=drive_link  

List of participants. 
Justice
https://docs.google.com/spreadsheets/d/1TFWv3QmgnwOJ6a1C7Q8jmAcP_5ChGFEE/edit?usp=drive_link&ouid=115811457014945646486&rtpof=true&sd=true  
health
https://docs.google.com/spreadsheets/d/1uwgS3SUQssU8YYWcv3yZSlDlTaiCBXrl/edit?usp=drive_link&ouid=115811457014945646486&rtpof=true&sd=true  


	
	
	
	2024

37 participants attended the training workshop on accessibility on sexual and reproductive health services in Jujuy.
33 self-perceived women and 4 self-perceived men.

	List of participants page 6. 

	
	
	
	2024

137 participants attended the training workshop. 
121 self-perceived women and 16 self-perceived men

	Participants
Inscriptions 

	
	
	
	2024

A total of 55 participants attended the workshops. 
25 OPD of 12 provinces were invited  

	Participants on all sessions 

OPDs invited 

	1.3 # and % of participants reporting increased knowledge or capacity to design or revise policies or systems to be more disability inclusive.















 
	0 
	
	2023

a. A survey was conducted at the end of the training and 26 participants responded. A total of 96% of the participants considered that the workshop was useful for their professional activity.

The training was aimed at teams from Argentina's public health system and was attended by teams from 8/24 provinces. 
Teams from provincial ombudsmen's offices in charge of sponsoring legal capacity restriction processes and ensuring access to justice for persons with disabilities were also trained, with the participation of officials from 18 of Argentina's 24 provinces

	
Executive Report
https://drive.google.com/file/d/1iXZ6pDQUyz3XWqX9HCRSjPTtbBYtG_d8/view?usp=drive_link 

	
	
	
	2024

All participants reported increased knowledge and overall satisfaction with the experience.
	Final document

	
	
	
	2024

A survey was conducted, only a response rate of 4% was obtained for the post-workshop survey. This is common in the judiciary. However, all the people who responded to the final survey reported having increased their knowledge and are satisfied with the workshop.
	Final survey

	1. 4 # of OPDs (disaggregated by type umbrella- disability specific- women- underrepresented others) that benefitted from capacity building activities (type of activities4) funded by UNPRPD programmes to strengthen the capacity of organizations of
	Not applicable[footnoteRef:3] [3:  The workshops were given to government and judicial officials, and not to members of civil society, so it is not possible to complete this indicator] 

	
	Not applicable
	Not applicable

	1.5 # of capacity building activities funded by UNPRPD programmes, directed at women and girls with disabilities on their rights and requirements and/or directed at underrepresented groups of persons with disabilities on their rights and requirements. (disaggregated by target group) 
	0
	
	2023 

A participatory process was carried out with two roundtables for the development of the technical document on Res 65/2015 of the Ministry of Health to broaden and deepen its scope, particularly with regard to the autonomy of persons with disabilities and the implementation of interventions and practices of sexual and reproductive health service providers to ensure the promotion of independent and autonomous life of persons with disabilities.

	Report on the "Status of Resolution 65/2015 referred to persons with disabilities in their relationship with the health system: challenges and proposals for its implementation."
https://docs.google.com/document/d/1D896GbeA9ETYjwAedOVRD4Ivr7kvFFPb/edit?usp=drive_link&ouid=115811457014945646486&rtpof=true&sd=true  
Concept note on the Exchange Meetings to reflect on the scope, implementation and challenges of Resolution 65/2015.
https://docs.google.com/document/d/1EcrJLOfMp0KBPJJKbZB9FWwdlADo9-Y0/edit?usp=drive_link&ouid=115811457014945646486&rtpof=true&sd=true 



	
	
	
	Overall indicator through implementation project (2022-2025)

Since it is not possible to repeat the activities, we want to emphasize that all the activities developed in the project have had a gender and intercultural perspective, prioritizing both women and girls with disabilities and indigenous people with disabilities as groups of special vulnerability in Argentina. In particular, activities related to sexual and reproductive health have focused on the rights of girls and women with disabilities. As well as activities developed in the Gran Chaco region, particularly in Jujuy province for indigenous women with disabilities rights.

	







Please add new tables if the programme has more outputs under 1.1 

	Output 1.2: 

	Capacity of OPD´s is strengthened to ensure their meaningful participation and to undertake advocacy strategies.

	Brief narrative description on completion of output 

	The participation of persons with disabilities and their representative organizations (OPDs) was a central pillar of the project across its different lines of work. Activities were developed in close collaboration with OPDs and experts with disabilities, who contributed in diverse roles to the design and implementation of initiatives. Particular attention was given to amplifying the voices of historically underrepresented groups within the disability movement, such as women, girls, adolescents, young persons with disabilities, and persons with intellectual and psychosocial disabilities.
The project implemented activities aimed at strengthening OPDs’ capacity to advocate for their rights and engage meaningfully in public policy processes. This included support for formalization processes and the creation of partnerships with other organizations, enabling them to access funding and participate in national and international human rights monitoring mechanisms. Training and support also focused on enabling OPDs to draft and submit reports and engage with follow-up mechanisms tied to the implementation of human rights instruments.
One significant milestone was the coordination of a nationwide OPD consultation ahead of the 2023 presidential elections in Argentina. The project contributed to the process led to the development of a consensus document outlining urgent demands and priority actions for the disability movement. The document was presented to presidential candidates and emphasized key issues such as the protection of sexual and reproductive rights and the rights of persons with intellectual and psychosocial disabilities, serving as a strategic tool for national advocacy.
During the reporting period, the project also sought to pilot a program to support OPDs in regularizing their legal status. However, implementation challenges emerged as OPDs indicated that the primary barrier was not legal formalization itself, but rather the lack of material and financial resources necessary to sustain an organizational structure. This evidence informed an adjustment in strategy, with greater emphasis placed on understanding systemic barriers and identifying alternative, more context-sensitive mechanisms to support OPD engagement in decision-making spaces.


Reporting on Output 1.2 Indicators (Refer to Annex 2)
	Indicator*
	Start level 
Baseline
(Beginning of the project reporting period)*
	Target*
	End level 
End line
(End of the project reporting period)*
	Means of Verification

	1.1 # of trainings (disaggregation by type of capacity building) developed and delivered in the UNPRPD programme.
	1  Webinar for OPDs with federal representation to strengthen SDG monitoring and reporting in Argentina.

1  Webinar on strengthening the dialogue between PwD organizations.
	
	2022
Participatory virtual workshop focusing on legal capacity and sexual and reproductive rights


	Strengthening dialogue among organizations of persons with disabilities – OPD Roundtable

PPT workshop

	
	
	
	2023

A workshop was held to strengthen the organizational capacities of the DPOs to promote knowledge of the formalization processes of the DPOs and strategies for collaboration in fund and project management processes.
	Work Plan by Diana Maffia. 
https://drive.google.com/file/d/1i1g61P1aBNHpT52MKiQhbE_KT8E_gaFQ/view?usp=drive_link
Final Report of the Workshop on Strengthening the Organizational Capacities of Organizations of People with Disabilities. 
https://drive.google.com/file/d/1n34-OmjSOSeR3HwNxX9n9l5DljHEqVt-/view?usp=drive_link 
Concept Note of the Workshop on Strengthening the Organizational Capacities of Organizations of People with Disabilities. 
https://drive.google.com/file/d/1LIbIFZ9SsErbSFJ6It0PgT9GuuBY2mGc/view?usp=drive_link 
Contents of the Workshop on Strengthening the Organizational Capacities of Organizations of Persons with Disabilities.
https://drive.google.com/file/d/19nwW_OnZ1fHJ6OPyRLHg3QJUkUMECh3A/view?usp=drive_link 
Presentation of the Tierra Violeta Workshop
https://drive.google.com/file/d/1sGEfK6XDQYeElTon4IrooERb1VKfUkiK/view?usp=drive_link 

	
	
	
	2023

Two training meetings were held to strengthen the capacities of OPDs to participate in the CRPD implementation monitoring reporting mechanisms, with the aim of supporting the process of producing alternative reports for the CPDC committee, other UN human rights mechanisms (UPR and SP) and other international bodies, in particular, the monitoring of the SDGs and reporting on their implementation. 

	 
Reports on the training meeting
https://drive.google.com/open?id=1pR54qHIy48AP64U0ygDSKEF49Lh1Fl4b&usp=drive_fs 

https://drive.google.com/open?id=1pOkRdTbyG60U0VRaakxp5djnhdL9s5AY&usp=drive_fs 


	1.2 # of participants (disaggregated by type of stakeholder3) disaggregated by sex,disability,rural/urban participating in capacity building activities funded or provided by UNP
RPD programmes .
	0
	
	2023 

Two training meetings were held to strengthen the capacities of OPDs to participate in the CRPD implementation monitoring reporting mechanism
	List of participants https://docs.google.com/spreadsheets/d/1LysJlS3he_-jvhSWszZn_ucl_4nY5-hb/edit?usp=drivesdk&ouid=115811457014945646486&rtpof=true&sd=true 

	
	
	
	2024

According to the workplan, we planned a pilot program to support OPDs in regularizing their legal status. However, contrary to our initial analysis, OPDs lack the material conditions to sustain legal entity status, posing challenges for their effective participation.

	
Note to the file, justification of changes in this activity

	1.3 # and % of participants reporting increased knowledge or capacity to design or revise policies or systems to be more disability inclusive.
	 
	
	
	

	1. 4 # of OPDs (disaggregated by type umbrella- disability specific- women- underrepresented others) that benefitted from capacity building activities (type of activities4) funded by UNPRPD programmes to strengthen the capacity of organizations of persons with disabilities.
	
	
	2022

2 virtual seminars:

1 Virtual seminar for
Organizations of Persons with Disabilities with federal representation of Argentina to strengthen the monitoring and reporting of the SDGs in Argentina. Participation of 14 OPD.
	
1 virtual on strengthening the dialogue between the
organizations of persons with disabilities. Debate and partnership building. Participation of 37 PwD.

	
The names and affiliations of participants are mentioned throughout the activity report

	
	
	
	2023 
Within the framework of the activities developed throughout the project during the year 2023, 34 OPDs participated in training activities.

Broken down by type of disability: 
4 OPDs for visual impairment
4 hearing disability OPDs
1 OPD on autism 2 OPD  psychosocial disabilities
13 intellectual disability DPOs
10 umbrella DPOs


	List of DPOs
https://docs.google.com/spreadsheets/d/1JXrfgIpjSz7dwpAnMk_cV-vNSWfO1fn0/edit?usp=drivesdk&ouid=115811457014945646486&rtpof=true&sd=true 

	1.5 # of capacity building activities funded by UNPRPD programmes, directed at women and girls with disabilities on their rights and requirements and/or directed at underrepresented groups of persons with disabilities on their rights and requirements. (disaggregated by target group) 
	0
	
	2023

A workshop was held with the aim of generating a space for reflection and exchange among young people to contribute to a more inclusive society through the use of social networks.
	Digital Barriers to Diversity Workshop. Disability and the role of youth in contributing to an inclusive society.
https://drive.google.com/drive/folders/1Jb12FNMfaHMt-OUmFNLeHWO0GMNLBEhT 


	
	
	
	2023

A roundtable was held for consultation and participation of OPDs with emphasis on underrepresented groups of OPDs (indigenous women, children and adolescents with disabilities) to strengthen capacities for participation in monitoring mechanisms for the implementation of the SDGs and the rights established in the CRPD
	 Concept Note on "Exchange meetings to strengthen the disability perspective in the monitoring and reporting mechanisms of the SDGs" REDI.
https://docs.google.com/document/d/1Q07vBcEkkgiOPQmPLJsjaQf7tl43xVXf/edit 


	
	
	
	2023

A round table of 3 meetings was held to present an agenda of demands of the OPDs to the candidates in the framework of the 2023 elections, focusing on mental health and sexual and reproductive health.

	Report on the proposal of electoral candidates.
https://drive.google.com/file/d/19mSOnKnVoOM4CuTfQ36tyh1sKy9kMAHo/view?usp=drive_link  
OPDs consultation and participation roundtables:
https://drive.google.com/file/d/19Cne0VPbsVPVw_fQzE8zMjq8KBJvCST8/view?usp=drive_link  

https://drive.google.com/file/d/1ECP6coPUtcBzgpzhf_5ZGR0-XEMudEq7/view?usp=drive_link 

Roundtable report for the presentation of an agenda: 
https://drive.google.com/file/d/1-JV4-KcOqxkTXwQOy0R5NEbD6cEbO7r3/view?usp=drive_link 



Please add new tables if the programme has more outputs under 1.2

	Output 1.3: 

	Capacities of UNCT Argentina strengthened the mainstream disability perspective in all UNS activities.

	Brief narrative description on completion of output 

	Training sessions were attended by UN staff from different areas—including communications, administration, procurement, programmes and technical teams, external consultants, and agency leadership—allowing for the identification of institutional good practices, as well as challenges in applying inclusive principles in day-to-day work. The participatory structure of these sessions encouraged cross-agency dialogue and solution-building, fostering a collaborative environment for addressing operational and strategic barriers to inclusion.

One of the key achievements was the design and delivery of specialized training for communication teams across all UNS agencies, focusing on accessible and inclusive communication practices for publications, digital content, and in-person and virtual events. These sessions laid the foundation for improved internal capacity and were structured to enable replication and dissemination within each agency, thereby expanding the reach and sustainability of the intervention.

Complementing the training, a practical accessibility guide was developed to support the implementation of inclusive communication practices throughout the system. The guide offers standardized criteria and concrete tools to ensure accessibility in documents, events, and outreach strategies. Its application reinforces the alignment of UNS Argentina with the principles of the CRPD and the Sustainable Development Goals (SDGs), promoting more equitable engagement with persons with disabilities.

By embedding accessibility into communication workflows and institutional culture, the initiative not only strengthened technical knowledge but also encouraged a structural shift towards inclusion. This approach enhances the ability of the UN system in Argentina to ensure that persons with disabilities are meaningfully included and represented in its activities, thereby contributing to more inclusive policy and programming outcomes.


Reporting on Output 1.3 Indicators
	Indicator*
	Start level 
Baseline
(Beginning of the project reporting period)*
	Target*
	End level 
End line
(End of the project reporting period)*
	Means of Verification

	1.1 # of trainings (disaggregation by type of capacity building) developed and delivered in the UNPRPD programme.
	0
	
	2022

IMS UN System annual reports
	

	
	
	
	2023

Conducted 2 Training Days for UNS staff on HRBA and inclusion of disability in the implementation of the UNSDCF and joint programs, projects or initiatives.

	 Final Report. 
https://drive.google.com/file/d/1bjTZzKaoDEWXSTgURsRc6ydCdzYZ8IqJ/view?usp=drive_link  
Concept Note on Training of United Nations System (UNS) staff on the human rights-based approach and disability inclusion.  
https://docs.google.com/document/d/1-TsIfjLY0a20RVdJPgheQx1vYFIU_xj_/edit?usp=drive_link&ouid=115811457014945646486&rtpof=true&sd=true   
Material used in the Training Seminars.
https://drive.google.com/file/d/1De3cLpzMEss08yBK82ETlQYCNPh_8Q6V/view?usp=drive_link   
https://drive.google.com/file/d/1CTxK6LrijzEylc6XSOvG5aWNXdRjuRJX/view?usp=drive_link  
https://docs.google.com/presentation/d/1aWup0omW1BBKlsyx2dOpt5yV5l-ib9c3/edit?usp=drive_link&ouid=115811457014945646486&rtpof=true&sd=true   
https://docs.google.com/presentation/d/1CVaG9HGlUG25gph6BDBcd96LHoG7J-ze/edit?usp=drive_link&ouid=115811457014945646486&rtpof=true&sd=true   
Photos and Videos. 
https://drive.google.com/drive/folders/1nX-huHY3Z3PN2vgdswM2ZCi_Mgm9XLMB?usp=drive_link 

	
	
	
	2024

A two-day training was conducted for the communication teams of all UN agencies in Argentina to enhance their skills in accessible communication across all system activities. The content was designed based on the results of two interest and needs assessments on the topic, one carried out in 2023 and another in 2024 as part of the workshop planning process
	Concept note for the workshop

Materials for communications teams 

Photos and videos

	1.2 # of participants (disaggregated by type of stakeholder3) disaggregated by sex,disability,rural/urban participating in capacity building activities funded or provided by UNP
RPD programmes .

	0
	
	2023

 A total of 32 participants from various United Nations agencies took part in the “2 Training Days for UN staff on Human Rights-Based Approach (HRBA) and the inclusion of disability in the implementation of the UNSDCF and joint programmes, projects or initiatives”.
	Attendance record:
https://drive.google.com/file/d/1M5AvqSo7w4jtmMtJNXPHNwOgmT62bY_d/view?usp=drive_link   
https://drive.google.com/file/d/1oYMmTAhaF6kbY5ayJiErq0qzoiVnr2dF/view?usp=drive_link  


	
	
	
	2024

Since the training was conducted in a workshop format and designed to be participatory, participation was limited to 20 people, with a maximum of two representatives per agency's communication team who could later replicate the content with the rest of their teams.

A total of 19 participants attended the two-day training. 

Five self-identified as men and 14 as women


	
Participants and satisfaction survey

	1.3 # and % of participants reporting increased knowledge or capacity to design or revise policies or systems to be more disability inclusive.
	0
	
	2024

All respondents indicated that they increased their knowledge 


	Participants and satisfaction survey

	1. 4 # of OPDs (disaggregated by type umbrella- disability specific- women- underrepresented others) that benefitted from capacity building activities (type of activities4) funded by UNPRPD programmes to strengthen the capacity of organizations of persons with disabilities.
	0
	
	2024
A guide was developed to facilitate accessibility and documents, events and communications of the SNU Argentina 
	Guide final document 

	1.5 # of capacity building activities funded by UNPRPD programmes, directed at women and girls with disabilities on their rights and requirements and/or directed at underrepresented groups of persons with disabilities on their rights and requirements. (disaggregated by target group
	0
	
	
	



Please add new tables if the programme has more outputs under 1.3

	Output 1.4: 

	Development and testing of knowledge products to address gaps in achieving autonomy for independent living for people with disabilities. 

	Brief narrative description on completion of output 

	The project addressed significant knowledge gaps that hinder the effective implementation of the Convention on the Rights of Persons with Disabilities (CRPD) by developing and disseminating accessible information products tailored to the needs of persons with disabilities, their families, and allies. These efforts aimed to promote awareness of rights, provide guidance on available enforcement mechanisms, and offer clear pathways for filing complaints in cases of rights violations.
Key areas of focus included access to and meaningful participation in legal capacity determination processes, redefined as procedures for the co-design of support systems, reasonable accommodations, and safeguards for autonomous decision-making. Additionally, efforts were directed at facilitating informed and independent access to quality sexual and reproductive health services, ensuring access to legal services for participation in diverse judicial proceedings, and incorporating an intersectional and intercultural approach to rights enforcement, particularly relevant in northern Argentina.
Knowledge products were developed in multiple accessible formats and inclusive language, enabling direct engagement by persons with disabilities. These resources supported both awareness-raising and the institutionalization of inclusive practices within key public services.
In the health sector, policy documents, training materials, and models of inclusive care, such as those developed in Jujuy and the City of Buenos Aires, provided actionable tools to improve service accessibility and uphold the sexual and reproductive rights of persons with disabilities. These models have laid the foundation for broader institutional adoption and replication.
In the justice sector, the project produced empirical evidence and policy recommendations to guide reforms related to legal capacity. The analysis of judicial rulings and structural barriers to access to justice informed legislative discussions and fostered dialogue with institutional stakeholders. This ensured that policy development and implementation are grounded in human rights standards and the lived experiences of persons with disabilities.
The project also created innovative communication tools, such as a video toolbox for deaf persons addressing gender-based violence, demonstrating a commitment to tailoring resources for underrepresented groups. This intersectional approach reinforced the importance of adapting strategies to diverse forms of disability and social identity.


[bookmark: _heading=h.nx8y6cyhkpk8]Reporting on Output 1.4  Indicators
	Indicator*
	Start level 
Baseline
(Beginning of the project reporting period)*
	Target*
	End level 
End line
(End of the project reporting period)*
	Means of Verification

	1.4.1. # of knowledge products (disaggregated by type of product23/thematic focus24) developed, piloted and disseminated to the relevant stakeholders to inform inclusive practices
	0
	
	2022

3  guideline on productive and sexual health



	1 guideline: 
Sexual and reproductive health: comprehensive and inclusive care

2nd guideline: 
Technical note on Voluntary interruption of pregnancy for people with disabilities 

3rd.guideline: Surgical contraception


	
	
	
	2022

1 Technical note on implementation on disability inclusion standards 

	
Document

	
	
	
	2022

2 policy papers
	
1.Implementation of supports and safeguards

2 Accessibility measures


	
	
	
	2023

A practical guide was developed for the participation of persons with disabilities in the process of determining legal capacity, especially in relation to Art. 37 of the CCC.
	 Guide to Legal Capacity. Process for determining legal capacity in easy reading.
https://drive.google.com/file/d/1b8gOKf2f5HHnSLSaFA52uqREN4vp0Zg8/view?usp=drive_link 

	
	
	
	2024

An information booklet for health professionals was prepared on the rights of persons with disabilities in access to sexual and reproductive health.
	Handbook on SRR for people with disabilities -12-8-24

	
	
	
	2024

Development of a digital graphic booklet on the rights of persons with disabilities in sexual, reproductive and non-reproductive health. 



	Booklets designed 

	
	
	
	2024

A methodoly design for a study of the justice needs and levels of access to justice of persons with disabilities in Argentina was carried out, in the application of indicator 16.3.3. of the SDGs, through a Consultation and Analysis Process on the Legal Capacity of Persons with Disabilities in Access to Justice
 
In this framework, a meeting was held with the collective intelligence methodology to feed the participatory design of an instrument to measure access to justice for people with disabilities in Argentina.

	
Final report 

Design of collective process

Instrument



Agenda

List of participants

Materials

	1.2.2. # of knowledge products developed that address gaps related to inclusion of women and girls with disabilities and/or underrepresented groups of persons with disabilities (disaggregated by thematic focus)
	0
	
	2023 

A knowledge product was developed on the barriers to access to sexual and reproductive health for people with disabilities, particularly women, girls and adolescents.

	Document "Barriers to access to reproductive and non-reproductive sexual health of women with disabilities".
https://drive.google.com/file/d/1_wJ5TssY-Dv6TKUdtFsYWtHTDKhw3cl6/view?usp=drive_link  

	
	
	
	2023 

A report was made on the needs for the inclusion of people with disabilities in the Northern Region.
	 Needs Assessment for the Inclusion of
inclusion of people with disabilities from the voices of the Northern Region.
https://drive.google.com/file/d/1llfTvhgT-DGyfkEjHNpCfQkpIfvJRuP5/view?usp=drive_link 

	
	
	
	2023 
Document on support systems, adjustments and safeguards. Definitions and recommendations for their implementation in Argentina.
	Support system, adjustments and safeguards document: https://argentina.unfpa.org/es/publications/sistemas-de-apoyo-ajustes-razonables-y-ajustes-de-procedimientos-definiciones-y 

	
	
	
	2023  
Guidelines to complement the Universal Design Initiative and accessibility of judicial portals in Argentina. It was carried out through a participatory process involving mainly visually impaired legal professionals
	Report of activities for the participatory elaboration of accessibility guidelines:  
https://drive.google.com/file/d/1Gh_oEMJYS-tbVXpFc_CeRSY_K0frq--N/view?usp=drive_link  
Guidelines for accessibility of judicial portals
https://docs.google.com/presentation/d/1wABI1_CX5PEM6I_MSEHyzCOf5I2SAD6I/edit?usp=drive_link&ouid=115811457014945646486&rtpof=true&sd=true   
Presentations on Accessible Judicial Portal.
https://docs.google.com/presentation/d/1-PL0XQGMq97n50tShusPiqRyiKV583MO/edit?usp=drive_link&ouid=115811457014945646486&rtpof=true&sd=true   
https://docs.google.com/presentation/d/18nX5S2Eg8gzz35_vih7v8asXoiTXcXpG/edit?usp=drive_link&ouid=115811457014945646486&rtpof=true&sd=true   
Report "Systematization of the testing process of the accessibility reform in the justice system" by Hector Chayer's consultancy. 
https://drive.google.com/file/d/1yfxsSvFTv23lCZfN0GeRESdEZjRFZlFW/view?usp=drive_link   


	
	
	
	2024

A public policy document was developed on the experience in the province of Jujuy in northern Argentina, in carrying out comprehensive sexual and reproductive health counseling for adolescents with disabilities. The document sought to promote the replicability of the experience based on the adaptation of the provisions of the Plan for the Prevention of Unintentional Pregnancy in Adolescence (Plan Enia) that was recently dismantled
	Final document  
 
Concept note Jujuy 

	
	
	
	2024

A public policy document was developed to systematize the care model promoted in a specialized health center for sexual, reproductive, and non-reproductive health care for persons with mental disabilities in Buenos Aires City.
	Final document 

	
	
	
	2024

A public policy document was developed to systematize the training experience led by the Ministry of Health of the province of Jujuy, aimed at sexual and reproductive health teams for the care of persons with disabilities. The training follows the guidelines established in the CRPD and local regulations.
	Final report 

	
	
	
	2024

A video toolbox for deaf people was developed, with the aim of providing tools for addressing and reacting to situations of gender violence against deaf people, mainly women and diversities. 
	Toolbox videos

	
	
	
	2024

An easy-to-read brochure was developed, which addresses the sexual and reproductive rights of people with disabilities, demystifying prejudices and promoting access to a full and autonomous sexual life.
	Brochure easy to read y 

	
	
	
	2024
A diagnosis was developed on judicial proceedings related to the restriction of legal capacity in Argentina, focusing on access to justice for persons with disabilities according to CRPD.

	Final report. Contains findings on a federal sample of judicial decisions regarding legal capacity of PwD. 


Appendices. Here are 10 documents with methodological, and logistical information on the research. 

	
	
	
	2024 
A regulatory analysis of the needs for reform at the federal level to strengthen the legal capacity and access to justice of persons with disabilities
	Policy Framework Analysis Paper

Final Report: Legal Capacity and Access to Justice for Persons with Disabilities: A Federal Policy Analysis 

Paper Blog 

	
	
	
	2024

An analysis of the institutional capacities of the Federal Council of Public Defenders in Argentina to guarantee access to justice for persons with disabilities was carried out.
	Final document 

Annexes 

	
	
	
	2024

A document of guidelines and recommendations to strengthen the institutional capacities of local governments was developed in alliance with REDI.
	Document with contributions to legal research on the rights of persons with disabilities in Argentina (REDI)

	
	
	
	
	




	Output 1.5: 

	Model platform for the participation of OPDs in monitoring of international human rights recommendations and access to justice developed.

	Brief narrative description on completion of output 

	Throughout the project, efforts were made to strengthen the role of organizations of persons with disabilities (OPDs) in monitoring international human rights recommendations and improving access to justice. Initial challenges included difficulties in reaching agreements among government enforcement authorities regarding the installation of monitoring systems. Despite these early setbacks, the project progressed towards more sustainable strategies to reinforce the participation of OPDs in governance and decision-making processes.
One of the key achievements was the co-creation of a virtual training program aimed at promoting disability inclusion and awareness. This program, supported by accessible materials such as systematization documents and presentations, serves as a scalable and replicable tool that empowers public officials and stakeholders to incorporate inclusive practices in their work. Its participatory design ensures alignment with the lived experiences and demands of persons with disabilities.
In parallel, a guidance note documenting good practices implemented by local governments was developed. This note provides a framework to assist regional and municipal authorities in institutionalizing inclusive policies and strengthening the engagement of OPDs in policy design and implementation. These efforts support the decentralization of inclusive governance and reinforce the role of OPDs at all levels of government.
Additionally, a comprehensive systematization and evaluation of OPD participation mechanisms was carried out to identify effective models and facilitate their replication in other local contexts. A regulatory note complemented this analysis by linking participation mechanisms to national and international disability rights frameworks.
These actions have contributed to enhancing the advocacy capacity of OPDs and increasing their visibility in human rights monitoring and justice reform initiatives. While further work is needed to broaden the reach and impact of these mechanisms, the progress achieved establishes a solid foundation for inclusive and participatory governance structures that are more responsive to the rights and priorities of persons with disabilities.


[bookmark: _heading=h.4mwlu4pfysm6]Reporting on Output 1.5 Indicators
	Indicator*
	Start level 
Baseline
(Beginning of the project reporting period)*
	Target*
	End level 
End line
(End of the project reporting period)*
	Means of Verification

	1.3.3. # of mechanisms25 to share and exchange learning and evidence to inform inclusive policies and systems. (Disaggregated by national/ regional/global mechanism)
	0
	
	2024

A virtual training program to promote and raise awareness on disability inclusion was created.
	Support material

	
	
	
	
	Systematization document 

PPT 

	
	
	
	2024
A guidance note on
good practices implemented by local governments (provinces 
and/or municipalities) for the participation of persons with disabilities and 
Organizations of persons with disabilities.

	Guidance note for local governments
for capacity building
institutions that promote disability inclusion


	
	
	
	2024

A document was prepared for the systematization and evaluation of all the mechanisms for the participation of persons with disabilities within the project to promote replicability in other contexts, including local public policies. 
	Systematization of experiences from
the evaluation of the Methodology
Participatory

Regulatory note 





	Output 2.1: 

	Review of national laws and policies for effective exercise of legal capacity focused on the Civil and Commercial Code, National Electoral Code, administrative resolutions and internal regulations.

	Brief narrative description on completion of output 

	This process has focused on identifying legal gaps, proposing reforms, and developing tools to strengthen existing programs and regulations, with particular emphasis on the alignment with the Convention on the Rights of Persons with Disabilities (CRPD).
A key milestone was the development of a detailed report on the scope, challenges, and implementation of Resolution 65/2015 of the National Ministry of Health. This resolution is central to interpreting the Civil and Commercial Code regarding legal capacity and the autonomy of individuals to make decisions about their own bodies. The analysis informed the development of several regulatory documents, including:
· Guidelines for institutional intervention procedures addressing sexual and reproductive health, incorporating support systems, safeguards, and reasonable accommodations,
· Implementation standards for Law 27,655 (2023), which amended Law 26,130 to prohibit forced sterilizations and strengthen reproductive autonomy for persons with disabilities,
· Guidelines on inclusive sexual and reproductive health counseling,
· Regulatory interpretations on access to voluntary and legal termination of pregnancy (IVE/ILE) under Law 27,610.
These documents, developed in collaboration with the National Directorate of Sexual and Reproductive Health (DNSSR), hold regulatory status and guide healthcare providers in ensuring rights-based approaches to sexual and reproductive health.
In the justice sector, a policy proposal was formulated based on findings from a national diagnosis on legal capacity restriction proceedings. Validated through consultation with OPDs and key stakeholders, this proposal targets improvements in procedures governed by Article 37 of the Civil and Commercial Code. The recommendations aim to reinforce due process guarantees and align legal frameworks with CRPD standards.
Efforts also extended to enhancing the political and social participation of persons with disabilities. A mapping of national norms revealed barriers and gaps in current regulations. Based on this, recommendations were developed to improve digital inclusion, accessibility, and participation mechanisms, with the support of multi-stakeholder roundtables. This participatory approach not only fostered collaboration among public and civil society actors but also informed regulatory proposals aimed at ensuring the inclusion of persons with disabilities in civic life.
Moreover, practical tools were created to support health professionals in designing accessible information on healthcare rights for persons with disabilities. These tools facilitate the implementation of inclusive service delivery practices and contribute to reducing barriers in access to health services.
By integrating evidence-based analysis, inclusive consultations, and regulatory development, the initiatives under this output have laid a solid foundation for legislative and policy reforms that uphold the rights of persons with disabilities and foster institutional change across health and justice systems.


Reporting on Output 2.1 Indicators
	Indicator*
	Start level 
Baseline
(Beginning of the project reporting period)*
	Target*
	End level 
End line
(End of the project reporting period)*
	Means of Verification

	2.1.1. # of national regulatory frameworks and systems changes targeted by the UNPRPD program disaggregated by 1) legislation/regulation, 2) policies/plans/strategies, 3) capacity building programs, 4) operational guidance/standards, 5) direct services/service overhaul/service modelling, 6) audits/reviews/assessments, 7) governmental programs, administrative procedures, 9) formal monitoring and accountability mechanisms or bodies, 10) regulatory/oversite/monitoring systems, 11) financing and budgeting  or 12) other (please explain)
	Legislation and policies not aligned or partially aligned with CRPD obligations.
	
	2022 

Technical assessment to ANDIS submitted 

	
The assessment was conducted to a series of technical meetings 

	
	
	
	2023

2 Guidelines for access to sexual and reproductive health for persons with disabilities, in particular women, girls and adolescents: 
 a. technical note 11. Interpretation of the rules for the access of persons with disabilities to voluntary and legal termination of pregnancy I'VE-ILE. DNSSR.
b.  Booklet "Towards an inclusive sexual and reproductive health counseling for people with disabilities". 

	 a. Technical note 11. Interpretation of the rules for the access of persons with disabilities to voluntary and legal termination of pregnancy I'VE-ILE. DNSSR.
https://drive.google.com/file/d/14ibcg1oWgeSkZixZXqjcHEP681OP6jtS/view?usp=drive_link 


b. Booklet "Towards an inclusive sexual and reproductive health counseling for people with disabilities". 
https://drive.google.com/file/d/1grMHj36Ib2qTCf3QLMWVeclB6hyphJ2J/view?usp=drive_link 

	
	
	
	2023

Technical document to strengthen the standards for the implementation of Law 27.655 of 2023 that reforms Law No. 26.130 on surgical contraception, to prohibit forced sterilizations and reinforce the protection of the reproductive autonomy of PcD. 
	 Technical Note 8: Surgical contraception and persons with disabilities. DNSSR. 2023.
https://drive.google.com/file/d/1ClbNxGQxTKtAdnWT1RrfuQ9AGDnCHR3z/view?usp=drive_link 

	
	
	
	2023

Practical guidelines on institutional intervention procedures (including support systems, safeguards and reasonable accommodation) in addressing the sexual and reproductive health of women and other persons with capacity to bear children with disabilities, with a focus on psychosocial and intellectual disabilities. 
	Document "Support systems for people with disabilities and reasonable accommodation and procedural adjustments for people with disabilities".
https://drive.google.com/file/d/1Z6hW4zR9vicJIthERA8n6m9gek-U2fwb/view?usp=drive_link 

	
	
	
	2023

Report on the status, scope, challenges and implementation of Resolution 65/2015 regarding persons with disabilities.
	Report on the "Status of Resolution 65/2015 referred to persons with disabilities in their relationship with the health system: challenges and proposals for its implementation."
https://docs.google.com/document/d/1D896GbeA9ETYjwAedOVRD4Ivr7kvFFPb/edit?usp=drive_link&ouid=115811457014945646486&rtpof=true&sd=true   

	
	
	
	2024

Guidelines were developed to strengthen the skills of health and health management teams for the design of information material on the rights in health care of persons with disabilities, in accordance with the provisions of Resolution 65/15 of the Ministry of Health of the Nation
	Guidelines for the design of information material on the rights in health care of persons with disabilities, in accordance with the provisions of Resolution 65/15 of the Ministry of Health of the Nation


	
	
	
	2024

A policy proposal based on the findings of the "Diagnosis on legal capacity restriction court proceedings at the federal level" with OPDs and key stakeholders in order to improve the determination of legal capacity proceedings, in particular in relation to Art. 37 of the CCC was developed. 


Validation of the regulatory proposal to improve the procedure for determining legal capacity and its publication.

	Contributions to: Final Report - "Diagnosis of the processes of determining the
legal capacity of persons with
disability", by Unidos por la Justicia

Regulatory note 




Contributions from Civil Society: Reflections
on the processes of determining the Legal Capacity of Persons with Disabilities in Argentina

	
	
	
	2024

Recommendations document for strengthening regulatory frameworks and implementation of mechanisms that facilitate the political or social participation of persons with disabilities to improve accessibility and/or digital inclusion to guarantee the rights established in the CRPD was developed.


	Recommendations for Strengthening the Regulations for the Political and Social Participation of Persons with Disabilities in Argentina and Their Implementation Mechanisms


PPT workshop

Blog Text: Nothing About Us Without Us: Participation as a Key to Access Rights for Persons with Disabilities

	
	
	
	2024

Systematization of the validation process for the  proposal to strengthen regulatory frameworks that facilitate the political or social participation of persons with disabilities to improve accessibility and/or digital inclusion to guarantee the rights established in the CRPD.
	Systematization Report of the Roundtable Dialogue "Public Participation of Persons with Disabilities: Regulatory Framework and Measures for Its Strengthening" Recommendations for Strengthening the Regulations for Political and Social Participation of Persons with Disabilities in Argentina and Its Implementation Mechanisms

	
	
	
	2024

A diagnosis and mapping of norms of political and social participation of persons with disabilities in Argentina and their implementation mechanisms was carried out
	Diagnosis and mapping of norms of political and social participation of persons with disabilities in Argentina and their implementation mechanisms



Please add new tables if the programme has more outputs under 2.1

	Output 2.2

	Proposal for developing multi-stakeholder accessible platforms with a people-centered approach for ensuring effective and meaningful participation of OPDs, service delivery and data collection for the design, reform, and implementation of disability inclusive laws policies elaborated.

	Brief narrative description on completion of output 

	Initial work involved the participatory development and validation of accessibility proposals with OPDs and legal professionals with disabilities. These proposals led to the creation of general guidelines for improving digital platforms. A pilot implementation process was initiated in collaboration with the Council of the Judiciary of the City of Buenos Aires, involving direct coordination with the IT department. This process resulted in the first set of accessibility improvements, with a commitment to expand efforts in subsequent stages.
In parallel, multi-stakeholder coordination mechanisms were established to enhance inclusive policymaking, data collection, and monitoring. One of the key achievements was the mapping of legal capacity solutions and the identification of structural barriers to justice, particularly for persons with intellectual and psychosocial disabilities. This mapping served as a baseline for future reforms and included the compilation of best practices and innovative approaches.
The program also focused on advancing the inclusion of Indigenous persons with disabilities through targeted initiatives in the Gran Chaco region. A legal workshop engaged Indigenous women and children with disabilities, uncovering legal and social barriers while promoting their participation in community decision-making. These findings informed a preliminary mapping of advocacy actors and contributed to localized awareness strategies.
In Rivadavia Banda Norte, a focused awareness-raising strategy was deployed, incorporating community diagnostics, social media, community radio, and accessible outreach materials. These actions helped ensure that persons with disabilities, particularly in rural and Indigenous communities, received information about their rights and legal resources in culturally and linguistically appropriate formats.
To foster digital equity, a co-designed Guide on Assistive Technologies and Universal Design was developed through consultations with experts with disabilities. This guide offers technical recommendations to enhance accessibility in visual, auditory, intellectual, and psychosocial dimensions, promoting inclusive access to digital services and political participation.
Finally, the creation of a Federal Replicability Manual and a Guide to Access to Justice for Persons with Disabilities consolidated lessons learned and good practices into scalable tools. These resources are designed to inform future initiatives and support institutional replication across diverse regions and government levels.
Together, these advancements have strengthened the foundations for inclusive governance, expanded the role of OPDs in shaping public policies, and improved access to justice and political participation for persons with disabilities. The sustained engagement of stakeholders and the development of adaptable tools contribute to long-term systemic transformation towards equity and inclusion.


Reporting on Output 2.2 Indicators (Refer to Annex 2)
	Indicator*
	Start level 
Baseline
(Beginning of the project reporting period)*
	Target*
	End level 
End line
(End of the project reporting period)*
	Means of Verification

	2.2.1 # of multi-stakeholder coordination mechanisms (disaggregated formal/informal) to support legislative policy and systems changes developed or strengthened
	
	
	2023

Contributions to the accessibility of the Judicial Litigant Portal of the Autonomous City of Buenos Aires (CABA). 
The litigant portal is the platform used by both legal professionals and users of justice services to access court cases. From there, the movements of each process are made and known. This is why the accessibility of these portals is key both for the professional practice of people with disabilities and for their access to justice. Up to the time this activity was carried out, the court decision ordering the revision of the accessibility conditions of the judicial platforms had not been complied with, as they made the work of legal professionals with disabilities extremely difficult. 
The proposed modifications and the first steps taken show important results to meet this objective.

	Implementations for the accessibility of the judicial portal of the CABA Magistrature Council
https://drive.google.com/file/d/1BijiNFFOAJUop7n6BAgpm4_qn1jVTPSF/view 

	
	
	
	2023

Training day on digital accessibility in the judiciary: The objective was to present the work done to promote the accessibility of judicial portals, promoting spaces for reflection with technical teams of judicial management, access to justice and technology development with people with disabilities to find common and possible strategies to improve accessibility.

	Training day on digital accessibility in the judiciary:
Contributions to the construction of an Accessible Judicial Portal.
https://docs.google.com/document/d/1Q0PG8S4q_9ps9Z-EahhBfy62hrNuDIwo/edit?usp=drive_web&ouid=100062833870042773392&rtpof=true 

	
	
	
	2023

International Meeting: Support strategies in community mental health - Experiences in Ibero-America. Initiative carried out with the aim of being able to know and learn about the trajectories of other teams/organizations from different regions that perform similar tasks to those of the Public Guardianship Ministry of Argentina, as well as to share the experiences of our space, always with the purpose of being enriched by the diversity of the different contexts in which the professional practice is developed and that from this exchange ideas arise to enhance the work of our task.
	Report: International Meeting: Strategies of support in community mental health - Experiences in Iberoamerica.
https://docs.google.com/document/d/1O9Zqb5pM6pVYX5r5Gkg_-vLGCDQllYdr/edit?usp=drive_web&ouid=100062833870042773392&rtpof=true  

Meeting recording
https://drive.google.com/drive/folders/1UX4eS1vsLT_e4CeL1cUL3ZKfHYbtRmII  


	
	
	
	2024

A mapping of solutions for the exercise of legal capacity of people with disabilities was carried out, with the aim of identifying barriers in access to justice for people with intellectual and psychosocial disabilities, assessing the impact of digitalization on these processes, and compiling existing solutions.
	Report on Mapping Solutions for Access to Justice for Persons with Disabilities

Preliminary Results and Findings

Second Consultancy Report – UNDP Assistant for Mapping Solutions for the Exercise of Legal Capacity of Persons with Disabilities

Third Consultancy Report – UNDP Assistant for Mapping Solutions for the Exercise of Legal Capacity of Persons with Disabilities

	
	
	
	2024

Workshops for people with disabilities in indigenous communities of the Gran Chaco, with a special focus on women and children. The activity sought to identify legal and social barriers, promote active participation in community decision-making, and raise awareness of the rights of persons with disabilities.
	Preliminary map of actors


 Exchange instances for the collection of information on the situation
of indigenous persons with disabilities in the Argentine Gran Chaco - Concept note 

	
	
	
	2024

An evaluation was conducted in a locality in Gran Chaco to assess specific needs and identify structural barriers faced by Indigenous persons with disabilities, aiming to enhance their inclusion and participation

Awareness and communication strategy


	Diagnosis of the Needs of Wichí People with Disabilities in the Chaco of Salta 

Community Strengthening for Indigenous People with Disabilities in the Argentine Gran Chaco  





 Awareness and communication strategy

	
	
	
	2024

An awareness-raising strategy to improve access to justice for indigenous people with disabilities in Rivadavia Banda Norte was developed. The initiative included community diagnostic workshops to identify barriers and perceptions of disability, dissemination of rights through social media campaigns, community radio and accessible materials in the Wichí language
	Awareness-raising strategy for access to justice for women with disabilities within Communities of Rivadavia Banda Norte
 

	
	
	
	2024

A Federal Replicability Manual was developed for a Guide to Access to Justice with a focus on people with disabilities
	Access to Justice for Persons with Disabilities: A Replicability Manual for Rights-Based Tools


	
	
	
	2024

A Guide to Promoting Access to Justice for Persons with Disabilities was developed
	Guide to Access to Justice for People with Disabilities 

	
	
	
	2024

A guide to assistive technologies and universal design was developed to ensure digital inclusion and equity in access to services and political participation of persons with disabilities. The guide was developed from virtual consultation instances with people with disabilities who are experts in accessibility, addressing specific needs in the visual, auditory and intellectual/psychosocial fields.
	Towards Digital Inclusion: Guide with Technical Recommendations to Promote Digital Equity




Please add new tables if the programme has more outputs under 2.2
	Output 3.1: 

	The inclusion of disability in the planning, implementation and monitoring of United Nations development activities is strengthened.

	Brief narrative description on completion of output 

	UN agencies contributed to the update of the Common Country Analysis (CCA) and drafting for the new UN development framework by providing key information on the situation of persons with disabilities and the challenges they face in exercising their rights and how UN cooperation could address them in a new programming cycle. This marked an important step in aligning UN strategies with the principles of the Convention on the Rights of Persons with Disabilities (CRPD) and the Sustainable Development Goals (SDGs).
A virtual workshop was held within the framework of the CCA process to engage directly with the persons with disabilities community. This consultation enabled the collection of first-hand experiences and insights, ensuring that persons with disabilities were meaningfully involved in shaping strategic cooperation frameworks and sustainable development policies. The initiative promoted participatory decision-making and reinforced the commitment to inclusive and human rights-based development strategic planning.
Building on these inputs, a policy document was developed to provide technical recommendations and practical tools for mainstreaming the disability perspective throughout the UN’s strategic actions in Argentina. This document offers a reference framework for incorporating accessibility measures and rights-based approaches in policy design, implementation, and evaluation across the UN system.
However, challenges remain in achieving consistent cross-sectoral engagement. For instance, planned technical support for integrating disability perspective in Argentina’s participation in the 2024 Future Summit could not be provided due to the government’s decision not to engage in the platform. This underscores the ongoing need for sustained advocacy and dialogue to secure broader commitment to disability-inclusive development.
Despite these limitations, the groundwork laid under this output has advanced the institutionalization of disability inclusion within the UN Country Team's actions and UNDIS implementation. Through participatory consultations, knowledge production, and alignment with human rights standards, these efforts have enhanced policy coherence and stakeholder engagement in the pursuit of more inclusive governance frameworks.


Reporting on Output 3.1 Indicators (Refer to Annex 2)
	Indicator*
	Start level 
Baseline
(Beginning of the project reporting period)*
	Target*
	End level 
End line
(End of the project reporting period)*
	Means of Verification

	3.1.2.  # UNSDCF where disability inclusion has been mainstreamed and/or targeted
	UNSDCF 2021-2025.

https://unsdg.un.org/sites/default/files/2021-11/Argentina_Cooperation_Framework_2021_2025.pdf 
	
	2022 -2023

UNSDCF Annual Report
CCA update 

	Document 

	
	
	
	2024

A virtual workshop was held for the community of persons with disabilities in Argentina as part of the United Nations Common Country Analysis (CCA) process. The objective was to gather perspectives and experiences on their situation to ensure their meaningful inclusion in public policy planning and sustainable development strategies. This initiative aligns with the Convention on the Rights of Persons with Disabilities (CRPD) and the Sustainable Development Goals (SDGs), reinforcing a rights-based and inclusive approach in national policymaking. 
	 Concept Note and Agenda: "Workshop on the United Nations Joint Country Analysis for Organizations of Persons with Disabilities 

OPD List for the Workshop 

Taller PcD consults CCA - August 2024 PPT

Workshop recording

Thematic conclusions or

Workshop Results

Blog post proposal

 PPT material 

Report of the Participatory Workshop


	
	
	
	2024

Technical assistance for  the inclusion of disability in the government's participation in the 2024 Future Summit.
This activity was not possible due to the government decision to not participate in this platform. 

	Note to file 

	
	
	
	2024

A document was developed with tools for the inclusion of the disability perspective in the United Nations strategy in Argentina
	Tools for the inclusion of the disability perspective in the United Nations strategy in Argentina 

Techniques and recommendations to guarantee the rights of persons with disabilities in the activities of the UNS 



Please add new tables if the programme has more outputs under 3.1

	Output 3.2: 

	Monitoring and follow-up mechanisms for the SDGs and the recommendations of treaty bodies and other universal human rights procedures, especially the CRPD, are supported to promote disability inclusion and the participation of persons with disabilities and their organizations.

	Brief narrative description on completion of output 

	The UN System in Argentina submitted key reports and inputs to various international human rights mechanisms, including the Universal Periodic Review (UPR), the CEDAW Committee, the CRPD and CRC Committees. These included both public and confidential contributions, focusing on the status of the rights of persons with disabilities in the country. Constructive engagement was also maintained with UN Special Procedures, including the Special Rapporteurs on debt and on extrajudicial, summary, or arbitrary executions, addressing the implications of their mandates on persons with disabilities.
Recognizing the need to strengthen national monitoring systems, the project prioritized building the capacities of organizations of persons with disabilities (OPDs) to engage meaningfully in these mechanisms. Training activities enabled OPDs to better understand existing human rights and SDG follow-up procedures, while also fostering the exchange of tools and strategies among organizations to support increased participation. These initiatives addressed existing gaps in participation and underscored the importance of involving persons with disabilities in monitoring and accountability frameworks.
In parallel, the programme contributed to improving national monitoring tools by proposing adaptations to SDG indicators and reporting mechanisms. These recommendations emphasized the integration of a social model of disability and the development of inclusive indicators, disaggregated data, and participatory evaluation processes. Technical proposals were submitted to the National Council for the Coordination of Social Policies (CNCPS) and the SDG Technical Commission, providing inputs to harmonize disability inclusion in national frameworks.
By advancing these strategies, the project helped position disability as a cross-cutting dimension in the monitoring of human rights obligations and development commitments. These efforts contribute to ensuring that national reporting processes reflect the lived experiences of persons with disabilities and support evidence-based, inclusive policymaking.




Reporting on Output 3.2 Indicators (Refer Annex 2)
	Indicator*
	Start level 
Baseline
(Beginning of the project reporting period)*
	Target*
	End level 
End line
(End of the project reporting period)*
	Means of Verification

	3.3.2 # of governmental coordination mechanisms with established consultation processes undertaken to ensure the active involvement of persons with disabilities, including through their representative organizations, in the planning, implementation and monitoring of SDGs
	The recent forum of Federal Civil Society Dialogue and Participation Round Table created by ANDIS and the SDG Technical Commission
	
	2023

Report for policy dialogue with the CNCPS and the Technical Commission of the SDGs to harmonize the disability inclusion perspective in reporting and monitoring mechanisms at the national level.

	Report "Persons with Disabilities in the Third National Voluntary Report of Argentina 2022".
of Argentina 2022".
https://drive.google.com/file/d/1K_EALh0VLSHMCyRnsu5ubvolCdDCn7Wj/view?usp=drive_link 

	
	
	
	2023

Roundtable for consultation and participation of DPOs, with emphasis on underrepresented groups of DPOs (indigenous women, children and adolescents with disabilities) in the monitoring of the SDGs and human rights.

	Concept Note on "Exchange meetings to strengthen the disability perspective in the monitoring and reporting mechanisms of the SDGs" REDI
https://docs.google.com/document/d/1Q07vBcEkkgiOPQmPLJsjaQf7tl43xVXf/edit 

	
	
	
	2023

Methodological adaptation of targets 3.7 and 5.6 of the sustainable development goals.
of the Sustainable Development Goals. Incorporation of the disability perspective for universal access to sexual and reproductive health.

	Methodological adequacy report: https://drive.google.com/file/d/1tLhZ3n52CzKPCcEOsUbI8W1Yq2gmSJjk/view?usp=drive_link 

	
	
	
	2023

Positioning Document
People with disabilities in the Third National Voluntary Report of Argentina.
of Argentina.

	Report: Position Paper
People with disabilities in the Third National Voluntary Report of Argentina
of Argentina
https://drive.google.com/file/d/192es9WNI75kmJ0R_0mIijqV7Tc3-uMIx/view?usp=drive_link 




3. Equality between men and women 
Please describe how the programme ensured equality between men and women by responding to the questions below.  
 
	How did the programme consider differences in the barriers faced by men and women with disabilities? 

	The programme was conceived and implemented from an intersectional perspective, acknowledging that women and girls with disabilities, as well as other gender identities, experience deeper and more complex barriers than men with disabilities. This understanding informed all stages of the intervention and guided efforts to address the most persistent challenges they face, particularly in accessing sexual and reproductive health services, exercising legal capacity, and participating in justice, political, and social systems.

A central focus was placed on the barriers encountered in medical and institutional settings, where physical inaccessibility and communication obstacles frequently limit the ability of women with disabilities to exercise autonomy and secure their rights. Police stations, hospitals, and legal institutions often fail to provide appropriate accommodation, reinforcing exclusion. Moreover, the lack of training among staff and the prevalence of discriminatory attitudes further exacerbate the marginalization of these groups. Attitudinal bias and institutional obstacles limit the recognition of women with disabilities as rights holders and obstruct mechanisms for filing and processing complaints.

To address these barriers, the programme developed informational resources in accessible formats, conducted training with a gender-sensitive approach for health providers and justice actors, and created tools for legal empowerment. These initiatives were supported by participatory processes, ensuring the inclusion of voices from women with intellectual, psychosocial, and Indigenous backgrounds, particularly in underserved regions like Gran Chaco and Jujuy. Strategies such as community workshops, social media outreach, and radio campaigns promoted awareness and fostered engagement.

Simultaneously, efforts to improve access to justice and civic participation were strengthened by identifying legal and procedural shortcomings and proposing reforms. The programme emphasized the need for safeguards and reasonable accommodations in judicial processes to enable women with disabilities to participate fully and autonomously. Across all components, gender considerations were integrated to ensure that interventions addressed not only functional limitations but also the compounded effects of social, cultural, and institutional discrimination.

Through this comprehensive approach, the programme aimed to dismantle the systemic inequalities that uniquely impact women with disabilities, ensuring their inclusion as central actors in the design, implementation, and evaluation of policies and services.

	In what way did the programme advance gender equality?  

	The programme advanced gender equality by consistently applying a gender-sensitive and disability-inclusive lens across all stages of design, implementation and evaluation. Acknowledging the compounded discrimination experienced by women, girls and persons with gestational capacity with disabilities, the initiative prioritized actions that addressed structural, attitudinal and institutional barriers across multiple sectors.

In the health sector, it developed and distributed policy documents, training resources and accessible materials specifically designed to address the needs of women with disabilities. These included guidelines to prevent coercive reproductive practices, improve counseling services and ensure access to voluntary and legal abortion. Training was delivered to healthcare teams in various regions, focusing on inclusive and rights-based approaches that respond to gender-specific challenges.

In the justice system, the programme identified and documented the legal and institutional obstacles faced by women with intellectual and psychosocial disabilities. Through participatory workshops and community engagement activities, especially in Indigenous regions such as Gran Chaco, it promoted legal empowerment and increased awareness of rights. 

Digital equity was strengthened through the creation of a guide on assistive technologies and universal design, offering practical tools to enhance access to information, services and political participation for women with disabilities. This contributed to reducing the digital divide and expanding opportunities for civic engagement.

Internally, the initiative promoted gender balance within its operational structure by encouraging the recruitment of women with disabilities, addressing historical labor inequalities and ensuring representation in decision-making and technical roles.

By embedding gender equality throughout its core strategies, the programme contributed to dismantling discriminatory systems, promoting autonomy and reinforcing the development of policies and services that reflect the diverse realities of women with disabilities.

	How have the specific actions undertaken by the programme contributed directly to the empowerment of women and girls with disabilities?   Please include here baseline and end line data on how women with disabilities were included and impacted while implementing the project. Kindly note that in the expenditure section below projects are requested to state the overall funding spent on these activities.


	The programme advanced the empowerment of women and girls with disabilities by strengthening their autonomy, access to rights, and active participation in decision-making spaces. Through policy development, training, and awareness-raising initiatives, the project equipped women and girls with disabilities with tools and knowledge needed to exercise their rights freely and independently, in line with CRPD and CEDAW obligations and other international human rights obligations.

One of the most significant contributions was the development of policy documents and training materials aimed at ensuring that sexual and reproductive health services are accessible, respectful, and human rights-based. The training of health professionals in the Gran Chaco region, along with the creation of easy-to-read educational materials on sexual and reproductive rights, provided concrete resources for women and adolescent girls with disabilities to make informed decisions about their bodies and reproductive health. By ensuring the availability of accessible information and services, the programme directly contributed to reducing barriers to healthcare autonomy.

In the area of justice and legal capacity, the programme strengthened the legal empowerment of women with disabilities, particularly those with intellectual and psychosocial disabilities. The participatory development of legal tools and the analysis of barriers in legal capacity determination procedures highlighted the systemic inequalities faced by women with disabilities in accessing justice. Additionally, the legal workshop for Indigenous women with disabilities in Gran Chaco provided a space to discuss rights, identify barriers, and develop community-based strategies for advocacy, reinforcing their agency in legal and social matters.

Furthermore, the programme promoted inclusive narratives by ensuring that knowledge products and awareness campaigns were developed with a feminist and intersectional approach. The involvement of women experts with disabilities in the creation of these materials not only centered their voices in the discourse but also contributed to shifting public and institutional perspectives on gender and disability.

By amplifying the voices of women and girls with disabilities, fostering knowledge-sharing, and promoting structural changes in health and justice systems, the programme strengthened their ability to claim their rights, challenge discriminatory practices, and actively participate in shaping inclusive policies.


	How did women with disabilities and women led OPD groups (informal/formal) participate in the implementation?  

	Women with disabilities and women-led OPD groups actively participated throughout the programme’s implementation. They were involved in consultation processes, co-design of activities, and validation of knowledge products, ensuring that their perspectives informed the development of guidelines, training materials, and advocacy tools. Their engagement was particularly relevant in initiatives addressing access to justice and sexual and reproductive health, where they contributed lived experiences and expertise to shape inclusive approaches. Women-led OPDs also played a key role in outreach and mobilization at subnational levels, facilitating participation from diverse territories and strengthening peer-to-peer learning within the disability movement.



4. Full and effective participation of persons with disabilities
Please describe how the programme ensured the full and effective participation of persons with disabilities and their representative organizations by responding to the questions below.  
 
	How did the programme consider the barriers faced by persons with disabilities for effective participation?  
 

	The programme addressed the barriers faced by persons with disabilities for effective participation by incorporating accessibility and inclusion measures across its activities. This included providing hybrid and virtual participation options to reach all provinces, ensuring accessible formats for materials, and using clear and inclusive language. Activities were co-designed with OPDs to reflect diverse needs and experiences, particularly those of women with disabilities, and to adapt content and methodologies accordingly. The programme also fostered safe and participatory spaces where persons with disabilities could engage on equal terms with other stakeholders, helping to overcome geographic, communication, and institutional barriers.
 

	How were persons with disabilities involved in the programme’s governance as well as in the planning, implementation, monitoring and evaluation phases?  
 

	Persons with disabilities, through their representative OPDs, were engaged in the programme’s governance and throughout its cycle. They participated in advisory and decision-making spaces, contributing to the definition of priorities and the design of activities. 
During planning and implementation, OPDs co-developed training content, policy guidelines, and advocacy strategies, ensuring alignment with the lived experiences and needs of persons with disabilities and CRPD principles
 Reasonable accommodations were ensured in all activities, including Argentine Sign Language (LSA) interpretation, captioning, plain language, adaptations for neurodivergent participants, and careful consideration of the number and type of participations to enable meaningful involvement. They also played an active role in monitoring progress, providing feedback on outputs, and validating knowledge products. In the evaluation phase, their perspectives were gathered to assess relevance, effectiveness, and sustainability, reinforcing a participatory and rights-based approach.

	How have the specific actions undertaken by the programme contributed directly to the full and effective participation of persons with disabilities?    
 

	The programme’s actions directly supported the full and effective participation of persons with disabilities by creating accessible, inclusive, and co-designed spaces for engagement. Training processes, policy guidelines, and advocacy tools were developed in collaboration with OPDs and persons with disabilities, ensuring that content reflected their priorities and realities. Activities were implemented with reasonable accommodations —including Argentine Sign Language (LSA) interpretation, captioning, plain language, and adaptations for neurodivergent participants— to remove communication and participation barriers. The programme also ensured diverse and balanced representation in all activities, engaged OPDs in governance and decision-making processes, and facilitated their involvement in planning, implementation, monitoring, and evaluation. These measures strengthened the capacity of persons with disabilities and their representative organizations to influence policy, service delivery, and inclusive governance practices.


 
 Please use the table below to summarize the details of OPDs the programme has engaged with.  

	Type of OPD (Umbrella, regional, national, specific disability type) 
	Contact details  
(Email address of contact person of the organization and website where available) 
	Overall OPD leadership (disaggregated according to sex and type of disability)  
	OPD representatives engaged in the programme (disaggregated according to sex and type of disability) 

	 Umbrella
	REDI- RED FOR THE RIGHTS OF PERSONS WITH DISABILITIES
marcelobetti@yahoo.com.ar
http://redi.org.ar/

	 Marcelo Fernando Betti
President
Male 
Type of disability: visual


	Cecilia Gonzalez Bellande

	 Type Disability: Visual
	FAICA (Argentine Federation of Blind and Amblyopic Institutions)
	 Soledad Gelvez
Woman
Type of disability: visual


	Soledad Gelvez

	 Umbrella
	Asociación Azul 
	Julián Vázquez
President

	Elena Dal Bo


	 Umbrella
	Cabildo Abierto 
	Amalia Dolinksy 
Woman 
Type of disability: visual

	Amalia Dolinksy

	 Umbrella
	Foundation “Tomar Acción” 
	Antonieta Plaza
Non-disabled lawyer

	 Antonieta Plaza

	 Umbrella
	 “Libertate”
	 Celeste Pavez
Woman 

	 Celeste Pavez

	 Umbrella
	 Disability Table- Córdoba 
	 Mariana Gandolfo
Woman
	 Mariana Gandolfo

	 Umbrella
	 Movida Rosario  

	 Giselle Ferrari
Woman

	 Giselle Ferrari

	 Umbrella
	MUDEBA (Women breaking down barriers)

	 Yesica Gutierrez
Woman

	 Yesica Gutierrez

	 Umbrella
	 “Orgullo Disca” 
	 Laura Alcaide
Woman
Type of disability: visual

	 Laura Alcaide

	 Umbrella
	 “Rumbos” 
	 Silvia Coriat
Woman
	 Silvia Coriat

	 Umbrella
	“Sin Barreras” 
	 Gabriela Bruno
Woman
Type of disability: physical

	 Gabriela Bruno

	 Type Disability: Visual
	 “Tiflonexos” 
	 Pablo Lecuona
Man 
Type of disability: visual
	 Pablo Lecuona

	 Type Disability: Visual
	 Network of Journalists with Visual Impairment

	 Jose Luis Nuñez
Man 
	 Jose Luis Nuñez

	 Type Disability: Visual
	 BAC (Argentine Library for the Blind) 
	 Carlos García 
Man
Type of disability: visual
	 Carlos García

	 Type Disability:
Auditive
	 C.R.I.O.S.- Center for Integral Oral Rehabilitation for the Deaf and Hard of Hearing 
	 Claudia Sánchez 
Woman
	 Claudia Sánchez

	 Type Disability:
Auditive
	 “Canales” 
	 Silvana Veinberg
Woman
	 Silvana Veinberg

	 Type Disability:
Auditive
	 “Fundasor”
info@fundasor.org.ar
	 Anahi Alesso
Woman
	 Anahi Alesso

	 Type Disability:
Auditiva
	 ASO (Association of the Deaf)

	
	

	 Type Disability:
Autism

	 Autistic Insurgency 
	
	

	 Type Disability:
Psychosocial
	 Observatory of Mental Health and Human Rights – Cordoba 
	 Martin Passini
Man
	 Martin Passini

	 Type Disability:
psychosocial
	 AJUPEF (Jujuy Association for the Help of People with Schizophrenia and their Families) 
	 Norma Churquina
Woman 
Type of disability: hearing
	 Norma Churquina

	 Type Disability:
Intellectual 
	 ANDAR 
	 Raul Lucero
Man 
	 Raul Lucero

	 Type Disability:
Intellectual
	 APADIM 
	 Martin Passini
Man
	 Martin Passini

	 Type Disability:
Intellectual
	 APEBI
	 Elena Zappoli
Woman
	 Elena Zappoli

	Type Disability:
Intellectual
	APSIDO
	 Marisa Asceval
Woman
	 Marisa Asceval

	 Type Disability:
Intellectual
	 Assembly of Mental Health Users for our Rights 
	 Fernando Ferreyra
Man
	 Fernando Ferreyra

	 Type Disability:
Intellectual
	 “Colibrí” Down Syndrome Association of Salta 
	 Irma Argañaraz
Woman
	 Irma Argañaraz
Woman

	 Type Disability:
Intellectual
	 “Despejarte” 
	 Maria Cristina Galetto
Woman
	 Maria Cristina Galetto

	 Type Disability:
Intellectual
	 “El Brote” 
	 Natalia Gomez
Woman
	 Natalia Gomez

	 Type Disability:
Intellectual
	 FETAP (Federation of Protected Workshops of the Province of Buenos Aires) 
	Carlos Venini
Man
	 Carlos Venini

	 Type Disability:
Intellectual
	 Foundation “Visibilia” 
	 Paola Hebe Jelonche
Woman
	 Paola Hebe Jelonche

	 Type Disability:
Intellectual
	 Lengua Franca 
	 Julia Otero/ Analía Gutierrez
Woman
	 Julia Otero/ Analía Gutierrez

	 Type Disability:
Auditive

	 Deaf without violence 
	 Mariana Reuter 
deaf woman 
	 Mariana Reuter


 

4. Ensuring the inclusion of marginalized and underrepresented groups of persons with disabilities 
 Please describe how the project ensured inclusion of marginalized and underrepresented groups of persons with disabilities by responding to the questions below.  
 
	How did the programme consider and identify marginalized and underrepresented groups of persons with disabilities? For example by considering type of disability, gender, age, location, minority status or other contextually appropriate demographic factors. 
 

	The programme considered and identified marginalized and underrepresented groups of persons with disabilities through a situational analysis conducted during the inception phase. This analysis, carried out in partnership with the Disability Observatory of the National University of Quilmes —a public university committed to inclusion for over a decade— used a participatory methodology to identify both the groups and the approaches needed to reach them. It highlighted the need to prioritize persons with psychosocial and intellectual disabilities, women with disabilities, and Indigenous persons with disabilities, particularly those living in northern Argentina. The process also took into account factors such as age, geographic location, and minority status, ensuring that intersectional considerations informed programme design and outreach strategies.
Additionally, the programme considered other UN interagency efforts and lessons-learned to establish synergies for a more effective cooperation and build on what has been done. For instance, Spotlight initiate that has addressed violence against women, particularly women with disabilities and Gran Chaco Initiative that has focused on indigenous peoples rights. 

	In what way did the programme advance equity regarding rights and needs of most marginalized groups?   
 

	The programme advanced equity for the most marginalized groups by generating participatory knowledge products that provided data and visibility on their situation, addressing critical information gaps. It supported the creation of alliances between civil society organizations from different territories and OPDs, helping to mainstream disability perspectives in regions where OPDs are scarce and often weak, particularly in northern Argentina. Efforts were made to ensure the participation of persons with psychosocial and intellectual disabilities in all activities and to consider their needs in the design of products and interventions. For girls, adolescents, and women with disabilities, the programme integrated a gender perspective throughout its actions and implemented activities in sexual and reproductive health that particularly benefited this group.

	How have the specific actions undertaken by the programme contributed directly to the inclusion of marginalized and underrepresented groups of persons with disabilities?   
 

	The programme contributed to the inclusion of marginalized and underrepresented groups of persons with disabilities by implementing actions that addressed both visibility and participation barriers. Participatory knowledge products were developed to generate data on groups whose situations had not been previously documented, including persons with psychosocial and intellectual disabilities, women with disabilities, and Indigenous persons with disabilities in northern Argentina. The programme supported alliances between local civil society organizations and OPDs to strengthen disability perspectives in regions with limited organizational presence. Reasonable accommodation was ensured in all activities, and targeted efforts were made to include these groups in consultations, training, and advocacy initiatives. The integration of a gender perspective and the implementation of sexual and reproductive health activities further contributed to the meaningful participation and representation of girls, adolescents, and women with disabilities.

	How did marginalized and vulnerable persons with disabilities and these groups led by marginalized and vulnerable persons with disabilities (informal/formal) participate in the implementation? 
 

	Marginalized and vulnerable persons with disabilities, along with groups led by them, participated actively in the programme’s implementation through consultations, co-design processes, and validation of activities and outputs. Their involvement was ensured in training sessions, policy discussions, and advocacy initiatives, with reasonable accommodations such as Argentine Sign Language (LSA) interpretation, captioning, plain language, and adaptations for neurodivergent participants. Particular efforts were made to include persons with psychosocial and intellectual disabilities, women with disabilities, and Indigenous persons with disabilities from northern Argentina, ensuring their perspectives informed the development of knowledge products, guidelines, and outreach strategies. These groups also played a role in mobilizing participation at the subnational level and strengthening alliances between local civil society organizations and OPDs to amplify the voice and representation of marginalized communities.


 
Please use the table below to list the type of marginalized and underrepresented groups of persons with disabilities who were included so far in programme implementation.  
 
	Type of Marginalized or Underrepresented group  
	Organization contact details  
(email address of Organization contact where available) 

	People with disabilities
	 REDI
Marcelo Betti 

	
	Red de comunicadores con discapacidad visual
José Luis Núñez 
https://www.reddecomunicadorescondiscapacidadvisual.org.ar

	
	Asociación Azul 
Elena Dal Bo

	
	Women Observatory-C/ Disability Rural Villages- Neighborhood of Tandil
Adriana Dominguez
Observatorio de la Mujer-C/ Discapacidad Pueblos Rurales-Barrios Tandil | Facebook

	
	Instituto de Derecho de las PcD - Colegio de Abogados del Departamento Judicial Junín
Raúl O. Fernández MacielInstituto de Derecho de las Personas con Discapacidad – Colegio de Abogados (cadjj.org.ar)

	
	Asamblea Permanente por los Derechos Humanos
Claudia Naomwww.apdh-argentina.org.ar

	
	FHyCS - UNaM
Liz Zamudio
Facultad de Humanidades y Ciencias Sociales (unju.edu.ar)

	
	Municipalidad de Santa Fe
Gabriela Bruno
www.santafe.gov.ar

	Women with disabilities who are victims of gender-based violence
	Deaf women without violence
Mariana Reuter 


	Persons with visual disabilities
	 Network of visually impaired journalists
Jose Luis Nuñez
https://www.reddecomunicadorescondiscapacidadvisual.org.ar 


	
	FAICA - FEDERACIÓN ARGENTINA DE INSTITUCIONES DE CIEGOS Y AMBLIOPES
https://www.faica./org.ar

	
	“Tiflonexos”
Pablo Lecuona 

	
	BAC (Argentine Library for the Blind)
Carlos Garcia 

	
	MUCAR - Movement of unity of the blind and amblyopic of Rosario.
Carlos Colerewww.mucar.org.ar

	Persons with hearing disabilities
	Fundación FUNDASOR
Mariana Reuterwww.fundasor.org.ar

	
	C.R.I.O.S.- Center for Integral Oral Rehabilitation for the Deaf and Hard of Hearing
Claudia Sanchez 

	
	“Canales” 

	
	ASO (Association of the Deaf) 

	Persons with intellectual or psychosocial disabilities
	Autistic Insurgency 

	
	Observatory of Mental Health and Human Rights - Cordoba
Mariana Gandolfo 

	
	ANDAR
Raul Lucero 

	
	APADIM
Martin Passini 

	
	APEBI
Elena Zappoli 

	
	APSIDO
Maria Asceval 

	
	Assembly of Mental Health Users for our Rights
Fernando Ferreyra 

	
	“Colibrí” Down Syndrome Association of Salta
Irma Argañaraz 

	
	“Despejarte”
Maria Cristina Galetto 

	
	“El Brote”
Natalia Gomez 

	
	FETAP (Federation of Protected Workshops of the Province of Buenos Aires)
Carlos Venini 

	
	Foundation “Visibilia” 

	
	“Lengua Franca”
Julia Otero y Analia Gutierrez 

	
	AJUPEF- Jujuy Association for the support of people with schizophrenia and their families.
Norma del Valle Churquinawww.facebook.com/groups/1731971650364594 

	
	Diacco - Diversidad Funcional En Acción En La Costa
Viviana Gabrielehttp://diacco.com.ar/

	Human rights organizations committed to the rights of persons with disabilities
	ALAPA (Argentine Patients Alliance)
Florencia Braga Menendez 

	
	APDH
Claudia Naom 

	
	CELS
Fabían Murua 

	
	ACIJ
Belén Arcucci 

	
	FACA
Ilda Alvarez 

	
	Observatory of Disability of Mendoza
Mónica Bascuñánwww.facebook.com/people/Observatorio-de-las-personas-con-Discapacidad-Mendoza

	
	Observatory of Women with Disabilities. Aldeas Rurales- Tandil Neighborhood
Adriana Dominguezhttps://www.facebook.com/groups/1071225839946480/ 

	
	Institute of Law for Persons with Disabilities. Bar Association of the Judicial Department of Junín
Raul O. Fernandez Maciel https://cadjj.org.ar/instituto-de-derecho-de-las-personas-con-discapacidad/ 

	
	Permanent Assembly for Human Rights
Claudia Naomwww.apdh-argentina.org.ar 

	
	FHyCS- UNaM
Liz Zamudio 
www.uniju.edu.ar 

	
	Municipality of Santa Fe
Gabriela Brunowww.santafe.gov.ar 

	
	Manos Abiertas
Lidia Alejandra Tejerinawww.manosabiertas.org.ar

	
	CEPADEHU – Participation Centre for Peace and Human Rights
Patricio A. CabezasCEPADEHU | Centro de Participación para la Paz y los Derechos Humanos

	
	National Observatory of Disability
Héctor C. Filippawww.argentina.gob.ar/andis/estructura-andis/observatorio-de-la-discapacidad

	Indigenous people with disabilities 
	REDI
Marcelo Betti 



6.  Partnership-Building
 
	Please provide a narrative on how the programme has contributed to greater UN inter-agency collaboration to advance the rights of persons with disabilities in the country.  

	The programme contributed to greater UN inter-agency collaboration in advancing human rights of persons with disabilities by engaging all UN agencies in Argentina, both through information-sharing and participation in activities specifically designed for them. Effective coordination among UNFPA, UNDP, PAHO/WHO, OHCHR, and UNICEF enabled efficient use of resources, maximizing each agency’s mandate to carry out joint actions and mainstream disability perspectives. This collaboration facilitated the identification of joint action lines and synergies, the development of shared and agency-specific materials to promote human rights of persons with disabilities, and the integration of disability inclusion across other projects and sectors. The programme has set the foundations for UNDIS implementation. By providing technical expertise, fostering inclusive consultation processes, and promoting unified action across UN agencies, the initiative has helped integrate a disability-inclusive approach into UN programming. This coordinated effort has enhanced the UN’s capacity to support government institutions and organizations of persons with disabilities, contributing to more coherent and impactful progress toward the full realization of human rights of persons with disabilities in Argentina.
It has also fostered successful inter-agency working strategies that can be replicated in future initiatives beyond the disability agenda, strengthening the UN system’s collective capacity to advance inclusion.

	Please describe the different stakeholders (for example Government departments, UN entities, OPDs and Civil Society) involved and how they worked together. 

	The programme involved a broad range of stakeholders, including government institutions at national and subnational levels, UN entities, organizations of persons with disabilities (OPDs), and other civil society organizations. Key government counterparts and authorities from justice, health, and disability have been engaged in dialogue, co-designed of activities, and validation of policy and practice guidelines. For instance, the Ministry of Health through the Sexual Reproductive health directorate, Human Rights Secretariat and the National Disability agency coordinated different activities throughout the programme and established work alliances and partnerships to ensure disability inclusion in public policies drafting. 
UN agencies —UNFPA, UNDP, PAHO/WHO, OHCHR, and UNICEF— collaborated closely, through shared planning, technical exchanges, and coordinated implementation aligning mandates and resources to implement joint actions to mainstream disability perspectives. OPDs played a central role in representing the voices of persons with disabilities, contributing their expertise and experience to planning, implementation, and monitoring. Civil society organizations, particularly those from underrepresented regions, partnered with OPDs to strengthen outreach and inclusion of marginalized groups.
Additionally, the programme also produced policy and practice guidelines on legal capacity and sexual and reproductive health for persons with disabilities, co-created with OPDs and executive and judicial authorities from different sectors, which can serve as models for inclusive service provision. 
This multi-stakeholder approach ensured that activities were informed from diverse perspectives and that responsibilities were shared to maximize impact.

	How has the programme contributed to generating new knowledge on how best to promote the rights of persons with disabilities to support policy and system changes?  
	The programme generated new knowledge to promote the rights of persons with disabilities through pioneering research in Argentina on legal capacity and the conditions for independent living. Notably, the analysis of judicial cases concerning determination or restriction of legal capacity provided critical evidence to inform strategies for improving the implementation of laws protecting the rights of persons with disabilities. Similarly, the study on barriers and challenges to accessing sexual and reproductive health services informed the joint development —with the national government under the previous administration ending in 2023— of protocols and technical notes to safeguard these rights. These and other research initiatives produced by the programme created an evidence base to support policy and system changes aimed at advancing disability inclusion.

	Please also describe in this section any unique expertise and products developed by the programme that could be used to support other countries within a south-south cooperation framework 

	The programme developed unique expertise and knowledge products that could be adapted and applied in other countries through south-south cooperation. These include innovative methodologies for participatory research on legal capacity and independent living, as well as tools for analyzing judicial cases to inform human rights-based legal reforms. The programme also produced policy and practice guidelines on sexual and reproductive health for persons with disabilities, co-created with OPDs and health authorities, which can serve as models for inclusive service provision. Furthermore, the  SDG 16.3.3 indicator methodology for measuring access to justice was adapted to incorporate and document the perspectives of persons with disabilities. In addition, it developed guidelines for accessible communication and for improving the digital accessibility of justice portals. In a global context where judicial procedures are increasingly shifting to digital platforms, ensuring accessibility for both lawyers with disabilities and users of justice services with disabilities is essential. Given the similarities in technology used across countries, these guidelines can be transferred to other contexts with the necessary adjustments and adaptations. The inter-agency strategies, capacity-building materials, and participatory approaches used to strengthen the role of OPDs and integrate disability perspectives into justice, health, and governance systems also provide transferable practices for similar initiatives elsewhere.





 

7. Creation of knowledge products 
	How has the programme contributed to generating new knowledge on how best to promote the rights of persons with disabilities to support national level policy and system changes?  

	The programme contributed to generating new knowledge to promote the rights of persons with disabilities and inform national policy and system changes through pioneering research and evidence-based tools. Studies on legal capacity and independent living —including the first analysis in Argentina of judicial cases on the determination or restriction of legal capacity— provided critical insights to strengthen the implementation of laws protecting these rights. Research on barriers to accessing sexual and reproductive health services informed the joint development, with the previous national administration ending in 2023, of protocols and technical notes to ensure inclusive service provision. The programme also developed guidelines for accessible communication and for improving the digital accessibility of justice portals, addressing a growing need as judicial procedures migrate to online platforms. 
These knowledge products, co-created with OPDs and relevant authorities, filled key information gaps and offered practical models to guide rights-based reforms and strengthen inclusive governance at the national level.

	Please also describe in this section any unique expertise and products developed by the programme that could be used to support other countries within a south-south cooperation framework 

	The programme developed unique expertise and knowledge products with strong potential for adaptation and use in other countries through south-south cooperation. These include innovative participatory research methodologies on legal capacity and independent living, as well as analytical tools for reviewing judicial cases to inform rights-based legal reforms. The programme also produced a comprehensive set of policy and practice guidelines on sexual and reproductive health for persons with disabilities, co-created with OPDs and health authorities, along with technical notes and protocols that provide a practical framework for inclusive service delivery in this area. In addition, it developed guidelines for accessible communication and for enhancing the digital accessibility of justice portals—an increasingly critical area as judicial procedures move online globally. These guidelines aim to ensure that both legal professionals with disabilities and justice service users with disabilities can access and navigate digital platforms on equal terms and it could be implemented in other contexts with appropriate adjustments. 
Additionally, the programme has created trainings for UN staff on accessible communication and disability mainstreamed on UN strategic analysis and strategic programming such as CCA and UNSDF that could be considered as a best practice for other UN Systems.
The inter-agency strategies, capacity-building materials, and participatory approaches used to integrate disability perspectives into justice, health, and governance systems also provide replicable practices that can strengthen disability inclusion efforts in other countries. 



Please list type of knowledge products the programme has developed using the table below . 
	 Name of product and type of product (report, guidelines, assessments etc) 
	Purpose   
Describe what was the purpose of the product  
	Process  
Describe who participated in the development of product (OPDs, NGOs, Academia etc.) and the different stages of development 
	Link /attachment  
	Accessible formats 
	Validation 
Has the product been validated by national actors. If yes by whom? 
 

	Promoting Sexual and Reproductive Health for Persons with Disabilities in Argentina
	Systematize the UNFPA Argentina initiative within the framework of the United Nations Partnership on the Rights of Persons with Disabilities Project.
	The systematization of the UNPRPD initiative in Argentina was authored by disability specialist Cecilia González Bellande. The development followed a two-stage strategy (2021–2024), starting with a situational diagnosis by the University of Quilmes (UNQ) and followed by a participatory implementation phase.
The process involved close collaboration between UNFPA, other UN agencies (UNDP, PAHO/WHO, UNICEF, OHCHR), and key OPDs such as REDI and Enlaces Territoriales para la Equidad de Género (Sordas sin Violencia). Development stages included the review of national legal standards (Laws 27.610 and 27.655), the creation of accessible materials for health teams, and consultations with persons with disabilities from various regions to identify specific barriers to sexual and reproductive health and legal capacity

	https://argentina.unfpa.org/sites/default/files/pub-pdf/2025-04/FINAL%20Documento%201%20-UNPRPD.%20Versi%C3%B3n%20accesible.pdf
	
	

	Gaps of the Argentine National Disability Law based on International Standards.

Assessment on the proposal on the Argentine National Disability Law based on International Standards.
	Analyze the draft national law on disability and prepare a UNS input document.
	The report itself was drafted by a legal expert , it draws upon prior analyses and consultations conducted under the UNPRPD programme, which involved the participation of national stakeholders including OPDs, human rights organizations, and UN agencies. The development process included three key stages: 1) the review of existing legislation and relevant international standards (such as the CRPD, CEDAW, and Inter-American Human Rights System); 2) the identification and documentation of legislative gaps in alignment with those standards; and 3) the drafting of recommendations for legislative reform aimed at full harmonization with the human rights model of disability
	https://docs.google.com/document/d/1QUm0WmpUGalRhGPMtw5vjtKcVk1aNfBj/edit?usp=share_link&ouid=117104607576772483264&rtpof=true&sd=true
	
	

	Program for trainers of trainers on legal capacity
	Design training of trainers´ programs on the exercise of legal capacity focused on intellectual and psychosocial disabilities with human rights and gender approach to (1) judicial officials at the federal level to comply with art. 12 of the CRPD and (2) health effectors.
	The Training of Trainers Programme on Legal Capacity was developed by legal and disability rights expert Malena Correa, with validation and conceptual contributions from REDI. The process included review of legal standards, curriculum design, accessibility strategies, and coordination with public institutions such as the Ministry of Health, Ministry of Justice, and UN agencies. OPDs were involved in reviewing the materials and identifying training needs.
	Program for trainers of trainers on legal capacity. Product1
Program for trainers of trainers on legal capacity
Product2

	
	

	Report on the “Webinar on the 2030 Agenda and Sustainable Development Goals.”
	Develop a webinar to inform OPDs about implementation of the SDGs and the UPR report to strengthen their capacity and thus ensure their meaningful participation and can undertake their advocacy strategies for the review, proposal or reform of regulatory framework to include the disability perspective. 
	The activity was part of the actions aimed at promoting strategies and the meaningful participation of OPDs in reports related to the 2030 Agenda and the SDGs.
	Final Report
Workshop 1
Workshop2
Webinar Details
	
	

	Report. Design of a research on “Strengthening the rights of people with disabilities in Argentina.”
	
	This preliminary writing to start to work on the diagnosis of needs and mapping of solutions for the exercise of legal capacity of people focused on the Gran Chaco region.
	Partial Report
	
	

	Resources for an approach to the fundamental concepts of disability from a human rights perspective
	Design of the material "Toolbox for the integration of disability" for a pilot training program on disability.
	REDI:Coordinación general: Cecilia González Bellande
Edición: Fernando Villalba.
Authors:Lucía Velazquez, Natalia La Rocca, Soledad Gelvez
	Report: Resources for an approach to the fundamental concepts of disability from a human rights perspective
	
	

	Regarding support, reasonable accommodations, and procedural adjustments. Definitions and recommendations for its implementation in Argentina
	Preparation of protocols and practical guidelines for access to sexual and reproductive health for people with disabilities, especially women, girls and adolescents
	REDI:
Coordinación general: Cecilia González Bellande
Edición: Fernando Villalba.
Authors:
Marcelo Betti
Johana Ureña
	Report: Regarding support, reasonable accommodations, and procedural adjustments. Definitions and recommendations for its implementation in Argentina
	
	

	“Report on “Strengthening the dialogue between organizations of people with disabilities. Round-table and building partnership”
	
	REDI
	Report: strengthening the dialogue between organizations of people with disabilities. Round-table and building partnership 
	
	

	Final report that includes good practices, learning and challenges
	
	REDI
	Final Report
	
	

	Protocols/guides for access to sexual and reproductive health for people with disabilities, especially women, girls and adolescents.
	
	REDI
	Protocols/guides
	
	

	Report "Guidelines for the programming of a prototype of an accessible judicial portal".
	Elaborate the design and
guidelines for the implementation of a prototype of a judicial portal accessible to persons with disabilities.
	Author: Hector Chayer. Lawyer and external consultant.
	https://drive.google.com/file/d/1Gh_oEMJYS-tbVXpFc_CeRSY_K0frq--N/view?usp=drive_link 
	
	
Yes. By: Judicial Council of the CABA

	Technical Report "Implementation
accessibility of the judicial portal of the Judicial Council of the CABA".
	Contains an analysis and evaluation of the accessibility standards of the Litigant Portal for people with disabilities. 
(https://eje.juscaba.gob.a/)  identifying barriers and making recommendations.
	Author: Hector Chayer. Lawyer and external consultant.
	https://drive.google.com/file/d/1BijiNFFOAJUop7n6BAgpm4_qn1jVTPSF/view?usp=drive_link 
	
	Yes. By: Judicial Council of the CABA

	Report on "Workshop on strengthening the organizational capacities of DPOs".
	The report contains the structure, development and findings of the workshop that aimed to provide practical tools to organizations of persons with disabilities for the constitution of their legal representation and to promote the empowerment of organizations of persons with disabilities in the spaces of political participation.
	Authors: Diana Maffia y Patricia Gomez.
	https://drive.google.com/file/d/1n34-OmjSOSeR3HwNxX9n9l5DljHEqVt-/view?usp=drive_link 
	
	

	Report on "Proposals for Electoral Candidates. 2023"
	It is a synthesis of an agenda of priority public policies related to the rights of people with disabilities, which are some of the main concerns of the group.
	REDI.
	https://drive.google.com/file/d/19mSOnKnVoOM4CuTfQ36tyh1sKy9kMAHo/view?usp=drive_link 
	
	REDI
Project DPO tables.

	Technical Note 11. "Interpretation of the regulations for the access of persons with disabilities to the voluntary and legal termination of pregnancy (IVE-ILE)".
	The technical note provides guidelines for health teams so that they can respect, protect, and guarantee the right of women and other
and guarantee the right of women and other persons with gestational capacity with disabilities to make autonomous
decisions regarding the voluntary and legal termination of pregnancy IVE-ILE in an autonomous manner.
	National Directorate of Sexual and Reproductive Health of the National Ministry of Health
Authors: Celeste Lonardi and Sonia Ariza Navarrete
	https://argentina.unfpa.org/es/publications/interpretaci%C3%B3n-de-las-normas-para-el-acceso-de-las-personas-con-discapacidad-la
	
	Working Group on
Sexual and Reproductive Rights and Persons with Disabilities.

	Document "Barriers to access to reproductive and non-reproductive sexual health for women with disabilities".
	This is a review of some of the main barriers faced by women with disabilities in Argentina in the area of sexual, reproductive and non-reproductive health.
in Argentina in the area of sexual, reproductive and non-reproductive health, as well as some possible recommendations to address this issue.
to address this issue.
	REDI
FUSA.
	https://drive.google.com/file/d/1_wJ5TssY-Dv6TKUdtFsYWtHTDKhw3cl6/view?usp=drive_link 
	
	

	Booklet "Towards an inclusive sexual and reproductive health counseling for people with disabilities".
	It is a material that specifically addresses aspects of sexual and reproductive health care for persons with disabilities. .
	Authors: Constanza Leone, Verónica González Bonet and Luciana Azcárate, members of the Working Group on Sexual and Reproductive Rights and Persons with
Working Group on Sexual and Reproductive Rights and Persons with Disabilities of the DNSSR and REDI.
	https://argentina.unfpa.org/es/publications/hacia-una-consejer%C3%ADa-en-salud-sexual-y-reproductiva-inclusiva-de-personas-con
	
	REDI.

	Technical Note 8. Surgical contraception and people with disabilities.
	
	DNSSR.
	Technical note 
	
	

	Report for the construction of a diagnosis on the implementation of accessibility measures, support and reasonable accommodation in the exercise of sexual and reproductive rights of women and feminized dissidents with disabilities.
	
	
	Report 
	
	

	Report "Status of Resolution 65/2015 referred to persons with disabilities in their relationship with the health system: challenges and proposals for its implementation".
	Two exchange meetings were held with the aim of reflecting on the scope, implementation and challenges of Resolution 65/2015. They also sought to exchange information on the current status of compliance with the Resolution.
	REDI
	https://docs.google.com/document/d/1D896GbeA9ETYjwAedOVRD4Ivr7kvFFPb/edit?usp=drive_link&ouid=115811457014945646486&rtpof=true&sd=true 
	
	REDI.
Project's DPOs Bureau.
Participating UNS agencies.

	Executive Report on the Virtual Workshop for Strengthening the Rights of Persons with Disabilities.
	Report on training for: (1) judicial officials and (2) health care providers on legal capacity and informed consent (in relation to support systems, reasonable accommodation and safeguards) in sexual and reproductive health practices for women with psychosocial and intellectual disabilities.
	The product was developed by Felicitas Rossi and Carolina Buccetti.
	https://drive.google.com/file/d/1iXZ6pDQUyz3XWqX9HCRSjPTtbBYtG_d8/view?usp=drive_link
	
	

	Report on the needs assessment for the inclusion of people with disabilities in the Northern Region.
	
	REDI.
	
	
	.

	Handbook on SRR for people with disabilities -12-8-24
	The purpose of the product was to provide accessible and inclusive information on sexual and reproductive rights for people with disabilities. It aimed to:

Educate individuals with disabilities and their communities about their rights, addressing common concerns and barriers they face regarding sexuality, autonomy, and healthcare access.
Guide healthcare professionals in delivering non-discriminatory, rights-based, and accessible services, emphasizing the importance of informed consent, privacy, and inclusive communication.
The material was designed to promote dialogue, challenge stereotypes, and support the full exercise of sexual and reproductive rights for persons with disabilities.
	The development of the product was a collaborative effort involving : 
Pan American Health Organization (PAHO/OPS) and United Nations Population Fund (UNFPA Argentina) led the implementation and coordination of the project.
Government Institutions:

Provincial Health Authorities in Jujuy, particularly the program on sexual and reproductive health, facilitated local implementation and engagement of healthcare professionals.
Healthcare Professionals and Institutions:

Local health teams in Jujuy, including general practitioners, gynecologists, pediatricians, nurses, administrative staff, and community health workers, participated in training and provided feedback on accessibility barriers.
	https://docs.google.com/document/d/1q3JbgaYq4kW033g2ZdWWSwxoRtVP1mT6/edit 
	Y
	REDI

	Booklets designed
	The purpose of the product was to develop two educational guides on sexual and (non)reproductive rights for persons with disabilities, targeting both healthcare professionals and individuals with disabilities. These guides aimed to:

Inform individuals with disabilities and their support networks about their rights regarding sexuality, reproduction, autonomy, and healthcare access.
Provide guidance to healthcare professionals on inclusive and rights-based approaches to sexual and reproductive health (SRH) services.
Challenge stereotypes and discriminatory practices in healthcare settings, ensuring that persons with disabilities can make autonomous decisions about their bodies and reproductive choices.
Promote accessibility in health services, advocating for reasonable accommodations and inclusive communication strategies.
	 Research and Needs Assessment

Identification of barriers to SRH services for persons with disabilities.
Review of international and national legal frameworks on disability rights.
Collection of input from OPDs, healthcare professionals, and advocacy groups.
Content Development

Drafting of two separate guides, one on sexual rights and another on (non)reproductive rights.
Integration of real-life scenarios, accessible communication strategies, and legal references to support healthcare professionals.
Design and Accessibility Features

Layout design ensuring readability, contrast, and compatibility with screen readers.
Use of icons, simple typography, and structured sections for easy navigation.
Validation and Feedback

Review by technical experts, OPDs, and health professionals to ensure accuracy and inclusivity.
Iterative modifications based on feedback.
Finalization and Distribution

Production of digital and printable versions for dissemination.
Distribution to healthcare institutions, OPDs, and government agencies to promote inclusive SRH practices.
	https://drive.google.com/drive/u/0/folders/1z8LGuoFODxi7ISFSyTq63DTt2FXhp095 
	Y
	The content was developed in consultation with local health teams to ensure its practical application in healthcare settings

	Final Report of  “Just and Inclusive Societies: Legal Capacity of Persons with Disabilities as a Key to Access to Justice under the UN Convention on the Rights of Persons with Disabilities” activity
	develop a methodology and measurement tool to assess access to justice for persons with disabilities in Argentina. The tool was based on the Justice and Sustainable Development Report of the UNDP 2030 Agenda, incorporating a person-centered approach to justice.
Key objectives included:

Identifying barriers and challenges that persons with disabilities face in accessing justice.
Adapting UNDP Indicator 16.3.3 to reflect the perspectives and lived experiences of persons with disabilities.
Providing a framework for evidence-based policymaking to support inclusive legal reforms.
Enhancing legal empowerment, ensuring that justice mechanisms are accessible and equitable​

	Research and Theoretical Framework Development
Analysis of international best practices and legal standards related to access to justice.
Review of existing methodologies for measuring justice accessibility.
Methodological Design

Adaptation of Indicator 16.3.3 to consider disability-specific legal challenges.
Inclusion of justice-related issues affecting persons with disabilities, such as supported decision-making.
Stakeholder Consultations and Collective Intelligence Process
Workshops with OPDs, legal experts, and justice sector representatives to refine the instrument.
Collection
	https://inclusionydiscapacidad.ar/articulos/sociedades-justas-e-inclusivas-un-instrumento-de-medicion-con-eje-en-el-acceso-a-la-justicia-de-las-personas-con-discapacidad

	Y
	Organizations of Persons with Disabilities (OPDs) played a key role in shaping the methodology by contributing firsthand experiences, advocacy, and insights into the barriers faced by persons with disabilities.
Academia and Research Institutions:

Legal experts and researchers participated in designing and refining the methodology.
Government and Justice Sector Representatives engaged in validating the methodology and ensuring alignment with existing legal frameworks

	Focus on Disability: Comprehensive Sexual Health Counseling for Adolescents - Guideline
	The purpose of the product was to develop an Inclusive Comprehensive Sexual Health Counseling Model for adolescents and young people with disabilities in Jujuy, Argentina. This initiative aimed to:

Ensure access to sexual and reproductive health (SRH) services for adolescents with disabilities, addressing existing gaps in accessibility and inclusion.
Adapt sexual health counseling models to the specific needs of young people with disabilities, incorporating reasonable adjustments and inclusive communication strategies.
Promote autonomy and informed decision-making, ensuring that young people with disabilities can fully exercise their sexual and reproductive rights.
Strengthen inter-institutional collaboration, integrating efforts from healthcare centers, rehabilitation facilities, and educational institutions to provide comprehensive support.
	Stakeholder consultations to determine key gaps and needs.
Development of the Inclusive Counseling Model
Adaptation of existing sexual health counseling frameworks to disability-inclusive methodologies.
Creation of accessible materials and tools to support counseling sessions.
Pilot Implementation in Jujuy
Testing of the counseling model at CEMIR and CAPS Los Alisos.
Engagement of healthcare professionals, social workers, and educators in delivering counseling sessions.
Incorporation of interactive workshops and peer discussions to ensure participatory learning.
Evaluation and Refinement
Collection of feedback from adolescents, families, and professionals.
Identification of challenges and areas for improvement in service delivery.
Adjustments to the model based on real-world application.
Finalization and Policy Recommendations.
Compilation of findings and best practices into a finalized model.
Advocacy for institutionalization of inclusive SRH counseling across the health system.
	https://drive.google.com/file/d/1HOnEPZPUA4IS7bUuObmnra2LT8LwKVuD/view 
	Y
	Health professionals and OPDs, who reviewed and refined the counseling approach to enhance accessibility and effectiveness.
Adolescents with disabilities, who actively participated in the pilot phase, providing direct feedback on accessibility, relevance, and effectiveness of the counseling model.

	Comprehensive Sexual and (Non)Reproductive Health Model for Persons with Disabilities 
	The product was developed to establish an inclusive and accessible framework for sexual and reproductive health (SRH) services for persons with disabilities, particularly those with psychosocial disabilities.
Reducing barriers to SRH services for persons with disabilities by implementing reasonable accommodations and inclusive communication strategies.
Ensuring the autonomy and legal capacity of persons with disabilities in making informed decisions about their sexual and reproductive health.
Providing an interdisciplinary and person-centered approach to SRH, integrating professionals from health, psychology, and social work fields.
Promoting institutional change by adapting health services to be inclusive and aligned with national and international disability rights frameworks.
	The process involved Context Analysis and Research
Identification of barriers faced by persons with disabilities in accessing SRH services.
Review of best practices and international recommendations for inclusive sexual health counseling.
Development of the Counseling Model
Adaptation of existing mental health and sexual health frameworks to the realities of persons with disabilities.
Incorporation of alternative communication strategies to ensure accessibility.
Testing of the counseling approach in real-life healthcare settings with persons with disabilities.
Integration of interdisciplinary perspectives from different health professionals.
Evaluation and Adjustments.
Collection of feedback from healthcare providers and persons with disabilities.
Refinements to improve the effectiveness and accessibility of the model.
Finalization and Standardization.
Systematization of the final model for broader implementation in mental health and primary healthcare centers.
	https://drive.google.com/file/d/1I2uQDaJ_9jL1PQxYH1WckTR3b6Xhl4XL/view 
	Y
	

	Finding on workshop “Sexual and Reproductive Health and Persons with Disabilities" - Report
	Its main objectives were:
Enhancing healthcare professionals' knowledge and practices on sexual and reproductive rights (SRR) for persons with disabilities.
Challenging stereotypes and misconceptions surrounding the sexuality of persons with disabilities.
Facilitating intersectoral collaboration between disability and health institutions.
Providing tools and strategies for healthcare teams to ensure accessible, inclusive, and rights-based SRH services.
	Planning and Coordination
Meetings with provincial health authorities to define key themes and workshop structure.
Selection of health professionals and OPDs as participants.
Training Workshop Implementation (December 6, 2024)
Conducted at the Council of Physicians of Jujuy.
Facilitated by Constanza Leone and Carolina Buceta.
Included theoretical sessions, participatory discussions, and practical case analysis.
Evaluation and Systematization
Participants provided feedback on barriers in healthcare services and strategies for improvement.
Findings were compiled into a public policy document outlining best practices and recommendations for institutionalizing inclusive sexual and reproductive healthcare​
	https://drive.google.com/file/d/15-ur2xorahD5QnZBijh2RHhgArKq_kLT/view 
	Y
	Healthcare professionals from various regions of Jujuy, who applied the knowledge in their work.
Provincial Ministry of Health, which supported and co-organized the workshop.
Persons with disabilities and OPDs, who participated in discussions and provided feedback on the accessibility and relevance of the training content.

	Brochure easy to read 
	Its primary objectives include:
Challenging harmful stereotypes that deny or limit the sexuality of persons with disabilities.
Providing accessible and clear information on sexual rights, intimacy, and autonomy.
Ensuring that persons with disabilities are recognized as rights-holders in their sexual and reproductive lives.
Encouraging healthcare providers to offer non-discriminatory and confidential services.
	Stages of Development
Content Drafting and Concept Development
Identification of key misconceptions and barriers regarding the sexuality of persons with disabilities.
Definition of clear, simple, and empowering messages for the audience.
Design and Accessibility Adaptations
Use of plain language, large fonts, and contrast-adjusted visuals to ensure readability.
Inclusion of direct, affirming statements about the sexual rights of persons with disabilities.
Review and Validation
Feedback from OPDs and professionals to refine messaging and accessibility.
Adjustments based on usability testing with the target audience.
Finalization and Printing
Production of digital and printed versions for wide dissemination.
	https://drive.google.com/drive/u/0/folders/1VHpUcmAoek6ecuHjFOZGGu_zz2L8g2SA 
	Y
	

	Final report. Contains findings on a federal sample of judicial decisions regarding legal capacity of PwD. 
	Its primary objectives include
Gathering empirical evidence on how legal capacity determinations are handled in judicial processes across Argentina.
Assessing the implementation of national and international disability rights frameworks, particularly the Convention on the Rights of Persons with Disabilities (CRPD).
Providing policy recommendations to align judicial practices with human rights standards.
Enhancing access to justice by identifying systemic barriers in legal capacity cases.
	Stages of Development
Research and Framework Design

Analysis of existing legal capacity cases and court procedures.
Identification of key indicators to assess implementation of disability rights in justice systems.
Drafting the Judicial Information Request

Structuring the request to align with national legal frameworks and CRPD principles.
Ensuring compliance with data protection laws (Law 25.326 on personal data protection).
Submission and Follow-Up.
Sending the request to provincial Supreme Courts across Argentina.
Establishing communication channels for clarifications and follow-ups with judicial authorities.
Data Collection and Analysis.
Processing received judicial data while maintaining anonymity.
Preparing policy recommendations based on findings​
	https://inclusionydiscapacidad.ar/articulos/restriccion-de-la-capacidad-juridica-y-garantias-procesales-analisis-de-sentencias-en-argentina-2015-2023

	Y
	The product was validated through a structured process involving key judicial actors. A survey was conducted among seven justice system professionals, of whom four experts provided detailed feedback. These experts represented different provinces in Argentina, including Chubut, Tucumán, Buenos Aires, and La Pampa, and held positions such as:

Family Court Judge
Legal Assistant in a Family Court
Advisor for Minors and Incapacitated Persons
Secretary in a Civil and Commercial Court

	Report on Legal Capacity and Access to Justice for Persons with Disabilities: A Federal Normative Analysis
	The purpose of this report is to analyze the need for normative reform at the federal level to strengthen access to justice for persons with disabilities in Argentina.
Mapping and evaluating provincial legal frameworks related to legal capacity and access to justice.
Identifying gaps and inconsistencies between provincial procedural laws and the standards established by the Convention on the Rights of Persons with Disabilities (CRPD).
Highlighting best practices that align with the human rights approach to disability.
Providing principles and guidelines to inform future reforms of provincial procedural codes.
	Analysis of provincial procedural laws related to legal capacity.
Identification of inconsistencies with international disability rights standards.
Mapping of Best Practices and Barriers
Review of existing reforms and judicial innovations in different provinces.
Identification of challenges in the implementation of legal capacity reforms.
Participatory Consultations and Validation Workshops.

Two participatory workshops with experts, OPDs, and judicial actors.
52 participants from nearly all Argentine provinces contributed their perspectives.
Development of Reform Guidelines
Creation of principles and recommendations to guide future normative reforms.
Final Report and Policy Recommendations
Compilation of findings and reform proposals into a final document.

	https://inclusionydiscapacidad.ar/articulos/capacidad-juridica-y-acceso-a-la-justicia-de-las-personas-con-discapacidad-un-analisis-normativo-federal 
	Y
	The report was validated through participatory workshops and consultations.
52 professionals participated in two workshops, including:
Legal experts and judges with experience in disability rights.
Academics specializing in disability law and access to justice.
Representatives of OPDs and activists with and without disabilities.

	Systematization of Institutional Capacities of the Federal Council of Public Defenders for the Inclusion of Disability in Access to Justice Policies - Report
	The purpose of this report is to analyze and systematize the institutional capacities of the Federal Council of Public Defenders in Argentina regarding the inclusion of disability in access to justice policies.
Key objectives include:
Assessing the role of Public Defenders in guaranteeing access to justice for persons with disabilities.
Identifying best practices and challenges in ensuring compliance with the Convention on the Rights of Persons with Disabilities (CRPD).
Providing recommendations for strengthening institutional capacities to better address the rights and legal needs of persons with disabilities.
Encouraging inter-institutional collaboration to improve legal assistance and decision-making support mechanisms
	The process involved Data Collection

A self-assessment survey was conducted among Public Defenders across Argentina.
Interviews and surveys were carried out with key institutional actors.
Analysis of Institutional Capacities

Review of existing legal frameworks and procedural gaps regarding disability rights.
Identification of best practices and areas for improvement.
Recommendations for Strengthening Capacities

Development of policy recommendations for Public Defenders to enhance their role in promoting access to justice for persons with disabilities.
Finalization and Dissemination

Compilation of findings into the final report to guide future legal and institutional reforms​
	https://docs.google.com/document/d/12n_f8OQv48c205UpI4S-DgQoQ7Emmpxx/edit 
	Y
	Yes. By: Federal Council of Public Defenders

	Contributions to Legal Research on the Rights of Persons with Disabilities in Argentina (Legal Analysis and Recommendations Document)
	The purpose of this document is to provide legal analysis and recommendations on the processes of legal capacity determination for persons with disabilities in Argentina. These contributions serve as a critical review of the final report "Diagnosis of the Processes for Determining the Legal Capacity of Persons with Disabilities", prepared by Unidos por la Justicia.
Key objectives include:
Aligning findings with international human rights standards, particularly the Convention on the Rights of Persons with Disabilities (CRPD).

	Detailed analysis of the "Diagnosis of the Processes for Determining the Legal Capacity of Persons with Disabilities" by Unidos por la Justicia.
Identification of strengths, gaps, and inconsistencies with human rights standards.
Legal Analysis and International Framework Review
Comparative study of Argentine judicial practices and international legal obligations under the CRPD.
Consideration of legal reforms, including the 2015 Civil and Commercial Code reform.
Intersections with Gender, Diversity, and Discrimination
Examination of gender-based and intersectional discrimination in legal capacity rulings
	https://docs.google.com/document/d/1AqHjWf5UkYXt4ni7I8h25Vk7nD8g_ioSts0HFQk0VKk/edit?tab=t.0 
	Y
	

	
	
	
	
	
	



8. Communications materials   
 
	Branding: Were there any visual assets developed? (For example, banners, notebooks, social media cards).  

	Visual assets were developed for the different campaigns. Additionally, a landing page with all the materials produced by the programme is online and its design was considered following accessible communication guidelines. https://inclusionydiscapacidad.ar/ 
 

	Dissemination: What tools work best for communication and dissemination, and what don´t? (For example, dissemination across social media platforms, which platforms have worked best from your experience and why do you think that is the case) Have you collaborated with any ‘influencers’ or organizations in the country for cross-promotion of the project, civil society or partner organizations? If yes, could you share their handles? Is there a dedicated webpage section or Flickr album. 

	 
During 2022 and 2023, social media campaigns were carried out in Argentina around the commemoration of the International Day of Persons with Disabilities (3 December) and the International Human Rights Day (10 December). All SNU agencies and Organizations of Persons with Disabilities (OPDs) participated actively, replicating the messages and communication products that had been jointly developed for both dates. All communication and visibility materials produced during the period were fully accessible.

In addition, comprehensive training sessions were provided to all communications teams within the SNU,and a jointly‑developed manual was created to harmonize and strengthen the system-wide approach to disability-inclusive communication in Argentina.

The project also developed a dedicated landing page integrated into the UN Argentina website. This platform is designed to centralize all project-related products and activities, ensuring accessibility, visibility, and long‑term availability with minimal maintenance needs. Importantly, this platform not only preserves the institutional memory of the project but also functions as an open repository that could be used to scale good practices and foster inter‑institutional cooperation. The landing page is aimed to serve as a key resource for all stakeholders, including agencies across the UN Argentina system, facilitating synergies with their initiatives and other projects, while promoting the effective mainstreaming of disability inclusion. 
This digital platform not only preserves the institutional memory of the project but also functions as an open repository that enables the scaling of good practices and promotes inter‑institutional cooperation.


	Media: Has there been any media coverage? If yes, what were the main obstacles when liaising with the media? Has there been any media request for interviews? 

	
 No, there wasn’t any media coverage. 


 
Please also list the type of communications material using the table below. 
	Name of Product
	Type of Product (toolkit,  Video, Poster, etc.)
	Purpose
	Dissemination
	Links/ Attachments
	Language
	Accessible formats

	#DayOfPersonsWithDisability
	Video/Spot
	To promote the human rights of people with disabilities in all fields and raise awareness about we can all work to eliminate them because the responsibility is collective.
	Instagram, Facebook, Twitter,
You tube
	SPOT 16-9_final.mp4
	Spanish
Sign Language
	The links informed are in accessible formats

	"I want to have an independent life and be equal to everyone"
	Audiograms
	To promote the human rights of people with disabilities in all fields and raise awareness about we can all work to eliminate them because the responsibility is collective
	Instagram, Facebook, Twitter,
You tube
	Clara 16.9 AUDIOGRAMA.mp4
	Spanish
Sign Language
	The links informed are in accessible formats

	"We are not seen in different spaces yet, and that is why we are not thought of as autonomous people”
	Audiograms
	To promote the human rights of people with disabilities in all fields and raise awareness about we can all work to eliminate them because the responsibility is collective
	Instagram, Facebook, Twitter,
You tube
	Joana 16.9- AUDIOGRAMA.mp4

	Spanish
Sign Language
	The links informed are in accessible formats

	"People with disabilities are autonomous, independent and capable people
to form their own opinions.”
	Audiograms
	To promote the human rights of people with disabilities in all fields and raise awareness about we can all work to eliminate them because the responsibility is collective
	Instagram, Facebook, Twitter,
You tube
	Daniela 16.9 -AUDIOGRAMA.mp4
	Spanish
Sign Language

	The links informed are in accessible formats

	#DayOfPersonsWithDisability
UNIC 
	Video/Spot
	To promote the human rights of people with disabilities in all fields and raise awareness about we can all work to eliminate them because the responsibility is collective.
	Instagram, Facebook, Twitter,
You tube
	https://argentina.un.org/es/209667-querer-cambiar-el-concepto-de-discapacidad-lo-llev%C3%B3-la-cima-del-himalaya-ganar-un-premio 

https://www.youtube.com/watch?v=-IOOgS3BlzQ&ab_channel=ONUArgentina 
	Spanish 

	The links informed are in accessible formats

	Democracy 40 years. Part 1
	Video.
	Raise awareness to prevent the regression of what has already been achieved in terms of legal capacity to promote autonomy, independent living, access to justice and sexual and reproductive health of persons with disabilities.
	Youtube
Instagram
Facebook
X

	https://www.youtube.com/watch?v=QPbmWbd_nC8 
	Spanish, 
Sign Language, 
Subtitles.

	The links are in accessible formats.

	Democracy 40 years. Part 2
	Video.
	Raise awareness to prevent the regression of what has already been achieved in terms of legal capacity to promote autonomy, independent living, access to justice and sexual and reproductive health of persons with disabilities.
	Youtube
Instagram
Facebook
X

	https://www.youtube.com/watch?v=WzkAeK5-Cgo 
	Spanish, 
Sign Language, 
Subtitles.

	The links are in accessible formats.

	Democracy 40 years. Part 1
	Video
	Raise awareness to prevent the regression of what has already been achieved in terms of legal capacity to promote autonomy, independent living, access to justice and sexual and reproductive health of persons with disabilities.
	Youtube
Instagram
Facebook
X

	https://www.youtube.com/watch?v=_CX8sy0G2fY&t=3s
	Spanish, 
Sign Language, 
Subtitles.
	The links are in accessible formats.

	Let's remove the barriers
	Video
	It is a video where we 
The video is intended to show the obstacles encountered and to provide tools for the implementation of the accessibility perspective

	YouTube
Instagram
Facebook
X

	https://youtu.be/6VS-5GVMHik
	Spanish, 
Sign Language, 
Subtitles..

	The links are in accessible formats.

	Mental Health is in Community
	flyer.
	It is a booklet related to mental health and human rights.
	YouTube
Instagram
Facebook
X
	https://drive.google.com/file/d/1idNfQSLiVYGhEWdUx-qbyG82IBgIT3Ws/view?usp=drivesdk 
	Spanish
	The links are in accessible formats.

	17th Meeting in Diversity Day
	flyer.
	Promotes the conference to discuss the mechanisms of exclusion and inequality within the group of people with disabilities.
	YouTube
Instagram
Facebook
X
	https://drive.google.com/file/d/1ihMWyOCmALmIuMDEdNTaa7GzVL0l2v-q/view?usp=drivesdk 
	Spanish
	The links are in accessible formats.

	Karina photo sentence 1
	photo
	Advocacy
	Instagram
Facebook
X

	https://drive.google.com/drive/folders/1UIn0uhik8DqxDKBaDIS6qN9WrjQPMdma
	Spanish.
	The links are in accessible formats.

	Karina photo sentence  2
	photo
	Advocacy
	Instagram
Facebook
X

	https://drive.google.com/drive/folders/1UIn0uhik8DqxDKBaDIS6qN9WrjQPMdma
	Spanish.
	The links are in accessible formats.

	Mariana photo 1
	photo
	Advocacy
	Instagram
Facebook
X

	https://drive.google.com/drive/folders/1qojao1SXmxLzvw0oFrye2JGIb114CEH4
	Spanish.
	The links are in accessible formats.

	Mariana photo 2
	photo
	Advocacy
	Instagram
Facebook
X
	https://drive.google.com/drive/folders/1qojao1SXmxLzvw0oFrye2JGIb114CEH4
	Spanish.
	The links are in accessible formats.

	Mirtha photo 1
	photo
	Advocacy
	Instagram
Facebook
X
	https://drive.google.com/drive/folders/15Kl8VSeSRT1zmQl_vovprJHPFxmpQy9y
	Spanish.
	The links are in accessible formats.

	Mirtha photo 2
	photo
	Advocacy
	Instagram
Facebook
X
	https://drive.google.com/drive/folders/15Kl8VSeSRT1zmQl_vovprJHPFxmpQy9y
	Spanish.
	The links are in accessible formats.

	Project landing page 
	Web
	
	
	https://inclusionydiscapacidad.ar/

	Spanish
	



9. Challenges
	Please describe any major challenges that arose during the programme implementation and how this affected the programme implementation.  

	During the years of GDF programme implementation in Argentina, the initiative faced several challenges that tested the adaptability and resilience of all parties involved. The programme had to address challenges related to changes in government management at the national and subnational levels. These changes required additional efforts from the UN agencies to meet intervention deadlines and also posed additional challenges regarding strategies to ensure the sustainability of support lines. Some of these efforts involved the need for continuous monitoring, rescheduling of dates, and so on. Indeed, the programme's role in supporting management changes was highlighted in an external evaluation last year. Similarly, it is worth noting the inherent advantages for agencies to be able to implement the program directly, thereby ensuring the continuity of processes in the context of constant institutional change.
The UNPRPD team, government and OPDs and civil society actors, maintain a constructive approach in all instances of dialogue, sharing needs and concerns to move forward and replan when the situation required it.
A key challenge during programme implementation was government authorities’ changes, especially in the National Disability Agency (ANDIS). Additionally, one of the biggest challenges was the new administration priorities, which brought significant shifts in the institutional approach to inclusion and persons with disability rights and tackled some of the sustainability policies that were supported during the programme. The transition period extended for more than six months before new authorities were appointed, and disability policies were subsequently placed under the health portfolio, limiting the comprehensive, cross-sectoral perspective developed in previous years. This restructuring, combined with the absence of formally designated focal points for the project in both the justice and health sectors until the programme’s conclusion, hindered consistent institutional engagement. In parallel, macroeconomic instability, marked by high inflation and currency devaluations, reduced the real value of available resources and required adjustments to planned activities, affecting the pace and scope of implementation.


	Please could you share what action you took to address identified challenges?  

	To address these challenges, the programme strengthened its subnational work, with particular emphasis on northern Argentina and the provinces comprising the Gran Chaco region, which had been identified as a priority area. Efforts were also directed towards enhancing outreach and collaboration with civil society, in order to build on the programme’s earlier achievements and sustain impact. This included promoting the implementation of existing, still-valid guidelines on sexual and reproductive health for persons with disabilities, as well as leveraging the findings from the analysis of access to justice to inform ongoing advocacy and capacity-building initiatives.
Moreover, partnerships and alliances with judiciary were essential to continue and give sustainability to the work on legal capacity. 
Open dialogue and flexibility in planning made it possible to overcome the obstacles imposed by the context and achieve the necessary coordination both within and outside the UN System. In this regard, the RCO played a key leadership role for action coordination, political and institutional assessment and reconduct actions if needed. 
Additionally, the Joint Programme demonstrated strong inter‑agency coordination, grounded in close collaboration among UN agencies. This inter‑agency cooperation was a key strength that supported programme coherence and implementation throughout its duration. Importantly, this inter‑agency coordination enabled a comprehensive and holistic vision of the programme, as well as detailed follow‑up of activities, which in turn facilitated timely collaboration to address the challenges identified and ensured consistent progress despite institutional and contextual constraints.
It should be mentioned that throughout the programme, we have worked very diligently with all the partners involved to ensure the sustainability of the actions. The focus on strengthening governmental and non-governmental institutional capacities has been key and will continue to be so in ensuring progress on human rights of persons with disabilities. 




10.  Project Sustainability
	Please provide an overview of initiatives planned by various stakeholders in order to follow up on activities initiated by the programme. 

	The programme has been working from the outset to ensure the sustainability of the actions once the programme closes. Despite current political challenges that may threaten the sustainability we have sought, we believe that much of the supported work will remain relevant in the country. On the one hand, we have made a significant investment in strengthening the capacities of officials at the national and subnational levels. These capacities have been consolidated and are part of the country's human capital, which will contribute to advancing disability agenda, regardless of changes in administration or political affiliation.
At the subnational level, several governments have expressed their commitment to continue the training of health teams for the provision of sexual and reproductive health care to persons with disabilities. This includes, for example, the province of Jujuy, where there is strong interest in sustaining these initiatives, subject to the availability of financial resources. 
In the area of access to justice, the Council of the Judiciary of the Autonomous City of Buenos Aires has implemented an initial set of accessibility adjustments to its online justice portal and has developed guidelines for a second phase, to be implemented according to available resources. Building on this progress, the Public Defender’s Office adopted the Council’s experience as a reference and subsequently redesigned its own institutional portal to make it accessible for persons with low vision and persons with visual disabilities. This replication of good practices demonstrated increasing institutional commitment to accessibility standards and contributed to strengthening long‑term sustainability.
Moreover, strengthening the capacities and work of OPDs, especially those belonging to unrepresentative vulnerable groups, has enhanced its organizational and advocacy skills. The programme has fostered collaboration and support between OPDs that will continue
 The programme has supported OPDs skills in human rights advocacy, public policy analysis and monitoring of the Convention on the Rights of Persons with Disabilities (CRPD), in order to be engaged meaningfully with decision￼makers.
Additionally, the programme has worked to build the capacity at the UN System to ensure OPDs are meaningfully consulted and represented in cooperation processes, inter￼agency coordination spaces, and development programs, with reasonable accommodations and accessible formats that are now part of UN guidelines. 
these actions empower OPDs to act as strong, autonomous actors and key partners in advancing the rights of persons with disabilities. 
The programme has also fostered collaboration among OPDs, civil society, government institutions, and UN agencies to share knowledge, amplify voices, and promote coordinated action that remains as an asset for cooperation on disability projects or initiatives. 
These are illustrative examples of a broader range of follow-up initiatives by various stakeholders, which aim to build on the programme’s achievements and ensure the continued advancement of disability inclusion.


	Please outline how the medium-to-long term sustainability of the work initiated by the project will be ensured after the end of the Project.

	The medium-to-long term sustainability of the work initiated by the project is supported by the institutionalization of key outputs and the strengthened capacities of participating stakeholders. Guidelines, protocols, and technical notes developed during the programme —including those on sexual and reproductive health for persons with disabilities, accessible communication, and digital accessibility of justice portals— remain in force and can be applied independently by relevant institutions. The active engagement of subnational governments, particularly in priority regions such as the Gran Chaco, and the strengthened alliances between OPDs, civil society organizations, and public sector actors provide a foundation for continued implementation. Furthermore, the participatory methodologies, inter-agency strategies, and knowledge products generated by the project are designed for easy adaptation and replication, enabling their use in future initiatives and ensuring that the progress made can be sustained and expanded over time.




11.Risk Reporting  
 Please describe any risks experienced during the programme’s implementation and how these were managed.  
	 Type of risk* 
(Contextual, programmatic, institutional) 
	Risk 
	Occurrence 
(Y/N) 
	Impact on result  
	Mitigation strategies 
	Risk treatment owners 

	Contextual
	Change of government leading to policy shifts and delays in appointing authorities, limiting cross-sectoral disability policies
	Y
	High – hindered institutional coordination and slowed planned activities
	Strengthened subnational engagement, especially in priority regions; enhanced collaboration with civil society to sustain impact
	UN agencies, subnational governments, OPDs

	Contextual / Programmatic
	Macroeconomic instability (inflation, currency devaluation) reducing real value of resources
	Y
	Medium – required adjustments to planned activities and timelines
	Reprioritization of activities, efficiency measures, and resource reallocation
	UN agencies, implementing partners

	Institutional
	Lack of formally appointed focal points in justice and health sectors
	Y
	High – reduced direct coordination for specific outputs
	Worked with existing technical teams and alternative institutional counterparts; leveraged inter-agency collaboration
	UN agencies, technical teams in ministries

	Programmatic
	Limited OPD presence and capacity in certain regions (e.g., northern Argentina)
	Y
	Medium – required additional efforts to ensure participation and representation
	Capacity-building activities, strengthening alliances between OPDs and civil society in target regions
	UN agencies, OPDs, civil society partners


 
* Please specify here the type of risk and refer to the following definitions: 
Contextual: risk of state failure, return to conflict, development failure, humanitarian crisis; factors over which external actors have limited control. 
Programmatic: risk of failure to achieve the aims and objectives; risk of causing harm through engagements. 
Institutional: risk to the donor agency, security, fiduciary failure, reputational loss, domestic political damage etc. 

12. Detailed expenditure in relation to sections 3, 4 and 5 above
	Category
	Activity (please describe)
	Budget Allocated
	Total Expenditure

	Direct impact on empowerment of women and girls with disabilities 

	(2022) Protocol on sexual and reproductive healths
	25% - USD 70,093
	$662

	
	(2023) Status of Resolution 65/20151 of the National Ministry of Health regarding persons with disabilities in their relationship with the health system: challenges and proposals for its implementation.
	
	$13,726.07

	
	(2023)Technical Note with guidelines for the regulatory implementation of Law No. 26,130 on Surgical Contraception.
	
	

	
	(2023)SRH Counseling Booklet: Towards an Inclusive Sexual and Reproductive Health Counseling for Persons with Disabilities. 
	
	

	
	(2023)Virtual workshop for strengthening the rights of persons with disabilities.
	
	

	
	(2023) Methodological adaptation of targets 3.7 and 5.6 of the Sustainable Development Goals.
	
	

	
	(2023) Strategic communication plan. Day of Persons with Disabilities #EliminemosLasBarreras
	
	

	
	(2024)Training of health professionals in Jujuy
	
	$11,544.01

	
	(2024)Digital graphic booklet on the rights of persons with disabilities in sexual and reproductive health and non-reproductive health
	
	

	
	(2024)An easy-to-read pamphlet addressing the sexual and reproductive rights of persons with disabilities, debunking prejudices, and promoting access to a full and autonomous sexual life 
	
	

	
	(2024)Public policy document on sexual and reproductive health counselling for youth with mental disabilities, considering the Jujuy experience. 
	
	

	
	(2024) Systematization and analysis of regulations on sexual and reproductive health for persons with disabilities.
	
	

	Full and effective participation of persons with disabilities/ OPD capacity building 
	(2022) Seminars and series of dialogue facilitated 
	30% - USD  84,112
	$10,898

	
	(2023)Design and planning of the action plan for the advocacy strategy "40 years of Democracy, for an Inclusive
	
	$9,031.76

	
	(2023)Training of 2 meetings for DPOs on the preparation of reports to be submitted to the CRPD, UN HR and SDGs.
	
	

	
	(2023)Workshop with the objective of generating a space for reflection and exchange among youth to contribute to a more inclusive society, from the use of social networks.
	
	

	
	(2023)Workshop to strengthen the capacities of organizations for people with disabilities.
	
	

	
	(2023)Positioning document
People with disabilities in the Third National Voluntary Report of Argentina 2022.
	
	

	
	(2023) Training on the preparation of Alternative Reports to be submitted to the United Nations, aimed at civil society organizations.
	
	

	
	(2024)Educational materials and guides for judicial officials and healthcare providers in accessible formats
	
	$57,096.50

	
	(2024) Systematization of support materials ensuring accessibility of instructional content
	
	

	
	(2024)Methodological proposal for training replication for health and justice teams
	
	

	
	(2024).Diagnosis on judicial procedures related to legal capacity restriction in Argentina
	
	

	
	(2024).Workshop for judicial and public ministry officials on legal capacity determination processes
	
	

	
	(2024).Participatory process with OPD, civil society, and stakeholders
	
	

	
	(2024)Workshop on federal regulatory reform needs to strengthen legal capacity and access to justice
	
	

	
	(2024).Analysis of institutional capacities of the Federal Council of Public Defenders in Argentina
	
	

	
	(2024).Study on justice needs and access levels for persons with disabilities under SDG 16.3.3 indicator
	
	

	
	(2024) Methodology and instrument to measure access to justice for persons with disabilities in Argentina
	
	

	
	(2024) Collective intelligence workshop designing a measurement instrument for access to justice
	
	

	
	(2024)Workshop on 'Sexual and Reproductive Health and Persons with Disabilities'
	
	

	
	(2024)Easy-to-read leaflet to guide rights holders on implementing RC PD, CCC, and NMSH
	
	

	
	(2024)Legal research on rights of persons with disabilities in Argentina
	
	

	
	(2024)Virtual course on attitudinal transformation
	
	

	
	(2024)Training on attitudinal transformation for inclusion of persons with disabilities
	
	

	
	(2024)Guidance note on good practices by local governments for participation of persons with disabilities
	
	

	
	(2024)Systematization of Experiences from the Evaluation of the Participatory Methodology
	
	

	
	(2024)Policy proposal based on findings of 'Diagnosis on legal capacity restriction court proceedings'
	
	

	
	(2024)Validation of regulatory proposal for legal capacity determination procedure improvement
	
	

	
	(2024)Proposals to strengthen regulatory frameworks and mechanisms for political and social participation
	
	

	
	(2024)Validation of a proposal to strengthen regulatory frameworks for digital inclusion and accessibility
	
	

	
	(2024)Mapping of solutions for legal capacity exercise for persons with disabilities
	
	

	
	(2024)Federal replicability manual for a Guide on Access to Justice for persons with disabilities
	
	

	
	(2024)Guide on Access to Justice for persons with disabilities
	
	

	
	(2024)Guide on assistive technologies and universal design for digital inclusion and political participation
	
	

	
	(2024)Virtual workshop for persons with disabilities within the UN Common Country Analysis (CCA) process
	
	

	
	(2024)Document with tools to include disability perspective in UN strategy in Argentina
	
	

	
	(2024) Workshop for communication teams of United Nations System agencies in Argentina on communication accessibility and the production of accessible audiovisual resources.
	
	

	Direct reach/inclusion of marginalized and vulnerable groups  
	(2002) Campaign
	5% - USD 14,019
	$ 4,672

	
	(2023)Report for the construction of a diagnosis on the implementation of accessibility measures, support and reasonable adjustments in the exercise of sexual, reproductive and non-reproductive rights of women and feminized dissidents with disabilities.
	
	$41,335.22

	
	
(2023)Practical guide: Process of determination of legal capacity in easy reading. 
	
	

	
	(2023)Diagnostic study on the judicial processes for the determination of legal capacity in Argentina.
	
	

	
	(2023)Training workshop on digital accessibility in the judiciary:    Contributions for the construction of an Accessible Judicial Portal.
	
	

	
	(2023)Proposal for candidates elections 2023.
Evaluation of the needs for the inclusion of persons with disabilities from the voices of the Northern Region.
from the voices of the Northern Region.
	
	

	
	(2023)Virtual workshop to strengthen the rights of persons with disabilities for health personnel.
	
	

	
	(2023)Strategic communication plan. Day of Persons with Disabilities #EliminemosLasBarreras
	
	

	
	(2024)Legal empowerment and capacity exercise workshop for indigenous communities in Gran Chaco
	
	$18,267

	
	(2024)Planning of an evaluation mission for inclusion and participation of indigenous persons with disabilities
	
	

	
	(2024)Virtual meeting to gather information on indigenous persons with disabilities in Gran Chaco
	
	

	
	(2024)Awareness strategy for improving access to justice for indigenous persons with disabilities
	
	

	
	(2024)Training session for health teams in Jujuy
	
	

	Accessibility costs
	(2022) Seminars and launching event
	USD 14,000
	$ 1,000

	
	(2023) Training day on digital accessibility in the judiciary:
Contributions for the construction of an Accessible Judicial Portal.
	
	$16,272.48

	
	(2023) Workshop/roundtable of two meetings for the formulation of guidelines to complement Resolution 65/2015 of the Ministry of Health to broaden and deepen its scope.
	
	

	
	(2023)Proposal for candidates elections 2023.
	
	

	
	(2023)Workshop with the objective of generating a space for reflection and exchange among youth to contribute to a more inclusive society, from the use of social networks.
	
	

	
	(2024)Preparation of a Legal Research Contribution Document on the Rights of Persons with Disabilities: Accessible versions of the document were created in easy-to-read formats and screen-reader-compatible formats
	
	$3,124

	
	(2024)Territorial Work in the Gran Chaco for Indigenous Persons with Disabilities: Translation of materials into indigenous languages was implemented, ensuring cultural and linguistic accessibility. Additionally, Argentine Sign Language (LSA) interpreters participated in the meetings
	
	

	
	(2024)Guidance Note for Local Governments on the Inclusion of Persons with Disabilities: Accessible virtual consultation sessions were conducted, ensuring the participation of persons with different types of disabilities
	
	

	
	(2024)Development of a Guide on Assistive Technologies and Universal Design - Accessibility: Consultations were conducted with persons with disabilities who are experts in digital accessibility, ensuring that recommendations were practical and effective. Accessibility tools for persons with visual, auditory, and intellectual disabilities were included 
	
	

	
	(2024)Interpretation for the workshop "Workshop on Federal-Level Regulatory Reform Needs" in LSA and simultaneous Spanish subtitles service)
	
	

	
	(2024)Interpretation for the workshop "CCA Workshop on the United Nations Common Country Analysis for Organizations of Persons with Disabilities" in LSA and simultaneous Spanish subtitles
	
	

	
	(2024) Meeting to Gather Information for the Digital Accessibility Document: A session was held to collect information for the development of the digital accessibility document. The meeting included discussions on barriers, necessary improvements, and best practices. Argentine Sign Language (LSA) interpretation and simultaneous Spanish subtitles were provided. 
	
	



14. Photos depicting Project related impact and outcomes 

Please share photos depicting programme in high resolution image files with appropriate consents of subjects having been taken as well as with the associated credits and along with permission for use in UNPRPD publications and communications materials including website. Please refer to the UNPRPD photography guidelines which have been shared with the country teams already.  
	Photo No.
	Photo description for use in alternative text for images to enable persons with visual impairments using screen readers to understand and perceive the image.
	Consent for Use of Photo obtained (Y/N)
	Photo Caption
	Photo Credit

	https://drive.google.com/file/d/1NSRBhd8mMKy2sjCXGdIzzPR25MIdl68r/view?usp=sharing
	Clara is sitting in a wheelchair and communicates through an assisted alternative communication system.
	Yes 
	"I want to have an independent life and be equal to everyone." Clara Goitia is 38 years old and is part of the Azul Association. She works for the respect of the autonomy of people with disabilities.
	Clara Campos

	https://drive.google.com/file/d/1NbqVLGkfntxoUbvdZWw8_tdinN1BL4Au/view?usp=sharing
	Daniela Gómez is a 35-year-old woman. She has black hair, a black T-shirt, and is sitting on a chair. Behind her, a window is seen.November 11, La Plata, Buenos Aires.  
	Yes
	"People with disabilities are autonomous, independent people and capable of forming their own opinions." Daniela Gómez is 35 years old and is part of the Network for the Rights of Persons with Disabilities. For her, it is key to guarantee the accessibility of the 2023 electoral campaign, as well as the right to vote.
November 11, Autonomous City of Buenos Aires
	Clara Campos

	https://drive.google.com/file/d/1b1cMAQxcb1VjY_NfRGc3ZFpmTBjvFXuz/view?usp=share_link
	Johana is a 28-year-old woman. 
	
	
	

	https://drive.google.com/file/d/1U6eqBcU02weUDSflSlmuIC2Yx_DNXZfI/view?usp=share_link
	Marcelo Betti, president of Redi; Valeria Isla, National Director of Reproductive and Sexual Health; Andrea Pochak, undersecretary for Protection and International liaison on Human Rights of the Human Rights Secretariat; Matías Sotomayor, National Director of the National Council for the Coordination of Social Policies. 
	
	
	

	https://drive.google.com/file/d/1T5hwvDHN4FbufjTdEHeZ_zhq4Ya0JCqh/view?usp=drive_link 
	At a square table with 13 women seated around it, participating in a UNICEF meeting. 6 of them have a computer in front of them, ready to be used during the meeting, and one of them has a braille text to make a presentation.
	Y
	OPS
	

	https://drive.google.com/file/d/1s14Sj-v_Tnv2e3gryvjotSrB861IXGKH/view?usp=drive_link 
	On a white square table around which several women are seated, participating in a UNICEF meeting. Behind them, the seated audience can be seen.
	Y
	OPS
	

	https://drive.google.com/file/d/1KYehO-lpfsrHtXF6vxIIsCgM1Iyt90cs/view?usp=drive_link 
	A woman is standing next to some flags. The first is the Argentine national flag and the second is the UNICEF flag, with the word "UNICEF" written in white on a light blue background. Next to the flags, there is a monitor showing a slide with the title "Charter of the United Nations" in blue letters on a white background. Just below, the subtitle "Origin of the United Nations" is shown in white letters on a light blue background.
	Y
	OPS
	

	https://drive.google.com/file/d/1eemFca4Qo5GcQhScg1UfxrQLUJzx-nJu/view?usp=drive_link 
	In the image, a group of six people can be seen seated around a table. In the center, there is a man next to five women, one of whom identifies herself as Carolina Buceta, who has a text in Braille in front of her. Next to her is a computer with two keyboards.
	Y
	OPS
	

	https://drive.google.com/file/d/1yK_PC8mfEidTfEkSOgCTKb9nk1sPctUw/view?usp=drive_link 
	This image captures a virtual workshop session on procedural code reforms for improving access to justice for persons with disabilities. A total of 14 participants are engaged in the discussion via a video conferencing platform. The group includes legal experts, policymakers, and civil society representatives. Some participants are actively speaking, while others listen attentively. Their backgrounds vary, with some appearing in professional office settings and others in home environments. The session fosters collaboration and knowledge-sharing to enhance inclusive justice frameworks.
	Y
	PNUD
	

	https://drive.google.com/file/d/1W3sUItCWXE6RPWD5zu35wj4jHyKF2bAv/view?usp=drive_link 
	This image captures a virtual workshop titled “Joint Country Analysis (CCA) Workshop for Organizations of Persons with Disabilities,”
In the image, multiple participants, including representatives from the UN, disability rights organizations, and accessibility experts, are engaged in discussion. A sign language interpreter is actively translating, ensuring accessibility for all attendees. Some participants have backgrounds featuring UN logos, indicating their affiliation with the initiative. Others appear in home or office settings.
	Y
	PNUD
	

	https://drive.google.com/file/d/10Q2wFMOCoZd9LgVIfeXuwo0FhEfEzhTj/view?usp=drive_link 
	This image captures a virtual session of the Workshop on Judicial Determination of Legal Capacity, held on November 14, 2024. The session is facilitated through Zoom, with a total of 17 participants actively engaged in discussions
	Y
	PNUD
	

	https://drive.google.com/file/d/1wOdAWk67bxm_3HDy48G5GzHhJiVmqJCp/view?usp=drive_link 
	This image captures an in-person workshop held at the Pan American Health Organization (PAHO) office in Argentina. Participants, including representatives from UN agencies, are seated around a long conference table. Each participant has official PAHO/WHO materials, including blue folders and documents. Water bottles and refreshments are placed along the table. Flags of Argentina and PAHO/WHO are displayed in the background, reinforcing the official setting.
	Y
	OPS
	

	https://docs.google.com/document/d/12Q7jVb5SF6-m41iRfkfWLKFJrbE9vEIWT300o-oijEs/edit?tab=t.0 
	This image captures the closing session of the in-person workshop "Sexuality and Persons with Disabilities," held on December 6, 2024.
	Y
	
	










Annex 1
	GDF IMPACT INDICATORS

	

	Proportion of population living below the national poverty line by sex and age (SDG indicator 1.2.1) and disability.  

	Proportion of men, women and children of all ages living in poverty in all its dimensions according to national definitions (SDG indicator 1.2.2) disaggregated by disability, before and after social transfers.  

	Rates of children with disabilities out of school, rate of enrolment, attendance, promotion by grade, completion, and drop out in mainstream primary, secondary, tertiary educational institutions, vocational training, lifelong learning courses, as compared to others, disaggregated by sex, age, disability. 

	Proportion of children and young people: (a) in grades 2/3; (b) at the end of primary; and (c) at the end of lower secondary achieving at least a minimum proficiency level in (i) reading and (ii) mathematics, by sex (SDG indicator 4.1.1), age and disability.  
 

	Coverage of essential health services/Universal Health Coverage disaggregated as a proportion of the population, by sex, age and disability (SDG indicator 3.8.1) 

	Percentage of persons with disabilities employed as compared to other persons and to overall employment rate, disaggregated by type of employment (public, private, self-employed), age, sex and disability 

	Average hourly earnings of female and male employees, by occupation, age and persons with disabilities (SDG indicator 8.5.1). 

	SDG indicator 11.2.1 Proportion of population that has convenient access to public transport, by sex, age and persons with disabilities. 

	#Number of persons with disabilities who have undergone a CRPD aligned disability assessment and are in possession of disability certification compared to statistical estimations of the number persons with disabilities. 

	Percentage of public spending on disability rights and inclusion, as a proportion of the GDP/sector budgets, disaggregated by disability specific budget allocations and allocations within mainstream budget. 

	Increase of disability data/disaggregation (including by sex) within standard data and CRPD compliant collection processes. 

	SDG indicator 16.7.2 Proportion of population who believe decision-making is inclusive and responsive, by sex, age and population group. 
 


 
Annex 2
GDF Outputs and outputs indicators  
 Output 1.1 - Capacity of national stakeholders, especially of key duty bearers and rights holders, is enhanced, to ensure more effective contributions towards disability inclusive policies, systems and - for the implementation of the CRPD and SDGs. 
 1.1.1 # of trainings (disaggregation by type of capacity building1)  developed and delivered in the GDF programme. (Dissaggregated by topics2)     
1.1.2 	# of participants (disaggregated by type of stakeholder3) disaggregated by sex,disability,rural/urban participating in capacity building activities funded or provided by GDF programmes  
1.1.3   # and % of participants reporting increased knowledge or capacity to design or revise policies or systems to be more disability inclusive.   
1.1.4    # of OPDs (disaggregated by type umbrella- disability specific- women- underrepresented other) that benefitted from capacity building activities (type of activities4) funded by GDF programmes to strengthen the capacity of organizations of persons with disabilities. 
 1.1.5  # of capacity building activities funded by GDF programmes, directed at women and girls with disabilities on their rights and requirements and/or directed at underrepresented groups of persons with disabilities on their rights and requirements. (disaggregated by target group)  
 Output 1.2 - Knowledge products (e.g., tools and guidelines) are developed and piloted, particularly to address gaps in achieving the preconditions for disability inclusion  
 1.2.1  	# of knowledge products(disaggregated by type of product5/thematic focus6)  developed, piloted and disseminated to the relevant stakeholders to inform inclusive practices 
 1.2.2  	# of knowledge products developed that address gaps related to inclusion of women and girls with disabilities and/or underrepresented groups of persons with disabilities (disaggregated by thematic focus) 
 1.2.3  	# actors involved in developing and testing of knowledge products (disaggregated by actor (GOV/NGOs/OPDs/Other) 
 1.2.4  	# of stakeholders reporting increased or strengthened policies and systems as a result of GDF funded KM tools (disaggregated by stakeholder) 
Output 1.3 Models of good practice, learning and exchange mechanisms are developed to share country level experiences, to increase understanding, and to inform innovative practices. 
 1.3.1  	# of GDF Situational Analysis through multistakeholder approach  
 1.3.2  	# of plannining and processes related to GDF-funded programs and/or beyond GDF-funded programs influenced by GDF Situational Analyses findings (disaggregation by GDF -funded programmes and beyond) 
 1.3.3  	# of mechanisms7 to share and exchange learning and evidence to inform inclusive policies and systems. (disaggregated by national/ regional/global mechanism) 
 1.3.4  	# actors involved in mechanisms to share learning and evidence to inform inclusive policies and systems disaggregated (UN/ GOV/OPDs, other) 
 
1.3.5   	# of models of good practice, learning and exchange mechanisms addressing the situation of women with disabilities and/or underrepresented groups of persons with disabilities (disaggregation women or underrepresented groups) (disaggregated by disability specific or mainstream) 
 Output 2.1 – Legal frameworks and systems (i.e., laws, policies, plans, programs, services and administrative systems) addressing the preconditions for disability inclusion are newly developed, reviewed, or reformed, to be in line with CRPD standards. 
 2.1.1  	# of national regulatory frameworks and systems changes targeted by the GDF program disaggregated by 1) legislation/regulation, 2) policies/plans/strategies, 3) capacity building programs, 4) operational guidance/standards, 5) direct services/service overhaul/service modelling, 6) audits/reviews/assessments, 7) governmental programs, 8) administrative procedures, 9) formal monitoring and accountability mechanisms or bodies, 10) regulatory/oversite/monitoring systems, 11) financing and budgeting  or 12) other (please explain)  
 2.1.2   	# type of change (development/review/reform) in legal frameworks and systems 
 Output 2.2 – Multi stakeholder participation and contribution to the design, reform, and implementation of disability inclusive laws policies and systems is enhanced 
 2.2.1  	# of multi-stakeholder coordination mechanisms (disaggregated formal/informal) to support legislative policy and systems changes developed or strengthened  
 2.2.2  	# of stakeholders within each mechanism (disaggregated by type of stakeholder Gov/ UN/OPDs/other). 
 2.2.3  	# stakeholders involved in consultation and validation processes (disaggregation by stakeholder(GOV/UN/OPDs/other) 
 Output 3.1 Disability inclusion is strengthened in planning, implementation and monitoring of UN development activities  at the country level including in humanitarian settings. 
 3.1.1       # of Common Country Analysis (CCA) including disaggregated data and analysis of the situation of   
                  persons with disabilities.  
 3.1.2   	# UNSDCF where disability inclusion has been mainstreamed and/or targeted. 
 3.1.3      # of joint programmes funded through MPTFs  where the rights of persons with disabilities  
                 have been addressed (disaggregation by disability group) through collaboration with GDF   
                 programmes. 
 3.1.4      # Humanitarian Response Plans (HRPs) and Humanitarian Needs Overviews (HNOs) addressing    
                 persons with disability needs and rights. 
 
 Output 3.2 – National development assessments, plans, budgets, programs and monitoring mechanisms supported under the SDG processes are designed to advance disability inclusion. 
3.2.1   	# of national and subnational SDGs implementation plans integrating and mainstreaming actions towards persons with disabilities. 
3.2.2   	# of adopted/ implemented COVID 19 inclusive response and recovery plans and frameworks containing systematic mainstreaming of persons with disabilities including the most marginalised  
3.2.3   	# SDGs implementation data collection, monitoring and accountability processes assessing progress against specific disability-inclusion targets 
 
3.2.4   	# SDGs budgets/financial planning with explicit allocations to disability inclusion 
Output 3.3 – OPDs are supported to systematically engaged in the national development coordination mechanisms and accountability frameworks, (gov/UN/Independent) around SDGs and in humanitarian coordination mechanisms. 
 3.3.1	#   UN led national and/or regional coordination mechanisms with established consultation processes undertaken to ensure the active involvement of persons with disabilities, including through their representative organizations, in the design, implementation and monitoring of instruments for planning and implementation of UN development activities at the country level 
 3.3.2   	# of governmental coordination mechanisms with established consultation processes undertaken to ensure the active involvement of persons with disabilities, including through their representative organizations, in the planning, implementation and monitoring of SDGs  
 3.3.3  # of identified persons with disabilities including through their representative organizations participating in the State’s formulation/implementation of COVID-19 policy responses 
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