Scaling Up Nutrition Multi-partners Trust Funds (SUN MPTF) for Civil Society Mobilization

MPTF OFfice GENERIC ANNUAL programme NARRATIVE progress report

REPORTING PERIOD: 1 january – 31 August 2015

| Programme Title & Project Number |  | Country, Locality(s), Priority Area(s) / Strategic Results |
| --- | --- | --- |
| Programme Title: Advocacy for Scaling Up Nutrition in Mozambique Programme Number SUN-Window 2 – 006 MPTF Office Project Reference Number: |  | (if applicable) Country/Region Mozambique – Africa |
|  |  | Priority area/ strategic results |
| Participating Organization(s) |  | Implementing Partners |
| ANSA |  |  |
| Programme/Project Cost (US$) |  | Programme Duration |
| Total approved budget as per project document: US$ 428,000 MPTF /JP Contribution: by Agency (if applicable) |  |  | Overall Duration (27 months); |  |
| Agency Contribution by Agency (if applicable) |  |  | Start Date (31.05.2013) |  |
| Government Contribution (if applicable) |  |  | Original End Date (31.03.2015) |  |
| Other Contributions (donors) (if applicable) |  |  | Current End date (30.08.2015) |  |
| TOTAL: |  |  |  |  |
| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| Assessment/Review - if applicable please attach Yes No Date: dd.mm.yyyy Mid-Term Evaluation Report – if applicable please attach Yes No Date: dd.mm.yyyy |  | Name: Carina Ismael Title: National Coordinator, CS Platform Participating Organization (Lead): ANSA Email address: carinaismael@gmail.com |

EXECUTIVE SUMMARY

This report covers the period of 1st January – 31st Agosto, 2015. During this period, sensitization to get new organizations had continue and resulted on few new members. At the end, around 100 organization had sign the Declaration of Commitment on the 4 provinces where CS platforms/networks were established: Maputo (24), Inhambane (22), Tete (30) and Nampula (25), but more organization had participated at different activities. The provinces had done a step down in trying to established contacts and CS networks in some district: Inhambane (CSN in 8 districts, and 2 focal points per district were trained on nutrition basic concepts) and Tete (organizations of Cahora Bassa, Changara e Moatize districts participate on the provincial network).

A process monitoring of PAMRDC implementation was conducted; it intended to analyze and document CS involvement on the PAMRDC and come up with recommendations. The main conclusion were: (i) CS at various levels, participate on PAMRDC monitoring through members participation on working groups and by analyzing strategic documents, such as provincial PAMRDC and others; (ii) since there are not a specific budget line for PAMRDC implementation, the funds are dispersed among different programs at different sectors, what makes difficult to monitor the financing; (iii) most of the indicators are related with accomplishment of sectorial interventions, and there is a need for CS to identify indicators for an independent monitoring at community level; (iv) in general, most of the main policy and plan are nutrition sensitive, but still a gap in to concretization of annual plans and budget; and (v) CS organizations need of more human and financial resources to implement. In terms of CS monitoring, the recommendations were that CS could do independent monitoring at community levels as well as to monitor the Medias to see how they address nutrition and PAMRDC.

An Advocacy campaign aiming to get a major appropriation and accountability of decisions makers in relation to chronic malnutrition was developed by the CS as a complementary advocacy work done by SETSAN. The CS continue actively involved on CSAN working group (headed by SETSAN and created to work on the Advocacy and Communication Strategy for PAMRDC). Continue to work also, with SETSAN and Nutrition Partners Forum (NPF), on the Governmental 5 year plan indicators matrix (2015-2019). As part of the advocacy strategy, SC also establish contacts with the first lady cabinet to sensitize and capture their interest to take Nutrition as a “flag”.

The final evaluation of the project was done in June. The main conclusions were: (i) CS Platform established, operational, actively participates in working groups for policies and plans formulation and monitoring, and helped raise awareness on the state of nutrition, at different levels; (ii) succeeded in training a significant number of members on issues related to nutrition; (iii) is a well-known actor and recognized by the Government, donors and other partners, as a credible and reliable entity; and (iv) did not monitor the implementation of PAMRDC, but did contribute to the monitoring instruments created recently. And the main recommendations were: (i) create CS networks on other provinces, while consolidating and strengthening the experience on the existing ones; (ii) develop a "nutritional surveillance points" in selected provinces and districts to use community monitoring methodology proposed above, and partnerships to monitor PAMRDC funding; (iii) Intensify work with the various forms of media to bring attention to nutrition; and (iv) develop and disseminate relevant position papers related with malnutrition.

Contacts with Graça Machel Trust Fund are in progress to get technical support for developing a Proposal to continue with Civil Society Platform activities under SUN movement and a Fund Raising Strategy. Contacts with other potential donors in country are planned for after conclusion of the proposal and fund raising strategy.

Continues dissemination of SUN, at different levels and groups; as well as participation on different national and international meetings related with food security and nutrition, and related areas.

# Purpose

The project focuses on building the capacity of civil society to monitor and support the implementation of the Multi-Sectoral Action Plan for the Reduction of Chronic Undernutrition (hereby referred to by its Portuguese acronym PAMRDC) and advocate effectively for the adequate allocation of resources for effective nutrition action.  The civil society platform will address issues linked to resource allocation; the reach and coverage of nutrition interventions; and the relevance and expected results of the priority actions in the Action Plan and other major interventions.

# Results

- Narrative reporting on results:

From January to December 2012, respond to the guiding questions indicated below to provide a narrative summary of the results achieved. The aim here is to tell the story of change that your Programme has achieved in 2012. Make reference to the implementation mechanism utilized and key partnerships.

- Outcomes: Outcomes are the strategic, higher level of change that your Programme is aiming to contribute towards. Provide a summary of progress made by the Programme in relation to planned outcomes from the Project Document / AWP, with reference to the relevant indicator(s) in these documents. Describe if any targets were achieved, or explain any variance in achieved versus planned results during the reporting period. Explain who the main beneficiaries were.

Outcome 1: An effective, inclusive and productive civil society that maintains strong relationships with key stakeholders

Four civil society platforms/networks established: central level and provinces of Inhambane, Tete and Nampula. New organizations had join the CSP, at central level (for ex. Associação Progresso and Water Aid) and some local organizations at provincial level.

At national level, the platform continue to participate in the NPF (development partners technical working group), in the technical working group for the coordination of PAMRDC (GT-PAMRDC) and CSAN working group (Advocacy and Communication Strategy for PAMRDC); the last two groups are hosted by the Technical Secretariat for Food Security and Nutrition (SETSAN). Also at central level the CS together with SETSAN and NPF are involved on the Governmental 5 year plan indicators matrix (2015-2019) and on the discussion regarding SETSAN “conversion” to Institute of Promotion for Food Security and Nutrition – IPSAN).

At provincial level, in Inhambane and Nampula, the CS participated on the elaboration of provincial PAMRDC; yet in Inhambane SC is part of the PAMRDC monitoring group; and Tete, that have a PAMRDC since 2013, CS continue to integrate the provincial SETSAN supervision group and is part of the “poverty annual observatories”.

In June was realized a national workshop with participants from Maputo CS platforms, focal points of CS provincial networks, and all other stakeholder – government, UN, donors and SUN business network. After 2 years implementation the workshop had as objectives to analyze CS performance during this period, share experiences and outline the way forward. It was an opportunity for stakeholder to share their achievements, constrains and lesson learns.

CS Platform had continuously participated on different forums discussion and process related with FSN, as the REACH independent join evaluation, next 5 year strategic plan for DANIDA, MDG1 med-term evaluation, just to mention some.

Outcome 2: A stronger and more visible civil society that actively participates in the development of nutrition and nutrition-sensitive policies and plans across all sectors, including advocacy for resource allocation

As one result of the mapping exercise of the community groups done with fund from MASC (a support mechanism for CS for good governance), CS network in Inhambane had created CS groups in 8 districts (with a total of 103 community organizations), and together with Nutrition sector-provincial health directorate, trained 2 focal points per district on nutrition basic concepts and advocacy.

A session on conflicts of interest was given to the CS platform members in Maputo, by one of the colleague. Participation at Workshop on Strengthening Effective Engagement for Scaling Up Nutrition: SUN Business Network Workshop (Day 1) & Functional Capacities for Scaling Up Nutrition (Days 2 and 3), in Nairobi.

The CS was invited by Results and co-funded by Results and Graça Machel Trust Fund, to participate at RESULTS International Conference, Washington DC, in July 2015 to learn more about Results work and to share experiences with Results global volunteer and partner network. Results volunteers, during the past 35 years have played a central role in advocating for funding and improved policies on global health and childhood undernutrition.

Outcome 3: Operationalization, funding and implementation of PAMRDC and other national and regional strategies and plans on nutrition monitored

CS had participated in the country annual progress report; exercise led by SETSAN-GT-PAMRDC, with REACH support. The CS also contributed to SETSAN report prepared to be presented to the Council of Minister, reporting the achievements and constraints.

A process monitoring of PAMRDC implementation was conducted by CS; it intended to analyze and document CS involvement on the PAMRDC and come up with recommendations. The main conclusion were: (i) CS at various levels, participate on PAMRDC monitoring through members participation on working groups and by analyzing strategic documents, such as provincial PAMRDC and others; (ii) since there are not a specific budget line for PAMRDC implementation, the funds are dispersed among different programs at different sectors, what makes difficult to monitor the financing; (iii) most of the indicators are related with accomplishment of sectorial interventions, and there is a need for CS to identify indicators for an independent monitoring at community level; (iv) in general, most of the main policy and plan are nutrition sensitive, but still a gap in to concretization of annual plans and budget; and (v) CS organizations need of more human and financial resources to implement.

The two main recommendations that came out from the process monitoring were that in the future CS could plan to do an independent monitoring at community levels to see the satisfaction and access to the services, and to monitor the Medias to see how they address nutrition, nutrition related issues and PAMRDC.

The final evaluation of the project was done in June. The main conclusions were: (i) CS Platform established, operational, actively participates in working groups for policies and plans formulation and monitoring, and helped raise awareness on the state of nutrition, at different levels; (ii) succeeded in training a significant number of members on issues related to nutrition; (iii) is a well-known actor and recognized by the Government, donors and other partners, as a credible and reliable entity; and (iv) did not monitor the implementation of PAMRDC, but did contribute to the monitoring instruments created recently. And the main recommendations were: (i) create CS networks on other provinces, while consolidating and strengthening the experience on the existing ones; (ii) develop a "nutritional surveillance points" in selected provinces and districts to use community monitoring methodology proposed above, and partnerships to monitor PAMRDC funding; (iii) Intensify work with the various forms of media to bring attention to nutrition; and (iv) develop and disseminate relevant position papers related with malnutrition.

Outcome 4:  The work of the different CSO at the various levels results in increased public awareness about nutrition, nutrition policies and monitoring and advocacy interventions

CS continue to participate on the CSAN working group (a group headed by SETSAN and created to work on Advocacy e Communication) on the production of information and advocacy materials.

A contact was established with the first lady cabinet (Mozambique had elections last October) to sensitize and capture their interest and advocate for Nutrition being taken as a “flag”;

An Advocacy campaign targeting the decision makers to get their major appropriation and accountability in relation to chronic malnutrition was developed by the CS as a complementary advocacy work done by SETSAN. The campaign address nutrition specific and sensitive areas as health (women and child), education, gender (early marriage) and the impact of it on the economic development. As communication material, it includes a creation of a strong brand for nutrition (logo), icons for the addressed areas, TV spots, outdoor advertise, newspapers ads, posters and flyer.

- Outputs: Outputs are the more immediate results that your Programme is responsible for achieving. Report on the key outputs achieved in the reporting period, in relation to planned outputs from the Project Document, with reference to the relevant indicator(s) in these documents. Describe if any targets were achieved, or explain any variance in achieved versus planned results during the reporting period. If possible, include the percentage of completion of the outputs and the type and number of beneficiaries.

See indicators on the log frame

ANSA sign a 2 years contract, starting in April, 2013 to March 2015, but asked for an extension without cost for more 5 months, ending at August 2015. For the first year implementation (Abril,2013–March,2014), it was planned to establish effective, inclusive and productive civil society network in four provinces (Maputo as central level, Inhambane, Tete and Nampula), that actively participates in the development of nutrition and nutrition-sensitive policies and plans across all sectors, including advocacy for resource allocation. To enable the members actively participate on the development of these policies and plans, a train on “Nutrition basic concepts, Political framework for nutrition and Advocacy – with focus on fundraising and lobbying” was also planned. Both proposed activities were successfully accomplished, even though the funds were available two months later, in June 2013.

The second year, starting Abril, 2014, having the networks being stablished and active, focus was given to monitoring and advocacy activities. Regarding monitoring, as mentioned before CS had actively participate on the process for definition of indicators to monitor PAMRDC/implementation tracking system (exercise led by SETSAN-GT-PAMRDC with technical support from REACH); and since the monitoring system was recently created, instead of monitoring the implementation CS did a process monitoring. The main results are presented above, and the complete report is annexed.

Regarding Advocacy, a Strategy was developed to be rolled out by the platform organizations members; and CS also actively participated on the elaboration of Advocacy e Communication Strategy for PAMRDC developed by SETSAN. As mentioned above an advocacy campaign targeting the decision makers to get their major appropriation and accountability in relation to chronic malnutrition was developed by CS. Yet, SC member continue to participate on different events, promoting SUN movement, nutrition and nutrition-sensitive activities, among different sectors and player.

A Final project evaluation was conducted at the end, and the results are mentioned above and the full report will be attached to this report.

- Describe any delays in implementation, challenges, lessons learned & best practices: If there were delays, explain the nature of the constraints and challenges, actions taken to mitigate future delays and lessons learned in the process. Provide an updated risk analysis (have any of the risks identified during the project design materialized or changed? Are there any new risks?). Were there any programmatic revisions undertaken during the reporting period? Please also include experiences of failure, which often are the richest source of lessons learned.

As any network, there are challenges to get all the members together at same time; for this reason we maximize the use of Email as one of the ways to get comments, consensus or approval from all members. Other challenge faced by most of the national/local organizations (normally small organizations depending on external funding) continues to be lack of resources for implement their own projects at community level.

Having allowed the provinces to take their time to analyze the proposal, decide when they would have the introductory meeting to establish the network, as well as all other meeting, how to proceed, and being themselves who point the provincial focal points had given them more ownership for all the process what had result on an appropriation of the network.

As best practices, CS is member of the other SUN networks already existing in country (Government – SETSAN and UN e Donors – NPS); business network still in the process of being officially launched, and CS was invited to be part of it.  This allows to share information among SUN stakeholders in country. At provincial level, CS was part of the elaboration of provincial PAMRDC what allowed from the beginning to advocate for the inclusion of nutrition-sensitive activities as well as to establish connection with staff from the different sectors, what resulted on the invitation to be part of the supervision and monitoring group created to monitor PAMRDC implementation.

A sense of “one family” was created among the members of the platform, at all levels, enabling an efficient sharing (obtaining and giving) of information in general, what works and what doesn´t; it also allows a constructive discussion about relevant issues, resulting in agreed ideas that can be then be presented and discussed with government sector as a CS position, this results in easier consensus building between stakeholders.

- Qualitative assessment: Provide a qualitative assessment of the level of overall achievement of the Programme. Highlight key partnerships and explain how such relationships impacted on the achievement of results. Explain cross-cutting issues pertinent to the results being reported on. For Joint Programmes, highlight how UN coordination has been affected in support of achievement of results.

- Overall, we are satisfied with the level of implementation, particularly taking in account that most of our outputs planned were achieved.

Using the Programme Results Framework from the Project Document / AWP - provide an update on the achievement of indicators at both the output and outcome level in the table below. Where it has not been possible to collect data on indicators, clear explanation should be given explaining why, as well as plans on how and when this data will be collected.

|  | Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification |
| --- | --- | --- | --- |
| Outcome 1 Indicator: Baseline: Planned Target: |  |  |  |
| Output 1.1: Terms of Reference draft available Indicator 1.1.1: Terms of Reference approved Baseline: none Planned Target: | 100% |  | Document |
| Output 1.2 : List of organizations working in nutrition, existing networks, and potential members of platform available Indicator 1.2.1: Comprehensive list available. Number of organizations invited to be part of the platform at national and provincial levels Baseline: Planned Target: | Done | Mapping done by provincial SETSAN’s, in all provinces | SETSAN mapping report |
| Output 1.3 : Central Level Platform established. Platform ToR approved. Focal Point mandate approved. Indicator 1.3.1: Platofrm established. ToR approved. Focal Point approved/ Baseline: 0 Planned Target: | 100% |  | TOR document |
| Output 1.4 : Civil Society Organizations and local governments aware of SUN, and expressed willingness to become members of platform (CSOs). Local government recognizing SUN. Indicator 1.4.1: Number of organizations becoming members of platform at national and target provinces. Baseline: 0, as CS for SUN movement Planned Target: | National – 24 Inhambane - 22 Tete – 30 Nampula - 25 |  | Commitment and Organizations member list |
| Output 1.5 : Focal points identified in the target provinces. Indicator 1.5.1: At least one focal point identified in each of the target provinces. Baseline: 0 Planned Target: | 100% |  | Focal points are mentioned on the ToR |
| Output 1.6 : Platform representations at provincial levels in place either through dedicated platforms or establishment of nutrition thematic group within existing platforms and/or forum Indicator 1.6.1: Platform representations in place in the target provinces Baseline: 0 Planned Target: | 100% |  | ToR and Commitment Agreement document |
| Output 1.7 : Platform members meeting regularly Indicator 1.7.1 : Platform at national level meeting at least every four months Baseline: 0 Planned Target: | 100% |  | Meetings notes |
| Output 1.8 Working groups for different task areas established and functioning Indicator 1.8.1 : Working groups meeting monthly Baseline: 0 Planned Target: | 100% (it is done any time a need exist) |  | Successful advocacy strategies and actions implemented |
| Output 1.9 : Platform members at provincial levels meeting regularly Indicator 1.9.1 : Provincial platforms meeting every four months Baseline: 0 Planned Target: | 100% |  | Meetings notes |
| Output 1.10 Plan of Action approved by members of platform Indicator 1.10.1 : Plan of action approved and in implementation Baseline: 0 Planned Target: | 100% |  | Plan of Action and implementation reports |
| Output 1.11 : Annual reports, accounts and plans of action approved, as well as critical nutrition issues discussed Indicator 1.11.1 : Reports and accounts accurate and approved. Baseline: 0 Planned Target: | 100% |  | Annual conference reports |
| Outcome 2 Indicator: Baseline: Planned Target: |  |  |  |
| Output 2.1: Platform members more capable to monitor policies, programmes, financial commitments, flow of funds, actors involved and to advocate on critical issues identified by the Platform Indicator 2.1.1: One workshops held by Province. Baseline: 0 Planned Target: | 100% | All 4 platform members trained as planned. | Training reports. |
| Outcome 3 Indicator: Baseline: Planned Target: |  |  |  |
| Output 3.1: Working group on monitoring established and functioning Indicator 3.1.1: Monitoring working group meeting regulary Baseline: 0 Planned Target: | 100% |  | Group reports |
| Output 3.2 : Platform concerns and issues presented to the different councils related to the PAMDRC and addressed Indicator 3.2.1 : Number and relevance of issues presented to the different councils at the various levels Baseline:0 Planned Target: | 3 (pos-2015, PAMRDC Inhambane and Nampula) |  | Event Notes/reports |
| Output 3.3 : Monitoring system in place and operational Indicator 3.3.1: Monitoring instruments and tools available and in use Baseline: Planned Target: | 100% |  | Tools and reports |
| Output 3.4 : Information and data on adoption and implementation of PAMDRC and other nutrition interventions timely available Indicator 3.4.1 : Monitoring system with updated information on PAMDRC and other nutrition intervention Baseline: 0 Planned Target: | Done | PAMRDC did not have a monitoring component (indicators identified) till May 2014 + SETSAN had requested a mid-term evaluation which was done between 17 July and 4 August 2014. Instead of a implementation monitoring civil society platform did a process monitoring (report in annex) | Monitoring Reports |
| Output 3.5 : Quarterly reports on implementation of PAMDRC and on national/regional strategies and plans related to nutrition timely available Indicator 3.5.1 : Relevance of issues raised by quarterly reports and timeliness of reports availability Baseline: 0 Planned Target: | Please see above (output 3.4) |  |  |
| Outcome 4 Indicator: Baseline: Planned Target: |  |  |  |
| Output 4.1: Working group on advocay established and functioning Indicator 4.1.1: Monitoring working group meeting regulary and decisions on issues for advocacy Baseline: 0 Planned Target: | 100% (group established; strategy and implementation plan developed) |  | Strategy, plan and Reports |
| Output 4.2 : Advocacy strategy in place Indicator 4.2.1 : Relevance and effectiveness of the advocacy strategy Baseline: 0 Planned Target: | 100% |  | Advocacy strategy |
| Output 4.3 : Media regularly publishing information on nutritional status of target population groups as well as on the implementation of nutrition related interventions Indicator 4.3.1 : Number and accuracy of articles/pieces published and/or broadcast by national media on nutritional status of population and on implementation of nutrition related interventions Baseline: 0 Planned Target: | 7 |  | Newspapers, radio, TV |
| Output 4.4 : Information and data collected through the different monitoring exercise shared with relevant sectors/actors, including recommendations for improvement of interventions Indicator 4.4.1 : Number, accuracy and relevance of issues raised through platform and verifiable improvements on implementation of PAMDRC and other nutrition initiatives in line with recommendations by platform Baseline: 0 Planned Target: | 3 |  | Participation on the monitoring reports done by GT-PAMDRC to be presented to the council of Ministers, and CS process monitoring of PAMRDC report |
| Output 4.5 : All sectors part of the PAMDRC planning and budgeting activities included in the PAMDRC in their regular planning and budgeting exercises Indicator 4.5.1 : Activities of the PAMDRC included in annual plans and budgets of the different government sectors Baseline: 0 Planned Target: | 100% | Although all 7 Ministries had included nutrition activities on their 2014 plan, not all activities suggested in PAMRDC were included (ex. from 8 suggested activities Min. Ag. only included three). | Sectoral plans and budgets |
| Output 4.6 : Nutrition related interventions with sufficient and timely available funds Indicator 4.6.1 : Level of funding and nutrition related interventions funded and implemented Baseline: 0 Planned Target: |  | It was not possible to get how much was invested on Nutrition, by the different player (Government and donors). |  |

iii) A Specific Story (Optional)

- This could be a success or human story. It does not have to be a success story – often the most interesting and useful lessons learned are from experiences that have not worked. The point is to highlight a concrete example with a story that has been important to your Programme in the reporting period.

- In ¼ to ½ a page, provide details on a specific achievement or lesson learned of the Programme. Attachment of supporting documents, including photos with captions, news items etc, is strongly encouraged. The MPTF Office will select stories and photos to feature in the Consolidated Annual Report, the GATEWAY and the MPTF Office Newsletter.

Problem / Challenge faced: Describe the specific problem or challenge faced by the subject of your story (this could be a problem experienced by an individual, community or government). Insufficient awareness and sensitization regarding nutrition and it consequences, at the highest decision making levels of government, i.e. politicians and government officials. Although Mozambique has a multi-sectorial plan for reduction of chronic malnutrition, since 2010, only 1% reduction was registered from 2008 (44%, DHS) to 2013 (43%, SETSAN baseline study). Programme Interventions: How was the problem or challenge addressed through the Programme interventions? The country subscribed to the SUN movement in 2011 and SETSAN was appointed as the government focal point and the MoH-Nutrition Department as the co-facilitator; in the same year Nutrition Partner Forum (NPF) was established to improve the joint effort for better coordination mechanism for donors and partners to provide support to the implementation of the (PAMRDC). In 2013, the CS network was created and integrated into the existent coordination bodies for PAMRDC, with a seat on the SETSAN GT-PAMRDC and the NPF. The Business network is to be launched and CS has being contacted to express their opinion on how the private sector should be involved on the SUN process. Mozambique had managed to create a strong collaboration among all involved partners; they are all engaged and willing to move the nutrition agenda forward. While not always agreeing, stakeholders have a consolidated understanding of the need for multi-sectoral action and coordination. Result (if applicable): Describe the observable change that occurred so far as a result of the Programme interventions. For example, how did community lives change or how was the government better able to deal with the initial problem? One result of the understanding of the need for multi-sectoral action and of the strong collaboration between stakeholders, is the focused advocacy efforts on high level decision makers. This was identified and agreed as the one of the essential tasks to be undertaken by all. The most successful manifestation of this collaboration is the up-coming meeting with the Prime Minister to raise his awareness and present him with a call for action to reduce the critical high levels of stunting in the country. The meeting is being brokered by the powerful figure of Graca Machel and will involve representation from all of the SUN networks. Lessons Learned: What did you (and/or other partners) learn from this situation that has helped inform and/or improve Programme (or other) interventions? A common understanding, good partnership and coordination between different players are crucial to create a harmonized platform to advocate for resources to fight against and eradicate malnutrition.

III.	Other Assessments or Evaluations (if applicable)

•	Report on Process monitoring of PAMRDC

•	Final evaluations

IV.	Programmatic Revisions (if applicable)

•	N/A

V. 	Resources (Optional)

•	Provide any information on financial management, procurement and human resources.

•	Indicate if the Programme mobilized any additional resources or interventions from other partners.

# Footnotes

The term “programme” is used for programmes, joint programmes and projects.

Strategic Results, as formulated in the Strategic UN Planning Framework (e.g. UNDAF) or project document;

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as  “Project ID” on the project’s factsheet page the MPTF Office GATEWAY

The MPTF or JP Contribution, refers to the amount transferred to the Participating UN Organizations, which is available on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

# Text boxes

ii) Indicator Based Performance Assessment: