RUNO ANNUAL PROJECT REPORT				TEMPLATE 4.4

PEACEBUILDING FUND (PBF)

ANNUAL PROJECT progress report

COUNTRY: Guinea-Bissau

REPORTING PERIOD: 1 january – 31 December

| Programme Title & Project Number |  |
| --- | --- |
| Programme Title: Promote Access to Protection and Civic Participation through Civil Registration Programme Number (if applicable) MPTF Office Project Reference Number: 000100142 |  |  |

| Recipient UN Organizations |  | Implementing Partners |
| --- | --- | --- |
| List the organizations that have received direct funding from the MPTF Office under this programme: UNICEF |  | List the national counterparts (government, private, NGOs & others) and other International Organizations: Ministry of Justice, Ministry of Health, National Institute of Statistics, SCOs, UNFPA. |
| Programme/Project Budget (US$) |  | Programme Duration |
| PBF contribution (by RUNO) 1,000,000 USD |  |  | Overall Duration (months) 24 |  |
|  |  |  | Start Date (dd.mm.yyyy) 20/04/2016 |  |
| Government Contribution (if applicable) NA |  |  | Original End Date (dd.mm.yyyy) | 31/12/2017 |
| Other Contributions (donors) (if applicable) NA |  |  | Current End date(dd.mm.yyyy) NA |  |
| TOTAL: | 1,000,000 USD |  |  |  |

| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| --- | --- | --- |
| Assessment/Review - if applicable please attach Yes No Date: Mid-Term Evaluation Report – if applicable please attach Yes No Date: |  | Name: Christine Jaulmes Title: UNICEF Representative Participating Organization (Lead): UNICEF Email address: cjaulmes@unicef.org |

PART 1 – RESULTS PROGRESS

  - Assessment of the current project implementation status and results

For PRF projects, please identify Priority Plan outcome and indicators to which this project is contributing:

Priority Plan Outcome to which the project is contributing. Outcome 4 - Increased access for women and youth to political participation and economic opportunities.

Priority Plan Outcome indicator(s) to which project is contributing.

For both IRF and PRF projects, please rate this project’s overall achievement of results to date:

For both IRF and PRF projects, outline progress against each project outcome, using the format below. The space in the template allows for up to four project outcomes.

Outcome Statement 1:  Access of vulnerable groups to social services and civic participation increased through improvement of civil registration and vital statistics.

Rate the current status of the outcome:

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Output 1: Civil Registration (CR) Inter-ministerial committee operational; administrative circulars outlining procedures for birth registration (BR) developed and delivered to regional health administration; TORs for comprehensive assessment of CR developed and consultant recruitment initiated; high level advocacy conducted with MoJ, MoH and MoE.

Output 2: 2,621 children registered in three functioning BR services in health facilities; four new services equipped and ready for inauguration; 80 health workers trained on BR; 4232 children registered in schools; capacity of CR services improved (working material, vehicles and motorcycles supplied).

Output 3: Communication strategy ready for validation; initial set of communication tools developed, including radio spots and posters; CSOs identified and discussions undertaken to plan joint initiatives to scale up CR at decentralized level by promoting CR and facilitating access to existing services for vulnerable and remote populations.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

UNICEF's contribution to achieve outcome project is in line with project strategies and theory of change that underpins it. Advocacy to strengthen political commitment and country ownership to reform civil registration and vital statistics (CRVS) systems resulted in high level stakeholder’s engagement during the reported period. As per the national strategy for scaling up access to birth registration, UNICEF is providing leadership and technical assistance to the Government to integrate birth registration services in health and education facilities, and to increase the civil registration system’s capacity. In addition to the routine services provided by civil registration offices run by the MoJ, this approach is offering additional opportunities to ensure access to registration and citizenship for new-borns and to those who have missed it at early ages. A MoU has been signed between the MoJ and the MoH to develop a joint framework and launch a pilot initiative to test the new approach and use lessons learned for further scaling up of birth registration in health facilities. So far, birth registration services were established at seven pilot sites in major national reference hospitals, and three of them are currently fully operational. To scale up birth registration in education facilities, UNICEF brokered a MoU between MoE and MoJ, under which all 46 schools participating in the Child Friendly School Initiative are joining the efforts to scale up birth registration for their students and other children within the community. Both ministries intend to develop a system of birth registration to ensure the identification and registration of children during the school enrolment. Agreement on the steps for the implementation of the strategy to establish routine systems of birth registration within schools are being stablished. To further support the scaling up of civil registration, an extensive mapping of needs for supplies in all regions of the country has been conducted. The plan has been developed to renovate civil registration offices in 4 regions. Key supply need were delivered and are already in use at decentralized level increasing community response. UNICEF is promoting discussions between the MoJ and its main partners to develop a comprehensive communication strategy to advance civil registration and further improve access to civil registration services for families and children. In parallel, a set of communication tools are being developed, particularly radio broadcasts. To ensure broad participation of local partners, and to intensify social mobilization, UNICEF and MoJ are engaging with key partners, at the decentralized level and among locally based CSOs, who have a critical role to work with vulnerable groups. Outcome’s contributions to peace building and conflict trigger are being strengthened through community mobilization and dialogue promotion  on civil registration, including among refugees’ and host communities.

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

PBF funds became available to UNICEF CO in May 2016. Since then, Ministers of Justice have been changed, which consequently delayed key decisions required for launching of the project. Main challenges encountered were related to the risk matrix. Current political and institutional instability is interfering with key civil registration (CR) reforms on the Government agenda and slowing decision-making processes, particularly related to legal reform of CR in the country. Also, lack of funding, including no funding allocation for CRVS reform, within the comprehensive public sector reform, is constraining Government capacity to implement complementary interventions to strengthen PBF outcome. So far, state budget was not approved at the National Assembly. To address these challenges, UNICEF, MoJ and main partners are working at decentralized level with Governmental structures and strengthening partnerships with CSOs. Efforts continue to develop sustainable joint strategies to strengthen the routine system of BR and better planning of interventions. Capacity development of key governmental IP and advocacy for budgeting is also being conducted.

Outcome Statement 2:  NA

Rate the current status of the outcome:

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

NA

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

NA

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

NA

Outcome Statement 3:  NA

Rate the current status of the outcome:

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

NA

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

NA

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

NA

Outcome Statement 4:  NA

Rate the current status of the outcome:

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

NA

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

NA

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

NA

  - Assessment of project evidence base, risk, catalytic effects, gender in the reporting period

| Evidence base: What is the evidence base for this report and for project progress? What consultation/validation process has taken place on this report (1000 character limit)? | The reporting system that enables monthly monitoring of the number children registered in the new service delivery sites, in health and education facilities, was established to track progress in BR. The technical advisory group composed by RUNO and the main implementing partner, Ministry of Justice, meets regularly (on a weekly basis) and organizes joint field visits to assess the level of implementation and to document progress at every step of implementation of the project. Ministry of Justice led the Inter-ministerial Committee for Civil Registration, where PBF project was presented and shared with key ministries members and other state institutions. This inter-ministerial committee meets every month. The committee conducted joint monitoring visits with Health and Education ministries and UNICEF. Reports of meetings and field visits are available as well as visibility materials (including in the social media). |
| --- | --- |
| Funding gaps: Did the project fill critical funding gaps in peacebuilding in the country? Briefly describe. (1500 character limit) | The project filled critical funding gaps in the country by addressing continued poor performance of the civil registration and vital statistics systems. Planned intervention under the PBF project will provide a critical support to boost the current national under-resourced and underfunded civil registration services. PBF funds will allow new and innovative interventions as well as strengthening capacity of services to respond at central and decentralized level. In addition to the EU/CPLP project to improve quality and proximity of public services (with a focus on the modernization of Civil Registration system), PBF project is a critical contribution to reinforce governance as it is contributing to improve state services and to guarantee citizens to fulfil fundamental human rights, such as the right to have a name and nationality. |
| Catalytic effects: Did the project achieve any catalytic effects, either through attracting additional funding commitments or creating immediate conditions to unblock/ accelerate peace relevant processes? Briefly describe. (1500 character limit) | Though at its early stage, the project has so far fostered the integration of civil registration services (before exclusively conducted by the Ministry of Justice) with other state provided services such as Health and Education, thus amplifying access to critical civil registration services. Partnering with health and education services provides necessary leverage for civil registration to scale up access to and utilization of civil registration services. In addition, by strongly fostering the link to the African Union's country commitments, the project has been promoting the engagement of other actors such as UNECA for technical and financial assistance which will result in a comprehensive assessment of the Bissau-Guinean CRVS, which is a major precondition to accelerate access to the financing of the CRVS action plan, by both national authorities and international donors. |
| Risk taking/ innovation: Did the project support any innovative or risky activities to achieve peacebuilding results? What were they and what was the result? (1500 character limit) | A part from the ongoing new birth registration services mainstreamed within the health structures (at central and decentralized level), innovative civil registration interventions using IT will be developed during the second year of the project, as planned. |
| Gender: How have gender considerations been mainstreamed in the project to the extent possible? Is the original gender marker for the project still the right one? Briefly justify. (1500 character limit) | Gender considerations are mainstreamed in the project as planned. So far, discussion were held with UNWOMAN and SCOs working with women's movements and associations to guarantee that intervention promoting access civil registration services will be linked with related programs that are currently promoting and supporting access of women, children and youth to social and health services, including economic empowerment and civic participation. CSOs working at community level are already identifying adolescent’s girls and women with no access to civil registration, who will benefit, in the second year of the project, from downstream interventions to guarantee that vulnerable girls and women access social services and are more empowered to engage in civic participation. |
| Other issues: Are there any other issues concerning project implementation that should be shared with PBSO? This can include any cross-cutting issues or other issues which have not been included in the report so far. (1500 character limit) | No additional information to convey at this stage |

1.3 INDICATOR BASED PERFORMANCE ASSESSMENT: Using the Project Results Framework as per the approved project document- provide an update on the achievement of key indicators at both the outcome and output level in the table below. Where it has not been possible to collect data on indicators, state this and provide any explanation in the qualitative text above. (300 characters max per entry)

|  | Performance Indicators | Indicator Baseline | End of project Indicator Target | Current indicator progress | Reasons for Variance/ Delay (if any) | Adjustment of target (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 Access of vulnerable groups to social services and civic participation increased through improvement of civil registration and vital statistics. | Indicator 1.1 % of children (0-5) registered at birth | 24% | 35% | 24% |  |  |
|  | Indicator 1.2 % in use of civil registration services by population. | tbd | tbd | tbd |  |  |
|  | Indicator 1.3 NA |  |  |  |  |  |
| Output 1.1 Enhanced enabling environment in place for the provision of civil registration services. | Indicator 1.1.1 # law revisions / gov. decrees for civil registration reform/ministerial agreements. | 0 | 3 | 1 |  |  |
|  | Indicator 1.1.2 # supportive policy papers for CRVS | 0 | 1 | 0 |  |  |
| Output 1.2 Civil Registration services, particular, birth registration, are available and functioning at central and decentralized level. | Indicator 1.2.1 # Functioning interoperability mechanisms between CRVS and Health systems and services | 1 | 10 | 5 |  |  |
|  | Indicator 1.2.2 # of country regions with civil registration services improved and operational. | 0 | 4 | 2 |  |  |
| Output 1.3 Communities are mobilized to demand services for civil registration, in particular birth registration | Indicator 1.3.1 :# of information and communication campaigns. | 0 | 3 | 1 |  |  |
|  | Indicator 1.3.2 # of country regions implementing community initiatives to promote civil registration. | 0 | 3 | 0 | Planned for 2017. |  |
| Outcome 2 | Indicator 2.1 |  |  |  |  |  |
|  | Indicator 2.2 |  |  |  |  |  |
| Output 2.1 | Indicator 2.1.1 |  |  |  |  |  |
|  | Indicator 2.1.2 |  |  |  |  |  |
| Output 2.2 | Indicator 2.2.1 |  |  |  |  |  |
|  | Indicator 2.2.2 |  |  |  |  |  |
| Output 2.3 | Indicator 2.3.1 |  |  |  |  |  |
|  | Indicator 2.3.2 |  |  |  |  |  |
| Outcome 3 | Indicator 3.1 |  |  |  |  |  |
|  | Indicator 3.2 |  |  |  |  |  |
| Output 3.1 | Indicator 3.1.1 |  |  |  |  |  |
|  | Indicator 3.1.2 |  |  |  |  |  |
| Output 3.2 | Indicator 3.2.1 |  |  |  |  |  |
|  | Indicator 3.2.2 |  |  |  |  |  |
| Output 3.3 | Indicator 3.3.1 |  |  |  |  |  |
|  | Indicator 3.3.2 |  |  |  |  |  |
| Outcome 4 | Indicator 4.1 |  |  |  |  |  |
|  | Indicator 4.2 |  |  |  |  |  |
| Output 4.1 | Indicator 4.1.1 |  |  |  |  |  |
|  | Indicator 4.1.2 |  |  |  |  |  |
| Output 4.2 | Indicator 4.2.1 |  |  |  |  |  |
|  | Indicator 4.2.2 |  |  |  |  |  |
| Output 4.3 | Indicator 4.3.1 |  |  |  |  |  |
|  | Indicator 4.3.2 |  |  |  |  |  |

PART 2: LESSONS LEARNED AND SUCCESS STORY

2.1 Lessons learned

Provide at least three key lessons learned from the implementation of the project. These can include lessons on the themes supported by the project or the project processes and management.

| Lesson 1 (1000 character limit) | Accelerating civil registration coverage by engaging the existing health and education services and smooth implementation of interventions requires strong political commitment and high level backing from sectoral Ministers and General Directors, as well as strong commitment of technical staff in respective institutions. Without this commitment and support it would have been extremely difficult to put in place new administrative procedures and protocols as well as to launch innovative approaches to BR. High level advocacy and involvement of UNICEF health and education programme specialists led to increased buy in by health and education sectors to this process. This was further formalized by nomination of focal persons for this action, development of joint action plan and development of joint administrative guidance to be followed at local level. |
| --- | --- |
| Lesson 2 (1000 character limit) |  |
| Lesson 3 (1000 character limit) | NA |
| Lesson 4 (1000 character limit) | NA |
| Lesson 5 (1000 character limit) | NA |

2.2 Success story (OPTIONAL)

Provide one success story from the project implementation which can be shared on the PBSO website and Newsletter as well as the Annual Report on Fund performance. Please include key facts and figures and any citations (3000 character limit).

PART 3 – FINANCIAL PROGRESS AND MANAGEMENT ARRANGEMENTS

  - Comments on the overall state of financial expenditure

Please rate whether project financial expenditures are on track, slightly delayed, or off track:

If expenditure is delayed or off track, please provide a brief explanation (500 characters maximum):

The project funds were allocated in May 2016, amid a protracted political crisis which resulted in the dismissal of the Government. Despite the institutional challenges resulting from this political situation, the implementation of planned activities has commenced in May. Considerable efforts were undertaken for comprehensive planning and mobilization of key partners. A new Minister of Justice took office on June and advocacy was conducted for high level commitment.

Please provide an overview of expensed project budget by outcome and output as per the table below.

| Output number | Output name | RUNOs | Approved budget | Expensed budget | Any remarks on expenditure |
| --- | --- | --- | --- | --- | --- |
| Outcome 1: Access of vulnerable groups to social services and civic participation increased through improvement of civil registration and vital statistics. |
| Output 1.1 | Enhanced enabling environment in place for the provision of civil registration services. | UNICEF | 121,000 | 4.911.60 | Recruitment process for international and national consultant to support development of national CRVS Comprehensive assessment will be concluded during 2016. According to workplan main activities will take place in 2017. |
| Output 1.2 | Civil Registration services, particular, birth registration, are available and functioning at central and decentralized level. | UNICEF | 604,000 | 122.171.09 | Commitments of funds are on 212.348.33 |
| Output 1.3 | Communities are mobilized to demand services for civil registration, in particular birth registration | UNICEF | 209,579 | 6.207.64 | Key activities at community level planned for 2017 as per workplan. |
| Outcome 2: NA |
| Output 2.1 |  |  |  |  |  |
| Output 2.2 |  |  |  |  |  |
| Output 2.3 |  |  |  |  |  |
| Outcome 3: NA |
| Output 3.1 |  |  |  |  |  |
| Output 3.2 |  |  |  |  |  |
| Output 3.3 |  |  |  |  |  |
| Outcome 4: NA |
| Output 4.1 |  |  |  |  |  |
| Output 4.2 |  |  |  |  |  |
| Output 4.3 |  |  |  |  |  |
| Total: |  |  |  | 133,290.33 USD |  |

  - Comments on management and implementation arrangements

Please comment on the management and implementation arrangements for the project, such as: the effectiveness of the implementation partnerships, coordination/coherence with other projects, any South-South cooperation, the modalities of support, any capacity building aspect, the use of partner country systems if any, the support by the PBF Secretariat and oversight by the Joint Steering Committee (for PRF only). Please also mention if there have been any changes to the project (what kind and when); or whether any changes are envisaged in the near future (2000 character maximum):

The project is being implemented under overall coordination and leadership of UNICEF, through the Child Protection programme. UNICEF is taking the responsibility to daily manage implementation of the activities with selected partners, especially the Ministry of Justice and ensure that reporting requirements are adhered to in a timely manner and are in accordance with UN rules and procedures, in particular HACT. The Ministry of Justice is the main implementing partner and within the Ministry a focal point was appointed for day to day project implementation. The MoJ is working in strong partnership with other key actors for project implementation (MoH, MoE and National Institute of Statistics). In early 2017 the partnership with CSOs will be strengthened, as planned. Also, the current project is implemented in coordination with the EU/CPLP project “Improve quality and proximity of public services – Modernization of Civil Registration system” where some interventions are complementary and will be developed jointly under the MoJ coordination. UNFPA will work closely with UNICEF and Ministry of Justice, during the second year of the project to provide assistance, through its comparative advantage, on planned activities aiming to improve vital statistics system. Along with the current project, another important PBF project will be supporting the outcome area 4. However, so far, project 2 (support youth and women’s political participation for peace and development in Guinea-Bissau) has not been launched. Also, due to the current political instability, planned activities to strengthened bilateral contributions from country donors such as Portugal and Brazil (which have assisted MoJ this domain) are still pending.

# Footnotes

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to “Project ID” on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed.

Please note that financial information is preliminary pending submission of annual financial report to the Administrative Agent.