RUNO END PRF PROJECT REPORTING					TEMPLATE 4.5

PEACEBUILDING FUND (PBF)

END OF PROJECT report

COUNTRY: Liberia

REPORTING PERIOD: November 2013 - December 2016

| Programme Title & Project Number |  |
| --- | --- |
| Programme Title: Enhancing Access to Security and Justice at the Decentralized Level – Harper Hub, covering Maryland, Grand Kru and River Gee Counties; Zwedru Hub, servicing Grand Gedeh and Sinoe Counties. Programme Number (if applicable) PBF/LBR/B-2 MPTF Office Project Reference Number: 00088191 |  |  |

| Recipient UN Organizations |  | Implementing Partners |
| --- | --- | --- |
| List the organizations that have received direct funding from the MPTF Office under this programme: United Nations Development Program |  | List the national counterparts (government, private, NGOs & others) and other International Organizations: The Liberian Judiciary; Ministry of Justice and its law enforcement agencies including the Liberia National Police, Bureau of Immigration and Naturalization, Solicitor General's Office, Bureau of Correction and Rehabilitation, Probation Program, Juvenile Diversion Program, SGBV Crimes Unit, Independent National Commission on Human Rights. |
| Programme/Project Budget (US$) |  | Programme Duration |
| PBF contribution (by RUNO) $3,062,405 - UNDP |  |  | Overall Duration (months) 25 Months |  |
|  |  |  | Start Date (dd.mm.yyyy) 22.11.2013 |  |
| Government Contribution (if applicable) In kind contribution of land in Maryland and Grand Gedeh Counties to construct Regional Hub facilities, plus providing existing infrastructures to house justice and security service providers in the absence of new construction. Salaries and recurring operational costs for personnel hired and deployed to enhance service delivery in justice and security institutions in Hubs 2 and 3 counties. |  |  | Original End Date (dd.mm.yyyy) | 31.12.2015 |
| Other Contributions (donors) (if applicable) ECOWAS construction of BIN and LNP border barracks in Hubs 2 and 3 regions. UNDP SGBV Joint Program support of approximately $130000 to enhance operational effectiveness in Grand Gedeh, Grand Kru and River Gee counties. Nationwide support of mobile trial screens, judges training and advance trainings for investigators. |  |  | Final End date(dd.mm.yyyy) 31.12. 2016 |  |
| TOTAL: |  |  |  |  |

| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| --- | --- | --- |
| Mid-Term Evaluation / Review - if applicable please attach Yes No Date: End of project Evaluation– if applicable please attach Yes No Date: |  | Name: Joyce G. Cassell Frankfort Title: Programme Manager Participating Organization (Lead): Ministry of Justice Email address: jfrankfort@gmail.com |

PART 1 – RESULTS PROGRESS

  - Assessment of the project implementation status and results

For PRF projects, please identify Priority Plan outcome and indicators to which this project has contributed:

Priority Plan Outcome to which the project has contributed. Enhanced access to justice and community security at the regional and county levels in preparation for UNMIL transition.

Priority Plan Outcome indicator(s) to which project has contributed. 1.1 - % of justice and security services provided by the Harper and Zwedru Regional Hubs. 1.2 - % of people who feel safe or very safe in their community (disaggregated by county in the Hub region). 1.3 - % of people who trust the court system (disaggregated by Hub region). 1.4 - % of criminal cases adjudicated per court term (CT) (disaggregated by type of case and by county). 1.5 - # of trials on SGBV cases held in the Hub regions (disaggregated by county and by court term).

For both IRF and PRF projects, please rate this project’s overall achievement of results to date:

For both IRF and PRF projects, outline progress against each project outcome, using the format below. The space in the template allows for up to four project outcomes.

Outcome Statement 1:  Outcome 1: People in Maryland, River Gee and Grand Kru

(Hub 2), Grand Gedeh and Sinoe (Hub 3) Counties have increased access to fair and

accountable justice services

Rate the current status of the outcome:

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

In June 2013 in an effort to improving access to justice in Hubs 2 and 3 counties, the JS Policy Management Board approved the roll out of six priority services including strengthening prosecution and public defence, providing information on services in hub counties, reporting human rights violation, supporting the prevention and prosecution of sexual gender base violence and providing civic education to citizens on how to access the justice system.  Equipped and trained criminal justice actors were deployed in the two regions in 2014.  Since then, a total of 29 sexual violence cases have been prosecuted in five circuit courts, gaining 21 convictions.  This increase in prosecution of sexual cases can be attributed to citizens public information on how to process these cases.  Citizens learned about improved justice services by participating in 580 palava hut discussions, containing 17,711 residents and engaging outreach officers in 212 interactive radio talk shows.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

With trained and logistically resourced criminal justice actors deployed in the two hub regions in 2014, significant progress to improving access to justice has been realised during the implementation of this project. The 2013 baseline perception survey conducted in the five counties covered by Hubs 2 + 3 showed that 68% of respondents took rape cases to the Court, as opposed to 11% who went to Town Chiefs for settlement.  Using this information, the project trained and deployed dedicted prosecutors for rape to each county to ensure the speedy prosecution of these cases.  The result of this improvement is shown in the increase of rape cases reported, standing at 55 and prosecuted, 29, since 2014 and it can be argued that two factors contribute to this increase.  Through information provided by the public outreach service, more people are aware of how to access the criminal justice system and with this knowledge, more people seek redress.  Equally and taking findings from the perception survey, traditional leaders were trained to ascertain what cases they can mediate.  Rape, due to the severity of the crime to the victims/survivors, was noted as one crime that should be  forwarded for redress to the formal justice system.

The public perception survey also showed that 46% of citizens interviewd in the five counties, and of those, 100% who took their cases to court, be it magisterial or circuit, paid a fee for taking their cases to court, thereby highlighting the need for public defense to indigent members of society.  With this, additional trained public defenders to support the office of the Public Defence were deployed and have since helped to provide free legal services to indigent citizens by defending a total of 276 cases since 2014.

Knowing the importance of information in improving access to any service, public outreach officers  increased awareness in the five counties covered by the two regions.  They visited a total of 580 communities, reaching 17,711 residents (11,914 males; 5,797 females) and hosted 212 interactive radio talk shows on local stations, reaching an unspecified number of residents to inform of improved services in the counties. This exercise, along with information provided by human rights officers during the regular monitoring of criminal justice actors and civil society organisations have improved citizens' perception of the system, thereby improving their access of services provided.

Along with this improved access to justice and judicial services, the Judiciary during this period and with funding from the Government of Liberia began the construction of the 7th Judicial Circuit Court located in Zwedru, Grand Gedeh county, with completion date scheduled for June 2017.  To ensure citizens' easy access to judicial services, the court is located in the town center.

All of these small, but effective efforts, have contributed to peacebuilding in these counties.

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

Overall, the project has made tremendous progress and is currently on track with significant peacebuilding results, such as the increase in prosecution, public defence, public awareness on services, reduction in pre-trial detention rate and monitoring and reporting on human rights violation.

However, the spread of the EVD in 2014 delayed the roll out of services in those parts of the country.  With the focus on reducing the inmate population by the Judiciary and Ministry of Ministry, by effectively using Section 18.2 of the Criminal Procedure Law (CPL), Liberia was able to reduce the possible spread of the disease in prisons and detention centers in the five counties.

Outcome Statement 2:

Rate the current status of the outcome:

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

Outcome Statement 3:

Rate the current status of the outcome:

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

Outcome Statement 4:

Rate the current status of the outcome:

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

  - Assessment of project evidence base, risk, catalytic effects, gender at the end of the project

| Evidence base: What was the evidence base for this report and for project progress? What consultation/validation process has taken place on this report (1000 character limit)? | Before services were rolled out in Hubs 2+ 3 in 2014, the Peace Building Office conducted baseline perception survey in the 2 hubs regions in 2013 against which progresses are measured. Like Hub 1, project reports are collected and collated by Regional Coordinators from participating criminal justice institutions. The Regional Coordinators then submit the reports to the Program Management Unit who campares the reports with reports submitted by heads of criminal justice institutions. The Program Management Unit then collates all reports, verifying statistics, compiles and share information through updates with the Sector Finance Committe and the JS Policy Management Board. |
| --- | --- |
| Funding gaps: Did the project fill critical funding gaps in peacebuilding in the country? Briefly describe. (1500 character limit) | The project did fill critical funding gaps in the region, as the strengthening of the justice system, in terms of trained justice and judicial actors, who will provide fair and accountable service is a major element and a pre-requisite for peace in any post conflict state, especially in the Hubs 2+3 counties, which were known for invasive interference during the civil war. After the war, the justice sector suffered from low human capacity with few trained and qualified personnel, including judges, prosecutors and public defenders. Before the roll out of these services, there was only one public defender and one prosecutor in each county, creating immense challenge in clearing the dockets of courts and contributing to citizens' fraustration and mistrust of the system. With the holistic strengthening and de-concentration of services as done by this project, the funding has been instrumental in securing the peace in the regions. Also, by providing civic and legal education to citizens and traditional leaders, it is good to report that the poliferation of some crimes in the regions have reduced, as citizens are understanding their role in the maintenance of peace. |
| Catalytic effects: Did the project achieve any catalytic effects, either through attracting additional funding commitments or creating immediate conditions to unblock/ accelerate peace relevant processes? Briefly describe. (1500 character limit) | Through the JSTF, funded by the Swedish Government, twenty city solicitors were trained and deployed nationwide in 2014. Hubs 2+3 regions benefited from four of the twenty prosecutors. This injection of trained prosecutors to work in the lower magisterial courts have helped to fill in the capacity gaps as identified by the Ministry of Justice. Equally, in the last year, the JSTF has again supported the training of 60 college graduates as associate magistrates. These newly trained officers will be deployed nationwide to strategic magisterial courts by end April 2017. During this period, the GoL implemented its Plan for UNMIL Transition. The GoL (US$10 million) and development partners (US$11,938) provided funds for the strengthening of security agencies to ensure that tasks carried out by UNMIL were assumed by GOL by 30th June 2016. We are happy to report that the GOL was able to assume full security responsibilities by the deadline date. Key donors who supported this process were the Swedes - trained and outfitted border, corrections and police officers, constructed magisterial courts (x4); the Japanese Government supported the logistical strengthing of the border for police and border officers; the US government trained and outfitted all police support unit and emergency response unit officers; the Chinese Government logistically capacitated security institutions and UNMIL amongst other key support, helped in the development of legal instruments and policies. |
| Risk taking/ innovation: Did the project support any innovative or risky activities to achieve peacebuilding results? What were they and what was the result? (1500 character limit) | Due to the timebound nature of UNMIL transition, the chair of the Justice and Security Policy Management Board focused on the preparedness of security institutions to take over security responsibilities from UNMIL. This process required project management skills to ensure the GOL Plan for UNMIL Transition was effectively implemented. The Programme Management Unit of the JSJP was instructed to ensure implementation of the GOL Plan - thereby ensuring institutions and officers readiness to take security responsibilities with effect from 1st July 2016. We are happy to report that this decision was timely and all eight tasks were successfully handed over. |
| Gender marker: How have gender considerations been mainstreamed in the project to the extent possible? Is the original gender marker for the project still the right one? Briefly justify. (1500 character limit) | Gender sensitivity remains a key factor during the implementation of the program. Gender issues are mainstreamed during all aspects of the project - planning, implementation and evaluation. To ensure that gender issues are covered and integrated, the Ministry of Gender participates throughout the process. For those projects implemented during this period, we can report that of the 108 police officers trained, 33 (31%) were females; while 15% of the 140 BCR officer trained constituted women. Although some institutions, like BCR and BIN, have reached and surpassed the gender marker, others are still working to ensure 30% of staff are female. It is important to state that justice and security institutions are working to ensure that women today are a part of the process, thereby supporting the original gender marker of the project. |
| Other issues: Are there any other issues concerning project implementation that should be shared with PBSO? This can include any cross-cutting issues or other issues which have not been included in the report so far. (1500 character limit) | The Justice and Security Policy Management Board's phased implementation approach, which focused on first, the enhancement of existing services in the region through the roll out of six priority services, instead of a simultaneous implementation of infrastructure construction and service delivery had a negative impact on service delivery in the regions. Criminal justices actors deployed to provide enhanced services are challenged with dilapidated or no infrastructure space to professionally provide the service for which they have been deployed. During the justification for the location of Hubs 2 and 3, it was noted that these five counties were vulnerable to security threats and therefore needed the deployment of security officers to the regions. However, due to the lack of infrastructure, LNP/PSU and BIN/BPU officers were delayed and only deployed during the transition period in the numbers required. In our last interaction with citizens of these counties, it was expressed that the absence of modern facilities affects the ability to deliver effective services and can be interpreted as marginalization of southeasterners and therefore must be considered going forward, especially in light of peace consolidation. |

1.3 INDICATOR BASED PERFORMANCE ASSESSMENT: Using the Project Results Framework as per the approved project document- provide an update on the achievement of key indicators at both the outcome and output level in the table below. Where it has not been possible to collect data on indicators, state this and provide any explanation in the qualitative text above. (300 characters max per entry)

|  | Performance Indicators | Indicator Baseline | End of project Indicator Target | Current indicator progress | Reasons for Variance/ Delay (if any) | Adjustment of target (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 People in Maryland, River Gee and Grand Kru (Hub 2); Grand Gedeh and Sinoe (Hub 3) Counties have increased access to fair and accountable justice services | Indicator 1.1 % of enhanced justice and security services provided by the regional hub. Harper - 6 services Zwedru - 6 services | Harper 2011: 0% Zwedru 2011: 0% Harper: 83.3% Zwedru: 83.3% 5 out of 6 services rolled out December 2015: 100% = 6 services | December 2016: 100% = 6 services | Harper: 100% Zwedru: 100% All 6 services rolled out |  |  |
|  | Indicator 1.2 |  |  |  |  |  |
|  | Indicator 1.3 |  |  |  |  |  |
| Output 1.1 Justice sector institutions have adequate human capacity to provide key justice services | Indicator 1.1.1 # of trained county attorneys and public defenders deployed into the Hubs 2 and 3 regions | April 2014: County Attorney = 5, 1 per county; Prosecutor = 0; Public Defender = 5 1 per county; All GOL support. November 2015: County Attorney = 5; Prosecutors = 7; SGBV Prosecutors = 2; Public Defenders = 10 | December 2015: County Attorney = 5, 1 per county; Prosecutor = 9, 3 per hub county; 1 per hub support county; Public Defenders = 10, 2 per county. | November 2016: County Attorney = 5; Prosecutors = 7; SGBV Prosecutors = 2; Public Defenders = 10 |  |  |
|  | Indicator 1.1.2 # of public outreach officers and human rights monitors deployed to Hubs 2 and 3 region | November 2014 PSO: 5 Human Rights Officers: 10 November 2015 PSO 5 Human Right Officers: 5 | Dec 2015 PSO 5 Human Rights Officer 10 | November 2016 PSO 5 Human Right Officers: 10 |  |  |
| Output 1.2 Infrastructure and operational arrangements in place to provide key justice services | Indicator 1.2.1 % of operational arrangements to county attorneys and public defenders (mobility, equipment, furniture ) | April 2014: 0% Vehicles = 0 Computer and printers = 0 Office Furniture = 0 November 2015: 100% Vehicles = 13 Computers = 14 Printers = 14 Office Furniture = 14 sets = 100% | December 2016: 100% | November 2016: 100% Vehicles = 13 Computers = 14 Printers = 14 Office Furniture = 14 sets = 100% |  |  |
|  | Indicator 1.2.2 % of criminal cases adjudicated per term of court (ToC) (disaggregated by type of case) | April 2014: Harper Hub = Maryland =TBC; River Gee = TBC; Grand Kru = TBC Zwedru Hub = Grand Gedeh = TBC; Sinoe = TBC Nov 2015: M/land: Nov '14 CT: 1 Feb '15 CT: 3 May '15:CT: 1 R/Gee: Nov '14 CT: 3 Feb CT: 2 May CT: 3 G/Kru: Nov '14 CT: 0 Feb' 15 CT: 1 May' CT: 2 G/ Gedeh: Nov '14 CT:0 |  | Nov 2016: M/land Nov '15-100% Feb '16 -83% May '16:100% Aug'16 :0% R/Gee: Nov '15-54% Feb'16 -57% May '16 -0% Aug' 16 -0% G/Kru: Nov '15-100% Feb'16-100% May'16-100% Aug'16-100% : G/Gedeh: Nov '15-95% Feb'16 -100% May'16-0% Aug'16-26% Sinoe: Nov'15-100% Feb'16-33% May'16-100% Aug'16-90% |  |  |
| Output 1.3 1.5 - # of trials on SGBV cases held in the Hub regions (disaggregated by county and by court term). | Indicator 1.3.1 # of trials on SGBV cases held in the Hubs 2 and 3 regions, disaggregated by county | Baseline 2014 Nov 2015: Hub 2: 5 Cases in total (3 Court Terms ) Maryland: 2 River Gee: 2 Grand Kru: 1 Hub 3: 7 Cases in total in ( 3 Court Terms) Grand Gedeh: 5 Sinoe: 2 | Target (Dec 2015)? | Nov 2016: Hub 2:13 Cases Maryland: 5 Nov'16- 2, Feb'16- 1 May'16-0 Aug'16- 2 River Gee: 6 Nov'16-1 Feb'16-3 May'16-2 Aug'16-0 Grand Kru: 2 Nov'16-1 Feb'16-1 May'16-0 Aug'16- 0 Hub 3:7 Cases Grand Gedeh: 6 Nov'16-0 Feb'16-2 May'16-3 Aug'16-1 Sinoe: 1 Nov'16-0 Feb'16- 0 May'16-1 Aug'16-0 |  |  |
|  | Indicator 1.3.2 |  |  |  |  |  |
| Outcome 2 | Indicator 2.1 |  |  |  |  |  |
|  | Indicator 2.2 |  |  |  |  |  |
| Output 2.1 People in Maryland, River Gee and Grand Kru Counties (Hub 2); Grand Gedeh and Sinoe (Hub 3) benefit from justice advisory, human rights monitoring, advocacy and support services provided by civil society. | Indicator 2.1.1 # of Human Rights Officers deployed in Hubs 2 & 3 | November 2014:10 December 2015: 10 | December 2015: 10 | November 2016: 10 |  |  |
|  | Indicator 2.1.2 |  |  |  |  |  |
| Output 2.2 People in Hubs 2 and 3 are empowered as communities to manage conflicts in a manner that is integrated with the formal systems and strengthens the interface between statutory and customary systems. | Indicator 2.2.1 # of local traditional leaders trained and working with CSOs and PSOs on justice advisory and governance issues in hubs 2 and 3 counties. | Baseline: November 2013: Harper Hub: Maryland- 0, River Gee - 0, Grand Kru - 0; Zwedru Hub: Grand Gedeh - 0, Sinoe - 0 | Target: 31 December 2015: Harper Hub: Maryland - 10, River Gee - 10, Grand Kru - 10; Zwedru Hub: Grand Gedeh - 10, Sinoe - 10 | December 2016: UNDP please provide information |  |  |
|  | Indicator 2.2.2 |  |  |  |  |  |
| Output 2.3 | Indicator 2.3.1 |  |  |  |  |  |
|  | Indicator 2.3.2 |  |  |  |  |  |
| Outcome 3 | Indicator 3.1 |  |  |  |  |  |
|  | Indicator 3.2 |  |  |  |  |  |
| Output 3.1 | Indicator 3.1.1 |  |  |  |  |  |
|  | Indicator 3.1.2 |  |  |  |  |  |
| Output 3.2 | Indicator 3.2.1 |  |  |  |  |  |
|  | Indicator 3.2.2 |  |  |  |  |  |
| Output 3.3 | Indicator 3.3.1 |  |  |  |  |  |
|  | Indicator 3.3.2 |  |  |  |  |  |
| Outcome 4 | Indicator 4.1 |  |  |  |  |  |
|  | Indicator 4.2 |  |  |  |  |  |
| Output 4.1 | Indicator 4.1.1 |  |  |  |  |  |
|  | Indicator 4.1.2 |  |  |  |  |  |
| Output 4.2 | Indicator 4.2.1 |  |  |  |  |  |
|  | Indicator 4.2.2 |  |  |  |  |  |
| Output 4.3 | Indicator 4.3.1 |  |  |  |  |  |
|  | Indicator 4.3.2 |  |  |  |  |  |

PART 2: LESSONS LEARNED AND SUCCESS STORY

2.1 Lessons learned

Provide at least three key lessons learned from the implementation of the project. These can include lessons on the themes supported by the project or the project processes and management.

| Lesson 1 (1000 character limit) | Strengthen both the "supply side" and the "demand side" of the rule of law equation. Service cannot be enhanced without infrastructure. |
| --- | --- |
| Lesson 2 (1000 character limit) | The monitoring and evaluation of any project is a key element. However, the JSJP suffered, as this element was not included within the program management unit, but noted as a responsibility of the PBO. |
| Lesson 3 (1000 character limit) | It is important to take into consideration how other areas of government affects service delivery. For example, even with the improved service delivery in five counties, citizens access to these services are hampered by bad road network, as the southeast of Liberia was cut off for six months during the "rainy season". With the onset of climate change, this isolation period may increase. |
| Lesson 4 (1000 character limit) | Leadership by national authorities is critical for buildiug confidence and for longterm sustainability |
| Lesson 5 (1000 character limit) |  |

2.2 Success story (OPTIONAL)

Provide one success story from the project implementation which can be shared on the PBSO website and Newsletter as well as the Annual Report on Fund performance. Please include key facts and figures and any citations (3000 character limit).

Beyond issues relating to security and justice reform, capacities to manage conflict at the local levels will require continued support to mitigate destabilizing factors (inter-personal violence, particularly SGBV, ethnic disharmony and a sense of grievance) and conflict drivers (land disputes, youth disempowerment) to be managed.  Community level dialogue processes and continued enhancement of peacebuilding capacities at the community and village level, including civic education and public outreach, can provide the foundation for such efforts and strengthen a sense of national identity. In parallel to a local level process that creates the space for a coming to terms with the past, critical rule of law questions, most notably land reform, need to be addressed so as not to become conflict triggers. In addressing conflict triggers and grievance from the past, this programme is mindful that the women of Liberia have played an essential role in peacemaking and reconciliation and must remain central to this process if it is to succeed. In addition, one of most valuable and cherished attributes of this country is the Liberian youth. As peace continues to flourish in Liberia, efforts will be made to provide employment opportunities for youth, while at the same time empowering young people to play a constructive role in all parts of society.  The vision behind the hubs has been achieved, that of providing a decentralized and holistic approach to security and justice service delivery and a means by which national agencies have provided  security in preparation for UNMIL’s transition. The holistic approach to the hubs has provided for a balanced strengthening of justice and security institutions - law enforcement, the courts, state prosecution and defence, and corrections - both in terms of capacity and infrastructure; the enhancement of linkages between these institutions; and the development of relationships between the institutions and the communities they serve.  Each of these aspects has been a complementary component of the hubs.

PART 3 – FINANCIAL PROGRESS AND MANAGEMENT ARRANGEMENTS

  - Comments on the overall state of financial expenditure

Please rate whether project financial expenditures were on track, slightly delayed, or off track:

If expenditure was delayed or off track, please provide a brief explanation (500 characters maximum):

Please provide an overview of project expensed budget by outcome and output as per the table below.

| Output number | Output name | RUNOs | Approved budget | Expensed budget | Any remarks on expenditure |
| --- | --- | --- | --- | --- | --- |
| Outcome 1: |
| Output 1.1 | Justice sector institutions have adequate human capacity to provide key justice services | UNDP |  |  |  |
| Output 1.2 | Infrastructure and operational arrangements in place to provide key justice services |  |  |  |  |
| Output 1.3 | 1.5 - # of trials on SGBV cases held in the Hub regions (disaggregated by county and by court term). |  |  |  |  |
| Outcome 2: |
| Output 2.1 | People in Maryland, River Gee and Grand Kru Counties (Hub 2); Grand Gedeh and Sinoe (Hub 3) benefit from justice advisory, human rights monitoring, advocacy and support services provided by civil society. |  |  |  |  |
| Output 2.2 | People in Hub 2&3 are empowered to managed conflict |  |  |  |  |
| Output 2.3 |  |  |  |  |  |
| Outcome 3: |
| Output 3.1 |  |  |  |  |  |
| Output 3.2 |  |  |  |  |  |
| Output 3.3 |  |  |  |  |  |
| Outcome 4: |
| Output 4.1 |  |  |  |  |  |
| Output 4.2 |  |  |  |  |  |
| Output 4.3 |  |  |  |  |  |
| Total |  |  |  |  |  |

  - Comments on management and implementation arrangements

Please comment on the management and implementation arrangements for the project, such as: the effectiveness of the implementation partnerships, coordination/coherence with other projects, any South-South cooperation, the modalities of support, any capacity building aspect, the use of partner country systems if any, the support by the PBF Secretariat and oversight by the Joint Steering Committee (for PRF only). Please also mention if there have been any changes to the project (what kind and when) (2000 character maximum):

The Justice and Security Program was implemented through  three levels of decision makers - the Joint Steering Committee oversees the overall approval of PBF funding; whilst the Policy Management Board has oversight responsibility of the approval and implementation of all projects funded through the program, to include PBF, Justice and Security Trust Fund and the Government of Liberia.   The Sector Finance Committee is responsible for the identification and recommendation of sector priorities. The JSJP, being a direct implementation modality, makes UNDP, being the fund manager of the JSTF and PBF fund, responsible to work with national partners and the Program Management Unit to implement projects as identified and approved by the Board. The Program Management Unit ensures the implementation of the GOL funding as provided for the operation of the hubs through the use of the Ministry of Justice systems.

The Program Management Unit of the JSJP has worked well; however, during this the implementation of this program, when the GOL focused on the implementation of the Plan for UNMIL Transition, the focus shifted to ensuring security preparedness, thereby distracting from the holistic and balanced approach of reforming the criminal justice system.  In so doing and giving that the objective of the JSJP was ensuring justice and security institutions readiness for UNMIL transition, issues covered under the JSJP were discussed and approved under the Joint Implementation Group, responsible for the implementation of the GOL Plan for UNMIL Transition, which was headed by the Minister of Justice and Chair of the Policy Management Board and international partners.

# Footnotes

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to “Project ID” on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed.

Please note that financial information is preliminary pending submission of annual financial report to the Administrative Agent.