| Project Number and Title: #16 IPC District Management | PROJECT START DATE: 19 Dec-2014 | AMOUNT ALLOCATED by MPTF $1,212,945 | RECIPIENT ORGANIZATION WHO |
| --- | --- | --- | --- |
| Project ID: 93255 (Gateway ID) |  |  |  |
| Project Focal Point: Name: Dr. Alex Gasasira WHO Representative E-Mail: gasasiraa@who.int | EXTENSION DATE: 31 Dec 2015 | FINANCIAL COMMITMENTS $... |  |
| Strategic Objective (STEPP) SOn - Description | PROJECTED END DATE: 06-Feb-2015 | EXPENDITURES as of [August 2015] $1,120,654 | IMPLEMENTING PARTNER(S): |
| Mission Critical Action MCAn - Description |  |  |  |
| Location: Country or Regional | Sub-National Coverage Areas: Bomi, Bong, Gbarpolu, Grand Bassa, Grand Kru, Lofa,Maryland, Margibi, Montserrado, Nimba, River Cess, River Gee and Sinoe. |
| MONTHLY PROGRESS REPORT RESULTS MATRIX OUTPUT INDICATORS Indicator Geographic Area Projected Target (as per results matrix) Quantitative results for the (one month) reporting period Cumulative results since Project commencement (quantitative) Delivery Rate (cumulative % of projected total) as of date Health Care workers trained on IPC and adhere to correct IPC guidelines, are mentored on the job and receive adequate supervision on the application of IPC practices and remain free of Ebola. Number of new health care workers infected by district Liberia 0 0 288* 100% EFFECT INDICATORS (if available for the reporting period) |
| *Liberia total reported number, data validation exercise is going on to validate the final reported figure. NARRATIVE Situation Update (please describe critical changes, if any, in the situation that affect the project (1-2 paragraphs)) Liberia had no reported new EVD cases since the last cluster of cases in Margibi and Montserrado in June 2015. The Ministry of Health (MOH) and WHO declared Liberia free of Ebola transmission for the second time on 3rd September 2015. Subsequently the country has entered a three-month period of heightened surveillance. WHO is supporting the 15 counties by deployment of international and national Infection Prevention and Control Expert (IPC) Specialists. The team works directly with the County Health Teams and partners in the field. |
| Key Achievements (please use this section to highlight your key achievements for the month, using bullet points if preferred): IPC activities have focused on the following: Continuous technical and financial support to a national IPC Task Force, providing technical assistance and one international staff working closely with the national coordination of IPC. The commencement of Safe Quality Services (SQS) TOT and roll-out training to counties. WHO conducted TOT training during August and finalized the roll-out plan with partner NGOs. Key documents developed during the reporting month include: Finalization and validation of Ebola Treatment Unit (ETU) Operational Guide. Assessment of Ebola and non-Ebola health facilities was undertaken against the IPC minimum standard. This month the number of facilities assessed increased by one-third compared to previous months, from 60 to 80 per week. The assessment evaluated key indicators, including if facilities met the IPC minimum standard, and if facilities had adequate triage facilities. Data compilation and analysis of assessment at county and national level was also supported. Detailed report will be shared by the end of September to show the trend in improvement. |
| Delays or Deviations (if any, briefly describe the delays or changes in focus, approach or targets, and provide a short justification for the change (1-2 paragraphs)) |
| Gender and Environmental Markers (Please provide disaggregated data, if applicable) No. of Beneficiaries Environmental Markers Women NA e.g. Medical and Bio Hazard Waste Girls NA e.g. Chemical Pollution Men NA Boys NA Total Please explain what strategies are being used to reach out to the most vulnerable sections of the population (women, children,etc) and how it is making a difference. |
| Additional Information (Optional) Activities planned for next month include: Roll out of SQS training to in 15 counties, and conducting joint M&E and quality assurance visits by WHO/MOH team. Clearly defining IPC indicators for routine reporting and monitoring, and support of comprehensive analysis. Continue working with partners, to identify gaps and recommend optimal solutions to strengthen IPC at the county and district level. |

# Footnotes

The date project funds were first transferred.

The Indicators should be disaggregated by gender, age and region as and where applicable