| Project Number and Title:00093136 Title: Ebola Children Protection | PROJECT START DATE: 01 December 2014 | AMOUNT ALLOCATED by MPTF (please indicate different tranches if applicable) $3,745,400 (programmable amount) Combine funds | RECIPIENT ORGANIZATION UNICEF-Child Protection |
| --- | --- | --- | --- |
| Project ID: 0000000 (Gateway ID) |  |  |  |
| Project Focal Point: Name: Mr. Sheldon Yett E-mail:syett@unicef.org | EXTENSION DATE: 29 May 2015 | FINANCIAL COMMITMENTS $3,745,400 |  |
| Strategic Objective (STEPP) SO3 –Ensure Essential Services | PROJECTED END DATE: 31 December 2015 | EXPENDITURES as of [date] $3,650,089.66 | IMPLEMENTING PARTNER(S): Ministry of Gender Children and Social Protection/MoGCSP, Ministry of Health/MoH Ministry of Youth and Sports/MoYSP Helping Hand Israel Aid |
| Mission Critical Action MCA 6 – Access to Basic Services |  |  |  |
| Location: Liberia | Sub-National Coverage Areas: Full list of countries and/or districts: Montserrado (All districts) Margibi ( All Districts) Lofa (All Districts) Bong (All Districts) Bomi (All Districts |

# MONTHLY PROGRESS REPORT RESULTS MATRIX

| OUTPUT INDICATORS |
| --- |
| Indicator | Geographic Area | Projected Target (as per results matrix) | Quantitative results for the (one month) reporting period | Cumulative results since project commencement (quantitative) | Delivery Rate (cumulative % of projected total) as of date |
| Description of the quantifiable indicator as set out in the approved project proposal |
| Number of interim care Centers (ICCs) providing care to children on 21 day observation who are separated from their primary care giver Number of Foster Carer households providing alternative care arrangements for children who are either “contacts”( needing 21 day observation period), survivors, or orphans with no one identified to care for them in the community setting Number of families who received one-off cash transfers support for caring for orphaned/abandoned children due to Ebola Number of children receiving mental health and psychosocial support (MPHSS) | Montserrado (All districts) Margibi ( All Districts) Lofa (All Districts) Bong (All Districts) Bomi (All Districts | Baseline: 1 ICC Target: 3 more ICCs Baseline: 2,000 (Foster Carers) Target: 7500 children Affected by EVD receiving the foster grant Baseline: Target: 7500 families receiving foster grant Baseline: 3542 children (MHPSS) Target: 10,000 children receiving MHPSS | 0 ICC and 1 transit Center on stand by Five Counties:45 Montserrado-45 197 children received MHPSS | 2 ICC and 1 transit Center on stand by Cumulative: 8613 Five Counties: 6743 Bong-528 Bomi-218 Montserrado-3750 Margibi-1177 Lofa-1070 Cuumulative:4436 children have received the US$150 one-time cash grant Cumulative:15,955 (7,203m,8,752f) Breakdown by County: Bomi 220 (107m,113f) Bong 528 (317m,211 f) Gbarpolu 161(96m,65f) G.Bassa 401(165m,236f) G.Cape Mount 433 (215m,218f) G. Gedeh240 (103m,137f) G. Kru 132 (64m,68f) Lofa 2303 (950,1353f) Margibi 4436 (1830m,2606f) Maryland (0m,0f) Montserrado 6326 (3006m,3320f) Nimba 580 (257m, 323f) River gee 46 (20m,26f) Rivercess 93 (40m,53f) Sinoe56 (33m,23f) | 75% with the transit center Over 100% |
| Number of Social workers and Mental Health Clinicians trained and providing family tracing, foster care placement, follow up of children in care, psychosocial support, community support and distribution of cash allowances and infection control and hygiene items. Number of Ebola survivors trained and employed as child carers, foster parents, working with social mobilization teams. | Montserrado (All districts) Margibi ( All Districts) Lofa (All Districts) Bong (All Districts) Bomi (All Districts | Baseline: 100 social worker and MPHSS specialists 20 Ebola Survivors Target: 200 Social Workers & Mental Health Clinicians 1200 Ebola Survivors | 0 0 0 0 | 120 Social Workers and 65 Mental Health Clinicians 15 Child Welfare officers 20 CP Data clerks Cumulative: 1200 (542m, 658f) Ebola Survivors Five County Totals:1102 Bomi 25 (6m,19f) Bong 72 (32m,40f) Lofa 170 (86m,84f) Margibi 184 (84m,100f) Montserrado 651 (288m,363f) | 120% 100% |
| Number of counties with strengthen CP and MPHSS coordination, Existence of CP and MPHSS networks coordination structures at the national and county level Number of counties with decentralized child protection Network coordination meeting; Functioning Child Welfare Committee in the most affected communities to identify, support and refer the most vulnerable children. | Montserrado (All districts) Margibi ( All Districts) Lofa (All Districts) Bong (All Districts) Bomi (All Districts | Baseline: 1 national 1 county 0 CWCs Target; 1 national 5 Counties 50 CWCs | 1 National Child Protection Network/CPN held 1 PSS Coordination Meetings held 2 Child Protection IMS meeting Held 7 Local Child Protection Network/CPN meetings 1 National CPN 1 National PSS meeting | 11 National CPN held 34 PSS Coordination meetings held 24 CP IMS 79 CWCs functional Bomi-23 Bong-11 Margib-7 Montserrado-33 Lofa;5 | 100% 100% |
| EFFECT INDICATORS (if available for the reporting period) |
| Strategic Objective 3 MCA6: Increased children’s access to basic services | Montserrado -Margibi -Lofa -Bong -Bomi | 7500 | 197 | 15,955 |  |
| Strategic Objective 3 MCA7: Increased capacity of the social welfare system to handle cases of children affected by EVD through increased number of workers | Montserrado -Margibi -Lofa -Bong -Bomi | 185 | 45 social workers and mental health clinicians trained 65 mental health Clinicians trained | Total: 220 Breakdown: 120 Social Workers 65 mental health Clinicians 15 Child Welfare officer and 20 data clerks |  |
| Strategic Objective 4 MCA11: Functioning community based child protection networks in the most affected communities identify, support and refer the most vulnerable children affected by EVD | Montserrado -Margibi -Lofa -Bong -Bomi | 200 | Total new CWCs: 0 | 79 Functional CWCs in the four counties with a membership of 11 persons per CWC ( 869 CWC members) Accumulative: 300 national volunteers nationwide. 143 Junior National Volunteers active in all 5 counties Cumulative: 1200 (542m, 658f) Ebola Survivors Five County Totals:1102 Bomi 25 (6m,19f) Bong 72 (32m,40f) Lofa 170 (86m,84f) Margibi 184 (84m,100f) Montserrado 651 (288m,363f) |  |

NARRATIVE Situation Update (please describe critical changes, if any, in the situation that affect the project (1-2 paragraphs)) UNICEF is utilizing the funds from MCA6 through the project ‘Supporting the Well-being and Protection of Ebola Affected Children in Liberia’ to serve 7500 affected children. Currently, the number of EVD affected children in the Ministry of Gender Children and Social protection (MoGCSP database) is 8613 bringing the accumulative figure of children documented and those who have received case management and PSS services to 15,955. During the month, UNICEF supported the MoH-Mental Health Department to organize a one week PSS training for mental health clinicians, social workers, and child welfare officers on basic counseling skills with children to be used in their structured play groups. This is part of a series of trainings teaching social workers and outreach workers to engage children to express their feelings and teach healthy behaviors that encourage social connection. UNICEF continues to support the MoGCSP and MoH to provide Case management and PSS support to families and communities affected, particularly families under precautionary observation. As well, the Social Workers and Mental Health Clinicians with these Ministries have provided support through the profiling of EVD affected children, the provision of case management and family tracing for vulnerable children, and MH assessment for persons in need. Social mobilization activities to fight the EVD continue in all counties with concentration on the two affected counties. Relevant services for children including specialized care in the Interim Care Center and transit home have been prepared and are on standby should in case there is need for such services for children. UNICEF continues to monitor the quality of standards and services being provided to the vulnerable groups and households. In the coming year, the case management services being offered by the social workers and mental health clinicians for child survivors of EVD and children who have lost parents or primary caregivers due to EVD will be expanded to other vulnerable populations beyond EVD affected persons. This is part of the Phase III strategy to return to development activities. UNICEF, through its partnership with the Ministry of Youth and Sports, continues to provide technical supervision and guidance to the deployed 300 national youth volunteers who are providing referral services to children affected by EVD. They continue to provide psychological first aid to persons in distress and social mobilization for the prevention of EVD.

Key Achievements Alternative care, Case management and PSS support to Children affected by the EVD Supported the Ministry of Gender, Children, and Social Protection and the Ministry of Health to increase the capacity and technical skills of 45 social workers, Child Welfare Officers and Mental Health Clinicians through one week PSS training on child appropriate activities and basic child counseling skills. Out of the five counties 6,216 have been registered as orphans of EVD (4,770 single orphans, 1,446 double orphans) and out of this number, 4,223 (67%) have benefitted from one-time emergency cash assistance. Registration continues nationwide. All of these children are in family based care. Revitalized and continuing to provide support to the National Child Protection Information Management System that is currently storing the data of all children in need of child protection services, especially children affected by the EVD. Several vehicles, motorbikes, rain gears, bicycles were provided to the MoGCSP to help facilitate the work of the social workers in the counties and to fast track the registration of children in remote communities. Monitoring visit was made to two counties to monitor programs and ensure social workers are delivering appropriate case management, psychosocial care and reintegration follow up visits to the EVD affected children. 300 National Volunteers (Nationwide) and 143 national junior volunteers continue to provide sensitization and awareness activities on EVD prevention, prevention of sexual and gender based violence in the five counties. Some also serve as volunteer teachers, nurses and provide guidance in the decision on children in their communities. The Hawa Massaquoi Transit Center continues to provide shelter and protection for 30 separated and unaccompanied children as family tracing and reunification services are in process. Adolescent girls The adolescent program in Zwedru- run through the County Health Team- conducted an awareness raising campaign this month in the town for the purpose of encouraging the prevention of FGM and raising awareness about teenage pregnancy and it’s negative effects.

Delays or Deviations UNICEF Child Protection has not experienced major deviations from programming during the past month except for payment of children, which while has been in process hasn’t been completed for more children this month- expect next month to have been completed. Delays in the MoGCSP liquidations have delayed the payment of incentives for some social workers. All efforts are being made to fast track the liquidation process and ensure that the Social Workers will receive their full incentive for 2015.

Gender and Environmental Markers (Please provide disaggregated data, if applicable) No. of Beneficiaries-November 2015 Environmental Markers Women 658 Girls 8752 Men 542 Boys 7203 Total 17155 Please explain what strategies are being used to reach out to the most vulnerable sections of the population (women, children, etc) and how it is making a difference. UNICEF continues to work with the MoGCSP and other NGOs to enhance the capacity of the social welfare system to properly manage cases of children affected by EVD along with other vulnerable persons in the community. These services provide psychosocial support, case management and alternative care services to those most in need. The system works to ensure that contact children without parental care are provided with appropriate care during the 21 day observation period and link them to coordinated services to ensure that basic needs are met, that they are reunified with families, that families are supported, and livelihoods are restored. We will continue to promote adolescent and child ambassador structures among slum communities, engaging children to conduct awareness, sensitization, monitoring and reporting of child protection concerns. We are continually working to strengthen the referral system to ensure that the most vulnerable receive services, which presently includes child survivors of Ebola who are faced with medical problems and need access to the relevant medical services. UNICEF also continues to work closely with the MoGCSP GBV unit and the Police to effectively respond to cases of sexual gender based violence and link them to the justice and protection system.

Additional Information (Optional) Child Welfare Committee members meet to discuss activities they are engaging in for the children in their community Some members of a Child Welfare Committee who have received a UNICEF donated bicycle to assist in the work with protecting children in their community A survivor and her two children in Bong Couty Beneficiaries of the one off cash grant. Social Workers, Mental Health Clinicians and Child Welfare Officer attending training on child friendly PSS activities in Bong County Motorbikes donated for the work of Bong County Social Workers & Mental Health Clinicians

Socials Workers, Mental Health clinicians and Child Welfare Officers being certificated after completing the fourth cycle of the Child Friendly PSS training- The training was provided by IsraAid through the partnership with MoH.

# Footnotes

The date project funds were first transferred.

The Combined MPTF funds  with the two grants Number: SM140647 and SM140603 allocated to UNICEF

This programmable balance is for the last Direct Cash Transfer payment to Ministry of Gender Children and Social Protection due by 15 December 2015.

The Indicators should be disaggregated by gender, age and region as and where applicable

The 7500 is targeting children who were affected by the EVD Nationwide

Total number of  of Ebola Survivors trained and employed in the five counties

Total number of Ebola Survivors nationwide.

Total number of Ebola Survivors nationwide.

The current number of EVD affected children registered by the Ministry of Gender, Children and Social Protection is 4,915. This number continues to be updated as new data comes in from the county-level social workers who are registering children who have lost one or both parents or primary caregivers due to EVD, child survivors of EVD and other EVD-affected children.

The initial planned number of 350 contact tracers was not required as, from other sectors in UNICEF and other partners, many contact tracers were mobilized and recruited.  Further, the number of cases was less than anticipated. Although the number of cases has come down, this important work at community level continues.

# Text boxes

Social Worker working in the field verifying payment records with a family.