RUNO ANNUAL PROJECT REPORT				TEMPLATE 4.4

PEACEBUILDING FUND (PBF)

ANNUAL PROJECT progress report

COUNTRY: Liberia

REPORTING PERIOD: 1 january – 31 December

| Programme Title & Project Number |  |  |
| --- | --- | --- |
| Programme Title: Community-based Truth Telling and Atonement Project Programme Number (if applicable) 00088111 MPTF Office Project Reference Number: 0008032 |  |  |

| Recipient UN Organizations |  |  | Implementing Partners |  |
| --- | --- | --- | --- | --- |
| List the organizations that have received direct funding from the MPTF Office under this programme: UNDP |  |  | List the national counterparts (government, private, NGOs & others) and other International Organizations: INCHR, National Civil Society Organizations, Ministry of Internal Affairs, National Traditional Council of Liberia, Liberia Peacebuilding Office, |  |
| Programme/Project Budget (US$) |  |  | Programme Duration |  |
| PBF contribution (by RUNO) 1,000,000.00 |  |  | Overall Duration (months) 36 |  |
|  |  |  | Start Date (dd.mm.yyyy) 01/10/2013 |  |
| Government Contribution (if applicable) |  |  | Original End Date (dd.mm.yyyy) | 31/10/2016 |
| Other Contributions (donors) (if applicable) 308,000.00 |  |  | Current End date(dd.mm.yyyy) 31/10/2016 |  |
| TOTAL: | 1,308,000.00 |  |  |  |

| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| --- | --- | --- |
| Assessment/Review - if applicable please attach Yes No Date: June 23, 2016 Mid-Term Evaluation Report – if applicable please attach Yes No Date: |  | Name: Sunny A. George Title: Project Manager Participating Organization (Lead): Independent National Commission on Human Rights (INCHR) Email address: sunageorge@hotmail.com |

PART 1 – RESULTS PROGRESS

  - Assessment of the current project implementation status and results

For PRF projects, please identify Priority Plan outcome and indicators to which this project is contributing:

Priority Plan Outcome to which the project is contributing. Communities in pilot locations have adequate mechanisms for dealing with the past through the Palava Hut process for truth telling, atonement and reconciliation.

Priority Plan Outcome indicator(s) to which project is contributing. 1.1: Proportion of cases taken up by the Palava Hut that are resolved (disaggregrated by cases submitted by men/women) 1.2: Proportion of women in the Palava Hut Committees 1.3: Percentage of citizens in pilot locations who are positive about the national reconciliation process disaggregated by men/women.

For both IRF and PRF projects, please rate this project’s overall achievement of results to date:

For both IRF and PRF projects, outline progress against each project outcome, using the format below. The space in the template allows for up to four project outcomes.

Outcome Statement 1:  Communities are reconciled and live in peaceful coexistence utilizing the Palava Hut system/approach to settle their differences.

Rate the current status of the outcome:

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

PMU has technical capacity with improved productivity. 13 INCHR/PMU staff trained in result-based reporting, human resources management, project design and management and monitoring & evaluation. Ethnographic report validated & distributed; Palava Hut (PH) methodologies & guidelines developed; two study tours conducted in Sierra Leone and Rwanda. 20 CSOs trained to conduct public outreach on PH;  Integrated outreach strategy developed; 30 communities identified for outreach; outreach officially launched; 8 PH committees restructured, trained & functional; Key govt, UN & CSO stakeholders informed of PH hearings.    8 Notes/Statements Takers, 2 Interpreters, 2 report writers and 12 Psychosocial Counselors trained and hired; 2 venues for hearings, 2 safe houses for witnesses, 2 county offices for use by PH Committees identifed and Witness Protection Strategy developed; traditional community cleansing strategy designed. 1 community memorial under construction.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

The successful development of PH methodologies and operational guidelines & training of 8 PH C'ttees on their use for the PH hearings, set the pace for communities to begin utilizing the PH system/approach to settle their war-related & other differences that impede reconciliation & peaceful coexistence. The knowledge & skills acquired by INCHR/PMU staff through capacity-building training opportunities offered by the project have significantly enhanced the capacity of the INCHR to effectively implement the project and its core functions. For example, 13 INCHR/PMU staff trained in result-based reporting, human resources management, project design & management & monitoring & evaluation, which increases institutional functionality & productivity. Lessons learned from 2 study tours to Sierra Leone and Rwanda are informing policy & technical decisions & actions to maximize results & build a profile expected of a national human rights body, including the INCHR's current effort of improving its relationship with the civil society & some new interventions proposed in this report for consideration. The project contributes to peacebuilding by  insisting on broad-based participation & gender-equality, contrary to exlusion and marginalization counted among conflict triggers in Liberia. Citizens were allowed to select members of the 8 revived PH C'ttees who include elders, traditional & religious leaders, women, youth & persons with disabilities; women are co-chairs;  and a total of 249 persons directly participated in trainings & other events of the project, with males constituting 53% and females 47%. The original gender marker for the project was increased by 17%. Females are now active players in public awareness groups in the communities where awareness campaign is being conducted. Citizens are increasingly being informed of the PH process & discussing it in communities since the launch of outreach by INCHR & LMDI. Public optimism & expectation about the start of the PH hearings has heightened. The ongoing construction of the Duport Road Memorial doubles public appreciation of the project's contribution to the process of healing, peace & reconciliation, in this case by memorializing the fatalities of the war as a means of teaching Liberians to seek peaceful solutions to their differences in lieu of violence.

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

Delay in preparation and approval of AWPs and Procurement and M&E Plans. Some delays in undertaking procurement within established timeframe by UNDP that has had implication for the project in undertaking its activities on time. The INCHR in order to overcome this has to the extent possible ensured that request for goods and materials have been submitted to the UNDP with sufficient lead time to ensure delivery of material at expcted date .

Outcome Statement 2:

Rate the current status of the outcome:

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

Outcome Statement 3:

Rate the current status of the outcome:

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

Outcome Statement 4:

Rate the current status of the outcome:

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

  - Assessment of project evidence base, risk, catalytic effects, gender in the reporting period

| Evidence base: What is the evidence base for this report and for project progress? What consultation/validation process has taken place on this report (1000 character limit)? | The PMU produced photos, newspaper stories, quarterly reports, half yearly report, study tour reports, regular consultations with Board of Commissioners on progress of project, report of research on perception of potential witnesses to appear for Palava Hut hearings by Marola Vaes from the Tilburg University in The Netherlands and audit report. |
| --- | --- |
| Funding gaps: Did the project fill critical funding gaps in peacebuilding in the country? Briefly describe. (1500 character limit) | The Government of Liberia has yet to provide funding for the National Palava Hut Program since 2013. As such, the funding provided under the PBF and the UNDP have addressed a significant funding gap by enabling the implementation of the Community-based Truth Telling and Atonement Project that is central to peacebuilding in the country. The fundings also delivered additional benefits to the country. For example, the Kofi Anna Institute of Conflict Transformation at the University of Liberia is presently using the report of the ethnographic study to learn various traditional peacebuilding processes and mechanisms in the contexts of the palava hut systems practiced by the principal linguistic communities of Liberia: Kwa, Mande, Mel and Settlers. Many Liberians have become more aware of the palava hut program through community forums and on radios. The project has integrated women and youth participation and voices in the Palava Hut that was once exclusively operated by males, which supports the cause of gender equality and engendered decision-making processes. There are signals of improved relationships in areas where the ethnographic study was conducted and Palava Hut Committees established; inhabitants have begun channelling grievances through the Palava Hut Committees. The committees have been able to resolve some of the cases and reconcile the disputants. |
| Catalytic effects: Did the project achieve any catalytic effects, either through attracting additional funding commitments or creating immediate conditions to unblock/ accelerate peace relevant processes? Briefly describe. (1500 character limit) | The PMU established relationship with Tilburg University, The Netherlands. This resulted in a 1-month visit of a student of the university, Marola Vaes, who conducted a research on "The perception of potential witnesses to appear before the Palava Hut". The project is promoting a spirit of oneness and unity among the population, which has positive effect on social cohesion; evidenced by the man-run traditional PH now tramsformed, engendered and inclusive of women, youth and minority ethnic groups. |
| Risk taking/ innovation: Did the project support any innovative or risky activities to achieve peacebuilding results? What were they and what was the result? (1500 character limit) | When the TRC took statements from the public and institutions of interest, the citizens had expected that the government would have taken immediate action in redressing the grievances of the victims. But that did not happen, to the disenchantment of many people. The INCHR started the Palava Hut program in 2012, beginning with the establishment of Palava Hut Committees and public awareness campaign across the country. But the process was abruptly suspended during the development of the Strategic Roadmap on National Healing, Peacebuilding and Reconciliation. These factors resulted in public cynicism about the Palava Hut when it resumed in 2013 in the framework of the Community-based Truth Telling and Atonement Project. With the conduct of the ethnographic study forums which brought together elders, traditional leaders, women, youth, CSOs and minority ethnic groups and giving them the opportunity to drive the process of reconciliation and peacebuilding through their respective traditional palava hut approaches, coupled with mass public education on the palava hut and its benefit, reduced the level of cynicism they had had. The persistency of subsequent activities, including continued education, and broad-based citizens' participation has brought about increased public confidence in and support to peacebuilding and reconciliation through the Palava Hut process. The inclusion of women in a male patriochial structure was also an innovation a deeply traditional society. |
| Gender: How have gender considerations been mainstreamed in the project to the extent possible? Is the original gender marker for the project still the right one? Briefly justify. (1500 character limit) | The project is gender-sensitive and gender-inclusive. The 8 PH Committees comprise 4 males and 3 females each, with females serving as co-chairs. The capacities of 15 INCHR-PMU staff members upgraded; they included 9 males and 6 females. A total of 249 persons directly participated in trainings and other events of the project, with males constituting 53% and females 47%. The original gender marker for the project was increased by 17%. Females are now active players in public awareness groups in the communities where awareness campaign is being conducted. |
| Other issues: Are there any other issues concerning project implementation that should be shared with PBSO? This can include any cross-cutting issues or other issues which have not been included in the report so far. (1500 character limit) | There are persons still carrying war-related particles in their bodies. The concern being raised by many persons is what could the project do if such cases surfaced during the Palava Hut hearings. The project does not currently have budgetary allotment to respond to such cases. Palava Hut hearings are one-shot events, which alone cannot deliver healing, reconciliation and positive peace. Traditional leaders and elders and religious actors are therefore proposing complementary post-hearings interventions that build on and sustain the outcome of the hearings.These include community cleansing to appease the ancestors, purify the land, rehabilitate and reintegrate penitent offenders and victim-offender mediation using traditional mechanisms."We want the Palava Hut to help us honor our people who died in the war without proper burial," said an Islamic cleric in Voinjama District, Lofa County. The need to make the Palava Hut human rights-friendly is equally important. The conduct of a perception survey in the 2 pilot districts is compelling to satisfy Indicator 1.3 of the Priority Plan Outcome. |

1.3 INDICATOR BASED PERFORMANCE ASSESSMENT: Using the Project Results Framework as per the approved project document- provide an update on the achievement of key indicators at both the outcome and output level in the table below. Where it has not been possible to collect data on indicators, state this and provide any explanation in the qualitative text above. (300 characters max per entry)

|  | Performance Indicators | Indicator Baseline | End of project Indicator Target | Current indicator progress | Reasons for Variance/ Delay (if any) | Adjustment of target (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 Communities are reconciled and live in peaceful coexistence utilizing the Palava Hut system/approach to settle their differences | Indicator 1.1 Palava Hut methodology and mechanism developed and utilized in communities | September 2013: No methodolocal framework for Palava Hut | Responsive technical capacity by 2014 | Ethnographic study report validated and operationalized. Context-specific palava hut methodologies and operational guidelines for 3 linguistic groups developed & training conducted on utilization. | NA | NA |
|  | Indicator 1.2 NCHR has capacity to implement project | Limited technical capacity. Leadership vacuum-with no presiding chairman 2013 | Results-based INCHR by 2014 | INCHR/PMU has trained, competent staff to implement project. The PMU now produces standardized AWPs, Procurement and M&E Plans, quality reports, concept notes, and is ably leading project implementation. PMU staff help facilitate some project trainings. | NA | NA |
|  | Indicator 1.3 |  |  |  |  |  |
| Output 1.1 Output:1 INCHR capacity strenthened to lead and coordinate the National Palava Hut Program | Indicator 1.1.1 Project Management Unit set up and functional in INCHR # of staff are trained # of logistical and technical supports is provided. # of reports technical reports available. # of staff recruited | No Technical Unit in place (2013): Limited logistics (vehicles etc) in place at INCHR | PMU set up by December 2013 M&E plan developed by March 2014 Functional Project Management Unit (PMU). | PMU has technical capacity with improved productivity. 13 staff trained. 4 laptaps, 2 portable generators, 10 megaphones, 1,000 T-shirts, 1,000 stickers, 8 banners and fuel received. Activity, monthly, quarterly, half yearly and annual reports available. | NA | NA |
|  | Indicator 1.1.2 |  |  |  |  |  |
| Output 1.2 Output:2 Studies conducted and Palava Hut methodology and operational guidelines developed | Indicator 1.2.1 # of research findings Study report | (2013): No report | Study conducted by 2014 | 3 findings of ethnographic study and study tours to Sierra Leone and Rwanda available. PH methodology and operational guidelines developed. 3 reports of ethnographic study and study tours to Sierra Leone and Rwanda available. | NA | NA |
|  | Indicator 1.2.2 |  |  |  |  |  |
| Output 1.3 Output 3: Nationwide outreach conducted on the Palava Hut Programme | Indicator 1.3.1 Number of outreach events held | 2013): No campaign events | (2015): Campaign conducted in all counties in all 16 languages | 20 CSOs trained to conduct public outreach on PH; outreach materials distributed; Integrated outreach strategy developed; 30 communities identified for outreach. | Vetting of CSOs, assessment of capacities and training of selected CSOs for conduct of outreach was time-consuming. In fact, the progress of the capacity assessment by UNDP was restrained because of bad road condition due to rain. | NA |
|  | Indicator 1.3.2 |  |  |  |  |  |
| Outcome 2 | Indicator 2.1 |  |  |  |  |  |
|  | Indicator 2.2 |  |  |  |  |  |
| Output 2.1 Output 4: Palava Hut process piloted in 2 communities | Indicator 2.1.1 Palava Hut discussions held | (2013): None undertaken | At least 3 discussions held in each county by 2015 | 8 PH committees restructured, trained & functional; Key govt, UN & CS stakeholders informed of PH hearings. 8 Notes/Statements Takers, 2 Interpreters, Reporters and 12 Psychosocial Counselors trained and hired; 2 venues for hearings, 2 safe housess, 2 local offices identified. | The time spent on processes of selecting qualified CSOs to conduct public outreach inevitably resulted in change of schedule for the conduct of the PH hearings because the outreach is a precondition. | NA |
|  | Indicator 2.1.2 |  |  |  |  |  |
| Output 2.2 Output 5: At least two Regional Memorials constructed in hard hit war affected communities | Indicator 2.2.1 # of Memorials constructed | One public memorial was constructed in Bong County by Transitional Justice Working Group with support from OSIWA 2013 | Construction of two memorials to honor the dead by 2015 | 1 community memorial under construction at the Duport Road mass gravesite. | The UNDP was constrained to suspend procurement of services to begin construction of the first memorial because the Office of the President had offered to underwrite the cost. But there was a delay, thus prompting the INCHR to request the UNDP to revive its procurement process. That caused a delay. | NA |
|  | Indicator 2.2.2 |  |  |  |  |  |
| Output 2.3 | Indicator 2.3.1 |  |  |  |  |  |
|  | Indicator 2.3.2 |  |  |  |  |  |
| Outcome 3 | Indicator 3.1 |  |  |  |  |  |
|  | Indicator 3.2 |  |  |  |  |  |
| Output 3.1 | Indicator 3.1.1 |  |  |  |  |  |
|  | Indicator 3.1.2 |  |  |  |  |  |
| Output 3.2 | Indicator 3.2.1 |  |  |  |  |  |
|  | Indicator 3.2.2 |  |  |  |  |  |
| Output 3.3 | Indicator 3.3.1 |  |  |  |  |  |
|  | Indicator 3.3.2 |  |  |  |  |  |
| Outcome 4 | Indicator 4.1 |  |  |  |  |  |
|  | Indicator 4.2 |  |  |  |  |  |
| Output 4.1 | Indicator 4.1.1 |  |  |  |  |  |
|  | Indicator 4.1.2 |  |  |  |  |  |
| Output 4.2 | Indicator 4.2.1 |  |  |  |  |  |
|  | Indicator 4.2.2 |  |  |  |  |  |
| Output 4.3 | Indicator 4.3.1 |  |  |  |  |  |
|  | Indicator 4.3.2 |  |  |  |  |  |

PART 2: LESSONS LEARNED AND SUCCESS STORY

2.1 Lessons learned

Provide at least three key lessons learned from the implementation of the project. These can include lessons on the themes supported by the project or the project processes and management.

| Lesson 1 (1000 character limit) | It was learned from the study tour to Sierra Leone that one of the affirmative actions taken by the government and people of the country to support and sustain the process of post-conflict healing, reconciliation and social cohesion, was the legislation of some of the recommendations of the country's Truth and Reconciliation, which are referred to as "Compulsory TRC Recommendations". They include, but not limited to, reparation and healthcare delivery. As such, the state and the government are statutorily obliged to ensure the implementation of these recommendations, rather than making them optional and unbinding. Liberia needs to replicate this legislative measure not only with the National Palava Hut Program as recommended by the four linguistic groups, who attended the ethnographic study forums in late 2015, but also with other key recommendations of the Liberian TRC Report. This will surely accelerate progress and ensure success of the transitional justice process. |
| --- | --- |
| Lesson 2 (1000 character limit) | Traditional leaders (males and females) at the traditional psychosocial healing training organized by the MIA, the conduct of Palava Hut or any public hearings in the context of transitional justice is complemented by special community cleansing ceremonies. Such ceremonies are meant for the appeasement of the ancestors, purification of the land, re-admission of penitent perpetrators into the community and affirmation of collective oath to remain reconciled and peacefully coexist. Examples include libations, animal sacrifice, picnics and other preferred rituals. Other relevant initiatives that help build confidence and promote social cohesion among victims, perpetrators and community members, such as victims-offenders mediation, are also vital to achieving the ultimate goal of the Palava Hut hearings. The implementation of similar activities contributed greatly to the success story of the Fambul Tok Program in Sierra Leone. |
| Lesson 3 (1000 character limit) | A well-known traditional leader, who was most likely to be selected to one of the PH Committees in southeastern Liberia, saved the credibility of the Committee and the entire PH process by confessing his participation in the civil war and disqualifying himself to serve on the committee that was being restructured in his district. The lesson is that, had the ethnographic study forums conducted for the 4 language groups of the country not generated the "Guiding Principles of the Palava Hut", one of which prohibits individuals who participated in the war from serving on the committees, the peacebuilding process in the context of the PH could have unintentionally lost credibility and relevance. |
| Lesson 4 (1000 character limit) |  |
| Lesson 5 (1000 character limit) |  |

2.2 Success story (OPTIONAL)

Provide one success story from the project implementation which can be shared on the PBSO website and Newsletter as well as the Annual Report on Fund performance. Please include key facts and figures and any citations (3000 character limit).

A 3-man team from the Project Management Unit (PMU) traveled to Grand Kru County in early April 2016 to restructure the PH Committee earlier established in Barclayville District. A stakeholders forum was convened at the Barclayville City Hall to restructure the Committee. With the opening of the the occasion done, the Project team informed the over 40 participants that there was no "sitting fees" (financial rewards) to be given at the close of the exercise.  In response, the then newly endorsed Paramount Chief of the Barclayville Chiefdom, Karmbor Nyanplu, regretably declared that it would have been needless for him and others to have turned out for the occasion, had they been told beforehand that would not be any financial benefits. But rather than dampened the enthusiasm of the attendees, which might have been his intent, his statement rather provoked the opposite. Many participants countered that addressing the wrongs of the war and fostering reconciliation and lasting peace in the county and Liberia in general through the Palava Hut was a lot more important than being compensated for attending the meeting. All attendees fully committed themselved to support the Palava Hut process in the absence of monetary rewards. The  occasion was successful with the highest number of participants. Given the depth of the issue and the importance that affeted members of society place on reconciliation, the PH has been overall successful is embedding an overall sense of community volunteerism to the PH process.

PART 3 – FINANCIAL PROGRESS AND MANAGEMENT ARRANGEMENTS

  - Comments on the overall state of financial expenditure

Please rate whether project financial expenditures are on track, slightly delayed, or off track:

If expenditure is delayed or off track, please provide a brief explanation (500 characters maximum):

Please provide an overview of expensed project budget by outcome and output as per the table below.

| Output number | Output name | RUNOs | Approved budget | Expensed budget | Any remarks on expenditure |
| --- | --- | --- | --- | --- | --- |
| Outcome 1: |  |  |  |  |  |
| Output 1.1 | Output:1 INCHR capacity strenthened to lead and coordinate the National Palava Hut Program | UNDP | 60,000 | 60,000 |  |
| Output 1.2 | Output:2 Studies conducted and Palava Hut methodology and operational guidelines developed | UNDP | 374,579 | 207248 |  |
| Output 1.3 | Output 3: Nationwide outreach conducted on the Palava Hut Programme | UNDP | 150,000 | 100,000 |  |
| Outcome 2: |  |  |  |  |  |
| Output 2.1 | Output 4: Palava Hut process piloted in 2 communitie | UNDP | 200,000 | 100,000 |  |
| Output 2.2 | Output 5: At least two Regional Memorials constructed in hard hit war affected communitie | UNDP | 150,000 | 120,000 |  |
| Output 2.3 |  |  |  |  |  |
| Outcome 3: |  |  |  |  |  |
| Output 3.1 |  |  |  |  |  |
| Output 3.2 |  |  |  |  |  |
| Output 3.3 |  |  |  |  |  |
| Outcome 4: |  |  |  |  |  |
| Output 4.1 |  |  |  |  |  |
| Output 4.2 |  |  |  |  |  |
| Output 4.3 |  |  |  |  |  |
| Total: |  |  |  |  |  |

  - Comments on management and implementation arrangements

Please comment on the management and implementation arrangements for the project, such as: the effectiveness of the implementation partnerships, coordination/coherence with other projects, any South-South cooperation, the modalities of support, any capacity building aspect, the use of partner country systems if any, the support by the PBF Secretariat and oversight by the Joint Steering Committee (for PRF only). Please also mention if there have been any changes to the project (what kind and when); or whether any changes are envisaged in the near future (2000 character maximum):

The implementing partners of the project have demonstrated appreciable effectiveness. However, delay in preparation and approval of AWPs and Procurement and M&E Plans, coupled with the slow UNDP procurement processes, sometimes affect progress of project implementation. The Palava Hut Committees include some members of the County Peace Committees established by the Ministry of Internal Affairs as a way of building synergies. The project funded two study tours to Sierra Leone and Rwanda related to the South-South Corporation. The project envisages the incorporation of important new interventions complementary to the present interventions. They include: 1. Support to survivors carrying war-related particles in their bodies and appearing for Palava Hut (PH) hearings; 2. Community cleansing ceremonies; 3. Mainstreaming human rights concept in PH processes; 4. Conduct of perception survey to determine the percentage of citizens in target communities who are positive about reconciliation; 5. Victims-Offenders Mediation; and 6. Follow up on implementation of key TRC recommendations by responsible government institutions         .

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to “Project ID” on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed.

Please note that financial information is preliminary pending submission of annual financial report to the Administrative Agent.