RUNO END PRF PROJECT REPORTING					TEMPLATE 4.5

PEACEBUILDING FUND (PBF)

END OF PROJECT report

COUNTRY: Yemen

REPORTING PERIOD: July 2014 – December 2016

| Programme Title & Project Number |  |
| --- | --- |
| Programme Title: PBF/YEM/D-1 Joint Emergency Capacity Development Support to National NGOs working in communities affected by conflict’ Programme Number (if applicable) MPTF Office Project Reference Number: 00091370 |  |  |

| Recipient UN Organizations |  | Implementing Partners |
| --- | --- | --- |
| List the organizations that have received direct funding from the MPTF Office under this programme: UNDP |  | List the national counterparts (government, private, NGOs & others) and other International Organizations: Ministry of Planning and International Cooperation, Ministry of Social Affairs and Labour (Government), WFP, UNICEF and UNFPA (United Nations) Humanitarian Forum (CSO) Social Fund for Development (Quasi-governmental) |
| Programme/Project Budget (US$) |  | Programme Duration |
| PBF contribution (by RUNO) USD 1,000,000 |  |  | Overall Duration (months) |  |
|  |  |  | Start Date (dd.mm.yyyy) 25.07.2014 |  |
| Government Contribution (if applicable) |  |  | Original End Date (dd.mm.yyyy) | 31.7.2016 |
| Other Contributions (donors) (if applicable) USD 457,596 |  |  | Final End date(dd.mm.yyyy) 1.12.2016 |  |
| TOTAL: | SD 1,457,596 |  |  |  |

| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| --- | --- | --- |
| Mid-Term Evaluation / Review - if applicable please attach Yes No Date: End of project Evaluation– if applicable please attach Yes No Date: |  | Name: Rawhi Afaghani Title: Project Manager Participating Organization (Lead): UNDP Email address: awhi.afaghani@undp.org |

PART 1 – RESULTS PROGRESS

  - Assessment of the project implementation status and results

For PRF projects, please identify Priority Plan outcome and indicators to which this project has contributed:

Priority Plan Outcome to which the project has contributed. Strengthened social cohesion at the sub-national and community level increases resilience to conflict

Priority Plan Outcome indicator(s) to which project has contributed. Indicator 1: Number of NGOs accredited by the project as sustainable, reliable and professional partners for the Government of Yemen, UN Agencies and international partners. Indicator 2: number of projects implemented by trained GB NGOs by end of December 201

For both IRF and PRF projects, please rate this project’s overall achievement of results to date:

For both IRF and PRF projects, outline progress against each project outcome, using the format below. The space in the template allows for up to four project outcomes.

Outcome Statement 1:  Governorate Based NGOs (GB NGOs) in Yemen are sustainable, reliable and professional partners, for the Government of Yemen, UN agencies and international partners  and thus increase the national capacity to: deliver aid to in need that cater to the distinct needs of  men, woman, girls and boys in need.

Rate the current status of the outcome:

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

Output 1:

- 140 members from 24 GB NGOs in 7 priority governorates were trained on: Basics of Development Work, Basics of Principles in Management, Project Cycle Management and Developing Fund Raising, Proposal writing and Simplified Accounting System. 31 NGOs provided relief and recovery respond during the war.

- Delivered training on three thematic areas in conflict sensitive approaches to (i) humanitarian assistance, (ii) early recovery and (iii) conflict-sensitive development. This included: Assessment of  153 NGOs, training manuals on the three thematic areas, trained 126 members of 66 NGOs in six governorates.

Output 2:

Awarded 12 small grants in the targeted governorates for the sum of $74,257.00. All project are implemented.

Output 3:

Lunched an online pool to build NGOs' coalitions and networks.

Output 4

Project planning and budgeting finalized and all monitoring and evaluation events finalized.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

Due to the eruption of the war in Yemen the project activities were suspended in second quarter of 2015. UNDP received No-Cost-Extension from PBSO and was able to resume the project activities in May 2016. In the new plan, UNDP focused its interventions on: (i) building the capacity of GB NGOs; (ii) providing them with small grants; and (iii) creating an online platform to facilitate networking and partnership. The project implanted its activities in six governorates: Sa’ada, Abyan, Hajjah, Sanaa, Aden and Taiz.

Despite the eruption of war and suspension of the project, GB NGOs that attended training courses during the first phase (prior to the war) of the project have made considerable progress in playing an active role in the emergency relief phase as well as in building capacities of IDPs families and, generally speaking, in bringing peace and stability to their areas of origin despite the heavy armed clashes and intra-governorate (i.e. Abyan, Amran) as well as inter-governorate (i.e. Hajja and Ibb) mass displacement. At least 31 out of 82 NNGOs that were trained early 2015 have been actively supporting relief and recovery response in the face of outspread conflict, the absence of local authorities - including security bodies – lack of resources, and lack of relief/recovery interventions by the Government of Yemen or other INGOs and UN Agencies. Additionally, during the second phase of the project at least 12 GB NGOs in 6 governorates implemented conflict-sensitive projects through small grands scheme.

At the end of the project, the project delivered the following concrete achievements:

- 140 persons (women and men) from 24 GB NGOs in 7 priority governorates (Hajja, Aden, Ibb, Abyan, Saada, Socotra and Hadramout) were trained on: Basics of Development Work, Basics of Principles in Management, Project Cycle Management and Developing Fund Raising, Proposal writing and Simplified Accounting System. 31 NGOs provided relief and recovery respond during the war.

- Delivered training on three thematic areas in conflict sensitive approaches to (i) humanitarian assistance, (ii) early recovery and (iii) conflict-sensitive development. This included:

-- Assessment of  153 NGOs in the six targeted governorates to identify the most qualified/active NGOs and their needs for training.

-- Produced and tested training manuals on the three thematic areas.

-- Trained 126 members of 66 NGOs in six governorates

- Awarded 12 small grants in the targeted governorates for the sum of $74,257.00. The implemented projects focused on community peacebuilding including women support in IDP camps, community dialogue, youth economic empowerment, support of women household, etc.

- Lunched an online pool to build NGOs' coalitions and networks to effectively share information and resources for better conflict-sensitive humanitarian deliver, early recovery and development.

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

Low achievements with respect to the pre-training can be traced to the suspension of activities following the escalation of the conflict in April 2015. The security conditions of the country deteriorated rapidly,  which greatly increased issues of access and safety for conducting the trainings and other activities. While conflict itself would have undoubtedly contributed to low achievement, the project team had found mechanisms to mitigate these effects through deployment of local actors and mobilization of community-based resources, expertise and solutions. Most of NGOs targeted by the project have reported feeling more motivated thanks to the project training to keep working even during the hardest phases of the conflict. To ensure continued project functionality, measures taken by the project included the revision of locally available training manuals, updated to suit the project objectives, in addition to expanding the roster of potential local trainers. The project further revised the training plan for core training courses, selecting comparatively safer venues to hold the training.

Outcome Statement 2:

Rate the current status of the outcome:

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

Outcome Statement 3:

Rate the current status of the outcome:

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

Outcome Statement 4:

Rate the current status of the outcome:

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

  - Assessment of project evidence base, risk, catalytic effects, gender at the end of the project

| Evidence base: What was the evidence base for this report and for project progress? What consultation/validation process has taken place on this report (1000 character limit)? | - The training component of the project is evidenced by the result of conducted survey in the six governorates to assess the NGOs and the three produced training manuals in the thematic areas of humanitarian core values, early recovery and conflict-sensitive development. Training is also evidenced by 266 trained members of 90 NGOs in total and received certificate. - Small grants -12 NGOs participated in the training received small grants. - Supporting evidence for the online pool is the webpage reachable at http://www.yngosonlinepool.org/ar/. - Evidence for hiring staff includes TORs and interview scoring. - For budgeting our implementing partner submitted budget and plans for the project remainder. - For monitoring the project, in addition to meetings agendas and minutes, interviews’ scoring and collected products (assessment report, manuals for training, training report), the project team conducted two fields visit since the project was restarted in June. |
| --- | --- |
| Funding gaps: Did the project fill critical funding gaps in peacebuilding in the country? Briefly describe. (1500 character limit) | The aimed of the project is to build the capacity of NGOs in specific thematic areas so that they can help mitigate local conflicts. The importance of the project is recognized by stakeholders in Yemen, especially in the current conflict situation, as it equips credible and capable NGOs with conflict mitigation, prevention and sensitive skills that they can adopt and replicate to implement high quality and conflict-sensitive projects, in partnership with international humanitarian and development actors. Scarcity of qualified implementing partners on the ground is one of the main constraints to the delivery of conflict sensitive assistance, in particular in the areas targeted by the project. |
| Catalytic effects: Did the project achieve any catalytic effects, either through attracting additional funding commitments or creating immediate conditions to unblock/ accelerate peace relevant processes? Briefly describe. (1500 character limit) | Right from the beginning the project attracted other sources of funding (OCHA US$ 457,596) and in kind contributions from SFD, UNFPA, WFP, UNICEF. Furthermore, the implementing partner contributed with their own funding to maintain the online pool for 6 months beyond the project lifecycle. Additionally, as a result of field visit to Saada and Hajjah, the project team agreed with the local authorities to help further train local NGOs on conflict sensitive humanitarian delivery, early recovery and development. In that regard, our local partner agreed to provide in kind support (facilities, trainers, management, etc.) to train 40 trainers (from the six targeted governorates) on the three manuals to help training other local NGOs. Most importantly, some impact is seen particularly in forming partnership between NGOs and the local "de-facto" authorities in the effort to help IDP in some governorates. For example, UNDP project staff held individual meetings with local authority and representatives from NGOs in Hajjah Governorate to explain the project and the intentions behind the program. The NGOs agreed that collaboration with local authorities has been effective over humanitarian assistance. Both side have also reported to UNDP staff that they are keen to collaborate to allow the delivery of the training through this project to targeted NGOs. They added the training will increase their capacity to deal with humanitarian crisis, particularly with IDPs. |
| Risk taking/ innovation: Did the project support any innovative or risky activities to achieve peacebuilding results? What were they and what was the result? (1500 character limit) | The security conditions of the country are deteriorating which is greatly increasing issues of access and safety for implementing activities. In September, new procedures introduced by Ministry of Foreign Affairs demanding that UN Agencies request prior written approval for holding any activity. Consequently, National Security barged into the event venue of one of the training and asked to stop the training. The new procedures risked delaying the implementation of the rest of the activities, which was taking place in November and December. The project team submitted a request and received an approval from the ministry to continue the training. The ministry provided the approval and the training continued. Additionally, UNDP introduced internal procedures on how to request the approval. Moreover, following field visits by the Project Team, it was realized that there was a need to conduct TOT in each targeted governorate so that other NGOs that could not participate in the training receive the training on the three thematic areas. In this regard, a budget revision was made and funds of $21,000 have been allocated to support a TOT training on the three thematic areas of training. |
| Gender marker: How have gender considerations been mainstreamed in the project to the extent possible? Is the original gender marker for the project still the right one? Briefly justify. (1500 character limit) | Gender mainstreaming was taken into consideration from the very design phase of the project to make sure that both men and women would meaningfully participate at the training activities. During phase I, 50 % of trained participants were female. Reports from Amran and Ibb showed that our trained NGOs implemented projects dealing with creating safe and friendly environment for women and children from IDPs families. In phase II of the training, out of 126 trained NGO participants, 54 women (43%) were trained and out of the 66 NGOs trained in six governorate, 14 NGOs are women-focused. Reports from Taiz, Sana’a, Abyan and Aden showed that the small grants awardees are implementing projects dealing with improving economic opportunities for women head of households and mitigating the psychological and economic war's impact on IDP women and women from the host communities. |
| Other issues: Are there any other issues concerning project implementation that should be shared with PBSO? This can include any cross-cutting issues or other issues which have not been included in the report so far. (1500 character limit) | Following the resumption of the project activities in May 2016, it became clear that the project strategies and activities are very relevant to the current NGOs’ need to help in humanitarian relief, peacebuilding and early recovery efforts in Yemen. Although the project reached considerable number of beneficiaries in 6 governorates, the project team highly recommend that UNDP/PBSO fund another round of the training activities in other or same governorates with more NGOs’ participants. It is imperative to offer the training to other NGOs who participated in the pre-training who were not able to participate at the thematic training such as NGOs from Amran, Al-Baida'a, Ibb, Hadramout and Socatra. In addition, NGOs from other governorates that are directly experiencing armed conflict or post-conflict such as Lahj, Shabwa, Mareb and Aljouf should be included in such initiative. This should also be coupled with TOT training for participants who could not join. Any further capacity development for NGOs in Yemen should be joined with other projects that directly target livelihoods and peacebuilding efforts. Local humanitarian, development and peacebuilding initiatives in Yemen require the support of civil society organizations, which entail building up their institutional capacities and knowledge in conflict-sensitive humanitarian delivery, early recovery and development |

1.3 INDICATOR BASED PERFORMANCE ASSESSMENT: Using the Project Results Framework as per the approved project document- provide an update on the achievement of key indicators at both the outcome and output level in the table below. Where it has not been possible to collect data on indicators, state this and provide any explanation in the qualitative text above. (300 characters max per entry)

|  | Performance Indicators | Indicator Baseline | End of project Indicator Target | Current indicator progress | Reasons for Variance/ Delay (if any) | Adjustment of target (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 Governorate Based NGOs (GB NGOs) in Yemen are sustainable, reliable and professional partners, for the Government of Yemen, UN agencies and international partners and thus increase the national capacity to: deliver aid to in need | Indicator 1.1 # GB NGOs accredited by the project as sustainable, reliable and professional partners for the Government of Yemen, UN Agencies and international partners. | Insufficient and poorly qualified GB NGOs partners. UN and INGO implementers consultants refer to weakness of local partner as well as the spread of social conflict including violence conflict as the major constraints in absorbing the foreign fund. | UN and INGOs have high caliber GB NGO partners in 6 priority governorates by end of 2016 | Finalized |  |  |
|  | Indicator 1.2 # Projects implemented by trained GB NGOs by end of December 201 | Insufficient and poorly qualified GB NGOs partners. | One conflict-sensitive project implemented in each targeted governorates | On Track |  |  |
|  | Indicator 1.3 |  |  |  |  |  |
| Output 1.1 Governorate based NGOs (GB NGOs ) in priority conflict affected governorates have the capacity to implement high quality conflict sensitive projects. | Indicator 1.1.1 -NGOs Assessment report - 3 Manuals on three thematic areas (humanitarian assistance, early recovery and conflict-sensitive development) produced | - No assessment of NGOs capacities done following the resumption of the project, a year after start of war. - Collection of existing training manuals produced by UNDP and others on the three thematic areas | - 120 NGOs in six governorates has been assessed -Three manuals on thematic areas produced | - Completed assessment report - Completed and tested 3 manuals on the three thematic areas. |  |  |
|  | Indicator 1.1.2 - # of NGOs trained in six governates -Automated accounting system established within selected GBNGOs | - Numerous NGOs mainly based at the governorates level, have weak capacity in general and absence in many key geographical areas. | - 40 GBNGOs in at least 4 governorates accredited as professional partners - Automated Accounting System is developed and installed on at least 30 GBNGOs - TOT conducted | - 24 out of original suggeted 40 NGOs received the Pre-traing - Completed training of 126 participants from 66 NGOs in 6 governorates. - Completed TOT of 45 participants - Automated accounting software is on track |  |  |
| Output 1.2 GBNGOs implement peacebuilding and conflict sensitive interven | Indicator 1.2.1 # of peacebuilding and conflict sensitive projects implemented by NGOs | NGOs have limited capacity to deliver conflict-sensitive projects and manage resources | At least 6 peacebuilding and conflict sensitive projects implemented in project target governorates | 12 NGOs out of 52 applicants have been awarded grants and started implementing projects in the six targeted governorates |  |  |
|  | Indicator 1.2.2 |  |  |  |  |  |
| Output 1.3 An online pool of accredited GBNGOs will be established to facilitate partnerships of GBNGOs with the government, national and international development and humanitarian agencies. ---------------- Output 1.4 Management and monitoring of the project. | Indicator 1.3.1 # of NGO and INGO profiles present in the pool and number of users registered for the online pool | No online pool with information on sustainable, reliable and professional partners | Sustainable online pool is established in consultation with potential users and functioning | Online pool completed - designed and lunched http://www.yngosonlinepool.org/ar/ |  |  |
|  | Indicator 1.3.2 ----------------------- Indicator 1.4.1 - Project staff recruited -Implementing Partner monthly report -Field visits by Project team | ---------------- Following the resumption of the project in July 2016 needed to hire staff to resume the activities | ----------------- Staff hired and delivered all activities -7 monthly report by Partner - 2 field visits | ----------------------- - Completed - All project staff hired - All progress reports received by project manager - Project team conducted two field visit to Hajjah and Sa’ada and met with local authorities and representatives of NGOs that have selected for t |  |  |
| Outcome 2 | Indicator 2.1 |  |  |  |  |  |
|  | Indicator 2.2 |  |  |  |  |  |
| Output 2.1 | Indicator 2.1.1 |  |  |  |  |  |
|  | Indicator 2.1.2 |  |  |  |  |  |
| Output 2.2 | Indicator 2.2.1 |  |  |  |  |  |
|  | Indicator 2.2.2 |  |  |  |  |  |
| Output 2.3 | Indicator 2.3.1 |  |  |  |  |  |
|  | Indicator 2.3.2 |  |  |  |  |  |
| Outcome 3 | Indicator 3.1 |  |  |  |  |  |
|  | Indicator 3.2 |  |  |  |  |  |
| Output 3.1 | Indicator 3.1.1 |  |  |  |  |  |
|  | Indicator 3.1.2 |  |  |  |  |  |
| Output 3.2 | Indicator 3.2.1 |  |  |  |  |  |
|  | Indicator 3.2.2 |  |  |  |  |  |
| Output 3.3 | Indicator 3.3.1 |  |  |  |  |  |
|  | Indicator 3.3.2 |  |  |  |  |  |
| Outcome 4 | Indicator 4.1 |  |  |  |  |  |
|  | Indicator 4.2 |  |  |  |  |  |
| Output 4.1 | Indicator 4.1.1 |  |  |  |  |  |
|  | Indicator 4.1.2 |  |  |  |  |  |
| Output 4.2 | Indicator 4.2.1 |  |  |  |  |  |
|  | Indicator 4.2.2 |  |  |  |  |  |
| Output 4.3 | Indicator 4.3.1 |  |  |  |  |  |
|  | Indicator 4.3.2 |  |  |  |  |  |

PART 2: LESSONS LEARNED AND SUCCESS STORY

2.1 Lessons learned

Provide at least three key lessons learned from the implementation of the project. These can include lessons on the themes supported by the project or the project processes and management.

| Lesson 1 (1000 character limit) | - Strengthening NGOs capacities in a highly volatile security environment implies high risks, but mainly requires the donors’/UNDP’s consistent and clear aim of building up NGOs capabilities to become viable partners on the ground. - NGOs are put under high risk during the war and are being targeted by all parties involved in the conflict. The donors and UNDP should lunch a dialogue between NGOs, the donors/UNDP and local government officials to insure NGOs’ safety and effectiveness of delivery. |
| --- | --- |
| Lesson 2 (1000 character limit) | - It was difficult to find the required number of organizations with adequate technical capacities. Introduction of a pre-training made it possible to upgrade the skills of weaker organizations and qualify them for the core trainings. These strategies were adopted and conducted during the first phase, 24 weak NGOs from 7 governorates were qualified during pre-training workshops held in March 2015. - Due to the short time period of Phase I of the project, there was no time for evaluating the practical application of the learning or providing on job support /mentoring. Trainings in Phase II was relatively sufficient to give time for applying learning during practical work within the organization. Also, time has been allocated for providing grants for implementation of projects, providing on job support, mentoring, etc. |
| Lesson 3 (1000 character limit) | - Training materials: More time should have been given to prepare the manuals and test them in the field to receive feedback. Although a six-day work shop was held with the trainers, the ToR of the consultant that prepared the manuals should include more methods for researching and test the manuals. Additionally, while the conducted NGOs’ capacity assessment informed the manual, the consultant that produced the manuals should have been also involved in the assessment. - Training: It was noticed during the training that the institutional capacity of NGOs from Aden and Abyen is weaker compared to other NGOs from other governorates. These NGOs needed more basic (institutional, financial, management) training to build their capacity. |
| Lesson 4 (1000 character limit) | TOT training: To select participants for the TOT training, our implanting partner gave priority to those who participated in the thematic training with high scores and based on their trainers’ recommendations and good resume. Additionally, to make sure that more NGOs are trained as TOT, we agreed with our partners not to select two participants from the same NGO even if they both have high scores. This method of selecting participants for TOT, however, led to disparity of skills between the participants, which was reflected during the TOT training. Thus, the selection processes should have been only based on scoring since the target is to build capacities on a governorate level. -NGOs’ proposal for small grants: The short time reflected in the project plan led to pushing the NGOs to submit their project before finalizing the training on early recovery. This led to receiving more proposals in the areas of humanitarian delivery and conflict sensitive development |
| Lesson 5 (1000 character limit) | - Though coordination at the sub-national level was critical to the success and quality of trainings. Partnership and work distribution was a key managerial component. However, there was no document making clear the roles and responsibilities of partners. This lead to certain difficulties during implementation. MOUs (with clear roles and responsibilities) have been developed and has been signed between SFD and HFY and other partners. |

2.2 Success story (OPTIONAL)

Provide one success story from the project implementation which can be shared on the PBSO website and Newsletter as well as the Annual Report on Fund performance. Please include key facts and figures and any citations (3000 character limit).

"Forgiveness and Coexistence can help us Build peace in our Country

Mr. Mohammed Farea is a representative of a Youth NGO from Taiz governorate who participated at the thematic training program in humanitarian essential competencies, early recovery and conflict sensitivity. Mohammed showed high motivation allowing him to be nominated to participate at the TOT training workshop held between 1-10 November 2016. As a result of the acquired knowledge and skills in the areas of conflict analysis, conflict mitigation and resolution and bringing about community consensus as well as training skills, he was able to plan and implement a training workshop immediately after he had returned to Taiz in the area of peace building and avoiding violent conflict. His training took place near Salah district of Taiz. While Mohammed was conducting the training, violent conflict in nearby area brock out. One of his participants (Mr. G.D.K) asked a permission to leave the training hall, after he had received a phone call informing him that there are two people, accused by the resistant of being collaborators with the Houthi militias, are to be executed. Evidence against them is that the brothers of the two people in custody were fighters with the Houthi rebels and had torture and lynching the father of Mr. G.D.K. When Mohammed asked him why he wanted to leave, he replied "I am going to apply the training concepts in peace building practically in the field."

When Mr. G.D.K went to Salah district after it had been taken over by the resistant, he found the two accused in custody of armed group.  Mr. G.D.K was able to negotiate with the group convincing them to release the two accused explaining that they were not the ones who tortured and lynch his father, but it what their brothers who have already left Salah and Taiz. Mr. G.D.K told the group that he has already forgiven them for what they did for his father."

PART 3 – FINANCIAL PROGRESS AND MANAGEMENT ARRANGEMENTS

  - Comments on the overall state of financial expenditure

Please rate whether project financial expenditures were on track, slightly delayed, or off track:

If expenditure was delayed or off track, please provide a brief explanation (500 characters maximum):

Please provide an overview of project expensed budget by outcome and output as per the table below.

| Output number | Output name | RUNOs | Approved budget | Expensed budget | Any remarks on expenditure |
| --- | --- | --- | --- | --- | --- |
| Outcome 1: Governorate Based NGOs (GB NGOs) in Yemen are sustainable, reliable and professional partners, for the Government of Yemen, UN agencies and international partners and thus increase the national capacity to: deliver aid to in need that cater to the distinct needs of men, woman, girls and boys in need. |
| Output 1.1 | GBNGOs in priority conflict affected governorates have the capacity to implement high quality conflict sensitive projects. |  | 385,460 | 393,775.10 |  |
| Output 1.2 | GBNGOs implement peacebuilding and conflict sensitive interventions in target areas. |  | 45,600 | 42,785.81 |  |
| Output 1.3 | An online pool of accredited GBNGOs will be established to facilitate partnerships of GBNGOs with the government, national and international development and humanitarian agencies. ---------------- Output 1.4 Management and monitoring of the project. |  | 26,250 159,143 | 22,540.46 157,113.27 |  |
| Outcome 2: |
| Output 2.1 |  |  |  |  |  |
| Output 2.2 |  |  |  |  |  |
| Output 2.3 |  |  |  |  |  |
| Outcome 3: |
| Output 3.1 |  |  |  |  |  |
| Output 3.2 |  |  |  |  |  |
| Output 3.3 |  |  |  |  |  |
| Outcome 4: |
| Output 4.1 |  |  |  |  |  |
| Output 4.2 |  |  |  |  |  |
| Output 4.3 |  |  |  |  |  |
| Total |  |  |  |  |  |

  - Comments on management and implementation arrangements

Please comment on the management and implementation arrangements for the project, such as: the effectiveness of the implementation partnerships, coordination/coherence with other projects, any South-South cooperation, the modalities of support, any capacity building aspect, the use of partner country systems if any, the support by the PBF Secretariat and oversight by the Joint Steering Committee (for PRF only). Please also mention if there have been any changes to the project (what kind and when) (2000 character maximum):

Scarcity of qualified implementing partners on the ground is one of the main constraints to the delivery of conflict sensitive assistance, in particular in the areas targeted by the project. The project was fully nationally owned and significantly benefitted from it local implementing partner. They were fully involved in the strategic direction of the project through the joint elaboration of the AWPs and – equally importantly – in the implementation phase. The implementing partner staff had direct access to UNDP project team and worked hand in hand for the completion of the major outputs of the project. It was only thanks to this full integration of the project in the national structures that the project could achieve all of its project’s targets at a time of extreme socio-political and security uncertainty.

Government contributions through the Ministry of Planning and International Cooperation, Ministry of Social Affairs and Labor were in kind and logistical help such as providing lists of potential and accredited National GB NGOs. While Social Fund for Development provided training manuals, lists of potential and accredited trainers and supervising and evaluating the training courses. The project has also sought and achieved close coordination with local authorities, community leaders and, as necessary, de facto authorities.

Although no change was envisaged in the strategy of the project, but since the project has been extended to the end of 2016 it was necessary to revise the activities. The suspension of activities had put the project under strain, both in terms of implementation timeframe and allocation of funds. NGOs are ever more needed under the current humanitarian crisis.

# Footnotes

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to “Project ID” on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed.

Please note that financial information is preliminary pending submission of annual financial report to the Administrative Agent.