RUNO END PF PROJECT REPORTING		TEMPLATE 4.5

PEACEBUILDING FUND (PBF)

END OF PROJECT report

COUNTRY: NEPAL

REPORTING PERIOD: 15 January 2015 to 15 October 2016

| Programme Title & Project Number |  |
| --- | --- |
| Programme Title: IRF-180: Localizing Women Peace and Security Agenda in Central Terai Districts of Nepal Programme Number (if applicable) 00093348 MPTF Office Project Reference Number: |  |  |

| Recipient UN Organizations |  | Implementing Partners |
| --- | --- | --- |
| List the organizations that have received direct funding from the MPTF Office under this programme: UN Women and UNDP |  | List the national counterparts (government, private, NGOs & others) and other International Organizations: National Counterparts: Ministry of Peace and Reconstruction (MoPR), Ministry of Home Affairs (MoHA), Ministry of Federal Affairs and Local Development (MoFALD), Ministry of Finance (MoF) and Local Development Training Center (LDTA) District Counterparts: District Development Committees (DDCs), District Administration Office (DAOs), Women and Children Office (WCO), District Gender Responsive Budget Committees (DGRBC), Nepal Police, CSOs, Inter-Party Women Alliance (IPWA), Women Political leaders, Alliance of Women Rights Defenders, Conflict Affected People’s Network, Local Peace Committees (LPCs) in Bara and Parsa. |
| Programme/Project Budget (US$) |  | Programme Duration |
| PBF contribution (by RUNO) US$ 576,602 |  |  | Overall Duration (months) 21 Months |  |
|  |  |  | Start Date (dd.mm.yyyy) 15.01.2015 |  |
| Government Contribution (if applicable) In kind support |  |  | Original End Date (dd.mm.yyyy) | 15.07.2016 |
| Other Contributions (donors) (if applicable) |  |  | Final End date(dd.mm.yyyy) 15.10.2016 |  |
| TOTAL: | US$ 576,602 |  |  |  |

| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| --- | --- | --- |
| Mid-Term Evaluation / Review - if applicable please attach Yes No Date: February 2016 End of project Evaluation– if applicable please attach Yes No Date: October 2016 |  | Name: Krishna Prasad Bhattarai Title: Programme Officer (Governance) Participating Organization (Lead): UN Women Email address: krishna.bhattarai@unwomen.org |

PART 1 – RESULTS PROGRESS

  - Assessment of the project implementation status and results

For PRF projects, please identify Priority Plan outcome and indicators to which this project has contributed:

Priority Plan Outcome to which the project has contributed. UNPFN Strategic Outcome: SO 6: An inclusive and gender-representative culture of dialogue and conflict transformation is expanded and strengthened, contributing to conflict prevention and social cohesion during Nepal’s transitional peacebuilding process

Priority Plan Outcome indicator(s) to which project has contributed.

For both IRF and PRF projects, please rate this project’s overall achievement of results to date:

For both IRF and PRF projects, outline progress against each project outcome, using the format below. The space in the template allows for up to four project outcomes.

Outcome Statement 1:  Enhanced participatory and gender responsive planning and budgeting processes at the local bodies (VDC, DDC and Municipality) for implementation and monitoring of National Action Plan (NAP) on women, peace and security [UNSCRs 1325 and 1820]

Rate the current status of the outcome:

| Indicator 1: Number of local bodies (DDC, Municipalities and VDCs) that have adopted gender responsive budgeting Indicator 2: Percentage of local budget allocated for directly gender responsive Indicator 3: Meaningful participation of women in local planning and budgeting process | Baseline: DDC =0 Municipality = 0 Target: DDC = 2 Municipality = 2 Progress:Bara DDC and Parsa DDC have formed District Gender Responsive Budget Committees (DGRBC), which hold regular meetings. Kalaiya Municipality and Birgunj Municipality have also recently formed Municipal Gender Responsive Budget Committees (MGRBCs). The Committee members have improved their knowledge and skills on gender-responsive budgeting and its localisation, and expressed commitment to adopt it at the local level. GRB Localisation Strategy was printed and disseminated by MoFALD to DDCs. Baseline: Although GRB classification software was made available in Bara and Parsa DDCs in 2015, such classification is yet to be operationalized for the DDCs. It is expected to be functional by the end of 2016. Target: Increase by 5% in absolute figure in next fiscal year (2016/17) Progress: An analysis of budget allocation of the DDCs and municipalities for GRB classification of current fiscal year is in process. The GRB Localization Strategy was endorsed by the Government of Nepal in 2016 and the first phase of capacity development training/orientation on GRB localization and GRB analysis using the GRB sub-classification criteria was provided to government officials of various local bodies during the project period. Although GRB classification software was made available in Bara and Parsa DDCs in 2015, such classification is yet to be operationalized for the DDCs. The system is expected to be functional by the end of 2016. Baseline: 1) Only some members attend local planning meetings 2) Very few (1-2) raise women’s concerns to be addressed in meetings 3) None of them perceive that their voices are heard and respected 4) A couple of concerns are addressed in the planning document at that level. Target: Significant number of women members from IPWA, WHRD and CAW attend local planning meetings and all of them raise concerns to be addressed in the meetings. Most of the women perceive that their voices are heard and respected. Most of the women agree that their concerns have been addressed in the planning process. Progress:40% of IPWA members and women rights activists (including WHRD and CAW) attended local planning meetings and raised their concerns based on the nine-point shared agenda developed. Four items (reduce sexual and gender based violence; reduce child marriage; reduce dowry system; and implementation of GRB) out of the nine-points shared agenda were incorporated into district annual plans. All IPWA and WHRD members advocated for GRB in local planning meetings. Intensive advocacy efforts by the community led to the integration of community security issues into local body's plans and GRB localization. 15 VDCs and two municipalities of Bara, and 15 VDCs of Parsa districts allocated a total budget of NPR 38,000,000 for women, children, and security issues and integrated the community security plan into the local body planning. |
| --- | --- |

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

Knowledge and skills improved for 1,216 staff (391 women, 825 men) of DDCs, sectoral line agencies, NGOs and women leaders on GRB, NAP on UNSCRs 1325/1820 and their localisation through 40 capacity development trainings. Dialogue and advocacy skills improved for 68 IPWA female leaders and 79 women rights activists, who became better equipped to raise their concerns at the local level,based on nine-point shared agenda that they developed. Four from the nine-point agenda incorporated into district  plan. Security issues of the most vulnerable groups of women were identified through 60 KIIs and 42 FDGs in 30 VDCs with 344 women and 308 men community members. Four community security plans were developed through VDC consultations with 798 participants (423 women, 375 men) including 25 police personnel and integrated into the local body plans. As a result of advocacy campaign, 30 VDCs and two municipalities allocated a total budget of NPR 38,000,000 for women, children, and security issues.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

With the knowledge and skill enhanced on the localisation of GRB and NAP, the officials of the local bodies including DDC, Municipalities, VDCs, DGRBCs and DDCs have shown commitment to institutionalise GRB and integrate it in the 14-step planning process. GRB Localisation Strategy was printed and disseminated by MoFALD to DDCs. The two DGRBCs are functional and hold regular meetings. Furthermore, two municipal GRBCs have been formed. Local government have expressed commitment to implement the action plan developed as per the findings of GESI audit conducted at one DDC, three VDCs, one sub-metropolitan and one municipality for making policies, plans and programmes of the local bodies more gender-responsive.

The project has noted a positive impact on peacebuilding by strengthening the integration of local security issues and community security action points into local body planning and budgeting processes. Enhancing knowledge and skill of service providers on gender-responsive local planning and budgeting was found instrumental in motivating them to allocate and spend more of their budget on women, children, and security issues. The local political leaders and women’s rights activists engaged with the local bodies continue lobbying for the allocation of budget for women and community securities issues. Due to the advocacy efforts to integrate community security plans into local body plans and to localise gender-responsive budgeting and implement UNSCRs 1325 and 1820 at the local level, 30 VDCs and 2 municipalities of Bara and Parsa districts allocated a total budget of NPR 38,000,000 to promote community security for women and children and prevent gender-based violence.

Nepal police officers regularly interacted and carried out joint activities with the community, thus increasing the feelings of trust and security in the communities.

Consultations with political party leaders on NAP on UNSCRs 1325/1820 reinforced their understanding about the resolutions’ role in ensuring women's participation and leadership in peacebuilding.

The dialogue, advocacy and negotiation skills of about five dozen district level women leaders enhanced for gender-responsive local development. With these skills and increased confidence, they adopted a systematic approach for raising their concerns. All the IPWA, District alliance of Women Rights Activists (DAWRA), Federation of Dalit Women, Conflict Affected Women and WHRD members advocated for GRB during the local planning period. Three women-led networks (IPWA, DAWRA and WHRD) in each district have been fully functional and have developed nine-point shared agenda, in both districts,on gender-responsive planning and budgeting as well as addressing gender inequality, violence against women and other challenges experienced by women in the districts. Four from the nine-point agenda incorporated into district  development plan.

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

Some notable and unforeseen challenges were faced during the project period. The project activities remained suspended for almost three months following the devastating earthquakes in April and May 2015. Although the programme districts were not directly hit by the earthquakes, the priority of the Government of Nepal shifted to immediate humanitarian assistance to earthquake survivors. Further, due to the political unrest in Terai following the promulgation of the Constitution in September 2015, many planned activities were temporarily halted until the first week of February 2016. Given the extremely challenging environment during the project implementation, a no-cost extension was required.

To review the impact of the situation on project implementation and to analyze the operational space on the ground, UN Women, UNDP and UNPFN held joint meetings and prepared a four-month (December 2015 - March 2016) contingency plan covering risks, mitigation measures and alternative ways of implementation, and adopted a strategy to expedite project implementation. Following a request to the UNPFN, a no-cost extension until 15 October 2016 was granted to provide additional time to complete the remaining activities.

Outcome Statement 2:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

Outcome Statement 3:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

Outcome Statement 4:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?



Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

  - Assessment of project evidence base, risk, catalytic effects, gender at the end of the project

| Evidence base: What was the evidence base for this report and for project progress? What consultation/validation process has taken place on this report (1000 character limit)? | The evidence base consists of : District/VDC annual plans, activity/event completion reports including capacity assessment report (pre-post tests), action plans/shared agendas of women-led networks, community security plans, project's mid-term review report that includes results of KIIs, FGDs and consultations with key stakeholders as well as the context analysis report. |
| --- | --- |
| Funding gaps: Did the project fill critical funding gaps in peacebuilding in the country? Briefly describe. (1500 character limit) | This funding supported peacebuilding initiatives by bridging the gap between the supply side and the demand side of the chain by enabling grassroots women's voice and agency to influence local planning processes. The project enabled the allocation of local resources through the application of GRB to enhance the implementation of the NAP on UNSCR 1325. This project ensured continuity and up-scaling of efforts on women, peace and security, supported previously by the UNPFN under EPST project. |
| Catalytic effects: Did the project achieve any catalytic effects, either through attracting additional funding commitments or creating immediate conditions to unblock/ accelerate peace relevant processes? Briefly describe. (1500 character limit) | The project was successful in obtaining written commitments from 15 VDCs and two municipalities in Bara and 15 VDCs in Parsa to allocate and spend NPR 38,000,000 in 2016 for women, children, and security issues. This was for the first time that the VDCs and municipalities allocated a budget of this amount (10% of total budget) for women, children and security issues in Bara and Parsa districts. |
| Risk taking/ innovation: Did the project support any innovative or risky activities to achieve peacebuilding results? What were they and what was the result? (1500 character limit) | The focus on strengthening the capacities of both local civil society organizations (including on collaborative leadership and participatory security planning) and local governance structures on gender-responsive planning and budgeting as a way to localize the NAP on UNSCRs 1325 and 1820 served as an important pilot, testing the replicability of the model in other areas of Nepal. This responds to the NAP mid-term review finding about the local level NAP implementation being more efficient if the budget, focus of work and roles are distributed through a one-door system. |
| Gender marker: How have gender considerations been mainstreamed in the project to the extent possible? Is the original gender marker for the project still the right one? Briefly justify. (1500 character limit) | Gender equality (GE) is a key area of focus in this project. GE is a central to project implementation. In terms of gender marker, the project is categorized at its highest level, i.e. #3. The project has been engaging men in the community to prepare the community security plans to address violence against women and girls. Gender Responsive Budget Committees have been formed at the DDC and the Municipality level. An analysis of budget allocation of DDCs and Municipalities for GRB classification of current fiscal year is in process. |
| Other issues: Are there any other issues concerning project implementation that should be shared with PBSO? This can include any cross-cutting issues or other issues which have not been included in the report so far. (1500 character limit) | There was an estimated saving of USD 75,000 form personnel, programme and travel costs under the UN Women component of GPI-CT project, which was transferred to UNDP to implement the project on ''Strengthening Social Cohesion through Support to the Women, Peace and Community Security Agenda in Bara and Parsa''. The project contributed to strengthening the gains achieved under the ongoing community security initiatives including awareness raising on violence against women. An exit strategy has been developed and partner organisations have committed to implement the exit strategy for sustaining the gains of the project. Right Direction Nepal Pvt. Ltd. conducted the final evaluation of the GPI-CT project from 1 August - 7 October 2016. The key findings of the evaluation are as follows: •The project has aligned its activities with 14 step planning process of Government of Nepal to integrate women, peace and security agendas. •The project is relevant for the gender responsive planning and budgeting process to contribute to peace building needs of the project districts. •The project has contributed in establishing the knowledge hub on GRB and national action plan on UNSCRs 1325 and 1820 at national and sub-national level. The evaluation team recommended expansion of similar initiative like GPI-CT project with some adjustments based on the local contexts of target project areas. |

PART 2: LESSONS LEARNED AND SUCCESS STORY

2.1 Lessons learned

Provide at least three key lessons learned from the implementation of the project. These can include lessons on the themes supported by the project or the project processes and management.

| Lesson 1 (1000 character limit) | The regular support and guidance from and monitoring by MoFALD, and the coordination and collaboration amongst the line ministries including MoFALD and MoF are necessary to institutionalise and localize GRB application in the districts and make the DGRBCs functional. It is important for MoFALD to make further arrangements for refresher training and orientation, and provide necessary support to DDCs for the effective implementation of GRB Localization Strategy in the future. Support from LDTA and UN Women will be instrumental for this. |
| --- | --- |
| Lesson 2 (1000 character limit) | GRB training/orientations need to be provided widely to all sectors and groups of people to support GRB localization as most of the government officials, civil society, and community people are unaware about the GRB concept, classification system and its practical implementation. |
| Lesson 3 (1000 character limit) | Creating community-police partnership, where local community members can identify and prioritise security issues together with the police and take joint action, enhances the feeling of mutual trust and security at the local level. |
| Lesson 4 (1000 character limit) |  |
| Lesson 5 (1000 character limit) |  |

2.2 Success story (OPTIONAL)

Provide one success story from the project implementation which can be shared on the PBSO website and Newsletter as well as the Annual Report on Fund performance. Please include key facts and figures and any citations (3000 character limit).

The female political leaders and women rights activists of Bara district collectively developed a nine-point shared agenda vis-à-vis gender-responsive planning and budgeting, which aims to address the challenges that the women in the district face. The leading women activists affiliated with Inter-Party Women Alliance (an umbrella organization of women leaders affiliated with major political parties) and Unified Alliance of Women Rights Activists agreed to act together for the first time so as to: institutionalize gender-responsive budgeting system; increase the women’s representation by 30% within a year in district level executive committees of political parties and social organizations; ensure at  least one-third representation of women in upcoming local election; reduce the incidents of dowry malpractices and domestic violence against women by 25% across the district; declare three VDCs as free of witchcraft incidents; and declare ‘Kolhawi Municipality’ as alcohol-free zone in a year, among others.

After the formulation of the shared agenda, former State Minister for Land Reform, Member of Constituent Assembly and Politburo Member of CPN-Maoist (Centre) Jwala Shah said, “The leading women activists of Bara have identified the common issues and goal for the first time for women’s empowerment and gender equality. I will actively lead and mobilize the political front to translate our shared agenda into action.” Focusing on the shared agendas, an interactive dialogue was held between district level government line agencies and women political leaders and women rights activists in Bara. The dialogue resulted in consensus on building a safe house with funds allocated from government’s budget in the district headquarters by 2017. The safe house will provide rehabilitation and protection facilities to the women survivors of sexual and gender-based violence and/or the displaced women. In the programme, Local Development Officer (LDO) said, “District Development Committee and other line agencies will take the shared agenda into account during upcoming annual planning and budgeting process and building safe house in the district is urgent. Therefore, construction of safe house will be initiated from current year’s programme and budget.” The government officials and the women leaders agreed to carry out coordinated efforts to enhance women’s participation in governance process and GRB localization.

PART 3 – FINANCIAL PROGRESS AND MANAGEMENT ARRANGEMENTS

  - Comments on the overall state of financial expenditure

Please rate whether project financial expenditures were on track, slightly delayed, or off track:

If expenditure was delayed or off track, please provide a brief explanation (500 characters maximum):

Please provide an overview of project expensed budget by outcome and output as per the table below.

| Output number | Output name | RUNOs | Approved budget | Expensed budget | Any remarks on expenditure |
| --- | --- | --- | --- | --- | --- |
| Outcome 1: Enhanced participatory and gender responsive planning and budgeting processes at the local bodies(VDC, DDC and Municipality) for implementation and monitoring of National Action Plan on women, peace and security [UNSCRs 1325 and 1820] |
| Output 1.1 | Demonstrate how a pilot on gender-responsive planning and budgeting improves/enhances service delivery for conflict-affected women and budgetary allocations from local resources, to further effective NAP implementation and monitoring in 2 municipalities | UN Women | US$ 377,710 | US$ 350,236.13 (including estimated committed amount of US$ 2,000 for Programme Officer's salary which is yet to be charged by UNDP ) | Possibility of a refund of US$ 27,473.87. |
| Output 1.2 | Conflict affected women and women leaders to influence the local planning processes and greater equality in access to leadership and decision making opportunity | UNDP | US$ 198,892 | US$ 198,892 |  |
| Output 1.3 |  |  |  |  |  |
| Outcome 2: |
| Output 2.1 |  |  |  |  |  |
| Output 2.2 |  |  |  |  |  |
| Output 2.3 |  |  |  |  |  |
| Outcome 3: |
| Output 3.1 |  |  |  |  |  |
| Output 3.2 |  |  |  |  |  |
| Output 3.3 |  |  |  |  |  |
| Outcome 4: |
| Output 4.1 |  |  |  |  |  |
| Output 4.2 |  |  |  |  |  |
| Output 4.3 |  |  |  |  |  |
| Total |  |  |  |  |  |

  - Comments on management and implementation arrangements

Please comment on the management and implementation arrangements for the project, such as: the effectiveness of the implementation partnerships, coordination/coherence with other projects, any South-South cooperation, the modalities of support, any capacity building aspect, the use of partner country systems if any, the support by the PBF Secretariat and oversight by the Joint Steering Committee (for PRF only). Please also mention if there have been any changes to the project (what kind and when) (2000 character maximum):

During the project period, significant efforts were made to enhance project coordination, management and implementation arrangements. UN Women and UNDP developed an integrated project work plan to ensure synergies between project activities. A project coordination team was established at the central level and district level to review project planning and implementation, and regular meetings were conducted. Two workshops were organized to orient the project staff on the project design and revise the result framework at the inception phase. The district level project launch meeting, context analysis workshop, baseline survey and mid-term evaluation were jointly planned and carried out by UN Women and UNDP. Taking advantage of UNDP's field presence, the UN Women's partner LDTA received support from UNDP for the field coordination when organizing orientations or trainings in the two project districts.

# Footnotes

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to “Project ID” on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed.

Please note that financial information is preliminary pending submission of annual financial report to the Administrative Agent.