RUNO END PF PROJECT REPORTING		TEMPLATE 4.5

PEACEBUILDING FUND (PBF)

END OF PROJECT report

COUNTRY: Nepal

REPORTING PERIOD: April 2013-September 2015

| Programme Title & Project Number |  |
| --- | --- |
| Programme Title: Strengthening the Rule of Law and Human Rights Protection System Programme in Nepal Programme Number (if applicable) PBF/00071084 MPTF Office Project Reference Number: |  |  |

| Recipient UN Organizations |  | Implementing Partners |
| --- | --- | --- |
| List the organizations that have received direct funding from the MPTF Office under this programme: UNDP and UN Women |  | List the national counterparts (government, private, NGOs & others) and other International Organizations: Supreme Court of Nepal (SC) Ministry of Law, Justice, Constituent Assembly and Parliamentary Affairs (MoLJCAPA) Ministry of Peace and Reconstruction(MoPR) |
| Programme/Project Budget (US$) |  | Programme Duration |
| PBF contribution (by RUNO) |  |  | Overall Duration (months) 25 months |  |
|  |  |  | Start Date (dd.mm.yyyy) 20.03.2013 |  |
| Government Contribution (if applicable) |  |  | Original End Date (dd.mm.yyyy) | 14.03. 2015 |
| Other Contributions (donors) (if applicable) |  |  | Final End date(dd.mm.yyyy) 31.10. 2015 |  |
| TOTAL: |  |  |  |  |

| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| --- | --- | --- |
| Mid-Term Evaluation / Review - if applicable please attach Yes No Date: March 2014 End of project Evaluation– if applicable please attach Yes No Date: Sep 2015 |  | Name: Tek Tamata Title: Programme Analyst Participating Organization (Lead): UNDP-Nepal Email address: tek.tamata@undp.org |

PART 1 – RESULTS PROGRESS

  - Assessment of the project implementation status and results

For PRF projects, please identify Priority Plan outcome and indicators to which this project has contributed:

Priority Plan Outcome to which the project has contributed. Result 1.1: Security sector reform and judiciary systems put in place and providing services that reinforce rule of law

Priority Plan Outcome indicator(s) to which project has contributed. Communities use justice systems to resolve conflicts without recourse to violence ensuring human rights of women/girls in particular

For both IRF and PRF projects, please rate this project’s overall achievement of results to date:

For both IRF and PRF projects, outline progress against each project outcome, using the format below. The space in the template allows for up to four project outcomes.

Outcome Statement 1:  Improved efficiency of courts and increased delivery of judicial services to the women and vulnerable groups

Rate the current status of the outcome:

| Indicator 1: # of women and members of vulnerable communities who have benefitted from court services in five districts (UNDAF 4.2.2) Indicator 2: % of backlogged cases decreased in district courts in five districts Indicator 3: National Judicial Academy’s Guide for Judges on Quality Court Decisions’ implemented effectively in five districts | Baseline: 151 women and members of vulnerable communities who have benefitted from court services in five districts Target: 20% increase in number of women and members of vulnerable groups who have received court services Progress:Over 4744 people (including 1845 women, 914 Dalits, 1628 Madheshis, 1252 Janajati and 950 others) benefitted from court service though court orientation desk in five districts. Baseline: 46.14% in five districts (source: court records) Target: 33% of cases in district courts in five districts are backlogged Progress:28% cases in five districts courts are backlogged [SC Annual Report, 2071-072 BS] Baseline: 0 districts have implemented the Guide Target: Guide is implemented effectively in five districts Progress:Guideliens that includes Standard Operational Procedure (SOP) on implementation of in-camera hearing and resource materials on judicial outreach developed and implemented effectively in five districts. Similalry, as a reference materials for district judges, implementation status of Supreme Court decision on public interest litigation published and disseminated to district courts. |
| --- | --- |

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

The court client orientation desks in 5 districts were establised and 4744 people (1845  women, 914 Dalits, 1628 Madheshis, 1252 Janajatis benefitted from the information. ToT for 24 court officials was held and an SOP guideline on In-camera hearing was revised, published and used for training the judges,senior court officials and police personnel.Training sensitized them on the confidential procedures, lapses and coordination skills in relation to special cases requiring in-camera hearing. The trainings and support on judgment execution contributed to encouraging recovery of fines(over 35.34 million USD) and incarceration of prison sentence (over 40,000 years) umimlemented for years. The referral networks developed interface between formal and informal justice institutions in five districts and supported 364 needy people to reach to the relevant service centres. The Mediation Council sensitized 973 (283 female, & 690 male) and trained 27(21 M, 6 F) Trainers on mediation skills.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

Poor infrastructures at courts, low sensitivity towards survivors of VAW cases and unclear laws and procedures contributed to jeopardize the rights and respect of the victims during their hearing process. Support to develop SOPs(in camera hearing), trainings to judicial officials on in-camera hearing(27), continuous hearing(24), judgement execution (353), and court communication (30) including the online services etc(over 430 officials including judges trained) is a prime factor of positive changes in victim justice.Likewise, execution of court judgments (over 35 million USD fine recovered and 40,000 years enforced) through mass campaign has spread a renewed hope that state acts against impunity and justice prevails. This particular element of hope among the sufferers also contributes to pacify the potential conflict and mass apathy towards justice institutions. The support on enhancing IT in justice admnistration contributed to reducing the backlogged cases. The SC report (dated 2071-2072 BS) states that District and Appellate Courts have only 578 cases in all 75 districts that exceed two years of time from registration. In the previous year, the figures were nearly double of this. The decreasing number of backlogged cases is an encouraging performance given the prevalent perceptions among the citizens that the courts do not deliver on time. The Justice Sector Coordination Committees (JSCCs) played a crucial role in enhancing the communication and coordination among the stakeholders. Likewise, new practice of referral networks offers instant ways to suffering people and provides hope that even informal system works to reinforce the efforts made by the formal institutions. SLAC itself had 175 persons referred in the last quarter whereas five separate networks referred other 364 justice seekers to the relevant places. The holistic legal aid services through socio-legal aid system has also been contributing in building confidence of people towards legal regime at community level. The mediation practices have been constitutionally recognized and it gives a huge space for ADR mechanisms to resolve the potential conflicts in the first instance.

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

Almost every activity was performed as expected by the end of the project. Some of the activities regarding transitional justice particularly under NHRC component could not happen due to a political reason. The NHRC was initially supposed to be part of bigger RoLHR programme. However they officially decided not to be part of during the signing phase. Which directly affected the implementation of the proposed activities. At the same time, delayed availability of baselines against some indicators were a difficulty to assess the progress made. Field Survey and other secondary means of data collection helped to fullfil the gap.Mediation related activities faced setback due to non-responsiveness of former leadership of Supreme Court, earthquake crisis and delayed implementation of Mediation Act.

Outcome Statement 2:  Women and  vulnerable groups have better access to legal aid services

Rate the current status of the outcome:

| Indicator 1: # of women and members of vulnerable communities who have benefitted from legal aid services in five districts (UNDAF 4.2.3) Indicator 2: % of women and members of vulnerable communities satisfied with legal aid services they have received in five districts. Indicator 3: | Baseline: 88 women and members of vulnerable groups benefitted from legal aid.(source DLAC) Target: 500 women and members from vulnerable groups have received legal aid services in five districts Progress: 3915 (2624 female & 1291 male) have received legal aid services in five districts. Baseline: 58% of women and members of vulnerable communities satisfied with legal aid services they have received in five districts. Target: 72% of women and members of vulnerable communities satisfied with legal aid services they have received in five districts Progress: 66% of legal aid beneficiaries are satisfied with available legal aid services in five districts (Source:NIDR survey, 2014). [Similalry, increasing the legal aid service beneficiaries by 167.5% in 2015 from 2014 is a positive indication of satisfaction.] Baseline: Target: Progress: |
| --- | --- |

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

Socio Legal Aid Centres (SLAC) in five districts served 3915 persons with remedial and 38794 persons with preventive legal legal services. It consisted of legal documentation(892 persons), counselling(11), referral(87), representation in courts(504), immediate relief(357) etc. The learning from these centres have contributed to enrich the draft integrated legal aid policy. SLACs increased their outreach to the rural settlements through mobile camps in 10 VDCs in each districts where over 22963 rural people received legal information.

Under Affirmative Legal education, the project supported the Faculty of Law/TU to update BALLB curriculum from standard human rights perspective. This included the revision of  75 syllabi in 7 thematic areas. Likewise, 75 (26 Male and 49 Female) young lawyers from women and vulnerable groups were trained under 6 month internship programme and supported to enter legal profession; likewise, 20(12F&8M)  students were awarded with BA/LLB scholarship.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

Access to justice of poor and marginalized people was enhanced through legal aid services and affirmative action in legal education including law practice. During the reporting period, SLAC extended their services to  3915 persons including 2624 (64%) women, 815 Dalits, 898 Janajatis, 85 Madheshis, 2092 Bahun/Chhetris and 25 others. During the reporting period, SLACs also refered 197 cases to various service centres. The mobile outreach camps and use of various media to sensitize, aware and educate vulnerable groups about their rights has resulted into increased demand of justice. The increasing numbers of case reporting in the SLACs validates it. Of 337 cases registered in five district courts through SLACs in 2015 alone, 88 were disposed and 66 cases resulted into favour of the victims. Likewise, a survey report by NIDR, 2014 shows that there has been increment of 8% (from 58% baseline data) in cleints' satisfaction with the legal aid services. All these evidences show that there is enhancement in confidence of people twoards justice system and contributing in managing the societal conflict.It is notable that the lack of access to justice of poor and vulnerable was one of the reasons behind the decade long conflict in Nepal. As part of affirmative action in legal education, the activities such as internship for laywers and scholarship for students of marginalised communities has marked nobel initiation, spreading a positive message and creating moral obligation on the university, state actors and others to sustain such outcomes. Faculty of Law/TU's initiation towards creating a scholarship fund in coordination with various stakeholders is the testimony of the same.

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

Under outcome 2, the only one of the outputs that could not be achieved was about implementing the Clinical Legal Education(CLE) programme. The reason was unavailability of a suitable service provider despite the national bid issued. The plan was dropped after that.

Outcome Statement 3:  Criminal justice system is more responsive to conflict victims and female victims/survivors of GBV

Rate the current status of the outcome:

| Indicator 1: # of conflict affected victims who have benefited from relevant information regarding redress through the victim support dialogues in five districts Indicator 2: % of conflict affected victims who are satisfied with the criminal justice system’s response to their needs in five districts Indicator 3: # of conflict affected victims who have received compensation (monetary or non-monetary) in five districts (UNDAF 8.1.3 | Baseline: 3912 conflict affected victims have benefited from information regarding redress through the victim support dialogues in five districts (Source: WVAF record as information collected from districts) Target: 4200 conflict victims benefited from relevant information through victim support dialogues in five districts Progress: 571 conflict victims benefited from legal aid service and other 4903 received information regarding existing laws, policies and programme of GoN related to conflict affected groups and relief/rehabilitation Baseline: 67% of conflict affected victims who are satisfied with the criminal justice system’s response to their needs in Bardiya [n.b. Bardiya had the highest approval rating. Dhading 47%, Mahottari 27%, Siraha 22% - source ICJ report 2013] Target: 75% of conflict affected victims who are satisfied with the criminal justice system’s response to their needs in Bardiya. Progress: Due to the controversial TRC Act and UN SG guidance note, there was no specific activities targetted to the transitional justice in partnership with government agencies. Baseline: 7480 conflict affected victims who have received compensation in five districts (Source: WVAF record as information collected from districts) Target: 8000 conflict affected victims who have received compensation in five districts Progress:8167 victims have received compensation (monetary and non-monetary) in five districts from government entities. |
| --- | --- |

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

In the March 2015 project revision, due to political/legal developments in Nepal surrounding the Truth and Reconciliation Act, the UN Country Team needed to dramatically change its approach due to the inclusion of an amnesty clause for serious human rights violation and gross violations of humanitarian law. In this regard the project focused on a victim centric approach and worked closely with a diverse set of victims groups in order to bring them together and develop their capacity. The conflict victims subsequently established the Conflict Victims' Common Platform. The project assisted them in outreach with other victims groups in remote districts and also increased their capacities through a peer to peer exchange in Bosnia and Hercegovina.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

VSF support to over 8000 victims in 5 districts and capacity building initiatives to stakeholders(trainings on UNSCR1325&1820, DNH etc) in the past provided a hope to conflict victims. Subsequently, over the past 18 months, in close coordination and with the cooperation of the RCO, there has been a concerted effort to bring the conflict victims together under one umbrella. This has been significant as this is the first time that any organization has been able to assist the conflict victims in organizing themselves. The RCO and UNDP subscribe to the view that a proper transitional justice process would deal with the root causes of the conflict that led to the need for transitional justice process to begin with. Over the period of the project it became apparent that certain assumptions were not going to hold true. Namely, that the government of Nepal would adopt a transitional justice law that was largely in accordance with international law and standards. What subsequently took place was a law that was short on both points, as determined by and OHCHR legal opinion on the Truth and Reconciliation Act. Under the leadership of the RCO and with significant programmatic technical and legal advice from UNDP, it was determined to adopt a victim centric approach to transitional justice. Under the RCO’s good-offices function, leaders of various conflict groups, from every political persuasion, were engaged which culminated in the Kathmandu Declaration and the formation of the Conflict Victims’ Common Platform (CVCP) at the end of 2014. The project has spent a great deal of energy in helping the CVCP organize. By engaging with the victims of the conflict and bringing them together it is believed that this can preempt any potential conflict between them. It also reduces the possibilities of the conflict victims being instrumentalized by political parties for their own purposes. The victims are also more able to advocate for their rights with this unity. Clear leadership to the victims’ groups also allows the UN to engage more affectively and prevent hostilities toward the government from “boiling over”. Lastly, the CVCP was adamant that they had long been the objects of transitional justice rather than the subjects and they felt that this needed to change. This often happened when activities were organized where they were the audience and presenters were “experts”; either academics, lawyers or politicians. The project began employing a peer-to-peer model using south-south cooperation. This afforded the CVCP an opportunity to meet victims of the war in Bosnia. It was the first ever oppportunity for CVCP to meet victims from another conflict and know much about the efforts that the victims have made to provide services for themselves and create livelihood programmes.These efforts will mitigate potential conflict as victims’ groups become more desperate for reparations through non-existent government services and limited job opportunities.

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

Due to the controversial TRC Act and UN SG guidance note, there was no specific activities targetted to the transitional justice in partnership with government agencies in 2015. Additionally, non-willingness of the donor partners to continue with the TJ related activities, the RoLHR programme had to separate TJ component in the latter part of the UNPFN project cycle (in 2015).As an alternate engagement, the project began employing a peer-to-peer model using south-south cooperation. This led formulation of the Conflict Victims'Common Platform (CVCP) which later afforded an opportunity to meet victims of the war in international fourm in Bosnia.

Outcome Statement 4:  N/A

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

  - Assessment of project evidence base, risk, catalytic effects, gender at the end of the project

| Evidence base: What was the evidence base for this report and for project progress? What consultation/validation process has taken place on this report (1000 character limit)? | The primary evidence of the report have been the periodic reports obtained from the Socio-legal Aid Centres(S-LACs), perception survey report, court records, partner reports such as Nepal Bar Association etc.The data and progress is also validated by means of internal monitoring, field ovservations, beneficiary testimony, media news and stories etc. |
| --- | --- |
| Funding gaps: Did the project fill critical funding gaps in peacebuilding in the country? Briefly describe. (1500 character limit) | There is no funding gap in the area of access to justice and rule of law. However due to some legal issues regarding the law related to transitional justice, there is no donor funding in this area as such. Some of the activities are being implemented in relation to the rights of conflict affected populations only. |
| Catalytic effects: Did the project achieve any catalytic effects, either through attracting additional funding commitments or creating immediate conditions to unblock/ accelerate peace relevant processes? Briefly describe. (1500 character limit) | The project's achievement in providing the free legal aid to poor and vulnerable groups, a positive message communicated by the launch of affirmative legal education, development of an integrated legal aid policy(awaiting finalisation), court outreach and information system, among other activities have been worth relating initiatives that provide catalytic effects. Likewise, television and community radio broadcasters acknowledged the project's interventions for a cause and they have shared the cost on many instances of media mobilisation. There was also an initiative to jointly organize various field level activities with UNDP's other projects like Micro Enterprise Development (MEDEP), Local Governance&Community Development (LGCDP), Armed Violence Reduction and Community Security (AVRSC). This initiative aims to package access to justice efforts with security, social mobilisation and enterpreneurship development of the beneficiaries without going beyond the designed framework of the project.The project's works in capacity building of the women lawyers attained greater recognition and that resulted into collaboration with an NGO called Women Joining Hands.More importantly, there was a significant change in the Legal Aid Act redefining the scope of legal aid beneficiaries that includes the victims of armed conflict and domestic violence. This is one of the great achievements in the law review and the project's continued advocacy and support on this area got a tangible success. |
| Risk taking/ innovation: Did the project support any innovative or risky activities to achieve peacebuilding results? What were they and what was the result? (1500 character limit) | The introduction of the SLACs by redefining the scope of District Legal Aid Committees itself marks a risky work because there were fears whether the proposed structure and approach of SLAC would be accepted to its spirit and support thereto. Given the comprehensive approach of legal aid, risk would be whether the government would be able to sustain even if the government has been developing integrated and one door legal aid system. Expansion of the existing definition of legal aid has been notable effort that the project embarked on and today an integrated legal aid policy has incorporated major learnings of these centres and is awaiting final consultation. Apart from financial criteria prescribed by the existing laws, social factors also have been proposed in the new policy in order to expand the horizon of free legal aid. |
| Gender marker: How have gender considerations been mainstreamed in the project to the extent possible? Is the original gender marker for the project still the right one? Briefly justify. (1500 character limit) | Gender and social inclusion have been the core element of project interventions. Gender responsive planning, disaggregation of beneficiaries, tailored activities such as trainings, media mobilisation, discourses, campaigns etc have been regular works to mainstream the gender aspects. Some of the policy level initaitves such as developing guidelines, policies and capacity building initiatives on the same have been instrumental in mainstreaming gender and social inclusion(GESI). The project saw all these efforts resulted into formulation of a GESI strategy which aims to increase the focus on the women and vulnerable groups from gender and inclusion lense. |
| Other issues: Are there any other issues concerning project implementation that should be shared with PBSO? This can include any cross-cutting issues or other issues which have not been included in the report so far. (1500 character limit) | Although project put enormous efforts in implementing the In-camera hearing practices in the courtrooms, the insufficient infrastructure(building space) and human resources at courts have been major issue. These aspects should be given additional thoughts for the full and effective implementation of the In-camera hearing. Likewise, the Guide for Judges on Quality Court Decisions’ as such could not be developed. However, some additional reference tools have been produced that include SoPs on in-camera hearing etc. The Clinical Legal Education was another part of project which could not be materialised due to reasons mentioned above. |

PART 2: LESSONS LEARNED AND SUCCESS STORY

2.1 Lessons learned

Provide at least three key lessons learned from the implementation of the project. These can include lessons on the themes supported by the project or the project processes and management.

| Lesson 1 (1000 character limit) | Partnership with the civil society is instrumental in maximizing efforts to expand outreach initiatives to address demand side issues such as creating awareness among right holders about existing legal and policy mechanism and to build their capacity to access those mechanisms. This proved instrumental in S-LAC operations, especially in organizing mobile legal aid camps. |
| --- | --- |
| Lesson 2 (1000 character limit) | Repeated follow ups and skill oriented workshops, interactions on GESI issues have contributed towards better reception of the issue in the justice sector. Earlier, GESI received very little attention in any discourse related to such reform in the judiciary, in particular. |
| Lesson 3 (1000 character limit) | Availability of access points and a person at courts significantly contributes towards fulfilling the information needs of court users. The number of information seekers at these Desks implies the same. It should be replicated elsewhere as well. |
| Lesson 4 (1000 character limit) | The performance of the S-LACs in the targeted districts has been quite encouraging. However, the outreach activities of these centres should be increased more and managed with more resources. |
| Lesson 5 (1000 character limit) | Further, for sustainability and better ownership, it is not only necessary to involve government counterparts in planning and monitoring, but also in co-financing and upscaling of the project interventions. Likewise, mainstreaming GESI at each and every possible occasion by RoLHR and its partners is a must, otherwise the GESI will be not be able to last as an approach. |

2.2 Success story (OPTIONAL)

Provide one success story from the project implementation which can be shared on the PBSO website and Newsletter as well as the Annual Report on Fund performance. Please include key facts and figures and any citations (3000 character limit).

The goal not hindered despite an amputated hand

On a rainy day of July, a drenched young man arrives at Narcotic Control Bureau of Nepal Police in Koteshwor. It wasn't difficult to speculate that the youth must be a lawyer as he was with a black coat on. Things got revealed that he was familiar among all police there and had come to see a detainee accused of smuggling drugs. After he left, one of the bureau officers said, “Look, he does not have a hand, but the hard work he does despite that is exemplary.''

It is Kumar Magar-33, a resident of Basaha-4, Udayapur who lost his left hand at the age of eight. While climbing a tree to pluck the leaves of Tanki vegetable, he slipped off the tree and broke the hand with bones smashed, which turned incurable later and had to be amputated. After he passed SLC from nearby government school in Beltar, he wanted to study health assistant's course. It was then one of his well wishers told him, “You would need both hands intact to work as a doctor, how would you do the surgical works just with one hand?” This sense of loss sent a chill down his spine.  “I was really disheartened to know that I would not be able to study medicine,'' Kumar recalls his past.  But with feeling of satisfaction to his present legal profession saying, “Sometime I feel that all happened was for good reason. I don’t think I would have got this level of satisfaction if I were a doctor.”

The family relying on subsistence agriculture had difficulty to educate 7 siblings (3 brothers and 4 sisters). Kumar's uncle, an employee with the Indian Army, took responsibility for his raising and schooling after he lost his hand. With the hopes to study medicine shattered, he wanted to become a lawyer by studying law. However, there was no provision of certificate level degree to start with then. The only option to study law was to obtain a bachelors' degree in any other non-law subjects first. So, he completed +2 degree in commerce stream and then graduated with BBS (Bachelor in Business Study) degree. Then Kumar came to Kathmandu for his further studies, but he confronted a dilemma as to whether he should study master's in business studies or a bachelor's degree in law. Finally, he chose to pursue a law degree and made it. Subsequently, he obtained a license of advocate from Nepal Bar Council and started practicing law in a private law firm. Nearly a year passed in the law practice proved to be rather disappointing as it did not help him found a consistent rhythm of lawyering.

Against such disheartening situation, Kumar found a way out when he came to know about the launch of a six month internship program for lawyers from poor and vulnerable groups by Nepal Bar Association with support of RoLHR/UNDP(Strengthening the Rule of Law and Human Rights Program UNDP. He applied for the course and got selected. With theoretical knowledge, professional experience and practical skills to analyze cases, and court proceedings he got to learn from during

PART 3 – FINANCIAL PROGRESS AND MANAGEMENT ARRANGEMENTS

  - Comments on the overall state of financial expenditure

Please rate whether project financial expenditures were on track, slightly delayed, or off track:

If expenditure was delayed or off track, please provide a brief explanation (500 characters maximum):

Please provide an overview of project expensed budget by outcome and output as per the table below.

| Output number | Output name | RUNOs | Approved budget | Expensed budget | Any remarks on expenditure |
| --- | --- | --- | --- | --- | --- |
| Outcome 1: Improved efficiency of courts and increased delivery of judicial services to the women and vulnerable |
| Output 1.1 | Institutional measures are in place at national level and court-public relations enhanced at local level |  | 585,000.00 | 580,542.00 | 4,457.00 |
| Output 1.2 | Interface between formal and informal justice system strengthened at the national and district level to increase informal justice mechanisms' ability to comply with HR standards |  | 390,000.00 | 383,463.00 | 6,537.00 |
| Output 1.3 |  |  |  |  |  |
| Outcome 2: Women and vulnerable groups have better access to legal aid services |
| Output 2.1 | Socio-legal aid system for service provisions developed to ensure greater inclusion of women and vulnerable groups in five districts |  | 500,000.00 | 495,827.00 | 4,173.00 |
| Output 2.2 | Affirmative law scholarship and internship scheme established for greater professional inclusion of women and vulnerable groups nationwide |  | 300,000.00 | 293,323.00 | 6,677.00 |
| Output 2.3 |  |  |  |  |  |
| Outcome 3: Criminal Justice System is more responsive to conflict victims and female victims/survivors of GBV |
| Output 3.1 | Conflict affected victims in five districts have increased capacity to hold criminal justice systems accountable to the issues related to GBV and rule of law |  | 400,000.00 | 272,127.00 | 127,873.00 |
| Output 3.2 |  |  |  |  |  |
| Output 3.3 |  |  |  |  |  |
| Outcome 4: Project Management and Performance |
| Output 4.1 |  |  | 25,0000.00 | 24,986.00 | 14.00 |
| Output 4.2 |  |  |  |  |  |
| Output 4.3 |  |  |  |  |  |
| Total |  |  | 22,00,000.00 | 2,050,268.00 | 149,732.00 |

  - Comments on management and implementation arrangements

Please comment on the management and implementation arrangements for the project, such as: the effectiveness of the implementation partnerships, coordination/coherence with other projects, any South-South cooperation, the modalities of support, any capacity building aspect, the use of partner country systems if any, the support by the PBF Secretariat and oversight by the Joint Steering Committee (for PRF only). Please also mention if there have been any changes to the project (what kind and when) (2000 character maximum):

# Footnotes

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to “Project ID” on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed.

Please note that financial information is preliminary pending submission of annual financial report to the Administrative Agent.