LEBANON RECOVERY FUND

MPTF OFfice GENERIC ANNUAL programme NARRATIVE progress report

REPORTING PERIOD: From JULY 2014 TO March 2017

| Programme Title & Project Number |  | Country, Locality(s), Priority Area(s) / Strategic Results |
| --- | --- | --- |
| Programme Title: Lebanon Stabilization and Recovery Program: Selected Rapid Delivery and Immediate Impact Interventions Programme Number: LRF 29 – Project ID 00090567 MPTF Office Project Reference Number: LRF29 |  | Country/Region: LEBANON |
|  |  | Priority area: North, Bekaa, South, Tripoli, Beirut Suburbs with some country-wide initiatives |
| Participating Organization(s) |  | Implementing Partners |
| Organizations that have received direct funding from the MPTF Office under this programme: UNDP |  | National counterparts (government, private, NGOs & others) and other International Organizations: Office of the Prime Minister Ministry of Social Affairs Ministry of Education and Higher Education Ministry of Public Health Ministry of Interior and Municipalities Local authorities Other National counterparts: (government, private, NGOs & others) and other International Organizations |
| Programme/Project Cost (US$) |  | Programme Duration |
| Total approved budget as per project document: MPTF /JP Contribution: by Agency (if applicable) | LRF contribution $ 5,802,053.4 |  | Overall Duration (months) | 32 months |
| Agency Contribution by Agency (if applicable) |  |  | Start Date | 01/07/2014 |
| Government Contribution (if applicable) |  |  | Original End Date | 31/05/2016 |
| Other Contributions (donors) (if applicable) |  |  | Current End date | March 2017 |
| TOTAL: |  |  | Have agency(ies) operationally closed the Programme in its(their) system? Expected Financial Closure date | Yes 30/06/2017 |
| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| Assessment/Review - if applicable please attach No No |  | Name: Title: Participating Organization (Lead): Email address: |

### List of Acronyms

ACTED		Agence d'Aide a la Cooperation Technique et au Developpement

APR			Annual Progress Report

BRHIA		Beirut Rafik Hariri International Airport

CBRN			Chemical – Biological – Radioactive - Nuclear

CDR			Council for Development and Reconstruction

CEDRO	Community energy efficiency and renewable energy demonstration project for the recovery of Lebanon

CNRS			National Council for Scientific Research

COM			Council of Ministers

DIM:			Direct Implementation Modality

DRC			Danish Refugee Council

DRM			Disaster Risk Management

DRR			Disaster Risk Reduction

GA:			Grant Agreement

GARD			Getting Airport Ready for Disasters

HFA			Hyogo Framework of Action

INSARAG		International Search and Rescue Advisory Group

ISF			Internal Security Forces

ITB			Invitation to Bid

LAF			Lebanese Armed Forces

LRC			Lebanese Red Cross

M&E			Monitoring and Evaluation

MoPH:			Ministry of Public Health

MOR			Mobile Operation Room

NCC			National Coordination Committee

NCLW			National Commission for Lebanese Women

NGO			None Governmental Organizations

NOR			National Operations Room

NRP			National Response Plan

PCPM			Polish Center for International Aid

PHCC:			Primary Health Care Center

PMO			Prime Minister Office

PV			Photovoltaic

QPR			Quarterly Progress Report

REACH		Society for Rehabilitation, Education and Community Health

RRP: 			Regional Response Plan

SOP			Standard Operating Procedures

UN ISDR 		United Nations Office for Disaster Reduction

UNDP			United Nations Development Programme

UNHCR		United Nations High Commissioner for Refugees

UoM			Union of Municipalities

WHO			World Health Organization

# EXECUTIVE SUMMARY

In order to effectively mitigate the impact of the Syrian crisis on the Lebanese host communities and the displaced Syrians, UNDP adopted a comprehensive, multi-level and multi-sectorial approach. Through the creation of job opportunities, the provision of social and basic services, the rehabilitation of community infrastructure and the promotion of conflict resolution mechanisms, UNDP contributed to improving livelihood and economic opportunities, improving the living conditions, strengthening public social services and mitigating tensions in the most vulnerable communities across the country. UNDP also contributed to strengthening the capacities of local and national institutions to be able to cope with the crisis and recover from it.

Lebanon is facing a major crisis as a result of large numbers of refugees fleeing the war in Syria, and finding shelter within Lebanese cities and villages across the country. Many countries and international organizations are assisting in securing basic needs for the Syrian refugees in terms of water, food, and shelter.

This project has been implemented in close collaboration with the Lebanese Ministry of Social Affairs (MoSA) as the main governmental counterpart, local authorities for implementation and follow up at the local level, and the Ministry of Education and Higher Education (MEHE), the Ministry of Public Health (MoPH), MoSA, and the Ministry of Interior and Municipalities (MoIM) as the main governmental counterpart for initiatives related to health and education. The collaboration with the above mentioned governmental counterparts has allowed UNDP to identify and develop sustainable and coordinated interventions, avoiding duplications and responding to the immediate needs of the host communities. In 2014, the collaboration was manifested in an agreement titled “Support to Integrated Service Provision at the local level,” and signed between UNDP and the aforementioned partners with the aim to develop integrated territorial welfare plans and services (health, social affairs, and education) at the local level.

Generally, the project strengthened local governance structures in targeted under-served regions for better representation, participation, and basic services delivery, and built the capacity of institutions and community groups for effective formulation and implementation of activities that include women and youth.

UNDP contributed to outcome 1, livelihood and economic opportunities increased through upgrading, repairing and improving the production infrastructure and creating short and medium term employment opportunities in the most vulnerable host communities. In North Bekaa, the projects contributed to improving farmer’s livelihoods and guaranteed a sustainable and efficient utilization of water and lands through the rehabilitation of irrigation canals. In Akkar, the projects allowed cooperatives to enter new markets and improved social and economic conditions of the farmers through the provision of equipment and specific trainings in different business development fields in collaboration with the Local Economic Development Agency (LEDA). The rehabilitation of irrigation canals in Chwaghir increased the number of irrigated and cultivated lands and improved the livelihood of the farmers Finally, through the extension of the wastewater network in Ain Kfarzabad and the installation of a treatment unit in Qab Elias, the project contributed to reducing the contamination of the water used for irrigation purposes, preserving the irrigated crops and protecting agricultural lands from pollution

Furthermore, UNDP contributed to outcome 2, strengthening the capacities of local and national actors in the delivery of social and municipal services through a participatory approach. Under the framework of the “Support to Integrated Service Provision at the local Level” initiative, the project contributed to promoting dialogue among all stakeholders involved at the territorial level i.e. representatives of line ministries and local authorities, directors of primary health care centers and public schools, and other actors to discuss and set up (with the support of technical experts) the territorial health plan. Furthermore, the project contributed to increased access to quality public primary health care services, increased awareness on health and improved sanitation conditions in selected public schools. Moreover, in order to support local authorities in the provision of basic services and to improve the health conditions of inhabitants, the project provided municipal infrastructure maintenance equipment and wastewater management equipment to five Union of Municipalities in the South. In addition, and in coordination with the Water Establishment of the South, the water maintenance centre of Qalaa was upgraded through the provision of equipment.

Energy is also a major problem in Lebanon both before the Syrian refuges crisis and now augmented with this crisis, where at least 9-12 hours of blackouts per day exist, and the delivery of hot water is not guaranteed; the need to deliver urgent and basic energy for lighting at the household level and the need to provide cooking and heating, especially for the cold season is critical. These utilities are needed by both the host-communities as well as the Syrian refugees to ensure safety, well-being and security. Using solar energy seems to be the only way to provide these rural communities with an additional cost-effective and independent source of electricity. Furthermore, for household heating and cooking, sustainable briquette stoves can be used instead of highly polluting diesel fuel or worse, wood collected unsustainably and often illegally from forests. UNDP aims at installing in the Akkar and Bekaa region approximately 550 solar lighting kits for various host community beneficiary houses to deliver basic lighting, and 594 briquette stoves for heating and cooking.

The support from the Lebanese Recovery Fund has been instrumental in mainstreaming disaster risk management and reduction. Effectively, a major breakthrough has been accomplished during the last three years in scaling up the Lebanese Government's capacities on different levels, in a standardized and uniform way, in preparedness and response to natural and man-made disasters. The Government's commitment in setting DRM as a priority within its agenda, along with the coordination and cooperation among concerned agencies, ministries, and governorates has pushed forward for the last three years DRM and DRR on the national level.

As a reflection of three years in review and thanks to funds received from LRF, Lebanon can now claim having a state of the art National Operations Room, National Mobile Operation Vehicle, pioneer flood risk assessment for Lebanon and response plans and operations rooms equipped with up-to-date communication systems coupled with DRM structure and HR capacities for the ministries of: Education and Higher Education, Social Affairs, and Agriculture, in addition to Beirut Rafic Hariri International Airport. A preliminary analysis of intensive and extensive disaster risk of the industrial sector in Lebanon has been formulated for the Ministry of Industry. Moreover a curriculum for mainstreaming DRM considerations into the activities of the public sector and Lebanese Armed Forces was developed, implemented and adopted at the Ecole Nationale d'Administration and Lebanese Armed Forces Command & Staff College. Additionally, capacities in DRM and DRR have been enhanced at the local level with the establishment of DRM structures, response plans, operation rooms and capacities within several governorates, cazas and municipalities including the governorates of South, North and Baalbak El Hermel. Response plans have been tested through simulations and table top exercises at the national, ministry and governorate level revealing a high degree of coordination and effectiveness among concerned agencies and decision makers. Awareness on disaster risk reduction has been enhanced at the national, ministry and local community level through the development and dissemination of DRR home guides for mass communities, prototype emergency kits for public and community institutions, and a pioneer DRR mobile application for Lebanon.

Finally, a Conflict Map was developed by UNDP in cooperation with the national Lebanon NGO Lebanon Support which is to date, updated on a daily basis. It provides different partners and the general public with accurate data on conflicts and incidents trends, which are divided into categories and over different regions. In parallel to the mapping exercise, four conflict analysis reports were produced focusing each one on a specific geographic area: one on Bekaa focusing on Arsal, one on Saida, another on Mount Lebanon, the fourth and final one on Beirut.

Also, a Mechanism for Social Stability (MSS) was established in West Bekaa (Gaza, Marj, Mansoura, Hawch Harimeh, Jeb Jennine, Machghara, Qaraoun, targeting a number of villages hosting Syrian refugees. The Mechanism was developed based on an in-depth locally lead conflict analysis, conducted by a group of identified local authorities and local actors who were trained throughout the programme time span on conflict management, peace building, communication skills, negotiation and mediation skills, and who decided to develop mechanisms that would directly respond to the main causes and sources of tensions at their local level. As a result of these mechanisms, local dialogue committees gathering Lebanese and Syrians were formed, improving the dialogue channels between the two communities and contributing to social cohesion; as well as between Lebanese who were able to tackle root causes of conflict and work on local reconciliation initiatives. Another main result of the process was the establishment of West Bekaa Peace Initiative which gathers participants from different villages and work on locally lead peace building activities.

# Purpose

Expected Outcome: Local governance structures in target under-served regions strengthened for better representation, participation, and basic local services delivery.

Expected Output: Capacities of institutions and community groups strengthened for effective formulation and implementation of regional and local development plans including women and youth.

The impact of the Syrian crisis on Lebanon reached an unprecedented scale in the history of complex, refugee-driven emergencies. In April 2012, 32,800 displaced Syrians were registered or awaiting registration with UNHCR, and by end of April 2015, that figure had sharply increased to over 1,200,000 - an increase equal to over 25% of the entire Lebanese pre-crisis population. To contextualize the impact further, Lebanon was already one of the most densely populated countries in the world, with an average of over 400 people per square kilometre of land. This sudden and large influx of displaced Syrians is now placing enormous pressure on the country and its people, especially those in the poorest areas, where refugee concentrations have been the greatest.

The majority of refugees are being hosted in communities that are among the poorest in the country. Given the significant periods of power cuts in Lebanon, where some regions have at least 9-12 hours of power cuts per day, the need to deliver urgent and basic energy for lighting at the household level and the need to provide cooking and heating, especially for the cold season is critical.

The crisis is not only challenging the country’s existing social and economic infrastructure, it is exacerbating significant development deficiencies such as unemployment, particularly among women and youth, and causing profound disparities between the wealthy and the poor. In addition, the crisis brings a new set of tensions to Lebanon that threaten to undermine Lebanon’s delicate social and political balance of power, while also amplifying pre-existing inter-Lebanese divisions and provoking increasingly negative reactions against the Syrian refugee presence.

A robust response to the complex crisis requires a combination of both urgent and developmental responses. The project therefore included rapid interventions, and contributed to stabilization and recovery in areas hosting displaced Syrians in Lebanon through the accomplishment of three main outcomes:

| Immediate Objective | Stabilization and recovery in the refugee hosting areas through quick impact and community support projects |
| --- | --- |
| Outcome 1 | Livelihood and economic opportunities increased in select refugee hosting areas through upgrading, repairing, and improving the production infrastructure, and creating short and medium term employment opportunities |
| Outcome 2 | Delivery of basic social services expanded and improved in target communities through equipping, rehabilitating, and upgrading the infrastructure, and improving the skills of service providers |
| Outcome 3 | Social cohesion in target areas improved through and improved skill base for peaceful dispute resolution |

The activities were integrated within the UNHCR-led Regional Response Plan (RRP) for Social Cohesion and Livelihoods, and Water and Sanitation Sectors, and are further coordinated within the international community via the Task Force on Support to Host Communities.

The intervention involved main international and national implementing partners with various roles:

- UNDP is in charge of implementing the activities through the adoption of the Direct Implementation Modality (DIM). It is also acting as the main executing agency, forming partnerships with the governmental, non-governmental, and corporate sector entities for the delivery of the stipulated goods and services. The UNDP Country Office oversees the implementation of the initiatives through its central office in Beirut, as well as its regional office networks in Akkar, Bekaa, Mount Lebanon, and South, and is also responsible for reporting on progress.

- The Ministry of Social Affairs serves as the main government counterpart. It is represented in the Project Steering Committee/Board and participates in the approval of the work plans and progress reports.

- Local Authorities participate in the implementation of initiatives at the local level, providing day to day follow-up, in addition to requesting offers whenever needed. Local authorities collaborate directly with UNDP to achieve the goals of the project.

- The Ministry of Education and Higher Education, the Ministry of Public Health, the Ministry of Social Affairs, and the Ministry of Interior and Municipalities serve as the main government counterparts for initiatives related to health and education sectors. All initiatives are carried out based on clear recommendations and standards set by the above-mentioned line ministries for standardization of quality of services at the national level.

Livelihood initiatives are implemented in Akkar under Outcome 1 area targeting local cooperatives, through the procurement of the necessary equipment for upgrading production, the purchase of vehicles for transportation and the conduction of trainings for the cooperatives members. In addition, local farmer’s conditions are improved in the Bekaa region through the rehabilitation of irrigation canals and the implementation of WASH related projects aiming at reducing water contamination. For Outcome 2, basic social services initiatives is target Public Schools and PHCC countrywide as well as municipalities in the South and Bekaa, on sewage and water related problems.

In addition, the use of renewable energy systems, such as the ones proposed under Outcome 2, saves on household spending while ensuring that the basic needs of local host-communities are met. The proposed equipment to be purchased and installed are: solar lighting kits capable of lighting 3 to 4 rooms with energy efficient light bulbs, briquette and stoves (small heating unit sufficient to warm a 100 m2 room on average): The unit is fed with sustainably-produced briquettes (manufactured from the agricultural waste and/or from sustainably managed forests) that are burnt in the system and emit heat. Some local manufacturing of briquettes has started in Lebanon and through the introduction of these systems, not only would heating be provided to Lebanese beneficiaries, but also potential new job opportunities for the manufacturing of sustainable briquettes from agricultural waste and forest residues.

These systems will be provided to households according to two main criteria: humanitarian and technical. Humanitarian criteria include households hosting Syrian refugees, households that are defined as being ‘extreme poor’ by the Ministry of Social Affairs, and those in need as identified by municipalities. Technical criteria include among other items the household infrastructure, ability to cover costs of monthly fees to community-based electricity generator or the availability of a privately-owned generator. These units will be purchased as pilot technologies that are environmentally-friendly and will complement the Winterization Programme of the UNHCR under implementation within the Regional Response Plan. The target villages will be the poorest host-communities in Akkar and Bekaa regions which have the infrastructure needed to introduce the equipment at the household level. The selection of the houses will be coordinated closely in the field with UNHCR and other agencies working in these areas.

Disaster risk management and reduction has been mainstreamed and implemented under both Outcome 2 and 3. Within Outcome 2, his concept has been delivered by the output 2.5 and the main objectives expected as per the program include:

- The establishment of a National Operations Room (NOR)

- Support to four national ministries in crisis preparedness and planning

- Support to 25 local authorities in North and Bekaa to adopt resilient city charter

- Support to the establishment of regional crisis response plans and operation rooms

- Awareness raising on crisis preparedness

- Distribution of emergency response kits

- Awareness raising through mobile app and leaflet distribution

With regards to Outcome 3 and as per the project document and Annual Workplan, the main objective of the programme is the Stabilization and recovery in the refugee hosting areas through quick impact and community support projects. And the outcome of this specific component (reported against here) is “Social cohesion in target areas improved through improved skill base for peaceful dispute resolution”. This outcome is related to the Output number 3: Local level dispute resolution strengthened and community security improved, under which one main activity is mentioned: Develop local level peace building strategies to mitigate tensions in selected conflict prone areas of Lebanon hosting Syrian refugees”.

# Assessment of Programme Results

- Narrative reporting on results:

Outcome 1: Livelihood and economic opportunities increased in selected refugee hosting areas through upgrading, repairing and improving the production infrastructure and creating short and medium term employment opportunities

Output 1.1: Support value added production of fruits and vegetables in Akkar through postharvest  processing

Jord Akkar is the major fruit producing area in the Akkar district, where apple is the major culivated crop, as well as other  annual crops and summer vegetables. Prior to the conflict across the border, Syria served as the main transit route for the export of fresh agricultural produce. The Syrian crisis and the consequent closure of the border limited the demand to the local consumers and resulted in a decrease in the prices of agriculture products in the region, affecting the income of farmers and the livelihood of their families. This situation is forcing many farmers to abandon their fields and orchards and the decrease in livelihood opportunities has been further exacerbated by the influx of refugees and is pressuring the local socio-economic fabric.

Following the intervention, the manifacturing capacity of Jord Akkar cooperative’s increased through the purchase of a fruit-drying-equipment that functions on solar energy. The machine was procured and delivered, and the workers were trained by the contractor on how to use it. In addition, a van was procured and delivered to transport the products to different markets. The introduction of a new production line (dry fruits) improves the market share of the cooperative and the diversification of the product line, and allows the cooperative to enter new niche markets, directly benefitting 145 individuals.

Furthermore, the implementation of the capacity-building component started on two levels: 1) the elaboration of a marketing strategy began with a team of experts who initiated data collection and review to elaborate onthe management and marketing history analysis, as well as the current production process, cycle, and steps; 2) the delivery of technical support for the cooperative to improve the quality of the new dried food production line.

After completing the rehabilitation of the production room and discussing expert findings, a workshop by the Local Economic Development Authority (LEDA) took place in the last week of August 2015 to present the findings of the studies and train the members of the cooperative on how to use the machines. During this workshop, the cooperative members learned about quality and hygiene standards that need to be applied during the production process. They were trained on how to use the production line step-by-step, starting with the washer to the grader, the slicer, and finally, the dryer. The members of the cooperative were also informed about the findings of the marketing study (prepared by the experts) that displays the potential and the increasing need of dried fruits in the local market.

Output 1.2: Enhance fruit marketing in Akkar

Joumeh area is considered one of the most prosperous areas in apple cultivation due to the availability of water, the quality of the soil, and the optimal elevation for apple cultivation.

The United Cooperative in the Joumeh region of Akkar is a union of three agricultural cooperatives that are active in fruit production in the villages of Rahbeh, Bazbina, Akkar El-Atiqua and the surrounding areas. The United Cooperative has established a refrigerated storage facility for the farmers in the region since 1999. In addition, it provides agricultural guidance for its members to improve the quality and quantity of fruits while working on reducing chemical use as much as possible. Nevertheless, given its recent re-establishment and the considerable increase in food production in the area, the cooperative faced various problems, from the lack of management skills of its members to structural problems related to the segmentation of work. In addition, the absence of a proper fruit sorting and packing unit, essential for appropriate preseravation of the fruit, makes the United Cooperative’s access to the market difficult and risky.

Prior to the itnervention, interviews were conducted with the person in charge of the storage unit in order to review the storing process, its methods, and needs; as a result, the construction of a hangar in front of the facility was identified as one of the main needs for storing the machine and for the new production line. The construction of the hangar took place and the procurement of 8,500 plastic crates, a transportation vehicle, and an apple production line machine (for washing, grading, and packing) for the new production line was completed. The intervention directly benefits 800 individuals.

The activity “Enhance fruit marketing in Akkar” was amended and officially approved on the January 14, 2015.

During 2015, in order to strengthen the United Cooperative storage centre and establish a new production line, North LEDA provided the cooperative members with specific trainings in different business development fields such as management, business, and financial planning. The training covered the following topics:

- Day 1: a training on entrepreneurship

- Day 2 & 3: a training on business models for the Union of Cooperatives. It consisted of a real life training based on the actual situation analysis, future vision for the entire concept, the already existing services, and the newly developed ones.

- Day 4: the early hours were dedicated to a brief on the final outcome of the newly prepared business model and for agreeing on fast action since the season was due to begin soon.

- Day 5: marketing principles and management models, marketing and communication strategies, and reuse of data from business models in presenting marketing campaign scenarios.

In addition, the inauguration of the two projects supporting the capacities of the cooperatives in agricultural production in Akkar was held on October 7, 2015 at the United Cooperative in Joumeh, Akkar. Among those present were the United Nations Resident and Humanitarian Coordinator and Resident Representative of the United Nations Development Programme (UNDP) in Lebanon Mr. Philippe Lazzarini, UNDP Country Director Mr. Luca Renda, H.E. the governor of Akkar, Mr. Imad Labaki, representatives from the Ministry of Social Affairs, Ministry of Economy and Trade, the German Embassy in Lebanon, and the Lebanon Recovery Fund, members of the Cooperative Association for Agriculture and Food Processing in Fnaydek, and the Cooperative Association in Akkar.

These projects helped improve the social and economic conditions of the farmers in Akkar, and promote economic activities in the area. The project implemented at the United Cooperative in Joumeh directly benefitted three hundred farmers , and 37 other members and staff of the Cooperative Association in Fnaydeq.

Output 1.3: Implement WASH projects in Bekaa

Reforestation activities planned initially in Bekaa were amended in 2014 and replaced with the activity  “Implement a cash for work reforestation activity in Bekaa’ which was also amended and officially approved on January 14, 2015.

1.3.1 	Construction of a wastewater network for better hygiene and health conditions in Ain Kfarzabad

The municipality of Ain Kfarzabad is responsible for managing the wastewater network in the village. Given the restricted budget available, the municipality made immense efforts to deliver proper services. The impact of the Syrian crisis and the dramatic increase in the population residing in the village intensified the pressure on the already weak public services. On one hand, further efforts are needed to process the wastewater produced. On the other hand, Ain Kfarzabad Municipality is overwhelmed and unable to fulfil its responsibility in providing good services. Hence, the local population and refugees face a critical hygiene and health situation, with a dramatic increase in the spread of diseases.

The intervention, implemented closely with the municipality, extended the sewage network to cover an additional 927 meters. The works were highly praised and the intervention had a direct impact on livelihood conditions, reducing the pollution of the agricultural lands and contributing to a better quality of agricultural products and improved health conditions for the inhabitants

1.3.2 	Enhancing the capacity of Chwaghir municipality in improving farmers livelihoods through the rehabilitation of the irrigation canals

Chwaghir municipality is a rural area where agriculture constitutes the main economic activity for its inhabitants. Most of the farmlands are irrigated through traditional irrigation canals that were in bad condition, causing water leakage. Given the limited financial resources and the immense work that needs to be done, the municipality and local farmers identified the scarcity of water and the decreasing farm productivity as the main problem within the sector. Limited access to irrigation water also increased the already high cost of production.

The intervention, implemented closely with the municipality, improved the conditions of the farmers through the rehabilitation of the irrigation system (400 linear meters). The rehabilitation directly benefitted 200 Lebanese and 100 Syrians. The intervention resulted in efficient utilization of water that lead to improved quality of agricultural products. This lead to an increase in the number of irrigated and cultivated lands, preservation of cultural heritage, improved livelihood of the farmers in Chwaghir given the increase in the amount of saved water, and a decrease in water leakage that results from vaporization and inefficient distribution.

1.3.3 	Integrated water resources management to improve environment and health conditions in the host communities of Qab Elias

In the village of Qab Elias, many households were connected to a local sanitation sub-network that was discharging wastewater to a collective cesspit to drain the sewage. The location of the cesspit is right above the main river that provides irrigation water to the agricultural plain of Qab Elias, and passes through a touristic site adorned with restaurants. As a result, the river was directly polluted with untreated domestic wastewater, posing health risks for consumers who use the river water both at home and in the field to irrigate their crops. This lead to increased waterborne diseases within the household itself or from the consumption of agricultural products. In turn, the project worked closely with Qab Elias municipality to improve the sanitation network.

The intervention consisted of the provision of a sewage treatment system with a capacity of serving a community of 100 inhabitants. The system is non-electric and only based on air. The treatment unit was installed and is operational fully functional, resulting in the following reductions in contamination: Suspended Solids (SS) reduction equal to 80%, organic matter reduction (BOD5) equal to 85%, thus having a considerable impact on the living conditions of the village’s residents.

Output 1.4: Increase irrigated agricultural areas in North Bekaa

This activity aimed at increasing irrigated agriculture areas in the refugee-hosting Bekaa region through the construction of irrigation canals in four villages in Northern Bekaa in the municipalities of Flawi, Boudai, Shaat (Zrazir) and Hermel. The agricultural lands in Flawi, Boudai and Shaat (Zrazir) depend on water collected from the Alyamuna stream through an infiltration gallery. The main water channel spreads into minor branches, many of which were earthen, causing massive water loss due to leakages, evaporation and perforation. Similar issues were faced by the communities in Hermel which rely on earthen water channels. The water loss from such channels was a major constraint since it hindered the expansion of irrigated lands and the intensification of cropping patterns resulted in the loss of economic opportunities. The irrigation canals of Flawi, Shaat (Zrazir), Bouday and Hermel were rehabilitated in order to achieve sustainable and efficient utilization of water, increase cultivated lands, promote preservation of cultural heritage, decrease the leakage of water and improve efficiency of distribution of water to the already cultivated lands in the area. The intervention directly benefits 200 Lebanese and 100 Syrians.

Outcome 2: Capacity of national and local actors (government and civil society) strengthened in the delivery of health, education and basic municipal services in a participatory manner and coordination of service delivery by all stakeholders.

Output 2.1: Increase access to quality public primary health care services and health awareness in public schools

The influx of displaced Syrians has put an additional burden on the already stretched capacities of the health and education systems in the host areas in Lebanon. The already dilapidated water and sanitation facilities, as well as the lack of awareness about primary health care in the public schools, are feared to become major sources of disease among the population. The delivery system for curative health is under major stress, given the existing amplified caseload, and is unlikely to be able to respond to any outbreaks.

The project worked on a local referral system in collaboration with the Ministry of Public Health (MPH), the Ministry of Education and Higher Education (MEHE), the Ministry of Interior and Municipalities (MoIM), the Council for Development and Reconstruction (CDR), and the local authorities.

On September 15, 2014, the United Nations Development Programme (UNDP), the Ministry of Public Health, the Ministry of Social Affairs, the Ministry of Education and Higher Education, and the Ministry of Interior and Municipalities signed the agreement titled “Support to Integrated Service Provision at the local Level.” The aim of the agreement was to develop integrated territorial welfare plans and services (health, social affairs, and education) at the local level.

Within the scope of increasing access to quality public primary health care services, and supporting the primary health care centers (PHCC) and public schools in the most vulnerable areas affected by the influx of displaced Syrians, the following interventions were carried out:

- Provision of dental materials, dental equipment, and instruments was completed in two Primary Health Care Centers (PHCCs): Haret Hreik and Al Najdah Al Shdabya (Halba).

- Provision of dental instruments and dental equipment was completed in two PHCCs: Furn El Chebback and Mreyjeh.

- Provision of dental material was completed in four PHCCs and 10 SDCs: Chiah PHCC, Karagouzian PHCC (Bourj Hammoud), Baakline PHCC (Wadi Khaled), Makassed PHCC, Chiah SDC, Ain el Ramanah SDC, Bourj Hammoud SDC, Jbeil SDC, Baakline SDC, Zahle SDC, Baalbek SDC, Racheen (Zharta) SDC, Halba SDC, and Bint Jbeil SDC.

- Hygiene Kits were distributed through the municipalities to 15 Public school in the Baabda and Metn Districts in Mount Lebanon (Haret Hreik, Chiah, Ghobeiry, Furn Al Cheback, Al Mreyjeh, and Bourj Hammoud)

- An assessment was conducted in 72 public schools in the targeted 29 municipalities to evaluate school’s infrastructure, and WASH and health conditions.

- 48 public schools were provided with IT, medical equipment, and furniture: Haret Hreik (First), Haret Hreik (Second), Al Chiah (First), Al Chiah (Second - Girls), Al Chiah (Second - Eng.), Jbeil Kindergaten, Jbeil First, Jbeil Second, Jbeil Fourth, Abou Chabaket, Baakline Public (Interm), Bar Elias Elementary (First), Bar Elias Intermediate, Bar Elais Secondary, Jarat Al Wadi, Housh Al Oumara, Zahle (First - Girls), Zahle (First - Boys), Zahle (Second - Girls), Zahle (Third - Boys), Zahle (Second - Boys), New Zahle, Wadi Al Arayish, Al Mealakah (Girls), Al Mealakah (Boys), Terboul Public school, Taalabaya Public School, Tal Al Abiad (Near Village), Al Labweh Intermediate, Kfarzena, Mazyara, Racheen, Haraf Ardeh, Ardeh, Assad Al Sabaaali, Al Bekeia'a, Al Moukbileh, Al Hishe, Al Fared, Nabih Awad, Al Awadeh, Al Amayer, Rajem Khalef, Rajem Khalef Al Kalkha, Al Karha, Heneidar (Mixed), Al Knaiseh Wadi Khaled, and Abdel Latif Saad.

- The rehabilitation of the Primary Health Care Centre of the municipality of Haret Hreik was completed in April 2015. The inauguration took place on May 14, 2015 under the patronage of the deputy of the Block for Fidelity to the Revolution, Mr. Mohammad Raad and with the presence of the representative of the Ministry of Public Health, Mrs. Randa Hamadeh, the Director of the Department of Primary Health Care at MoPH, UNDP Country Director, Mr. Luca Renda, the Lebanese Recovery Fund, Mr. Rony Gedeon, mayors, and civil society members.

- The rehabilitation of the Primary Health Care Center of Al Mreyjeh municipality was finalized in September 2015 (60% of the needed funds were covered by LRF and 40% by the government of Monaco Government). The site was handed over to the contractor in the presence of the municipality representatives and UNDP on June 22, 2015.

- The works for the rehabilitation of nine medical rooms in the public schools of Jbeil Kindergarten, Jbeil First, Jbeil Second, Jbeil Fourth in Jbeil, Abou Chabaket in Zouk Mikael, Kfarzena, Mazyara, Racheen, and Ardeh in Zgharta were completed in August 2015 and handed over to MEHE in the presence of the involved engineer. An air conditioning system was installed in each medical room at the end of November 2015.

- The rehabilitation works for Halba kindergarten were completed in September 2016. The works included the restoration of student toilets, water points, and the medical room, in addition to waterproofing works for the roof.

A cycle of workshops began on July 25, 2015 and ended on November 21, 2015 facilitated by six experts from the American University of Beirut (AUB). The municipalities or cluster of municipalities involved are the following: Bourj Hammoud, Haret Hreik, Chiah, Baakline, Jbeil in Mount Lebanon; Chebaa and Binj Jbeil in Nabatiyeh; Baalbeck/Labweh in Baalbeck-Hermel, Terboul/ Bar Elias, Taalbaya/Zahleh in Bekaa; the eight municipalities of Wadi Khaled and Halba in Akkar; and the six municipalities of Zgharta in the North. The working groups were set up in the above-mentioned municipalities or cluster of municipalities. Meanwhile, the same working groups were organizing meetings on the side in order to support the workshop process. The members of the working groups include representatives of SDCs, PHCCs, public schools, and municipalities. The total number of participants is 400. The groups produced the integrated health plans of each municipality, and below is a summary of the planning cycle.

Output 2.2: Provide four Septic Pumper Trucks and a Sweeper to five Union of Municipalities in the South

The activity “Provide Septic Pumper Trucks to five Union of Municipalities (UoM) in the South” was amended and officially approved on January 14, 2015.

Most of the 658,000 residents of the Chqif, Jabal Amel, Tyre, Bint Jbeil, and Iqlim Tefah regions in South Lebanon suffer from the absence of sewage networks in their villages. Thus, the majority of the houses use cesspits with high cleaning costs that often results in negligence, therefore leading to leakages and related health problems. Presently, the households pay private dump-truck owners to periodically remove the sewage from the cesspits and dispose of them in sewage drainage canals or treatment units in the nearest available facility. On average, each household has to pay around USD700 per year – a hefty sum for the poor. The situation has become even more precarious with the large influx of displaced Syrians, which has introduced significant additional stress on the environment.

The project resulted in the procurement of four septic trucks respectively for Jabal Amel, Tyre, Bint Jbeil, and Iqlim Tefah and a sweeper for the UoM of Chqif. This will have a considerable impact on the environment and health conditions of the targeted Union of Municipalities improving the living conditions of its inhabitants.

The municipality then expressed the need for a sweeper to clean the streets, particularly the highway. By cleaning the surfaces and removing dirt and rubbish from the major roads and small streets, the UoM of Chqif will ensure a healthy and safe environment for its inhabitants. In addition, since UN-Habitat provided a septic truck to the UoM of Jabal Rihan during the project review period, the UoM of Iqlim Tefah was identified to be targeted as an alternative, since it was in need of a septic truck due to the absence of a sewage network. Furthermore, given that DFID is supporting the UoM of Arqoub by enlarging the wastewater treatment unit of Habbarieh, there was no longer a need for a septic truck. However, Bint Jbeil has been identified to be targeted since it has no sewage network and is in need of a septic truck.

Therefore, the project resulted in the procurement and delivery of four septic trucks respectively for Jabal Amel, Tyre, Bint Jbeil, Iqlim Tefah and a sweeper for the UoM of Chqif.

Output 2.3: Improve the water infrastructure in the Union of Municipalities of Qalaa

Many villages in South Lebanon suffer from shortage of household water, and the situation has worsened following the Syrian crisis and influx of displaced Syrians. One of the main reasons behind this is the old water conveyance network that often develops raptures and leakages, causing waste of this precious and essential resource. Currently, the 80,000 inhabitants of the 10 villages within the Federation of Municipalities of Qalaa (Tibnin, Haris, Kafra, Aita El-Jabal, Safad Al-batikh, Jmaijmeh, Deir Antar, Kfar Donin, Qalaway, and Yater) receive drinking water only two days a week, provided there is no leakage in the water system. The South Water Establishment, which covers the whole South region, is unable to respond to all the maintenance demands of the water network, especially the ones within the villages, due to the lack of proper tools and resources for detecting and repairing the raptured pipelines.

The project worked closely with the Federation of Municipalities of Qalaa to provide the water maintenance center with all the equipment and machinery necessary for repairing any possible problem occurring in the water network in the most efficient way. As per December 2014, the equipment and machines were provided to the center.

In addition, a training on water management and maintenance for the five technicians already employed by the municipalities was held on pipe network maintenance and management. The Union of Municipalities and the Water Authority are working together to establish a common Unit for Water Management and Maintenance. An MOU between the Union of Municipalities of Qalaa and the Water Authority of the South was signed for the implementation of the training, strengthening cooperation and improving coordination on water management. The project not only benefitted the Union of Municipalities of Qalaa but also other neighboring villages. It displayed its true effectiveness when the main pipe which irrigates Kafra, Haris and Bint Jbeil areas was repaired within 36 hours.

Output 2.4: Provide sustainable lighting and heating to host communities

The provision of sustainable heating and cooking through stoves and briquettes and solar lighting kits involves several steps from (1) beneficiary identification, (2) site/beneficiary confirmation, (3) technical specifications of systems and procurement, (4) implementation, (5) monitoring of implementation, (6) operation and maintenance training, and (7) awareness-raising and donor visibility. These items are described below, along with respective progress.

2.4.1	Beneficiary identification

Beneficiary identification is one of the more challenging parts of this project in terms of defining those most in need, i.e., the vulnerable population. To ensure that we deliver the systems and respective products to those most in need, the UNDP-CEDRO team has undertaken consultations with the Ministry of Social Affairs, the National Poverty Targeting Project (NPTP) of the World Bank coordinated by the Office of the Prime Minister, the UNHCR Office in the Bekaa and the North, the UNDP offices in these respective regions, and the various municipalities in the villages selected.

For proper implementation of the project, and for reasons of lowering the risk of any disputes, it was decided that the systems will be delivered, to the extent possible, to clusters of communities in areas and villages within areas. On the one hand, the implementation of this project in this clustered approach would facilitate the follow-up and monitoring required as opposed to spreading the systems out to 500 beneficiaries in each of the two large areas (Akkar and Bekaa).

For Akkar, these areas were decided upon after intensive discussions with the Host Community Support Unit in Akkar consisting of the UNHCR, ACTED, DRC, PCPM, and REACH, among others. Work has been well advanced in Akkar, and a ‘vulnerability’ map has been produced, as shown below in Figure 2.4.1.

Figure 2.4.1. Vulnerability mapping of REACH – UNHCR based on several criteria.

From Map 1, work was decided to focus on the ‘red colored’ relatively higher vulnerable areas and/or villages, and these are mainly in Wadi Khaled, and some other villages like Bebnine in Akkar. To select beneficiaries within these villages, the lists from the Ministry of Social Affairs and the NPTP were officially requested for these particular areas, identifying those that are in ‘extreme poverty’ by names, contact information and addresses. These are the targets currently being focused on.

Similarly in the Bekaa, lists were also received from UNHCR Bekaa Office, that included actual names and numbers of beneficiaries that the UNHCR regarded as ‘vulnerable’. The list focused on Marej, Zahleh, Baalbeck, Majdal Anjar, and Aarsel. Aarsel was later dropped out due to the security situation. The UNHCR list was augmented by a list from the Ministry of Social Affairs of those considered ‘extremely poor’, similarly with updated names and addresses and these beneficiaries are the focus of selection.

For both regions, coordination and communication with local municipalities was ensured before and during the installation of the equipment in the households.  Most municipalities facilitated the work of the site engineers on the ground and supported in the coordination of the installation works.

2.4.2	Site/beneficiary confirmation

After the short-listing of households was completed based on the lists, the project site engineer undertook the detailed technical assessment based on the survey questionnaire (technical survey shown in Annex 1).  From the information collected, a further identification of the households that could technically support the installation of these systems and that are in need for additional electricity or heating systems (i.e. those not already connected to a private generator or that do not already have stoves or central heating systems for example) was undertaken.  This exercise was supported by the CEDRO team in Beirut as well.

Figure 2.4.2. Zahle, Bekaa (house) – Example from site visits

2.4.3	Technical specifications and procurement

The UNDP-CEDRO hired two international consultants to support in the development of the technical specifications for (1) the biomass stove and briquettes, and (2) the solar lighting kits.  The design of these systems had to be catered for the specific needs of Lebanon while at the same time, to select the latest products that are available in the market.

For the biomass stoves and briquettes, the terms of references were posted on the UNDP website on August 15th and the deadline for submission was originally 11 September 2014, yet extended for 1 week after multiple requests from bidders (only 1 week was given in order to ensure winter is met). Evaluation of five bidders was undertaken by CEDRO team and the contract was awarded to the winning contractor.

For the solar lighting kits, the terms of reference was posted on August 14th 2014 and the deadline was originally for September 8th 2014, however it was postponed for two weeks after multiple requests. Evaluation of eleven bidders was undertaken by CEDRO team, where a rebid had to occur given that no one of the contractors met the full required criteria set in the bidding document. Therefore, the procurement process was re-launched on the UNDP website. Six offers were received in the second process, and the contract was awarded to the most technically/financially compliant contractor.

For the briquetting plant in Aandket, the terms of reference, prepared by an international consultancy were posted on the UNDP website on January 08th, 2015 and the deadline for submission was February 16th, 2015. Evaluation of three bidders was undertaken by CEDRO team and the contract was awarded to the most technically/financially compliant contractor (being Solarnet).

2.4.4	Implementation

Stoves and briquettes: given that the bidding process resulted in some financial savings as a result of competitive pricing, additional number of stove and briquettes were procured. The overall quantity distributed was 594 units for both Akkar and the Bekaa. The stoves along with an initial supply of approximately 1,280kg of briquettes per household were delivered. A second batch of briquettes of 320 kg per household was delivered. The locations and distributed items are described in Table 2.4.1 and 2 and Figure 2.4.3.

Table 2.4.1. List of the villages: supply and installation of the biomass briquettes and stoves in Bekaa region

| Item | Region | Selected Beneficiaries | Stoves delivered | Briquettes (1st delivery: 1,280 kg/beneficiary) | Briquettes (2nd delivery: 320 kg/ beneficiary) |
| --- | --- | --- | --- | --- | --- |
| 1 | Al Marej | 27 | 27 | 27 | 27 |
| 2 | Brital | 7 | 7 | 7 | 7 |
| 3 | Baalbek | 103 | 103 | 103 | 103 |
| 4 | Doures | 2 | 2 | 2 | 2 |
| 5 | Ein Kafar Zabad | 27 | 27 | 27 | 27 |
| 6 | El Khodor | 10 | 10 | 10 | 10 |
| 7 | Heleniye | 2 | 2 | 2 | 2 |
| 8 | Kousaya | 22 | 22 | 22 | 22 |
| 9 | Majdal Anjar | 25 | 25 | 25 | 25 |
| 10 | Nahle | 23 | 23 | 23 | 23 |
| 11 | Nabe Youchaa | 1 | 1 | 1 | 1 |
| 12 | Tal Abyad | 5 | 5 | 5 | 5 |
| 13 | Younine | 20 | 20 | 20 | 20 |
| 14 | Zahle | 14 | 14 | 14 | 14 |
| 15 | Ansar | 3 | 3 | 3 | 3 |
|  | TOTAL (BEKAA) | 291 | 291 | 291 | 291 |

Table 2.4.2. List of the villages: supply and installation of the biomass briquettes and stoves in Akkar region

| Item | Region | Selected Beneficiaries | Stoves delivered | Briquettes (1st delivery: 1,280 kg/beneficiary) | Briquettes (2nd delivery: 320 kg/ beneficiary) |
| --- | --- | --- | --- | --- | --- |
| 1 | Amayer - Rajm Issa | 30 | 30 | 30 | 30 |
| 2 | Bebnin | 30 | 30 | 30 | 30 |
| 3 | Fnaydek | 42 | 42 | 42 | 42 |
| 4 | Kfartoun | 30 | 30 | 30 | 30 |
| 5 | Hichi | 25 | 25 | 25 | 25 |
| 6 | Majdel | 19 | 19 | 19 | 19 |
| 7 | Rama - Germaya | 36 | 36 | 36 | 36 |
| 8 | Saed | 7 | 7 | 7 | 7 |
| 9 | Rajem Hussein | 22 | 22 | 22 | 22 |
| 10 | Knaysse | 19 | 19 | 19 | 19 |
| 11 | Rajem Khalaf | 18 | 18 | 18 | 18 |
| 12 | Karha | 10 | 10 | 10 | 10 |
| 13 | Hnayder | 15 | 15 | 15 | 15 |
|  | TOTAL (AKKAR) | 303 | 303 | 303 | 303 |

Figure 2.4.3. Pictures of the installed biomass briquettes and stoves with beneficiary households.

Solar lighting kits: 550 PV lighting kits were distributed in both Bekka and Akkar areas. (Original contract for 500 kits with additional 50 kits in amended contract). In addition, the project finalized a simple operation and maintenance manual in Arabic for the lighting kits that was distributed with the equipment to the beneficiaries. The provision of these kits have given the beneficiaries a feel of security and warmth in their households. The locations and distributed items are described in Table 2.4.3 and 4.

|  |  | Solar lighting kits delivered |
| --- | --- | --- |
| Akkar | Bebnine | 30 |
|  | Qarha | 15 |
|  | Hnayder | 16 |
|  | Hichi | 15 |
|  | Kfartoun | 30 |
|  | Majdel | 24 |
|  | Saed | 5 |
|  | Knayseh | 33 |
|  | Amayer | 15 |
|  | Fnaydek | 19 |
|  | Rajm Houssein | 29 |
|  | Rajm Khalaf | 16 |
|  | Sir Donniyeh | 3 |
|  | Total Selected | 250 |

Table 2.4.3. Solar lighting kits delivered in Akkar.

|  |  | Solar lighting kits delivered |
| --- | --- | --- |
| Bekaa | Zahleh | 15 |
|  | Nahleh | 25 |
|  | Baalback | 60 |
|  | Younin | 18 |
|  | Majd Anjar | 16 |
|  | Al Marej | 24 |
|  | Britel | 6 |
|  | Ansar | 2 |
|  | Ain Kfarzabad | 21 |
|  | Kouseya | 11 |
|  | Al Khodor | 10 |
|  | Siriin El Tahta | 26 |
|  | Hadath Baalback | 26 |
|  | El Qaa | 26 |
|  | Lebanese Army | 6 |
|  | Hermel | 1 |
|  | Ansar | 2 |
|  | Tal Abiad | 3 |
|  | Doures | 1 |
|  | Nabi Rched | 1 |
|  | Total Selected | 300 |

Table 2.4.4. Solar lighting kits delivered in Bekaa.

The briquetting plant in Aandket implementation was completed in September 2015. It is currently operated by the municipality and contractor to insure adequate capacity building is transferred.

2.4.5	Monitoring of implementation

The UNDP-CEDRO team monitored the installations of the winning contractors to ensure that the requisites identified in the terms of reference were implemented to the standards required.  Nearly daily monitoring and verification was undertaken by the site engineers so that the quality and satisfaction of the beneficiaries was met.

2.4.6	Operation and maintenance training

All the systems come with a performance guarantee for two years (with the exception of the briquettes that will be burned). However, the proper operation of the systems (stoves and solar lighting kits) are critical for ensuring their longevity. To this end, the UNDP-CEDRO project finalized a simple operation and maintenance manual in Arabic for the stoves; it was distributed with the equipment. In addition, an operation and maintenance manual for the lighting kits was distributed to the beneficiaries. Also, a training for the beneficiaries on the systems took place upon installation of each piece of equipment.

2.4.7	Awareness raising and donor visibility

The operation and maintenance (O&M) manual mentioned above includes awareness-raising information on the benefits of using biomass stoves, briquettes and solar lighting kits. The O&M manual also included the donors’ logos of the systems. In parallel, all work was indicated in CEDRO’s newsletters, website, and promotional material, inclusive of Donor recognition and/or logos.

Most of the work is also photographed and shared on CEDRO’s website, Facebook and Instagram pages.

Furthermore, two documentaries were undertaken by the UNDP and the project; the first documentary captured the distribution and installation of the stoves, and the second documentary captured the installation of the PV lighting kits and can be found on the UNDP’s website and Facebook, as well as on CEDRO’s website;

https://www.facebook.com/video.php?v=910369802317027&set=vb.734820073205335&type=2&theater

2.4.8	Delays in implementation, challenges, and lessons learned & best practices:

The project was completed; however, the following issues had to be noted:

Delays in implementation in Akkar and Bekaa had been significant, in terms of visiting potential beneficiaries and filling the technical surveys. This delay was mostly due to security issues in both regions and road closures.

- Request for extension of procurement deadlines had been likewise experienced where many contractors requested the extension of the deadline date for bid submission.  This is mainly because the systems being procured are not standard and have not been purchased before in Lebanon.

- As for the PV lighting kits procurement process, a delay had occurred where a rebid had to occur given that no one of the contractors met the full required criteria set in the bidding document.

- Delays occurred due to the mandatory use of an armored vehicle for Wadi Khaled to comply with UNDP security rules and regulations.  UNDP purchased an armored vehicle for the site however many teams share this vehicle which sometimes results in delays.

2.4.9	Qualitative assessment

The reception from all the beneficiaries, as well as the concerned municipalities, was very positive with impacts highlighted in the short documentaries; i.e.:  https://www.facebook.com/video.php?v=910369802317027&set=vb.734820073205335&type=2&theater

Output 2.5: Improve government response to crisis and major civilian operations

Throughout the reporting period and with support from the LRF, UNDP and the Prime Minister’s Office scaled up their efforts towards improving the Government’s capacity on preparedness and response to manmade and natural disasters and crisis. This objective, led by the Prime Minister’s Office, is now further reflected as being a civilian led operation through the space given to the UNDP DRM team to implement its activities, under the leadership and in close cooperation with the Secretary General of the Council of Ministers.

One of the main achievements during the reporting period is the cooperation that different government institutions reflected towards the UNDP DRM team, whether security institutions or civil public institutions at the national, sectoral and local levels. This is a clear indicator to UNDP’s success in putting Disaster Risk Management on the agenda of public instructions, which is an ongoing UNDP objective, now closer than ever of being achieved through many years of advocacy and cooperation with the Lebanese institutions.

Another key success is the substantive progress achieved in developing a comprehensive preparedness and response mechanism, governed by state institutions at the national, local and sectoral levels. To date, a number of ministries, governorates in addition to the Prime minister’s Office have been equipped with Operation Rooms (containing advanced IT and Communication equipment) and their respective crisis teams have led on and participated in the development of risk assessments, response plans and table top exercises or simulations.

Finally, and during the reporting period, more focus was given to DRR awareness through the extensive use of different communication tools including social media (Facebook and twitter), board games, interviews, TV reports, newspapers and radio shows/interviews to share DRR related messages, success stories, activities and recommendations.

2.5.1	The establishment of a National Operations Room (NOR)

NOR Equipment and Launching

In 2012, UNDP achieved a milestone in the development of the National Disaster Risk Management Strategy focusing on all four phases of mitigation, preparedness, response and recovery.

By 2013, UNDP had finalized the National Response Framework which has become a reference document for all concerned agencies, stakeholders and decision makers. At the institutional level, a decree was issued in 2013 for the establishment of a National Coordination Committee (NCC) which includes Director Generals of concerned ministries, representatives of concerned agencies, and decision makers.

In 2014 and thanks to the support received through the LRF fund, UNDP started developing the National Operations Room (NOR) as described in the NRP. Having the location of the NOR within the premises of the Prime Minister’s Office which reflects the government's commitment to risk reduction.

By 2015, the NoR was equipped with Office furniture, IT and Audio Equipment, Network and Communication Systems, Infrastructure and Equipment and a Video Wall system.

The NOR provides a platform for decision makers in order to communicate efficiently with sector/ministry and regional response teams involved in the response mechanism. The NOR is also considered a central information hub where all operational information gathered from the field will be routed to, thus enabling the National Coordination Committee NCC and the Prime Minister to take appropriate political decisions. Moreover, the NoR will be the hub used to gather, analyze and disseminate information for early warning. The NoR design is based on best practices and international expertise and standards, that UNDP was able to provide public servants through several study visits including to the “Montgomery Emergency Operations Center” in the USA, to the "Centre Opérationnel de Gestion Interministérielle des Crises (COGIC)” in France and to the Italian Civil Protection.

The NOR was launched on the 27th of May 2015 under the auspices and presence of His Excellency the President of the Council of Ministers, Mr. Tamam Salam and with the participation of several ministers and decision makers. The event signaled a new phase in disaster and crisis response in Lebanon as the operations room completes the National Response Plan in terms of having a center where response management and decision making and guidance at the national level is implemented, and for DRR and resilience in Lebanon is achieved.

Moreover, the development of the NOR technical team was launched in December 2015, several capacity building trainings were implemented for the team with the support of other funds.

In 2016, a national table top exercise was conducted on July 15 under the auspices and participation of H.E Prime Minister Sallam to test the NOR team effectiveness on disaster response in line with the National Response Plan (Refer to annex 1 for the press release). The table top focused on strengthening the management, operational and coordination capacities of the NOR team where 22 agencies, ministries and concerned stakeholders are represented in the context of international assistance. The results of the exercise were remarkable and allowed the team to increase their technical expertise in the management of international procedures within international standards.

2.5.2	National Simulation

As part of enhancing and testing the response skills at the national, sector and regional levels, UNDP conducts annual field simulation exercises as since 2014 to push forward the implementation of the National Response Plan for crisis and disasters.

Thanks to the contribution received from the LRF, a national field simulation was conducted on the 28th of March 2015 in Saida for testing the South Mouhafaza response plan. For the first time, the simulation was partly broadcasted live on Future TV to raise awareness among the mass population on DRR. The exercise which included NCC members and the Response Committee of the Governorate of South Lebanon put in practice search and rescue operations including at sea, deployment of a mobile hospital, evacuation of school students, first aid and sorting of injured, firefighting of burned vehicles, removal of debris and closing perimeters. Apart from the successful organization and implementation of this simulation and most importantly, the Governorate of South Lebanon showed an unprecedented commitment both in the organization of the event, but also in pursuing the collective efforts in building the resilience of the region, and the whole country. Field simulations also ensure that response plans are being implemented in a standardized way at the national, sector and regional levels and that response agencies work according to set standard operating procedures based on their mandates. Simulations also allow agencies to train on coordinating actions among each other and on communicating field information for political decisions. (Refer to Annex 2 for the Press release Simulation of South)

2.5.3	Establishment and setting up of a Mobile Operations Room (MOR)

On October 17, 2016, the Mobile Operations Vehicle (MOV) was finally delivered to the premises of the Prime Minister’s Office and is now part of the Government’s assets (refer to annex 3 for the official decree).

This pilot project took around 14 months of implementation (starting from contract signature with the vendor) and is the first of its kind in Lebanon. Within the framework of crisis and/or disaster response, the MoV’s main purpose is to provide a physical meeting space for heads of security (and other public institutions) agencies leading the field response, to discuss and share information gathered from their teams, discuss operational actions, take informed operational decisions and transfer information to the National Operation Room (if necessary) when there is a need for political decision making.

The MoV was tailor made to the Lebanese context and was designed by UNDP with the help of 2 senior experts from the French Civil Defense, who also accompanied UNDP during the implementation phase of the project and attended the 3 inspection visits that were organized with the vendor in Eastern France, to make sure that the project was being implemented in accordance with the plans, the technical specifications and the international industry standards.

The MoV offers a working space for 7 officials (in addition to the 2 vehicle operators) and is equipped with computers, phones, TV screens, and a video conferencing system. To maximize the autonomy of the MoV and ensure its ability to operate for long periods of time, the MoV is designed to operate through 3 alternative sources of power supply (50m cable, a soundproof generator integrated to the structure of the Vehicle, a UPS with a 12V power supply capable of sustaining all computer and communication equipment as a last resort) and with 3 main sources of internet and telephony connectivity (analogue cable, 8 GSM Sim cards with 3g/4g connection, satellite system). The MoV is also equipped with a video conferencing system and a satellite television system linked to 3 separate TV screens. The MOV is equipped with an automated self-leveling system and a side awning to respectively offer minimum standards of comfort and ensure an outdoor working space for line officers away from natural elements (sun, rain…).

Between October 19 and 21 2016, a training session was organized at the PMO by UNDP and the vendor for the ISF staff assigned to operate the MoV, covering the usage and maintenance of all equipment and systems (refer to annex 4 for the training agenda). The training was attended by 8 ISF members and 1 UNDP team member located at the Serail.

Finally, the MoV took part in the 2016 field simulation exercise (funded by EU) which was organized in an industrial area in Keserwan-Governorate of Mount Lebanon and will be part of the 2017 field simulation exercise which will take place in May 2017 in Baalbek-Hermel governorate (with funds from Netherlands).

It is worth noting that apart from the generous contribution from the Lebanon Recovery Fund to this project, SDC, Kuwait, EU and also contributed to funding it.

2.5.4	HFA Annual Progress Report

As part of reporting on the progress achieved in implementing the Hyogo Framework of Action, UNDP developed and submitted through consultation with major partners and stakeholders the final HFA Report for 2013-2015 in March 2015  prior to the 3rd world Conference on DRR.

The final report (Refer to annex 5) highlights the major accomplishments, government’s commitment and responsiveness to DRM, while allowing strengthening cooperation and coordination among different public stakeholders, enhance understanding and work of DRR at the national, sectoral and local level.

While the report indicates important progress it also identifies gaps and challenges that need to be overcome such as the approval of DRR laws,  being more proactive to DRR and safety, funding DRR actions that support resilience at the government, sector and local authority levels, implementation of the National Disaster Strategy, increasing awareness, maintaining hard won development gains, developing holistic maps, developing capacities (especially within critical sectors), reinforcing preparedness actions.

Sendai Report

In March 2015, the Sendai Framework for Disaster Risk Reduction (SFDRR) was approved during the third world conference in disaster risk reduction which took place in Japan in replacement of the Hyogo framework of action.  A set of new indicators to measure progress in the implementation of the Sendai Framework for Disaster Risk Reduction 2015–2030 were processed. As such, the UNISDR selected Lebanon (from the Arab States), to pilot the SFDRR indicator proposal. For this purpose UNDP and with the collaboration of UNISDR conducted a workshop on the 7th and 8th of September 2015 to engage all national DRM, development and climate change adaptation actors as well as some members of the UNCT to present the concept of the new indicator system as well as linkages to SDGs and climate conventions.  The workshop also served as an opportunity to gather Lebanese experiences in the collation and monitoring of various related indicators. Once adopted the participants will actually practice the new reporting system and better highlight progress and challenges based on the new priorities.

2.5.5	Supporting the CNRS in establishing the flood risk map

According to the World Bank approximately 70 percent of all global disasters are linked to hydro-meteorological events. Flooding poses one of the greatest natural risks to sustainable development. Since 2013 UNDP has been working in partnership with CNRS in the development of flood hazard mapping. To complement the work already achieved in the area of flood assessment mapping, UNDP agreed with CNRS to assess the flood risk over Lebanese watersheds and to develop a comprehensive methodology for flood risk mapping in order to protect life and property, support emergency services, promote public awareness, and encourage the development and implementation of long-term, cost-effective and environmentally sound mitigation projects.

Within this context, the UNDP also signed an agreement with the CNRS in November 2014 to develop the "Flood Risk Assessment and Mapping for Lebanon" which aimed at the:

- Prioritization of flood risk areas of hazardous rivers, analyzing the elements at risk, and building a flood events database.

- Development of a comprehensive field format and identify the vulnerability of the elements at risk.

- Building risk tables of the elements at risk and develop their damage assessment at 10%, 2%, & 1% flood exceedance probabilities.

- Development of flood risk maps at 10%, 2%, & 1% flood exceedance probabilities which allow assessment of the risk levels and estimation of the damage intervals and amounts.

- Making the maps available to the proper decision-makers, planners and relevant community stakeholders.

The final report was accomplished in September 2015, printed and disseminated in November 2015 (refer to annex 6 for the report) to major stakeholders to guide the National DRR strategy and will be integrated in the CDR land-use master plan. The developed flood risk maps is considered as a national product, and will therefore be used to guide the National DRR strategy. (Refer to Annex 7 for the Press release Launching of Flood Risk Mapping for Lebanon)

2.5.6	Collaboration and support of concerned Ministries

Within the framework of supporting key sectors in DRM and in accordance with the national response plan, UNDP and through the LRF fund supported the Ministry of Social Affairs, Ministry of Education, Ministry of Agriculture, and BRHIA in developing their respective response plans, establishing their operation rooms and testing its efficiency through table top exercises.

In each of the above institutions, the following mechanism was implemented:

Developing Response Plans

The development of response plans includes the following major actions:

- Submit official request to the minister;

- Present the National response plan;

- Establish DRR committees;

- Develop general SWOT analysis with a focus on major hazards and needs;

- Develop DRR organogram;

- Develop roles and responsibilities of sections in preparedness, response and recovery;

- Gathering relevant data;

- Develop SOPs for the different phases of response;

- Finalize the response plan;

- Submit the response plan for comments, reintegrate comments and recommendations;

- Follow up with decision makers on to the integration of the plan within the sector;

- Develop the DRR action plan and support the sector in implementing the action plan if needed.

This process includes implementing bi-weekly meetings with each sector and requires around 1 year to be accomplished. Nevertheless, the impact that this process leaves is highly rewarding as it ensures that the sectors have integrated DRR within their programmes and that they are more capable to prevent and respond to disasters, while using the same tools and coordination with other stakeholders and linking their work and results to the National level.

Establishing Crisis Management Cells

Crisis Management cells were equipped with the following:

- Furniture: 1 Conference table and chairs (around 12 per room), desks (4 average), drawers, cabinets (2 cabinets average), fixed chairs (around 30 per room);

- IT Equipment: 4 laptops, 1-2 desktops, 1 printer, 1 fax, 1 projector, 1 screen;

- Communication system : VLAN System and related serveur

These Crisis Management cells are now all linked together through a secure communication system, and are in turn linked to the National Operation Room located at the Prime Minister’s Office. These rooms are essential for providing the necessary physical space, equipment and straight communication lines for the DRR teams to efficiently prepare for and respond to potential disasters and/or crisis.

It is worth noting that through extra fund received from the LRF in 2016 within the scope of this project, UNDP further upgraded the operation room within the Governorate of South. The upgraded operation room consists of two rooms one for technical teams from different agencies and stakeholders and another for decision makers. As such the new decision makers rooms has been upgraded with a conference table, 12 chairs, 12 laptops, an interactive smart board and related softwares.

Implementation Table Top Exercises / Simulations

Table top and simulation exercises provide an excellent opportunity to test the efficiency and effectiveness of response plans and also to test the coordination among concerned stakeholders. UNDP organized the related table top exercises for the MoSA (15 December 2014), MoEHE (5 March 2015) MoA (9 of March 2015).

These exercises are a necessary step in the process of developing public institutions’ capacities to prepare for and respond to disasters and crisis, and are meant to test the related DRR teams’ understanding of their role, their ability to work together to analyze data, discuss actions to be taken, take informed decisions, use the Operation Rooms and the equipment it contains and put into application the developed SOPs of the response plans. This is a good opportunity for the DRR teams to identify the weaknesses they have in Disaster preparedness Strengthening Disaster Risk Management and identify actions to be taken in the future to improve.

Implementation of the GARD Plan

Airports in general are considered to be one of the most important critical infrastructures especially important in the event of disasters, emergencies and crisis as they are essential to receiving or sending aid during disasters and they have strategic locations for logistics and communication. In 2014, UNDP had implemented the Getting Airports Ready for Disaster (GARD) initiative through a pioneer simulation to test its communication methods between different concerned agencies and shift work from theoretical to practical with the objective of increasing the effectiveness of response. The simulation supported assessing and evaluating the situation leading to better and more effective decision making. Moreover the simulation helped in developing plans to increase the effectiveness of concerned response agencies during disasters and crises. In 2015 and through LRF/Germany funds, UNDP updated the BRHIA response plan and operation room with necessary tools and equipment including IT, database and visual aids devices in addition to furniture, office stationary and latest state of the art communication system.

Support the Ministry of Industry to conduct risk assessment for major industrial areas to disaster risk

As part of implementing the National Strategy for Disaster Risk Management in Lebanon that was developed by UNDP and since the industry constitutes a critical sector, a related strategy for the industrial sector was developed. A senior consultant was contracted to develop the strategy and several meetings with key stakeholders with the objective of attaining an accurate description of the risk picture within the sector. The report "A preliminary analysis of intensive and extensive disaster in Lebanon" was accomplished in October 2015 and sent to the concerned agencies for commenting. The proposed strategy for disaster risk management in the industrial sector, is in line with international recommendations and state of the art practice in several important ways: 1) it recognizes that the level of detail of the hazard and risk assessment should be proportional to the level of risk. 2) it recognizes the need for site specific hazard assessments, particularly for fire, explosion and earthquake hazards of critical industrial facilities, 3) it recognizes the possibility of explosions occurring in industrial facilities, either independently of or due to earthquakes and fires, 4) it recognizes the importance of social, economic and institutional factors that contribute to vulnerability, and 5) it recognizes the importance of reducing cost while maintaining safety as a sustainable path towards improving the productivity of the industrial sector.

2.5.7	Introduce DRR concepts into the ENA and Military Academy Curriculums

Within the objective of integrating DRR within key public sectors including public servants and the Lebanese Armed Forces and part of UNDP's objective to raise national capacities; UNDP developed in 2013 a draft DRR curriculum on mainstreaming DRR within the public sector. In 2015 UNDP finalized the curriculum based on previous recommendations and implemented two training of trainers for public institutions. The curriculum which is the first of its kind includes a training of trainers manual, PowerPoint presentations with trainers outline objectives for each session, exercises, supporting documents and evaluation forms. The curriculum covers the major DRR and DRM topics and concepts including:

- DRR Terminology,

- HFA, Sendai Framework,

- increasing resilience in critical infrastructure,

- national overview of Risks in Lebanon,

- the national strategy for disaster risk management in Lebanon,

- analysis of disaster losses in Lebanon, linkages between disaster risk factors,

- lessons learned from across the globe on mainstreaming risk reduction considerations within public sector,

- sustainable development in the Arab world,

- financing disaster risk reduction activities for sustainable development,

- DRR capacity building,

- disaster risk governance, and

- early recovery.

The sustainability of delivering the curriculum and its integration within the public institutions sector has been ensured through its adoption by the ENA and Lebanese Armed Forces.

DRR training for the ENA

A training of trainers in Disaster Risk Reduction (DRR) and Sustainable Development was implemented with the collaboration of the Ecole National d'Administration (ENA). The training was conducted on the 13th, 15th and 16th of June 2015 and targeted 30 participants from different sectors and agencies including trainers from the ENA. The TOT focused on the different phases of DRR, Lebanon Risk profile, the National Strategy for DRM in Lebanon, implementation of DRR strategies and the role of public administrations, international initiatives on DRR and sustainable development who will ensure the sustainability of implementing DRR trainings for the public servants on a periodic basis.

DRR Training for Lebanese Armed Forced

Following the completion of the DRR and Sustainable Development curriculum a training of trainers' workshop on Mainstreaming DRM Considerations into the Activities of the Public Sector was held at the Fuad Chehab Command and Staff College in Yarze, Lebanon. The TOT was conducted from the 28th of September till the 2nd of October 2015 and included a total of 20 ranking officers. The training was divided into two focus areas, the first three days the participants received lectures on DRM and its interaction with development and sustainable development. While the last two days the participants, in groups of 2, presented pre- selected topics on DRM so as to put into practice the theoretical concepts. The participants considered the topics to be relevant to their work and of high importance.

As a follow-up to the training the following recommendations were proposed:

- Create a DRM mainstreaming Bureau within the Army to mainstream DRM into the work of its different directorates. One of the first tasks of this Bureau would be to review the mandates of the respective directorates and propose their augmentation with DRM tasks.

- Review the design specifications for the  Army  structural  installations  to  ensure  it  accounts  for  DRM considerations.

- Carry out a qualitative assessment of the Army installations and prioritize them according to risk categories.

- Identify options for strengthening.

- Identify financial needs required to implement the strengthening. Develop a long term multiyear program for their strengthening (e.g. 10 to 20 years).

- Develop a Strategy for Mainstreaming DRM into the work of the Army, with an action plan; time bound activities and financial needs for implementation.

2.5.8	Support to 25 local authorities in North and Bekaa to adopt resilient city charter

Implementation of Municipalities Curriculum

Within the "World Disaster Reduction Campaign “Making Resilient Cities – My City is Getting Ready” which targets local governments with the objective of achieving resilient, sustainable urban communities.  The UNDP – Disaster Risk Management Unit at the Presidency of the Council of Ministers and with the support of UNISDR regional office and UNISDR Office for Northeast Asia at Incheon – GETI conducted Training of Trainers workshop on building the capacity of local stakeholders namely regional and Mouhafaza representatives for Making Cities Resilient to Disasters at the Grand Serail in Beirut, Lebanon from the 23rd till the 24th of July 2015. A closing ceremony was attended by Gen. Mohamed Kheir, Secretary General of High Council of Defense of the Government of Lebanon; Mr. Luca Renda Country Director of UNDP in Lebanon who highlighted the importance of this training in making cities resilient through adequate implementation of the 10 checking points and support in increasing Lebanon's resilience.

The TOT was attended by more than 20 representatives from Lebanon's governorates, Caza and major cities with the objective of getting trained so that they can train all of the municipalities within their districts on how to adopt the campaign and implement the 10 checking points.

The training of trainers which was implemented for three days is another building block in supporting local governments integrate DRR into sustainable development and increase their resilience.

The training has achieved its objectives in:

- Training a team from national, ministry and local governments on the campaign ten essentials and tools to adequately implement the campaign

- Drafting City Resilience Assessment Reports

- Drafting City Resilience Action Plans

- Drafting of Strategy paper on how to further finalize, ensure endorsement and effectively implement the City Resilience Action Plans

Moreover and through other funding sources, UNDP continued its support to local level municipalities mainly through capacity building, awareness and DRR actions.

Support the establishment of regional crisis response plans and operation rooms

Within the comprehensive approach of reaching out and building capacities for disaster risk reduction including preparedness and response to emergencies at the national, sectoral and local levels, UNDP supported 4 Governorates (Governorate of of South, North-Tripoli and Baaklbek Hermel), 3 Caza (Caza of Byblos, Caza of Chouf and Caza of Metn), 2 Union of municipalities (Union of Tyre and Union of Dannieh), by developing their response plans, crisis management cells in line with the National Response Plan. The same methodology and tools implemented for the ministries was also conducted for the implemented for the Governorates including development of response plans, crisis operation rooms and table top exercises.

2.5.9	Awareness raising on crisis preparedness

DRR Campaign Implementation of the IDRR Day

In 2015, UNDP implemented several activities to raise awareness of different stakeholders and the general public with the objective of promoting disaster risk reduction at the individual, household, community and institution level.

This included implementing training sessions on DRR with the collaboration of NCLW targeting women NGO's in Chiah and Baaklin regions and the distribution of emergency kits for replication within major governorates, local level authorities and public institutions (Union of Municipalities of  Tyre, Governorate of South, CNRS,  NCLW, Governorate of Akkar, Kaemakam Metn, Governorate of North -  Tripoli, Governorate of Beirut, Governorate of Mout Lebanon, Governorate of Baalbek, Governorate of Bekaa, Caza of Aley, Lebanese Army). UNDP also implemented the 2015 the International Day for Disaster Reduction "Knowledge for life" which is a day to celebrate how people and communities are reducing their exposure to disasters and raising awareness about the importance of DRR. IDRR was highlighted using media tools including interviews, reports and live presentations on the following TV, radio, and newspapers; MTV, Future, Teleliban, Telelumiere, Radio Nostalie, Radio Liban Libre, L'Orient le Jour. (Please Check Annex 8 Press release L'Orient Le Jour IDRR Day)

Promote the idea of making personal and family emergency kits

As part of raising awareness on disaster preparedness and response at the population level within the International Disaster Risk Reduction Day activities the project updated and reprinted 100,000 copies of the DRR home guide for disaster preparedness and response covering various natural hazards such as earthquakes, Tsunamis, Forest fires, landslides, storms and a guide on what to include in preparing for an office or home emergency kit.

The home guides were distributed in collaboration with the Internal Security Forces all over the Lebanese regions and the activity was accompanied with a social media campaign through the ISF twitter account.

DRR Emergency kits

Spreading awareness among government entities, the civil society and the private sector on emergency preparedness is a fundamental element in disaster risk reduction. In this context, and as part of supporting disaster preparedness UNDP procured 1,000 new emergency kits. The emergency kits were distributed in January 2015 to major stakeholders as prototypes for replication with the objective of raising awareness and preparedness. A comprehensive list of these stakeholders was developed focusing on the three levels of the project stakeholders national, sectoral with a particular focus on the local level stakeholders including municipalities with highest vulnerabilities and Syrian refugees.

Develop an interactive disaster risk reduction mobile application DRM Lebanon

Access to vital information before, during and after emergencies and disasters is critical to help saving lives. Knowledge, science and technology play an important role and empower people to get prepared and manage disasters. With the objective of creating solutions to reduce natural disaster risks and to better prepare for and respond to major natural disasters, the project developed a mobile application targeting the Lebanese public to help raise their awareness, preparedness, early warning and response on disasters. Within this scope, the project mobile application performs a variety of functions including:

- Information on the major natural hazards that could affect Lebanon,

- Information on how to be prepared for different types of natural hazards: before, during and after,

- Information on building your emergency kit

- Link to useful Disaster Risk Management Contacts (hotlines)

- Subscription to early warning and alerts as well as receiving early warning messages

By a simple click subscribers to the mobile application will be better informed, prepared for and respond to major natural disasters. The application and notifications are free of charge, currently the application is being used by all partners and stakeholders within the governorates operation rooms and is being promoted among local communities.

2.5.10	Qualitative assessment:

Since 2014, UNDP made a major breakthrough in supporting Lebanon in preparing and responding to disasters.  UNDP fostered partnerships and built collaboration with the main concerned stakeholders and agencies of DRR which includes: the Prime Minister's Office (PMO), the NCC which constitutes representatives of all ministries and concerned agencies, higher council of defense, relevant ministries, Governorates, Caza, Kaemakam, municipalities, red cross, civil defense, media, private sector, academics (universities) Moreover the project fostered collaboration with international agencies such as COGIC and Italian Civil Protection.

This collaboration has resulted in higher degree of visibility as well as reinforced partnerships for the DRR at high level decision making in Lebanon as well as local authorizes and stakeholders.

Moreover the support received by the Lebanese Recovery Fund through the German Embassy has further advanced project activities.

Outcome 3: Local level dispute resolution strengthened and community security improved

Output 3.1: Develop local level peace building strategies to mitigate tensions in selected conflict prone areas of Lebanon hosting Syrian refugees

The two objectives of this output are the conflict mapping and conflict analysis (CMA) exercise and the establishment of a local peace mechanism in Bekaa area.

The conflict mapping/conflict analysis exercise developed in cooperation with Lebanon Support NGO (http://cskc.daleel-madani.org/cma) achieved more than expected. The current online map developed by UNDP is an interactive tool which has different options in filtering information related to the mapping (by date, by geographical locations, by type of incidents, by number of injured and death tool). In addition, new options were developed such as Actors Profiles (overview of main actors of conflicts); timelines for specific events. Conflicts are also classified.

After consultative meetings with key experts in conflict mapping, an interactive and collaborative conflict profiling platform and mapping system was developed and launched online and became public by the end of August 2014 and was sent to more than 15,000 email addresses (Lebanon Support database). This platform is a visual interface to explore conflict-related data and analysis in Lebanon. The system aims at providing partners involved in peace building, humanitarian and stabilization activities in Lebanon with accurate data and relevant information on areas prone to conflict. The system tracks incidents, protests, and conflicts between individuals, groups and communities and maps their location throughout Lebanon and is continuously updated. It currently provides users with different means and tools to browse and read different conflict incidents reports through various categorization schemes. Reports can be generated based on dates, locations, types of incidents, and number of individuals injured or the number of deaths resulting from conflicts. The system can also generate reports based on different classifications of conflicts. Classification of conflicts include: boundary conflicts (Lebanon/Syria); individual acts of violence; conflicts of social discrimination; conflicts of socio-economic development; power and governance conflicts; and policy conflicts. Users are able to filter out results based on these indicators and assess trends and locations of conflict in Lebanon. The map is updated on a daily basis and data collected in the mapping system is based primarily on media reports which are validated by cross-checking reports using different sources, and are then mapped, categorized, classified and published on the map. Some linkages, were also made with key NGOs working on the field from which reports and data are being collected (until January 2016, the map has garnered more than 5,400 page viewers).

The map has established UNDP as a reference for conflict mapping and analysis which attracted national and international attention to the product. Lebanon Support mentioned having received many inquiries and positive feedback about this tool, from national and international parties: Princeton University (UK), ODI (UK), LHIF Lebanon, Teslagovernment (USA), Aix Marseille University (France), Roskilde University (Denmark); as well as from many Lebanese and foreign journalists, and many officials in a number of embassies.

On the Conflict Analysis part, four reports were produced and gathered very positive feedback. These reports focusing each on a specific geographical area, look closely at the causes of conflicts, trends, dynamics, actors, triggers, etc. The methodology includes interviews, focus groups, desk reviews, etc. They provide an analytical summary of the conflict contexts in each region: Bekaa, Saida, Mount Lebanon and Beirut, with a focus on the relationships between Lebanese and Syrians. Reports are based on a socio-political qualitative assessment based on experiences and perspectives of key sources as well as Lebanese and Syrian residents of the different regions. These key sources were selected to include individuals with knowledge that covers the region or the sub-region broadly and to reflect a variety of expertise, political learnings and sectarian belonging. Existing social network of researchers were used, in addition to recommendations by civil society activists (Refer to annexes 10, 11, 12 and 13).

Regarding the establishment of a local peace mechanism in Bekaa, UNDP also achieved more than expected. The intervention wasn’t only limited to the capacity building per say, neither to a quick response to the challenges caused by the Syrian crisis on social cohesion but engaged the local community into medium term strategies dealing with root causes of conflicts, both at the Lebanese-Lebanese relations level as well as the Lebanese-Syrian level. It also aimed at building the local infrastructure for peace, which is supposed to remain as a key resource to the municipalities and local actors, and is intended to help them dealing with any tension and conflict they might face.  The seven targeted municipalities in West Bekaa (Gaza, Marj, Manara, Mansoura, Hawch el Harimeh, Jeb Jennine, Machghara and Qara’oun) are part of the most vulnerable communities as per the Government and the UN classification. The process which included different steps led to very positive results and months after the end of activities, the mechanisms are still in place and functioning.

The main steps followed which reflects the main achievements of the process of establishing these peace mechanisms can be summarized as follow:

- Individual meetings with each mayor and key actors in each of the seven municipalities in order to introduce the project, collect information on the context and dynamics of the area, as well as recommendations and suggestions to contextualize the process and ensure the participatory approach. These meetings were also key in terms of selecting the participants which took part in the process, based on a specific criterion: ability to commit in time and in the principles of the project; having a good relationship with the local community; having an accepted character from the different political parties; having people from different sectors (education, political, youth, social, etc.); gender diversity

- Conflict analysis was conducted in each of the seven villages’ level. It identified the main causes of conflict, conflict dynamics and actors. It was also an opportunity to identify the main needs in terms of capacity building (Refer to the Conflict Analysis report in Annex 14). The commitment of participants was very strong and the level of attendees reach 100% during the conflict analysis sessions.

- A training programme was designed based on the needs identified and several sessions were delivered gathering each time more than 25 participants. The programme focused on conflict resolution, causes of conflicts, peaceful means of resolving conflicts, dialogue skills, communication skills, conflict management skills, and negotiation and mediation skills. The following observations were noted:

  - The high level of participation and commitment of participants

  - The good gender representation

  - Their idea to establish a joint committee as a follow up to the process that would deal with inter and intra communal tensions. (Refer to the retreats workshops report in Annex 15).

- Development of the peace building mechanism through coaching meetings to follow up on the main results of the trainings and discuss specific conflict issues and workshops based on which it was decided that a joint peace initiative would be created, the West Bekaa Peace Initiative. The level of commitment and participation was high throughout the process and even after it the committees are still meeting. Gender balance was ensured and diversity of participants.

Additional activities were also implemented:

A Special edition of the UNDP Joint News Supplement on Tripoli

The 20 pages of this newspaper gathered journalists, professors, artists from Tripoli, from diverse political and religious backgrounds who wrote positive articles about the city of Tripoli with the aim to create an alternative discourse on the city and to portray its positive image. On March 20th 2015, 38,000 copies of this supplement were produced and published and distributed with the three leading newspapers in Lebanon: Annahar, Assafir, and The Daily Start (in English). In addition 2000 copies were distributed through Libanpost to all ministries, embassies, municipalities, media outlets, universities and NGOs.

“This supplement will definitely be a tool to be used during large-scale meetings to discuss Tripoli and its issues” Mr. Adib Neemeh, participant in the supplement.

On the same day of the publication, around 3000 persons viewed the post related to the supplement on UNDP Lebanon Facebook page where it was shared. A discussion session was then organized gathering journalists, activists and prominent figures from Tripoli (around 55 participants) (Refer to Annex 16 for the Supplement).

“Nehna Ahel” campaign implemented by LOST NGO:

The Lebanese Organization of Studies and Trainings (LOST) launched a dialogue initiative, “Nehna Ahel Campaign”, aiming at preparing the ground for a reconciliation initiative that would engage local, non-partisan and civic partners willing to play an active role in rebuilding trust and creating new means of communication between Arsal and the neighboring villages. First a committee of 27 youth was formed in order to discuss the issues and problems faced in North Bekaa and come up with relevant solutions. This committee that met more than 6 times during three months, discussed all the project’s activities: the draw peace, the murals, the slogans that will be printed on the banners, the positions of the banners after consultation with the different municipalities. By the end of the three months, 20 banners promoting messages of peace were hanged on the main road leading from Arsal to Hermel. Peace drawings and murals gathered youth from the two areas and were done in Arsal, Ras Baalbeck, el Ein and Labweh. The drawings, murals, canvas and banners carried peace building messages and called for reconciliation, tolerance and acceptance of the other (especially relevant after Arsal clashes).

“Supporting Lebanese and Syrian youth promoting social cohesion through video production”, implemented by Zakira NGO:

The image Festival Association- Zakira launched a project in cooperation with UNDP to support Syrian and Lebanese youth promoting social cohesion through video production. The aim of the project is to build the capacity of 30 Syrian and Lebanese young people aged between 18 and 24 years living in West Bekaa, mainly in Marj and Mansoura by providing video and editing training courses through a series of workshops. The project also aimed at launching a dialogue among youth, inviting them to share their stories, their past and present. This project helped youth develop 15 short videos entailing stories from five to seven minutes, covering aspects of the Syrian refugee communities living in Lebanon, as well as stories from the neighboring Lebanese host communities. After conducting 17 training sessions on video and editing, Zakira helped youth develop 7 short videos entailing stories from five to seven minutes, covering aspects of the Syrian refugee communities living in Lebanon, as well as stories from the neighboring Lebanese host communities. These videos were finalized and the closing ceremony was held in July 2015 during which participants had the chance to present their work publically in Madina Theatre in Hamra and interacted with the public and explained the ideas of their movies (Refer to annex 17 for the 7 movies). In addition to the experience and knowledge students were exposed to, they showed progress in interacting and building friendship and acceptance between one another. They also had the chance to translate their problems and talk about their environment and society gaps through their films.

“Nihna Jiran” project implemented by SALAM NGO:

With support from UNDP, Salam LADC NGO launched a project called “Nihna Jiran” to raise awareness about infection diseases in informal settlements and other health issues. Under this project the following activities were implemented during the reporting period:

- Three recreational activities for kids, sensitizing 118 children from three Informal Tented Settlements in Bekaa (in Marj, Jeb Jennine and Qara’oun) on various topics such as: acceptance of differences, understanding of the different “other” and the importance of team work.

- Nine workshops were held inside the settlements, targeting 120 women in order to raise their awareness on the risks of infectious diseases and how to prevent them, building trust with their children, creating a safe space for kids to express their thoughts and ideas.

- Five workshops targeting 86 adult men and women aiming at developing emergency and rescue plans in three different settlements and their surroundings.

- Three committees were formed in three settlements playing the “liaison role” with other committees formed of hosts with the aim of building consent and trust between the two communities. Moreover the additional roles were assigned to sub-committees (health, emergency, logistics)

Supporting Lebanese-Syrian- Palestinian Spaces for Cultural Dialogue through a Cultural Festival in Shatila Refugee Camp

In celebration of the one-year anniversary of its Arts and Cultural Center, Basmeh and Zeitooneh organized and implemented a three-day arts festival within the center in Shatila refugee camp. The celebration organizers were able to bring together artists from Syrian, Palestinian, Lebanese and non-Arab backgrounds, while attendees came from the refugee, host and expatriate communities, encouraging greater social cohesion and mutual cooperation between them. The activities lasted three days, and included musical performances, art exhibitions, dance shows and the inauguration of the Arts and Cultural Center’s new public library. The walls of the center were repainted, new artwork were hung on the walls, and special hooks and lighting were installed in the exhibition room in preparation for the art and photography display. The new library was also decorated, with colorful drawings painted onto its interior and exterior walls. In order to advertise the event, the Arts and Cultural Center’s team members produced 300 posters in both English and Arabic, displaying the name of the celebration (‘Shatila: The Meeting Point’ in English), the activities on offer, and the necessary information about how to reach the Center. A Facebook page was also set up specifically for the celebration, and community members were invited from all nationalities and ages. In order to ensure that the event remained active on social media, staff members updated the page regularly with news and photographs. On the celebration’s first day, the Center doors were opened at 4pm, with community members of all backgrounds, from inside and outside Shatila, welcomed and greeted with a selection of soft drinks and sweets from one of Basmeh and Zeitooneh’s Small Grants businesses. Approximately 150 people attended the opening day, with a significant number of people coming from outside the refugee camp, and including those from Syrian, Palestinian, Lebanese, American, British and French backgrounds, among others. After the opening speeches and screening of a documentary on Basmeh activities, a tour of the art and photography exhibition was carried out by the organizers where audience interacted with the participating artists and photographers. The library was then officially inaugurated. A screening of short movies by “Nadi Li Kol el Nass” group was organized, showing works of Lebanese young movie makers, followed by dabkeh performances by two Lebanese-Palestinian dabkeh groups. The first day was closed by a performance of the popular Lebanese singer Sandy Sham’oun. The two following days witnessed the same types of activities.

Youth promoting peace in times of crisis (implemented by Tafawwoq wal Saada NGO)

The objective of the project is to promote, during a period of two months, awareness about social stability among 30 Lebanese and Syrian youth in Wadi Khaled, Al Fared and Al Amayer localities through a capacity building programme and youth-led communal activities between Lebanese and Syrian youth, with the participation and support from the respective municipalities of the targeted localities. The project achieved the following outputs:

- Enhanced the capacities of youth to moderate discussions among Lebanese and Syrian youth

- Promoted awareness about social stability among youths (approx. 500 youths)

- Mobilize  the establishment of youth group

- Trained youth on conflict resolution and peace building skills, communication, negotiation and moderation skills

- Organized and moderated two movie screenings with a guest speaker (this activity was organized on the commemoration day of the Lebanese civil war, 13th of April)

- Established a youth group in the targeted localities to lead this experience in other neighborhood villages in Wadi Khaled area in the future

Qualitative assessment:

The main implementing partners involved in this activity with UNDP are: from one side, and for the “Local Level Conflict Mitigation Activity” the main partners are the municipalities (West Bekaa) and the local actors active in their communities and the national NGOs (LOST, ZAKIRA, SALAM, Basmeh and Zeitooneh and Tafawwoq wal Saada). These actors took part in the conflict analysis which decided on the best social cohesion strategy that should be designed and in its implementation contributing to reducing tensions.

From another side and for the “Conflict Analysis” part, the main partner is the Lebanese NGO Lebanon Support. Lebanon Support was responsible for implementing the Conflict Mapping/Conflict Analysis exercise conducted on a regular basis.

Using the Programme Results Framework from the Project Document / AWP - provide an update on the achievement of indicators at both the output and outcome level in the table below. Where it has not been possible to collect data on indicators, clear explanation should be given explaining why, as well as plans on how and when this data will be collected.

|  | Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification |
| --- | --- | --- | --- |
| Outcome 1: Livelihood and economic opportunities increased in selected refugee hosting areas through upgrading, repairing and improving the production infrastructure and creating short and medium term employment opportunities. |
| Output 1.1: Support value added production of fruits and vegetables in Akkar through postharvest processing | The activity is implemented through direct procurement modality. The bidding process was finalized; the machine was procured and delivered and the workers were trained by the contractor on the use of the machine. A van was also procured and delivered. A workshop took place during the last week of August 2015 to train cooperative members about quality and hygiene standards during the production process and on the potential of dried fruits in the local market. | N/A | Procurement of goods |
| Output 1.2: Enhance business skills of local farmers/producers in Akkar | The activity is implemented through direct procurement modality. 8,500 plastic crates, a transportation vehicle, and the apple production line machine (for washing, grading and packaging) were procured and delivered. The hangar construction is completed. North LEDA provided the cooperative members with specific trainings in different business development fields such as management, business, and financial planning. | N/A | Procurement of goods |
| Output 1.3: Implement wastewater and water projects in Bekaa | The provision of a sewage treatment system in Qab Elias, implemented through direct procurement modality is completed. The rehabilitation of irrigation canals in Chwaghir and the extension of the waste water network in Ain Kfarzabad were implemented through grant agreement modality. In this respect, two grant agreements were signed with the targeted municipalities. Both projects are completed. | N/A | Services implemented |
| Output 1.4: Increase irrigated agricultural areas in North Bekaa | The works in the four localities are completed. |  |  |
| Outcome 2: Capacity of national and local actors (government and civil society) strengthened in the delivery of health, education and basic municipal services in a participatory manner and coordination of service delivery by all stakeholders. |
| Output 2.1: Increase access to quality public primary health care services and health awareness in public schools | The project is implemented through direct procurement modality. The provision of dental material, dental equipment and instruments, and Hygienic kits to PHCC and SDCs is finalized. The furnishing of medical rooms with IT, medical equipment and furniture in selected vulnerable schools is also completed. The rehabilitation of the medical rooms of the public schools of Jbeil Kindergarten, Jbeil First, Jbeil Second, Jbeil Fourth in Jbeil; Abou Chabaket in Zouk Mikael; Kfarzena, Mazyara, Racheen, and Ardeh in Zgharta was completed. The medical rooms handover to MEHE was completed. The rehabilitation of Al Mrayjeh PHCC was completed in September 2015. The updated Health Information System technical report was issued. The rehabilitation of Halba kindergarten was finalized in September 2016. An assessment was conducted in 72 public schools in the targeted 29 municipalities, to evaluate school’s infrastructure, and health conditions. A cycle of workshops aimed at producing an integrated health plan was finalized by end of November 2015. | N/A | Procurement of goods |
| Output 2.2: Provide Septic Pumper Trucks to five Union of Municipalities in the South | The project resulted in the procurement of four septic trucks respectively for Jabal Amel, Tyre, Bint Jbeil, Iqlim Tefah and a sweeper for the UoM of Chqif, and is implemented through direct procurement modality. The septic trucks and the sweeper were procured and delivered. | N/A | Procurement of goods |
| Output 2.3: Improve the water infrastructure in the Union of Municipalities of Qalaa. | The project was implemented through direct procurement modality. The van and the compressor were procured and delivered. A MOU between the Union of Municipalities of Qalaa and the Water Authority of the South was signed for the implementation of the training, strengthening cooperation and improving coordination on water management and maintenance. | N/A | Procurement of goods |
| Output 2.4: Increase access to energy and enhanced well-being of people in host communities through the installation of sustainable heating and lighting units Indicator: - Capacity of national and local actors (government and civil society) strengthened in the delivery of health, education and basic municipal services in a participatory manner, with coordination of service delivery among all stakeholders. Planned Target: - Provide sustainable lighting and heating to host communities | Site engineer hired Vehicle purchased Beneficiary identification completed through coordination with the Ministry of Social Affairs, National Poverty Targeting Project at the Office of the Prime Minister, UNDP North and Bekaa Office, and the UNHCR Questionnaire/survey finalized for technical assessment of identified beneficiaries (see Annex 1) 100% of target beneficiaries identified through household-level assessment/verification All the stoves were installed along with the briquettes supply All the PV lighting kits were installed Briquetting plant in Aandket completed Specification documents prepared for both technologies: solar lighting kits and stoves and briquettes The 550 solar lighting kits and 594 stoves and briquettes contracts were awarded to 2 different contractors Operation and maintenance manual and training to beneficiaries completed | Not Applicable. | Terms of Reference Offers Procurements Contracts Photos Press Releases List of beneficiaries |
| Output 2.5: Improve government response to crisis and major civilian operations Indicator 2.5.1: Support the establishment and set up of a fully functional and operational central National Operations Room (NOR) Baseline: Increased natural and man-made disasters in Lebanon Increased pressure from Syrian influx of refugees on resources Settlement of Syrian refugees is concentrated in the most vulnerable and poorest areas. Increased number of casualties from disasters. Lack of preparedness measures within the concerned response agencies. Weak coordination among concerned agencies during response to disasters. No unified disaster management language. Difficulty to access information. National operations room not institutionalized yet. National operations room not established. Increasing internal and external risks Mobile Operation Room not established Planned Target: Establishment of a National Operations Room Software and Equipment for D - Sattellite GIS Images - Furniture and equipment - Back up Serves - Exposure visit - Training and simulation - Finalization and integration of crisis response plan - Deployment of technical advisor to NOR Establishment of the Mobile Operation Room Indicator 2.5.2: Support to Four national ministries (MEHE, MoSA, MoA, BHRIA) in crisis preparedness and planning Baseline: Ministries lack response plans. Major ministries do not have a disaster management unit. Coordination and networking among sectors is limited. Sectors officers and staff have limited skills to DRM. Ministries lack crisis cells Planned target: Compilation of sectoral response plans Establishment of crisis cells Indicator 2.5.3: Support to 25 local authorities to adopt resilient city charter Baseline: Major municipalities in vulnerable and critical areas re not acquainted with the resilient cities campaign Major municipalities in vulnerable areas are not supported and presented with facilities to develop and integrate resilience within their local authorities development goals Local authorities officers and staff have limited skills in DRM Planned Target: Local level and technical support Indicator 2.5.4: Support establishment of regional crisis response plan and operations room Baseline: Major Mouhafazat , Caza and Unions do not have a response and action plan Major Mouhafazat and Caza do not have Regional operations room (ROR) Mouhafazat and local authorities have limited skills in DRM Planned target: Regional plan formulation for 3 Mouhafaza, 2 Caza and 2 Union of Municipalities Training and simulation of regional response plan Equipment of Ops room Training and simulation of OR Indicator 2.5.5: Awareness Raising on crisis preparedness Baseline: Limited media campaigns on DRR Limited public awareness on DRR and safety measures Planned Target: Distribution of emergency response kits Awareness raising through mobile app and leaflet distribution Awareness for different segments of the population | NOR established and fully equipped with IT and communicated equipment, staff trained; and NOR was part of table top and disaster simulation exercises. MoV established and fully equipped and delived to PMO, staff trained and MoV part of 2016 simulation exercise. NOR officially launched NOR team nomination in process MOR terms of reference developed MOR procurement and evaluation conducted | Not Applicable. | Terms of Reference Offers Procurements Contracts Other donor Reports Photos Press Releases Government decrees |
|  | Response Plan for MEHE, BRHIA, MoSA, MoA developed. Crisis cells / operation rooms in 4 sectors established Capacities in MEHE, BRHIA, MoSA, MoA built and Table Top Exercises at MoEHE, BRHIA, MoSA, MoA implemented |  | Copies of response plans Terms of reference Procurements and contracts Photos Press Releases |
|  | Development of workshop concept note Training workshop implemented Adoption of local authorities to resilient charter |  | Copy of concept note Reports List of Participants Photos |
|  | Response plan for Governorate of the North- Tripoli, Governorate of South, Mouhafaza of Baaklbek Hermel, accomplished Response Plans for the Caza of Metn and Caza of Chouf, Union of Municipalities of Sour, and Minnieh Donnieh drafted. Operations room for Governorate of South, Mouhafaza of North/, Mouhafaza of Baalbek Hermel established Capacities for regions is built in parallel to the development of the response plans Table top exercise for Governorate of North – Tripoli implemented Simulation for Governorate of South implemented Upgrading of Governorate of South accomplished through equipping the decision makers room |  | Reports Copies of response plans Terms of reference for the operations room Procurement and contracts Photos Contracts |
|  | 1000 emergency kits disseminated to major stakeholders Mobile application developed 100,000 DRR home guide produced, delivered and disseminated |  | Terms of references Procurements and contracts Sample of the emergency kit Sample of home guide Photos and testing of mobile application |
| Outcome 3: Social cohesion in target areas improved through and improved skill base for peaceful dispute resolution |
| Output 3.1: Develop local level peace building strategies to mitigate tensions in selected conflict prone areas of Lebanon hosting Syrian refugees Indicator 3.1.1: Conflict Assessment exercise conducted Baseline: Lack of tangible data on conflicts and lack of locally and nationally oriented conflict analysis Planned Target: Develop an online open source map of conflicts and produce conflict analysis reports focusing on areas and covering eventually all Lebanon Indicator 3.1.2: Local Capacity building and peace building activities conducted Baseline: Weak management of the crisis resulted from the impact of the Syrian crisis Planned Target: Implement peace building and social cohesion activities in affected areas Indicator 3.2.3: Management and technical support provided for implementation of activities Baseline: need for a technical support for the project Planned Target: Provide technical support to the project for the implementation of the planned activities | -Production of the online map -Production of first periodic conflict analysis report focusing on Bekaa -Production of second periodic conflict analysis report focusing on Saida -Production of third periodic conflict analysis report focusing on Mount Lebanon -Production of fourth conflict analysis report focusing on Beirut | NA | Actors in the response using the map and positive feedback on both the map and the conflict analysis report shared with UNDP in several occasions (meetings, discussion sessions, coordination meetings, etc.) |
|  | -Mechanisms for conflict prevention for the 7 municipalities and local actors from West Bekaa developed - Implementation of LOST, SALAM, Zakira, Tafawwoq wal Saadah, Basmeh and Zeitooneh NGOs projects - Production of a special issue of the joint news supplement on Tripoli | NA | Participants in the mechanism The Expert/facilitator working with the team on the establishment of the mechanism |
|  | Project’s staff recruited both in central and local level (Bekaa) | The Conflict Analysis Assistant has not been recruited since the project decided to use its own resources to follow up on the conflict mapping/conflict analysis exercise |  |

iii) Evaluation, Best Practices and Lessons Learned

- During the implementation of the projects, the main challenge faced by the UNDP staff was working in red zones and border areas, specifically in the Bekaa and in the North. Due to the security situation, finding a contractor willing to work in those areas was difficult and the UNDP staff faced challenges in accessing the areas. However, UNDP’s extensive experience in the field through the presence of its sub-offices in every region, helped them manage the situation very well.

- Duplication of efforts were avoided through the well-established coordination structure of UNDP at the national and local level for both Social Stability and Livelihood sectors. Regular meetings between key local actors involved in the crisis and UNDP staff were set up in the different regions to guarantee coordinated actions and to avoid duplication of efforts.

- The importance of coupling the hard component of livelihood initiatives with market studies and capacity building activities ensures the sustainability of the project.

- It is always challenging to deliver a limited quantity of goods when the need is great and the competition is high between beneficiaries. Some friction with the municipality surfaced when they tried to influence the selection of beneficiaries by promoting the inhabitants of their respective villages. However, UNDP works through a conflict-sensitive participatory needs assessment methodology in the identification of the most urgent priorities of the local population to avoid this kind of risk. In this sense, a transparent selection of the projects takes place.

- More capacity building support to cooperatives is needed to improve their managerial and financial skills. This need resulted from the local assessment and the challenges that the cooperatives are facing require a longer timeframe of implementation.

- The closure of the borders with Syria has deeply limited the demand of local products damaging the local economy in the selected municipalities. Even if this represented one of the main challenges for UNDP, the interventions, in support to the local agricultural production, implemented in close collaboration with key local actors such as LEDA, positively impacted the livelihoods of the inhabitants, the income of the farmers, and the local market itself.

- In February 2015, UNDP issued an internal outcome evaluation (refer to annex 9) of its work on disaster risk management covering the period from 2009 to 2014. The report was written by the UNDP regional expert on DRR Mr. Zubair Murshed. This report was the basis upon which UNDP developed the new phase of its DRM project covering the period from 2016 to 2019.

- At the national and political levels, one of the greatest challenges that remains is the political instability, with the security threats of man-made disasters and unrest.

- Keeping DRM on the agenda of the central and regional Government requires ongoing and continuous efforts from UNDP team members including from its senior management. Despite the progress achieved on this front during the reporting period, any advocacy efforts from partners and stakeholders with the Government remains a necessity;

- Another alarming issue is the high number of Syrian refugees which estoimated at 1.5 million exerting more pressure on already weak infrastructure and services.

- Coordination among governorates, key sectors and UN agencies has been vital towards the standardization and coherence in disaster preparedness and response efforts;

- Making use of international expertise and cooperation in the field has greatly supported UNDP such in the case in the development and procurement of the mobile operation room.

- At the operational level, maintaining a high degree of effort and momentum of work with continuous follow up from the management and program has supported in attaining the targets in due time;

- The new project documents that was developed reflects the project evaluation, priorities of the Sendai Framework, priorities and needs for Lebanon to strengthen its resilience in the upcoming period especially with the impact of the Syrian Crisis.

- In 2016, UNDP issued an internal outcome evaluation (refer to annex 18) of its overall peace building programme in Lebanon covering the period from 2013 to June 2016. The report was written by Malin Herwig, Conflict Prevention and Peace Building Advisor at UNDP’s regional Hub for Arab states. This report is currently being used by UNDP Lebanon to develop the new project document related to its peace building programme.

- The volatile security situation especially in Bekaa area: UNDP recruited a Local Level Assistant from Bekaa and for Bekaa who can have an easier access to the areas of intervention

- The new security measures imposed on Syrian refugees that made the participation of Syrians in mechanisms and activities of partner NGOs more difficult: amendment in reach out modality (organization of sessions closer to the Informal Tented Settlements)

- The sudden death of Lebanon Support executive manager with whom the agreement (from the part of Lebanon Support) has been made and with whom the agreement on the methodology of the work and mainly the part related to the conflict analysis. With his death the project had to liaise with another new focal point at Lebanon Support who isn’t always on the same page with the team.

- It was crucial to allocate more time for the Conflict Mapping/Conflict Analysis activity. Nine months were critical to launch a new tool, test it and work on improving it. Also in terms of mapping conflicts, the team felt more time was needed in order to have some data and be able to extract something out of it. This is relevant too for the conflict analysis since there was a need to produce more than a report and be able to dig more into conflicts dynamics and analyze them over a longer period of time.

From another side, establishing local mechanism for conflict resolution definitely requires more than just nine month, which is again why UNDP required an extension. Building trust and confidence with local communities, which is the number one rule before launching any peace building work in any community, takes time. UNDP was keen on using a comprehensive solid methodology to do that, which starts with the conflict analysis (after identifying thoroughly the participants and key actors), going through trainings and capacity building and ending by the formulation and implementation of the mechanisms.

Linking local and sectoral public institutions working on their response with the national response plan was a pilot exercise which the team will greatly benefit from during the coming years, when engaging with additional stakeholders at the local and sectoral levels.

Another lesson learnt was how to balance actions between preparedness, response and early recovery despite the situation in the country.

iv) A Specific Story

Story – Output 2.3

Water maintenance works quickly and effectively addressed by the Union of Municipalities of Qalaa

Problem / Challenge faced: In Al Qalaa, water supply networks are old, insufficient, and in continuous need of repair and maintenance. The most critical situation is that of the main pipe network which is very old and leaks water regularly (more than 50% of the network is 40 years old). Parts of the network need to be promptly replaced, and the galvanized iron pipes must be substituted by PET or PVC for improved water distribution in the area. Before the project implementation, the inhabitants of Al Qalaa Union of Municipalities (UoM) received drinking water two days a week as a best-case scenario. Neither the Al Qalaa UoM, nor the South Water Establishment had the capacity and equipment to conduct the needed maintenance works. Moreover, the refugee flow increased the need for water dramatically, and consequently placed more pressure on local authorities. Programme Interventions: UNDP, in close collaboration with the Al Qalaa UoM and the South Water Establishment (SWE), implemented a project aimed at ensuring timely and efficient water maintenance services to ensure regular water supply to local host communities and refugees living in the area. The intervention consisted of the provision of specialized equipment for maintenance works, a capacity building and training programme for the SWE technicians, and the set-up of a coordination system between the Union and the SWE. Result: Cost Decrease: Prior to this project, the UoM was obliged to pay for any WASH intervention in their areas and villages. Now that the tools are owned by the UoM and managed by experts, the cost of the intervention and contractor payments were significantly reduced. Efficient Time Management: Prior to this project, time management was a problem since the UoM depended on the availability of the SWE or contractor. Currently, the intervention is managed directly by the UoM in close coordination with the SWE, and this has allowed rapid interventions and improved trust between the local authorities and the community. Improved water supply: A resident local resident shared his experience: “six months ago, the main water line burst and was leaking water profusely. Our houses were at risk of being flooded with mud, and the streets began to crumble. =A neighbour told me that he faced a similar problem with the water network and called the municipality which put him directly in touch with the water maintenance centre. When gave me the contact details of the person in charge, I called and was totally surprised that they responded so quickly. He explained that they have specialized and professional equipment for this type of plumbing repair. Before, we used to wait over ten days for the maintenance team to intervene. I would like to thank the team and the Union of Municipalities for their prompt response - otherwise our houses would have been flooded with mud.” - Hussein Zeineddine, resident of Al Qalaa Lessons Learned: The UoM noted that the project was essential to provide efficient water supply in the entire area. Close coordination with the relevant regional and local authorities, and civil society was essential for the success of the project, its sustainability, and follow up.

Story – Output 2.4

The success stories about the installation and distribution of stoves & briquettes, and the PV lighting kits;

Stoves and briquettes and PV lighting kits: http://www.cedro-undp.org/Media/documentary

# Footnotes

as stated in the Country Programme Results and Resource Framework

# Text boxes

ii) Indicator Based Performance Assessment: