RUNO END PRF PROJECT REPORTING					TEMPLATE 4.5

PEACEBUILDING FUND (PBF)

END OF PROJECT report

COUNTRY: Kyrgyzstan

REPORTING PERIOD: 2014-2016

| Programme Title & Project Number |  |
| --- | --- |
| Programme Title: "Youth for Peaceful Change" Programme Number (if applicable) KGZ/A-5; MPTF 00089449 MPTF Office Project Reference Number: 00089449 |  |  |

| Recipient UN Organizations |  | Implementing Partners |
| --- | --- | --- |
| List the organizations that have received direct funding from the MPTF Office under this programme: UNDP, UNICEF, UNFPA |  | List the national counterparts (government, private, NGOs & others) and other International Organizations: State Agency for Youth Affairs, Physical Culture and Sports (former Ministry of Labour Migration and Youth) , Ministry of Education and Science, Ministry of Social Development, Agency for Local Self-Governance and Interethnic Relations, State Commission on Religious Affairs of the Kyrgyz Republic, LSG bodies, Defense Council, NGO "Institute for Youth Development"; NGO "Y-PEER" (youth network) |
| Programme/Project Budget (US$) |  | Programme Duration |
| PBF contribution (by RUNO) UNDP: USD 171,382 |  |  | Overall Duration (months) 33 |  |
|  |  |  | Start Date (dd.mm.yyyy) 01/01/2014 |  |
| Government Contribution (if applicable) |  |  | Original End Date (dd.mm.yyyy) | 30/06/2016 |
| Other Contributions (donors) (if applicable) |  |  | Final End date(dd.mm.yyyy) 30/09/2016 |  |
| TOTAL: |  |  |  |  |

| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| --- | --- | --- |
| Mid-Term Evaluation / Review - if applicable please attach Yes No Date: End of project Evaluation– if applicable please attach Yes No Date: |  | Name: Erkina Urazbaeva Title: UNDP Peace and development PO Participating Organization (Lead): Email address: erkina.urazbaeva@undp.org |

PART 1 – RESULTS PROGRESS

  - Assessment of the project implementation status and results

For PRF projects, please identify Priority Plan outcome and indicators to which this project has contributed:

Priority Plan Outcome to which the project has contributed. Policies, pilot initiatives and approaches are developed and implemented that enable the further development of a common civic identity, multilingual education and respect for diversity and minority rights.

Priority Plan Outcome indicator(s) to which project has contributed. 13. Percentage of citizens in targeted communities who have positive disposition toward “others”.

For both IRF and PRF projects, please rate this project’s overall achievement of results to date:

For both IRF and PRF projects, outline progress against each project outcome, using the format below. The space in the template allows for up to four project outcomes.

Outcome Statement 1:

Project Outcome 3.1: Vulnerable young women and young at-risk men have better opportunities to acquire civic participation skills to positively engage in society and develop respect for diversity.

Rate the current status of the outcome:

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

- 3000 young people from different ethnic groups became local activists and leaders of youth-led projects in their communities promoting youth initiatives in close partnership with LSGs;

-200 young people (50% girls) participated in LSG led youth action planning processes;

- 500 young people in target communities had opportunities to participate at the National Youth Forums on business development; security; personal development and self-motivation.

- In a 7-month course on youth work that has been attended by 28 young civil society leaders and 17 civil servents  has toughts them basics of child protection, diversity management, social designing, local youth development planning and many other important disciplines vital for promoting youth work

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

Compared with previous years, there has been a significant decrease in the level of tensions and conflicts among young people. Thus 5 deconstructive youth behavior was recorded over the endline period against 44 registered as a baseline. In some communities with no prior youth project experience the UN was seen by young people as a unique opportunity for development and gave them an incentive for a positive change.

11 out of 14 LSGs developed youth action plans were supported through local budgets and by local and international donors. This project resulted in an intensification of our work with youth in targeted communities. Nationwide activities such as National Forums and Role Model Forum, which brought together youth from different parts of the country and different ethnicities contributed to breaking stereotypes, strengthening communication between youth and increased self-confidence. As heads of LGSs and other eldely activists underline, those young people, including vulnerable youth changed their behaviour and became agents of positive changes in pilot communities. Social infrastructure projects that have been established during the project, created a platform for exchange for young people from different ethnicities.

In 2016 17 LSGs have allocated 115 000 USD for youth work. In 3 communities, the funding provided by local authorities was allocated direclty to youth comitees for further independent plans implementation.

The project has achieved some important system changes with regard to the situation of youth and their prospect to develop a favourable environment. The Youth Work curricula review made peacebuilding and civic participation themes more salient. Participants of the youth work curricula course had an opportuntity to excange experience with their peer youth workers in other country regions that have not been part of PBF engagement. The subject called "State Youth Policy" was introduced to MA course in "Public and municipal administration" which is delivered in 90 hours and three credits.

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

.

Outcome Statement 2:  Project Outcome 3.2: Vulnerable young women and young men at-risk express their concerns, participate in decision-making at various levels and have better access to economic opportunities to reduce the likelihood of youth involvement in violent conflict

Rate the current status of the outcome:

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

About 150 job opportunities were created for youth through income generating small-projects. 33 young people (14 girls) received certificates in the most demanded areas of vocational specializations. 12 young entrepreneurs (7 girls) attended internship courses in larger companies in Bishkek. Around 1600 young people have participated  in the activities organized through he Small Grants for young people.

In six of the pilot communities LSGs have created Youth Committees as a specific department within the LSG structure. About 43,000 USD was allocated for Youth Committees in 2015. The position of a specialist to work with youth was introduced in Aktash municipality during LSG restructuring. The project prompted important change on the system level as youth work has also been introduced in the MA course on municipal and public service.

Further, 3 groups of young volunteers from Bishkek, Osh and Batken (55% girls) performed 28 plays in Bishkek.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

The project has helped to raise awareness about youth issues among the local authorities and other decision makers. Local authorities were convinced by the youth leaders to allocate funds for the youth sector.

Through the organization of trainings on development skills, exchange of experiences, communication of different young people, as well as providing real support for the implementation of business and other social ideas, the project has made an important contribution  to the economic and social empowerment of youth. Passive and indifferent young residents of the target communities became part of local youth teams and active agents of change at the level of their villages.

During the project period 13 small-grants out of 50 had a direct focus on women empowerment. In particular, there were projects to create various conditions for women to start and/or develop their business such as sewing, education, bakery and event agency.

The 12 issues selected for FT plays went through a process of FT critical responses with the communities, and conflict analysis. TV company selected, OTRK with national coverage, received a lot of positive feedback from the audiences, including from the regions. The records of the programs were placed at the TV company's website, UNFPA and TV company's youtube channels, the average number of views per program reached 512, the most popular were programs devoted to issues of youth unemployment and migration, which in Feb 2016 got close to 8000 views.  The most successful in engaging audiences in online dialogues, were programs produced by Tumar radio in Bishkek, and for less extent, by Yntymak radio.

More than 15 different youth oriented local services are established at municipality levels in close cooperation with the LSGs. The guideline on local youth development strategy was became a basis for further fruitful cooperation.

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

Some LSGs felt mistrustful and insecure to cooperate with young people. Local leaders, representatives of the older generation did not always acknowledge the social importance and role of young people in development, therefore they were not able to effectively use the potential of youth. In particular, there were cases, when local authorities refused to provide equipment and other assests (provided by the project) intended for business or services to young people, considering that young people will not be able to use them effectively. In such cases, interventions have happend through negotiations or engaging third parties (the Government) to support the access of young people to the project goods.

Outcome Statement 3:

Rate the current status of the outcome:

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

Outcome Statement 4:

Rate the current status of the outcome:

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

  - Assessment of project evidence base, risk, catalytic effects, gender at the end of the project

| Evidence base: What was the evidence base for this report and for project progress? What consultation/validation process has taken place on this report (1000 character limit)? | Baseline and Endline surveys. Interim M&E observations. IPs' reports; vendor's reports; monitoring reports; consultations with young volunteers and youth presented at the community performances; observations in the community and TV performances. |
| --- | --- |
| Funding gaps: Did the project fill critical funding gaps in peacebuilding in the country? Briefly describe. (1500 character limit) | The baseline survey revealed that only 3 target communities out of 14 had plans and a budget for youth oriented empowerment activities. In other communities, LSGs could not identify and formulate pressing needs and problems of local youth. Overall, the socio-economic situation of young people was extremely weak. The lack of services or enabling environment for development of young people was also observed. Thus this project filled a critical funding gap through building capacities of responsible LSG staff on how to organize youth work, creating employment opportunities, constructing or rehabilitating social facilities, creating conditions for youth involvement in decision making processes and for educational and physical development of young people. |
| Catalytic effects: Did the project achieve any catalytic effects, either through attracting additional funding commitments or creating immediate conditions to unblock/ accelerate peace relevant processes? Briefly describe. (1500 character limit) | -Not less than 30% of the budget of small-projects for local communities were supported by the LSG budgets as their own contribution. This approach ensured sustainability of the project and demonstrated the interest of local communities to invest in youth development activities. -7 youth development plans received nearly 28,000 USD as local budget support. -Young activists and local authorities in some of the target communities decided to create a Youth Development Fund. -Some of the young participants and activists of the project developed their leadership skills and have tested themselves as local politicians and leaders of their communities, for example one of the trained leaders in Batken has become a member of the local council. -Youth committes in 4 municipalities started functioning and supporting the LSG on working with youth. PBF funding has particularly helped to sensitize gender equality to the youth work curriculum. At least 43 % of the participants of the course on youth work were women and 50% of those young people who benefited from youth work in the pilot communities are young girls and women. |
| Risk taking/ innovation: Did the project support any innovative or risky activities to achieve peacebuilding results? What were they and what was the result? (1500 character limit) | -The project had a special approach on supporting the development of sports and business opportunities, which is quite an innovative approach in the conditions of Kyrgyzstan. Available sports like street soccer, basketball, volleyball, street workout are popular sports that have been supported in our pilot communities. Young people as entrepreneurs also bear the agenda of cooperation, trust and assistance. It improves the integration of young people and reduces the risk of conflict with the participation of young people. -Use of FT methodology gave youth the opportunity to share their concerns and seek for solutions, was certainly both innovative and bold, due to chanelling sensitive issues such as early marriages, GBV, bullying, discrimination and corruption, youth migration and unemployment on TV. The TV company had also concerns regarding the quality of the performance of non professional TV anchor and volunteer actors performing on national TV. |
| Gender marker: How have gender considerations been mainstreamed in the project to the extent possible? Is the original gender marker for the project still the right one? Briefly justify. (1500 character limit) | The project applied both qualitative and quantitative approaches to women and girls empowerment. It ensured women's inclusion in each activity (e.g. at least a 40% women's representation in trainings, workshops, grant preparation and implementation processes). 13 out of 50 projects directly focused on women empowerment. All media component project participants: young volunteers, community audiences and TV guests represented almost equally men and women. Besides, 4 out of 12 topics of TV programs and in average 15% of all topics released on radio-programs were directly dedicated to gender issues such as early marriages and GBV (two issues on domestic violence and migration and unemployment issues). 45% out of total participants of the activities within the Small Grants were females; |
| Other issues: Are there any other issues concerning project implementation that should be shared with PBSO? This can include any cross-cutting issues or other issues which have not been included in the report so far. (1500 character limit) |  |

1.3 INDICATOR BASED PERFORMANCE ASSESSMENT: Using the Project Results Framework as per the approved project document- provide an update on the achievement of key indicators at both the outcome and output level in the table below. Where it has not been possible to collect data on indicators, state this and provide any explanation in the qualitative text above. (300 characters max per entry)

|  | Performance Indicators | Indicator Baseline | End of project Indicator Target | Current indicator progress | Reasons for Variance/ Delay (if any) | Adjustment of target (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 | Indicator 1.1 |  |  |  |  |  |
|  | Indicator 1.2 |  |  |  |  |  |
|  | Indicator 1.3 |  |  |  |  |  |
| Output 1.1 | Indicator 1.1.1 |  |  |  |  |  |
|  | Indicator 1.1.2 |  |  |  |  |  |
| Output 1.2 | Indicator 1.2.1 |  |  |  |  |  |
|  | Indicator 1.2.2 |  |  |  |  |  |
| Output 1.3 | Indicator 1.3.1 |  |  |  |  |  |
|  | Indicator 1.3.2 |  |  |  |  |  |
| Outcome 2 Vulnerable young women and young men at-risk express their concerns, participate in decision-making at various levels and have better access to economic opportunities to reduce the likelihood of youth involvement in violent conflict | Indicator 2.1 % of youth who believe that diversity in society is an asset for the development of the country | 59% | 15% increase | 6% increase: according to endline survey in target communities as of February 2016, 65% of youth who believe that diversity in society is an asset for the development of the country | These are data collected in February 2016. |  |
|  | Indicator 2.2 % of vulnerable young women and young men that are optimistic (think positively) about their future (and their future opportunities) | 63 % | 15% increase | 11 % increase: according to endline survey in target communities as of February 2016, 74% of vulnerable young women and young men that are optimistic (think positively) about their future (and their future opportunities). | Same as above |  |
| Output 2.1 | Indicator 2.1.1 |  |  |  |  |  |
|  | Indicator 2.1.2 |  |  |  |  |  |
| Output 2.2 11 % increase: according to endline survey in target communities as of February 2016, 74% of vulnerable young women and young men that are optimistic (think positively) about their future (and their future opportunities) | Indicator 2.2.1 |  |  |  |  |  |
|  | Indicator 2.2.2 # of media products # of media products in minorities languages | 0 0 | 12 TV programs; 48 radioprograms prepared and broadcasted at least 12 media products in minority language | 12 TV programs (6 Kyr, 6 Rus); 48 radioprograms (18 Kyr, 10 Rus, 10 Uzb) 6 TV programs and 20 radioprograms |  |  |
| Output 2.3 | Indicator 2.3.1 |  |  |  |  |  |
|  | Indicator 2.3.2 |  |  |  |  |  |
| Outcome 3 Outcome 3.1: Vulnerable young women and young men at-risk have better opportunities to acquire civic participation skills to positively engage in society and develop respect for diversity. | Indicator 3.1 % of youth who believe that diversity in society is an asset for the development of the country | 59% | 15% increase in number over baseline by end of 2016 | 65% | Echo of 2010 events are not yet fully passed the stage of rehabilitation. The latent distrust between ethnic groups still exists in the south, particularly among youth. For normalization of inter-ethnic relations and the restoration of confidence obviously longer time is needed. |  |
|  | Indicator 3.2 % of youth that have participated in community development activities | 63% | 15% increase over baseline by end of 2016 | 74% | Despite the 11% progress (instead of 15%), 74% of young people agree that the level of their participation in local development is quite high. |  |
| Output 3.1 Project Outcome 3.2: Vulnerable young women and young men at-risk express their concerns, participate in decision-making at various levels and have better access to economic opportunities to reduce the likelihood of youth involvement in violent conflict | Indicator 3.1.1 % increase in constructive participation of youth in decision-making processes at all levels | Over the baseline period recorded 44 non-constructive conflict events involving youth. The base value of 44 fact - it is 100% | 15% increase in number over baseline by end of 2016 | Over the endline period recorded 5 non-constructive conflict events involving youth. Progress is 88%. |  |  |
|  | Indicator 3.1.2 |  |  |  |  |  |
| Output 3.2 | Indicator 3.2.1 |  |  |  |  |  |
|  | Indicator 3.2.2 |  |  |  |  |  |
| Output 3.3 | Indicator 3.3.1 |  |  |  |  |  |
|  | Indicator 3.3.2 |  |  |  |  |  |
| Outcome 4 | Indicator 4.1 |  |  |  |  |  |
|  | Indicator 4.2 |  |  |  |  |  |
| Output 4.1 | Indicator 4.1.1 |  |  |  |  |  |
|  | Indicator 4.1.2 |  |  |  |  |  |
| Output 4.2 | Indicator 4.2.1 |  |  |  |  |  |
|  | Indicator 4.2.2 |  |  |  |  |  |
| Output 4.3 | Indicator 4.3.1 |  |  |  |  |  |
|  | Indicator 4.3.2 |  |  |  |  |  |

PART 2: LESSONS LEARNED AND SUCCESS STORY

2.1 Lessons learned

Provide at least three key lessons learned from the implementation of the project. These can include lessons on the themes supported by the project or the project processes and management.

| Lesson 1 (1000 character limit) | In rural areas, the majority of young people are receptive of information in Kyrgyz. Russian language is understood, but not in a professional manner. For completeness of understanding all the necessary documents and communication activities on the ground should be in accessible in locals languages, mainly in Kyrgyz. |
| --- | --- |
| Lesson 2 (1000 character limit) | In some cases, grants and other project activities in target communities are uncoordinated, which ultimately affects the overall performance of the project. It is necessary to assign for each project a responsible person from local authorities. |
| Lesson 3 (1000 character limit) | Youth planning process requires preparatory work such as stakeholder mapping – identifying youth leaders, opinion makers, alliances, power relations etc. Therefore, it is important to work closely with LSGs who possess more information about local youth dynamics. To build this process in a right way external facilitators have been tasked to collaborate with responsible LSG staff (usually specialists on social welfare) and to the extent possible engage them into the process. Such partnership approach contributed to mobilize youth, all LSG officials in order to sustain a participatory model of constructing youth work. |
| Lesson 4 (1000 character limit) |  |
| Lesson 5 (1000 character limit) |  |

2.2 Success story (OPTIONAL)

Provide one success story from the project implementation which can be shared on the PBSO website and Newsletter as well as the Annual Report on Fund performance. Please include key facts and figures and any citations (3000 character limit).

On October 7, Bishkek hosted the National Youth meeting “Lessons of Success” that brought together more than 70 young boys and girls aged 14 to 16 years from Osh, Jalal-Abad, Batken and Chui oblasts of Kyrgyzstan.

Roza Otunbayeva  (former president of the Kyrgyz Republic), Salizhan Sharipov, (pilot-cosmonaut, Hero of the Kyrgyz Republic and the Russian Federation) and Atay Omurzakov (performer of modern dance) gave lessons of success for the youth. They were chosen based on the results of the voting held this summer among young people in all 14 municipalities.

The speakers presented their formula for success, shared interesting and informative stories from their life that inspired young people to new positive achievements. It is expected that the meeting with well-known personalities of Kyrgyzstan, who combine all the necessary qualities to succeed, will be a positive impulse for the youth in their further self-development.

“A person is required to set a goal and have a dream. It is necessary to start with the one-day goal, then set a task for a month, a year, etc.”, - advised the cosmonaut Salizhan Sharipov.

Atay Omurzakov said that in Kyrgyzstan many are not believing in themselves. “My mother believed in me, and this really helped me. I had a small room with a small mirror, looking at it and seeing my reflection I imagined my performance on the stage in Europe. Around there were cameras, the lights, applause. My dream came true in 2011 on Czechoslovak scene. Believe in yourself, work on yourself and everything will come true”, - Atay Omurzakov said.

Roza Otunbayeva emphasized gaining knowledge. “Education is the most important. Every day you need to read a book for at least 20 minutes. Read. Read for yourself. Read to our brothers and sisters, and you will become a Person with a capital letter. Reach out for knowledge. Educated people are always in the business”.

According to the survey of the needs of youth in the regions, which was held in the framework of the project, a sports section or the conditions to exercise are among the most demanded needss, followed by the need for employment, further education and obtaining different non-cognitive skills.

This meeting was designed to activate the issues such as tolerance, respect for diversity, and a more active civic participation of young people in the development of the country. Meeting with role models contributes to the socialization of young people reducing the sense of isolation and exclusion.

The national youth meeting “Lessons of Success” was held in the framework of the implementation of the project of UNDP, UNFPA and UNICEF with the support of the UN Peacebuilding Fund.

PART 3 – FINANCIAL PROGRESS AND MANAGEMENT ARRANGEMENTS

  - Comments on the overall state of financial expenditure

Please rate whether project financial expenditures were on track, slightly delayed, or off track:

If expenditure was delayed or off track, please provide a brief explanation (500 characters maximum):

Please provide an overview of project expensed budget by outcome and output as per the table below.

| Output number | Output name | RUNOs | Approved budget | Expensed budget | Any remarks on expenditure |
| --- | --- | --- | --- | --- | --- |
| Outcome 1: Vulnerable young women and young men at-risk have better opportunities to acquire civic participation skills to positively engage in society and develop respect for diversity. |
| Output 1.1 | Young women and men have improved networking and mechanisms to overcome impediments to increase engagement in peace building and decision making in selected communities |  |  |  |  |
| Output 1.2 | Youth work curricula for youth in and out of school have been piloted in selected districts and relevant institutions have the capacity to replicate the delivery of the curricula elsewhere | UNICEF | 186,200 | 209,397 |  |
| Output 1.3 |  |  |  |  |  |
| Outcome 2: Vulnerable young women and young men at-risk express their concerns, participate in decision-making at various levels and have better access to economic opportunities to reduce the likelihood of youth involvement in violent conflict; |
| Output 2.1 | Youth in selected districts constructively participates in community peace building, decision-making and advocacy to ensure that their concerns are addressed; | UNDP | 86,272.95 | 86,272.95 |  |
| Output 2.2 | Youth in selected districts successfully uses media and communications to express their grievances and promote peaceful coexistence at the community level; | UNFPA | $385,000.00 | $387,324.00 |  |
| Output 2.3 | Youth have improved and more equal access to economic opportunities | UNDP | 85,108.95 | 84,239.48 |  |
| Outcome 3: |
| Output 3.1 | Adminsitrative costs/salaries/GMS |  |  |  |  |
| Output 3.2 | Staff and other personnel costs, indicrect support costs | UNICEF | 80,444 | 57,247 |  |
| Output 3.3 |  |  |  |  |  |
| Outcome 4: Other costs |
| Output 4.1 | M&E | UNFPA | $15,000.00 | $12,527.00 |  |
| Output 4.2 | Staff cost | UNFPA | $50,000.00 | $30,368.00 |  |
| Output 4.3 | Other (indirect costs <=7%, admin. etc) | UNFPA | $31,500.00 | $51,282.00 |  |
| Total |  |  |  |  |  |

  - Comments on management and implementation arrangements

Please comment on the management and implementation arrangements for the project, such as: the effectiveness of the implementation partnerships, coordination/coherence with other projects, any South-South cooperation, the modalities of support, any capacity building aspect, the use of partner country systems if any, the support by the PBF Secretariat and oversight by the Joint Steering Committee (for PRF only). Please also mention if there have been any changes to the project (what kind and when) (2000 character maximum):

# Footnotes

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to “Project ID” on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed.

Please note that financial information is preliminary pending submission of annual financial report to the Administrative Agent.