# RUNO Half Yearly Reporting 					TEMPLATE 4.3

[COUNTRY: Kyrgyzstan]

PROJECT HALF YEARLY PROGRESS UPDATE

PERIOD COVERED: JANUARY – JUNE 2016

| Project No & Title: | PBF/KGZ/E-1: PBF Secretaria |
| --- | --- |
| Recipient Organization(s): | UNDP |
| Implementing Partners (Government, UN agencies, NGOs etc): | - Department on Ethnic, Religious Policy and Corporation with Civil Society, Office of the President of Kyrgyz Republic - Joint Steering Committee - JSC Co-Chairs - PRF RUNOs |
| Total Approved Budget : | 850000 |
| Preliminary data on funds committed : | 291.950 USD | % of funds committed / total approved budget: | 34.34% |
| Expenditure: | 562.684 USD | % of expenditure / total budget: (Delivery rate) | 66.18% |
| Project Approval Date: | 07.06.2013 | Possible delay in operational closure date (Number of months) | 3 months |
| Project Start Date: | 30.09.2013 |  |  |
| Expected Operational Project Closure Date: | 31.12.2016 |  |  |
| Project Outcomes: | Outcome 1:Accelerated PBF Secretariat coordination, communication and resource mobilization support to national authorities, civil society and UN agencies. Outcome 2: Enhanced capacity of the JSC members and key stakeholders to monitor and better guide the implementation of PPP |
| PBF Focus Area (select one of the Focus Areas listed below) | 4.3 |

# Qualitative assessment of progress

| For each intended outcome, provide evidence of progress during the reporting period. In addition, for each outcome include the outputs achieved. (1000 characters max per outcome.) | Outcome 1: Outcome 1:Accelerated PBF Secretariat coordination, communication and resource mobilization support to national authorities, civil society and UN agencies. Output 1.1: Project proposal developed, selected and approved. - Coordinated the draft of 5 proposals for the Youth Promotion and Gender Promotion Initiative - Hired a consultant to develop a project proposal on radicalization. Output 1.2: Established coordination mechanisms that contribute to achieving PPP outcomes - Monthly coordination meeting with focal points for the IRF Cross-border project - Conducted 3 Joint Steering Committee meetings and 4 Outcomes working group meetings Output 1.3: Increased awareness of national authorities, civil society and wider public on PRF activities and enhanced capacity to use information for decision making and information sharing. PBF Secretariat provided information on a regular basis through newsletters (6), press-releases (1), publications in media outlets (32) in Russian, English and Kirg Outcome 2: Outcome 2: Enhanced capacity of the JSC members and key stakeholders to monitor and better guide the implementation of PPP Output 2.1. M&E system that provides information about achieving PPP outcomes at all levels (national and local) for strategic decision making in the area of peacebuilding is established. - The recruitment of an international consultant to conduct the endline survey has been finalized and the end line survey will take place in the coming months. - A workshop was organized to increase the capacity of the oversight group on M&E related issues and the oversight group started the field visit for 2016 at the end of May 2016. Output 2.2. Increased capacity of the Joint Steering Committee and other relevant stakeholders to implement oversight and better guide PRF project activities JSC members are informed on progress in PPP and PBF projects implementation through regular meetings, participation at Oversight Group's working and other relevant activities Outcome 3: Outcome 4: |
| --- | --- |
| Do you see evidence that the project is having a positive impact on peacebuilding? (1000 characters max.) | The project is having a positive impact on peacebuilding by coordinating all the PBF funded interventions in the country. The Secretariat is coordinating projects at different levels. PBF Secretariat is responsible of supporting the work of the Joint Steering Committee ensuring that relevant issues are addressed with its members, for the organization of outcomes' group meeting in which agencies working on similar topics can meet and identify potential synergies and space for cooperation. The Secretariat is also facilitating the coordination of a joint project and is particularly involved in the coordination of the cross border project between Kyrgyzstan and Tajikistan. All these efforts contribute to foster the impact of the interventions conceived within the framework of the Peacebuilding Priority Plan in the country. |
| Were there catalytic effects from the project in the period reported, including additional funding commitments or unleashing/ unblocking of any peace relevant processes? (1000 characters max.) | N/A |
| If progress has been slow or inadequate, provide main reasons and what is being done to address them. (1000 characters max.) | The PBF Secretariat will request an extension of 3 months to be able to work until the end of 2016. This extension is not related to the under performance or any inadequate progress but due to the fact that 70% of projects within the PBF portfolio requested and obtained no cost extension and hence the Secretariat will need more time for the administrative closure of projects and to support the final evaluation of the PPP. |
| What are the main activities/expected results for the rest of the year? (1000 characters max.) | In the upcoming months the PBF Secretariat will continue its regular coordination activities by organizing coordination platforms such as Joint Steering Committee and Outcome meetings with RUNOs and National Partners and the monitoring activities of the Oversight group. The focus of the work of the Secretariat in the last months of its activities will be on the endline survey for which the recruitment of an international consultant has been recruited and will start to work at the end of June and on the administrative procedures for the closure of the projects. |
| Is there any need to adjust project strategies/ duration/budget etc.? (1000 characters max.) | Given the fact that the most part of projects obtained no cost extension and will run until the end of September instead of until the end of June 2016, the PBF Secretariat obtained the endorsement of the JSC to be extended until December 2016. |
| What is the project budget expenditure to date (percentage of allocated project budget expensed by the date of the report) – preliminary figures only? (1000 characters max.) | 562,684 USD , 66.18% of total |
| Any other information that the project needs to convey to PBSO (and JSC) at this stage? (1500 characters max.) | N/A |

INDICATOR BASED PERFORMANCE ASSESSMENT: Using the Project Results Framework as per the approved project document- provide an update on the achievement of key indicators at both the outcome and output level in the table below. Where it has not been possible to collect data on indicators, state this and provide any explanation in the qualitative text above. (250 characters max per entry)

|  | Performance Indicators | Indicator Baseline | End of project Indicator Target | Current indicator progress | Reasons for Variance/ Delay (if any) | Adjustment of target (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 1. Accelerated PBF Secretariat coordination, communication and resource mobilization support to national authorities, civil society and UN agencies. | Indicator 1.1 % of resource mobilization proposals approved against those submitted | 0 | 50% | 25% 13 projects approved against 25 submitted |  |  |
|  | Indicator 1.2 The level of satisfaction with Secretariat’s job among JSC and RUNOs | N/A | 80% | 81% |  |  |
|  | Indicator 1.3 |  |  |  |  |  |
| Output 1.1 PBF projects development and selection: project proposals developed, selected and approved. | Indicator 1.1.1 # of project proposals developed and submitted | 9 | 13 | 14 project proposals were developed and submitted (9 existing projects+1 project on media+3 for GPI +1 cross-border project). |  |  |
|  | Indicator 1.1.2 |  |  |  |  |  |
| Output 1.2 Coordination: Established coordination mechanisms that contribute to achieving PPP outcomes | Indicator 1.2.1 % of coordination activities conducted as planned | 0 | 100% (20 coordination meeting) | 35% 7 coordination meetings conducted |  |  |
|  | Indicator 1.2.2 |  |  |  |  |  |
| Output 1.3 Advocacy and communication: Increased awareness of national authorities, civil society and wider public on PRF activities and enhanced capacity to use information for decision making and information sharing. | Indicator 1.3.1 % of communication activities conducted as planned (in communication strategy and AWP). | 0 | 50 | 40% of communication activities (4 activities) |  |  |
|  | Indicator 1.3.2 % of communication activities conducted as planned (in communication strategy and AWP). | 0 | 100% (7 activities) | 10 of communication products developed and disseminated (video film, PSA, newsletters in Russian, Kyrgyz and English, PBF booklets in Russian and Kyrgyz, Cross-border communication guidance). |  |  |
| Outcome 2 Enhanced capacity of the JSC members and key stakeholders to monitor and better guide the implementation of PPP | Indicator 2.1 % of project reports submitted regularly and on time as planned | 0 | 100% | 50% (semi annual reports and end of project reports) |  |  |
|  | Indicator 2.2 % of JSC members who increased their capacity in peacebuilding | 0 | 75% | 45% |  |  |
| Output 2.1 M&E system that provides information about achieving PPP outcomes at all levels (national and local) for strategic | Indicator 2.1.1 Community based M&E system is established in 10 target municipalities and provides data for the JSC and the Secretariat twice a year | 0 | 10 | 0 | This target will not be achieved and no community based system will be put in place because of constraints given by the context of intervention |  |
|  | Indicator 2.1.2 # of field visit reports with recommendations prepared by the Oversight Group and presented to the JSC | 0 | 4 | 3 |  |  |
| Output 2.2 | Indicator 2.2.1 # of JSC members and relevant stakeholders who increased their knowledge and skills for monitoring PPP implementation | 0 | 40 | 11 |  |  |
|  | Indicator 2.2.2 # of trainings conducted (on gender responsive peacebuilding, HRBA, DS) | 0 | 6 | 3 (2 OG workshop included the M&E session and human rights) 1 session within JSC meeting "Women, Peace and Security Agenda: Building Inclusive and Peaceful Societies in the Aftermath of Conflict" |  |  |
| Output 2.3 | Indicator 2.3.1 |  |  |  |  |  |
|  | Indicator 2.3.2 |  |  |  |  |  |
| Outcome 3 | Indicator 3.1 |  |  |  |  |  |
|  | Indicator 3.2 |  |  |  |  |  |
| Output 3.1 | Indicator 3.1.1 |  |  |  |  |  |
|  | Indicator 3.1.2 |  |  |  |  |  |
| Output 3.2 | Indicator 3.2.1 |  |  |  |  |  |
|  | Indicator 3.2.2 |  |  |  |  |  |
| Output 3.3 | Indicator 3.3.1 |  |  |  |  |  |
|  | Indicator 3.3.2 |  |  |  |  |  |
| Outcome 4 | Indicator 4.1 |  |  |  |  |  |
|  | Indicator 4.2 |  |  |  |  |  |
| Output 4.1 | Indicator 4.1.1 |  |  |  |  |  |
|  | Indicator 4.1.2 |  |  |  |  |  |
| Output 4.2 | Indicator 4.2.1 |  |  |  |  |  |
|  | Indicator 4.2.2 |  |  |  |  |  |
| Output 4.3 | Indicator 4.3.1 |  |  |  |  |  |
|  | Indicator 4.3.2 |  |  |  |  |  |

# Footnotes

Please note that where there are multiple agencies, only one consolidated project report should be submitted.

Approved budget is the amount transferred to Recipient Organisations.

# Funds committed are defined as the commitments made through legal contracts for services and works according to the financial regulations and procedures of the Recipient Organisations. Provide preliminary data only.

# 4 Actual payments (contracts, services, works) made on commitments.

5 PBF focus areas are:

PBF Focus Areas are:

1: Support the implementation of peace agreements and political dialogue (Priority Area 1):

(1.1) SSR, (1.2) RoL; (1.3) DDR; (1.4) Political Dialogue;

2: Promote coexistence and peaceful resolution of conflicts (Priority Area 2):

(2.1) National reconciliation; (2.2) Democratic Governance; (2.3) Conflict prevention/management;

3:Revitalise the economy and generate immediate peace dividends (Priority Area 3);

(3.1) Employment; (3.2) Equitable access to social services

4) (Re)-establish essential administrative services (Priority Area 4)

(4.1) Strengthening of essential national state capacity; (4.2) extension of state authority/local administration; (4.3) Governance of peacebuilding resources (including JSC/ PBF Secretariats)