RUNO END PF PROJECT REPORTING		TEMPLATE 4.5

PEACEBUILDING FUND (PBF)

END OF PROJECT report

COUNTRY: Myanmar

REPORTING PERIOD: 30 November 2013-30 June 2016

| Programme Title & Project Number |  |
| --- | --- |
| Programme Title: Contributing to Myanmar Peace Dividend Projects in Mon and Kayin States, Myanmar Sub-Project Titles: 1. Strengthening Government social services in ethnic minority areas and improved collaboration with non-state actors led by UNICEF. 2. Creating a favourable protection environment for IDP and refugee returnees and supporting durable solutions through monitoring, capacity building and documentation led by UNHCR. 3. Empowerment of Mon women through participation in peacebuilding and prevention of and response to gender-based violence led by UNHCR and UN Women. 4. Empowering ethnic youths as peacebuilders in Mon and Kayin States led by IOM. 5. Capacity development of mass media institutions in support of peace-building and local development in Mon and Kayin States led by UNESCO and UNDP. Programme Number (if applicable) PBF/IRF-75 MPTF Office Project Reference Number: 00088269 |  |  |

| Recipient UN Organizations |  | Implementing Partners |
| --- | --- | --- |
| List the organizations that have received direct funding from the MPTF Office under this programme: 1. UN WOMEN 2. UNHCR 3. UNESCO 4. UNICEF 5. IOM 6. UNDP |  | List the national counterparts (government, private, NGOs & others) and other International Organizations: 1. UN WOMEN with Metta Foundation and Mon Cetana. UNHCR with Marie Stopes International. 2. IOM with Kayin Baptist Convention, Mon Youth Educators Organisation, UNFPA, UNAIDS. 3. UNDP and UNESCO with Myanmar Egress, Internews Europe and the Mizzima Media Group. 4. UNICEF with State and Township Government agencies in Mon & Kayin States and local CSOs. 5. UNHCR only. |
| Programme/Project Budget (US$) |  | Programme Duration |
| PBF contribution (by RUNO) $1,600,000 |  |  | Overall Duration (months) 31 |  |
|  |  |  | Start Date (dd.mm.yyyy) 30 November, 2013 |  |
| Government Contribution (if applicable) |  |  | Original End Date (dd.mm.yyyy) | 31 May 2015 |
| Other Contributions (donors) (if applicable) |  |  | Final End date(dd.mm.yyyy) 30 June 2016 |  |
| TOTAL: |  |  |  |  |

| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| --- | --- | --- |
| Mid-Term Evaluation / Review - if applicable please attach Yes No Date: End of project Evaluation– if applicable please attach Yes No Date: June 2016 |  | Name: Peter Barwick Title: Peace and Development Adviser Participating Organization (Lead): Office of the Resident Coordinator (RCO) Email address: peter.barwick@one.un.org |

PART 1 – RESULTS PROGRESS

  - Assessment of the project implementation status and results

For PRF projects, please identify Priority Plan outcome and indicators to which this project has contributed:

Priority Plan Outcome to which the project has contributed.

Priority Plan Outcome indicator(s) to which project has contributed.

For both IRF and PRF projects, please rate this project’s overall achievement of results to date:

For both IRF and PRF projects, outline progress against each project outcome, using the format below. The space in the template allows for up to four project outcomes.

Outcome Statement 1:

Outcome Statement 1: Social cohesion and multi-ethnic trust are increased with vulnerable groups (IDPs, women, youth and ethnic minorities) being given a voice in peace negotiations and programming.

Outcome 1.1: Women’s priority needs and concerns are addressed in peace negotiations and discussions on post-conflict recovery by the conflicting parties.

Outcome 1.2: Increased awareness of sexual and gender-based violence and exploitation in communities. Women’s vulnerability to GBV is reduced leading to improved physical and psychological well-being, enhanced participation within the community.

Outcome 1.3: Target youths are openly discussing the peace process and reconstruction issues. Youths’ voices (concerns and hopes) on the peace process expressed and fully documented.

Outcome 1.4: Lack of trust and suspicion in target communities addressed through open dialogue and community participatory activities involving youths.

Outcome 1.5: Felt sense of peace dividends in communities.

Outcome 1.6: Existence of mechanisms for youths to network and provide support to each other.

Outcome 1.7: Proven model for engagement with youth as peace-builders in Myanmar field-tested and is available to be replicated by stakeholders in other ceasefire States.

Outcome 1.8: National, local and ethnic news media outlets are engaged in conflict sensitive reportage and promote peace as a desired value.

Outcome 1.9: Local community leaders and members use community media as platform to actively participate in peace-building initiatives, have greater sense of ownership of the process, and confident of its full attainment.

Outcome 1.10: Local communities have greater awareness, understanding, appreciation and tolerance of other ethnic groups through exposure to media content.

Rate the current status of the outcome:

| Indicator 1: Outcome Indicator 1.1.1: number of women included in the peace negotiations including discussions on identification of needs after ceasefire agreements; Outcome Indicator 1.1:2: percentage of women in women's groups targeted for action who feel that the peace process is taking into account the needs of women; and Outcome Indicator 1.1:3: percentage of leadership of the New Mon State Party (NMSP) surveyed that agree that women's views are important in the peace process. Indicator 2: Outcome Indicator 1.2.1: number of women participating in awareness training feel and express that they are empowered to take on an active role in their own protection; and Outcome Indicator 1.2.2: number of documented cases of gender based violence (GBV) in Mon State in which services are provided. Indicator 3: Outcome Indicator 1.3.1: number of discussions on peace and development held among youth in target area, issues identified and actions taken. Outcome Indicator 1.4.1: increase in the percentage of perception of improved trust among communities in Mon and Kayin States. Outcome Indicator 1.5.1: increase in the percentage of targeted communities’ sense of the improved quality of life as a result of increased access to services and opportunities as a result of cessation of conflict. Outcome Indicator 1.6.1: the youths targeted by the project become a part of the larger youth networks which provide support to each other. Outcome Indicator 1.7.1: quality and availability of a field-tested model of engagement with youths as peacebuilders. Outcome Indicator 1.8.1: percentage of news media coverage of the peace process which display qualities of depth, accuracy and precision, objectivity, fairness, language sensitivity, etc. Outcome Indicator 1.9.1: number of communities using community media to actively participate in peace-building initiatives and number of communities with greater sense of ownership of the peace process and confident of its success. Outcome Indicator 1.10.1: percentage of community members who report greater awareness, understanding, appreciation and tolerance of other ethnic groups. | Baseline: One woman in the negotiations team of the NMPS (1.1.1). TBD (there were no baselines before the new activity) (1.1.2). TBD (there were no baselines before the new activity) (1.1.3). Target: At least 30% in different roles in peace negotiations (1.1.1). At least 50% increase (1.1.2). At least 50% increase (1.1.3). Progress:There is one woman from the NMSP in the negotiation team. Women's representation increased to three seats out of a total of 53 at the Union Peace Conference (UPC) in January 2016 (one seat for the ethnic representative, another for a technical person and one for a Mon women's party representative). This is the result of Mon women’s advocacy. In addition, the baseline of zero Mon women participating in the formal NCA-related peace process increased to six Mon Women together with 60 women of other ethnicities participating in consultations run by UN Women and EBO Myanmar on the inclusion of women and their priorities in the framework for political dialogue and contributed to identifying what women wanted to see in the FFPD. Four gender provisions were included in the FFPD. UN Women advocated with the leadership of NMSP to secure participation of six Mon women. The FFPD consultations and UPC advocacy was not funded by PBF, but these issues of women’s participation were raised with NMSP in the PBF-funded workshops, and UN Women and Mon women who were trained with PBF funding advocated with NMSP to select Mon women to attend the UPC (1.1.1). According to the Statement of Women's Peace and Political Agenda released after the Women's Peace Conference, at least 30% of women understand and feel that the peace process is taking into account the needs of women. (1.1.2) 30% of women participation is accepted by EAOs. Moreover, EAOs have proposed and advocated for women's participation and leadership in the peace process (1.1.3). Baseline: Zero (there were no baselines before as new activity) (1.2.1). Zero (no documented cases before start of the project) (1.2.2). Target: At least 50 % of the women participating in the awareness trainings (1.2.1). 50% (1.2.2). Progress: 75% female participation, main challenge was to gain broader male participation (1.2.1). 85% (of all cases referred to MSI, however the total number of incidents is believed to be much larger due to the reticence of survivors to come forward) (1.2.2). Baseline: Zero (1.3.1). Zero (1.4.1). Zero (1.5.1). None (1.6.1). Non-existent (1.7.1). 6 % of news covered by Myanmar Media deal with peace processes in the country (1.8.1). Non-existent (1.9.1). Target: 15 (1.3.1). 30% of target population report improved trust and decreased suspicions among communities in Mon and Kayin States (1.4.1). 60% (1.5.1). Yes (1.6.1). Field tested model exists and is disseminated to partners and stakeholders (1.7.1). At least 50% of national media and 60% of local and ethnic news media are engaged in conflict sensitive reportage (1.8.1). One community media (CMC or community radio) set up in a selected township of Mon and Kayin States. All townships with community media established, report active community participation in local peacebuilding (1.9.1). At least 25% of community members in project sites believe they have greater awareness, understanding, appreciation and tolerance of other ethnic groups (1.10.1). Progress: 40 (1.3.1). 31% of Kayin and 40% of Mon (1.4.1). 100% of Kayin and 79% of Mon (1.5.1). Yes (1.6.1). Yes (1.7.1). 126 journalists participated in the series of Conflict Sensitive Reporting (CSR) training. 70 from Mon and Kayin States and 56 from Yangon. All participants showed satisfaction with the course, and post-course surveys showed that 80% of them are ready to apply the new competences. 223 stories have been recorded in the weeks following the trainings where journalists applied CSR principles (1.8.1). While community radio could not be established due to legal framework delays in licensing in Myanmar, the percentage of CSOs from all townships in Mon and Kayin stating that their community has ways to participate in peacebuilding / peace process increased from 47% (74/156) to 55% (86/156), with the change in the number of community forums or conferences on peace making up 37% of the increase (1.9.1). In Mon and Kayin, community level impacts were not measured because community radios could not be implemented as planned. However, based on alternative activities, 78% of CSO representatives in areas in Mon and Kayin reported opportunities for participation in inter-ethnic activities (1.10.1). |
| --- | --- |

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

1.1 Women have dedicated space and increased opportunities to provide inputs into the peace process. Activities included training, dialogues and identification of priorities by Mon women.

1.2 SGBV awareness campaigns and advocacy meetings were conducted. Medical and psychosocial support for SGBV survivors were provided. Clinics upgraded with response packages. Dignity kits provided. Trainings conducted.

1.3-1.7 40 youths participated in trainings and developed action plans. They facilitated discussions with 474 community members. They developed and implemented 40 community projects benefitting 38,000 people supported by a small grant scheme. They established youth peace networks.

1.8-1.10 126 journalists were trained. 223 stories were recorded where CSR competencies were applied. Meetings and workshops were held on the peace process, dialogue skills and community radio.  Mon State Civil Societies Forum of Peace and South East CSOs Peace Conference were held.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

1.1 Dedicated space has been created for women to engage in politics and discussions on peace and opportunities for women to engage in political discussion have been increased. 10 consultation meetings provided a platform to learn about women’s participation in peace processes. Mon women’s peace priorities were developed and used by women's groups in the dialogue with political stakeholders on the peace process in Mon State. The dialogues and meetings resulted in the Mon State Government and the New Mon State Party committing to address women, peace and security issues, and contributed to the nomination of 52 women candidates for elections for the 2015 elections in Mon State.

1.2 There is evidence of receptiveness to the project based on the participation of women, the reach of awareness campaigns and engagement with the Government and EAOs. The mapping of services to help raise awareness and prevent SGBV, and the provision of response services, are developing. The time span of the project was too short to show dramatic shifts in addressing SGBV but the inclusion of SGBV in the project sent a signal to the Government and EAOs that this issue needs to be addressed within the peace process.There are challenges to effectively tackling SGBV and few resources are being directed towards services. However, the project was able to clarify the challenges as well as raise awareness of the importance of SGBV.

1.3-1.7 The youths reported that their increased knowledge of peace issues enabled them to engage and influence their peers and take greater leadership roles in their communities. The target youths' average rating on the usefulness of the training was 4 out of 5. Cooperation between youths and other community members had increased and youths gained space to participate in their community activities. A July 2015 survey covering 490 stakeholders showed that the increase in trust as a result of the project was 31% in Kayin and 40% in Mon. The two youth networks had been included in larger youth networks. When a conflict erupted in Kayin State in October 2015, youths from the area used the network to mobilize support for the injured and to alert each other. The Research Consortium on Education and Peacebuilding, funded by UNICEF’s Learning for Peace Programme, used the project as a case study for a report that is being drafted.

1.8-1.10 The stories produced following the training proved that the trained journalists are now capable of applying CSR skills when writing conflict related stories. Trust and collaboration has also been strengthened between civil society and media through two forums. This has enabled the publication of  fairer, more sensitive and more accurately produced stories. Community-level CSO leaders are more informed about the status of peace processes and understand the contents of Nationwide Ceasefire Agreement. There has been an increased engagement and ownsership of community-level CSO leaders in local peacebuilding activities.

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

1.1 None.

1.2 There have been challenges in engaging in Kayin State in general due to the continued concerns by Government on security. This has resulted in less access in many areas to undertake activities, including SGBV. The environment continues to see a heavy presence of military personnel and armed actors. Weak rule of law in many parts of the south-east and challenges in the area of justice means that confidence among survivors of SGBV is low. The south-east of Myanmar remains a fragile peace-making/peace-building environment. The situation may improve as ceasefire negotiations and political dialogue moves forward.

1.3-1.7  No reasons for low achievement identified as sufficient progress being made.

1.8-1.10 Progress using community media as the main tool for achieving the outcome has been slow because the legislative framework for licensing community broadcasts was enacted at the end of August 2015 and the bylaws are not yet in place. Alongside preliminary civil society capacity development for community media, alternative activities have been identified to achieve the outcome of increased community participation in and ownership of peacebuilding processes.

Outcome Statement 2:

The Government is more responsive to the needs of vulnerable groups (IDPs, women, youth and ethnic minorities) living in ceasefire areas.

Outcome 2.1: State and township level authorities perform their duties effectively and become more responsive to the needs of ethnic minorities living in ceasefire areas.

Outcome 2.2: State and township level government planning and response to the needs of the communities are done with active consultation, participation and collaboration of non-state actors, civil society groups and representatives from ethnic minorities.

Outcome 2.3: Basic social services (education, health and WASH) in selected ethnic minority ceasefire areas in Mon and Kayin are established and improved.

Outcome 2.4: Government and aid agencies responsiveness to needs of IDP and refugee returnees enhanced, due to improved and informed programming, and better positioning to address arising challenges.

Outcome 2.5: IDP and refugee returnees provided with citizenship rights and durable solutions in accordance with international standards, contributing to sustainable peace.

Outcome 2.6: Sustainable return and reintegration of IDPs and refugees is supported through increased knowledge of Government officials/civil society actors on key human rights and protection standards, enabling an environment for returnees to enhance their participation and contribute to the processes involved in building a sustainable peace at different levels.

Rate the current status of the outcome:

| Indicator 1: Outcome Indicator 2.1.1: conflict-affected communities interviewed feel that the Government is paying attention to their social needs. Indicator 2: Outcome Indicator 2.2.1: non-state actors, civil society groups and representatives from ethnic minorities expressed satisfaction over improved participation and collaboration with the government. Indicator 3: Outcome Indicator 2.3.1: by the end of the project period those communities identified through the baseline survey for education/health/WASH inputs have received them. Outcome Indicator 2.4.1: number of verified return locations (communities verified as having received refugee or IDP returnees in which Government or aid agencies provide targeted re-integration support). Outcome Indicator 2.5.1: percentage of verified return villages in which returnees hold civil documentation; and Outcome Indicator 2.5.2: percentage of verified return villages in which returnees report having faced pressure to return or limitations on freedom of movement. Outcome Indicator 2.6.1: number of government officials/civil society actors and members of non-state armed groups participating in capacity-building workshops on international standards related to durable solutions to displacement. | Baseline: The baseline survey conducted to gauge the perceptions of communities on the government’s performance and delivery of social services, acknowledged that "little attention is given to address the social needs and no data/evidence is used to carry out any proper sector planning". Target: A similar survey by the end of the project period will be done showing marked increase in the respondents’ level of satisfaction. Progress: In general, the endline survey results have shown that the initiation of this process has been seen as a positive experience for all actors towards the building of trust and the strengthening of peace, as Government authorities have been seen to be more responsive to ethnic minorities' needs, notably for social services. Baseline: Very limited participation and collaboration by NSAs, civil society and ethnic minorities in Government social service planning and delivery reported across all surveyed townships. Majority of local government officials had little or limited understanding of inclusive planning (perceiving inclusion to mean community labour or financial support). Target: A similar survey by the end of the project period will be done showing marked increase in the respondents’ level of satisfaction. Progress: Endline survey continues to show overall low levels of participation and collaboration of communities, NSAs, civil society, and ethnic minorities, with the exception of concurrent community, government, and NSA (small majority) perception of improved inclusion in Kyainseikgyi township, especially in education. Baseline: All respondents in a rapid needs assessment identified improved health, education, and water and sanitation services as key needs and expected peace dividends (2.3.1). Zero (new activity, no verified return locations before project started) (2.4.1). Undetermined (2.5.1). Undetermined (2.5.2). Zero (2.6.1). Target: Endline survey of basic service needs in specific project locations reveal basic service needs have been addressed (2.3.1). 20 (2.4.1). 80% (2.5.1). Zero (2.5.2). 215 (2.6.1) Progress: Endline survey shows majority of respondents (>60%) expressing the view that there are no or very little unmet needs in education/health/WASH in two out of three surveyed townships and divided opinions in one township (no majority for identifying needs as unmet or met) (2.3.1). 38 (2.4.1). Progress data not available (2.5.1). Zero (2.5.2). 263 individuals (2.6.1). |
| --- | --- |

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

2.1-2.3 Officials responsible for education, health, and WASH are better able to plan, manage, and implement social services. Training and workshops were held. 5405 households now have access to improved water and 30 communities are Open-Defecation Free. 60 primary schools have WASH facilities. Schools were constructed/renovated and learning materials provided. Medicines and equipment for treatment of childhood illnesses were provided along with 18,000 anti-malaria insecticidal nets.

2.4-2.6 An Information Management Unit was established and a system for monitoring spontaneous returns of refugees and IDPs was developed. 159 return assessments were completed. UNHCR extended a standing offer to the Government to provide technical assistance in identification, prevention and reduction of statelessness, and the protection of stateless persons. 19 trainings were conducted to build capacity among Government, EAOs and civil society to support durable solutions for refugees and IDPs.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

2.1: Endline survey showed ethnic communities believe Government services have become more responsive to their needs. This suggests Government providers are applying more inclusive and responsive service planning and implementation approaches. In the health sector, in which particular improvements were noted, the Government at township and state-level has become more reponsive to requests for support from NSA counterparts and community leaders.

2.2: With the exception of one of the three surveyed townships, the endline survey shows limitations in NSA, civil society, and ethnic communities participation and collaboration with Government, especially in the education sector. This suggests that while progress was made, the outcome was not fully reached. This is not surprising given that this outcome described a culture shift in Government decision-making, from top-down to bottom-up. An example of progress are the Education and Health coordination platforms established in Mon and Kayin States in 2015 that are facilitating collaboration to address sectoral shortcomings.

2.3 In the three selected townships of Kayin, some progress has been made to improve basic social services for communities on both the government and EAO sides. Apart from the provision of hardware (construction, furnitures, learning materials), some capacity building of government, NGOs and Community volunteers was also undertaken. All of these improvements are tangible peace dividends that help instill confidence in the peace process and create incentives for non-violent conflict resolution.

2.4 Return monitoring continues to produce excellent results and is already feeding into UNHCR's plans and preparations for returnees. It has enhanced UNHCR's ability to engage with Government and other stakeholders in terms of mapping potential needs of IDP and refugee returnees, and will be a vital tool for 2016 and 2017 programming. The return of refugees from Thailand will be a key indicator of enduring peace in south-east Myanmar.

2.5 UNHCR continued to work closely with the authorities to stress the importance of civil documentation, especially for protecting persons of concern. Due to the spontaneous return of refugees and ongoing return monitoring conducted at the community-level, the identification of returnees in need of documentation is not comprehensive. However, cases are referred to authorities when identified. Training and advocacy with the authorities emphasises the need for documentation for returnees. The engagement with the authorities has been generally positive although returnees are not their main focus.

2.6 The project has contributed to efforts to prepare for the eventual return of IDPs and refugees, however, the operational environment remains not conducive for returns. While spontaneous returns are taking place, UNHCR is not yet at the stage of facilitating or promoting returns.

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

2.2: The township-level health microplanning workshop could not be conducted because this planning exercise can only be undertaken after the development of standardized tools which is an on-going process led by DoH and supported by health development partners.

2.4-2.6 In general the lack of access due to security permissions has slowed progress, especially in Kayin State. Most notably, while UNHCR was able to begin return assessments immediately in Kayah, Mon and Tanintharyi in June 2013, government approval for full-scale monitoring in Kayin required far longer negotiations, and only since mid-2014 has UNHCR been able to embark upon return monitoring in Kayin. The south-east is also a vast and inhibiting environment logistically, characterized by extremely poor infrastructure, exacerbated by flooding during the rainy season. The operational environment is complex and advances in the peace process will be vital for further project elaboration.

Outcome Statement 3:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

Outcome Statement 4:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

  - Assessment of project evidence base, risk, catalytic effects, gender at the end of the project

| Evidence base: What was the evidence base for this report and for project progress? What consultation/validation process has taken place on this report (1000 character limit)? | 1.1 A self-evaluation carried out by an implementing partner in July 2015 was very positive. Further evidence included quarterly progress reports. 1.2 Field monitoring/evaluation by UNHCR, partner reports, engagement in GBV discussions/advocy, case response. 1.3-1.7 Workshops and trainings were documented as were discussions with youths. A survey was conducted to collect community feedback and a joint project review meeting was held. 1.8-1.10 Evaluation forms were completed by trainees, reports were prepared, stories were written by journalists, feedback was provided by forum participants, media was monitored and analysed and surveys were conducted. 2.1-2.3 An endline survey rapid assessment was conducted by a team of Mawlamyine University students led by an NGO in June 2015 on the basis of the questionaire used for the baseline survey. 2.4-2.6 Return verification/assessments are based on field visits; partner reports; government data; and a UNHCR database of training provided. |
| --- | --- |
| Funding gaps: Did the project fill critical funding gaps in peacebuilding in the country? Briefly describe. (1500 character limit) | 1.1 Women were empowered to engage in politics and discussions on conflict and peace, and space was created for them to engage in dialogues with the Government and EAOs. 1.2 In 2013, the PBF funding was of importance since the project could not have started without it due to other humanitarian needs in the country. Due to the initial success of the project, UNHCR was able to use internal funding to continue the activities. 1.3-1.7 Youths were inspired to initiate processes to contribute to consolidating peace at the community level and beyond. The project enabled conflict-affected youths to identify and design areas where they can contribute as change agents on peacebuilding in their communities. The project needs a longer timeframe and more resources for structural changes. 1.8-1.10 Training opportunities for journalists are very limited in Myanmar. Most journalists do not have any specific training on journalism and on topics such as conflict sensitive reporting or peacebuilding. Training on peace topics were made available to journalists for the first time. Limited funding was available for community-level civil society leaders to engage in peacebuilding. 2.1-2.3 Yes, the project filled critical funding gaps given that there is limited funding available for activities in conflict-affected areas in the south-east. 2.4-2.6 The PBF funds did not cover the full costs of the project; UNHCR internal funds were prioritised at the expense of other activities. |
| Catalytic effects: Did the project achieve any catalytic effects, either through attracting additional funding commitments or creating immediate conditions to unblock/ accelerate peace relevant processes? Briefly describe. (1500 character limit) | 1.1 None. 1.2 The project allowed UNHCR to engage in a wider discussion with key actors on peacebuilding. The catalytic effect consisted of greater willingness to discuss GBV issues among various political forces from the government and non-state actors. Having those actors focusing on the same issue to benefit the empowerment of women has been the main effect of this project. 1.3-1.7 Target youths designed the training program, knowledge sharing sessions and community-level activities where they learnt from each other. 35 communities voluntarily raised funding among themselves and from the local government, a political party and EAOs. Several communities jointly developed projects such as building bridges and roads. 1.8-1.10 Support for Mon's Civil Society Forum of Peace catalyzed CSOs who were previously reluctant or fearful of engagement on peace issues to become more enaged in the peace process. This led to the establishment of the South-East CSOs multi-ethnic information-sharing and coordination platform. 2.1-2.3 It experimented with new approaches that were capitalized on and scaled up by regular programmes, notably by expanding programme coverage to better incorporate EAO schools and hospitals. 2.4-2.6 The capacity building aspects of the project saw good participation by Government officials and non-State actors. This increased the potential to engage both actors in cooperation around eventual returns and durable solutions. |
| Risk taking/ innovation: Did the project support any innovative or risky activities to achieve peacebuilding results? What were they and what was the result? (1500 character limit) | 1.1 None. 1.2 SGBV awareness, prevention and response is a sensitive matter. In raising awareness, the project used the best available communication methods available, including radio shows, theater performances and public events/initiatives. The topic was made accessible to a larger audience in Mon State, including more remote areas. 1.3-1.7 The project linked participants with representatives and youths from other post-conflict areas in Myanmar, where peace process took place nearly two decades ago. They openly shared their experiences on political, security and social conditions and changes that took place as a result of peace building. 1.8-1.10 The project brought together media pracitioners, owners, editors and CSOs to strengthen the trust and collaboration between media and civil society. This modality has proven effective to correct published information and in providing access to information related to peace-building initiatives carried out by CSOs. 2.1-2.3 Coverage was extended to uncovered or even unaccesible areas, which required negotiations and agreement with both State Government and EAOs for access and project implementation. Negotiating and overcoming access restrictions is time-consuming and the risk of programme delays have at times materialised. 2.4-2.6 UNHCR's approach to collection of data in the South-East on returns and assessment of potential return areas is innovative and new to the region and organisations active in the target area. |
| Gender marker: How have gender considerations been mainstreamed in the project to the extent possible? Is the original gender marker for the project still the right one? Briefly justify. (1500 character limit) | 1.1 The original project's gender marker score is 3 which is still the right one as the project is specifically on women's empowerment. 1.2 Given the nature of the project and expertise of MSI, gender was a heavy feature of the project activities, especially taking account of the experiences and challenges faced by girls and women. The project struggled to engage boys and men due to the nature of the subject. 1.3-1.7 The project identified equal numbers of male and female youths. Gender sessions were conducted during the training. Gender analysis was a part of community level activities. 1.8-1.10 Women's equal participation was promoted in CSO planning and participation in broad CSO forum/conference activities on peace in the south-east, resulting in over 30% women participation and the inclusion of gender and peace as key themes on agendas and resulting public statements and action plans. 2.1-2.3 Gender considerations have been mainstreamed in policies and implementation in education, WASH and health. In this context, one notable gender consideration relates to protection (domestic violence); it is believed that improvements in social services all markedly contribute to lower levels of domestic violence and improved fulfilment of women's rights. 2.4-2.6 The project has considered the needs on the basis of gender and considerations related to age and diversity, in particular in assements related to potential returns. |
| Other issues: Are there any other issues concerning project implementation that should be shared with PBSO? This can include any cross-cutting issues or other issues which have not been included in the report so far. (1500 character limit) | 1.1 None. 1.2 Please refer to the report "Joint UN Project Sensitisation Mission with Myanmar Peace Centre (24-25 April, 2014)", which details analysis of overall project relevance and lessons learned, as well as catalytic effects. This report views the projects in an holistic way rather than on a project by project basis. 1.3-1.7 None. 1.8-1.10 None. 2.1-2.3 None. 2.4-2.6 Please refer to the report "Joint UN Project Sensitisation Mission with Myanmar Peace Centre (24-25 April, 2014)", which details analysis of overall project relevance and lessons learned, as well as catalytic effects. The report views the projects in an holistic way rather than on a project by project basis. |

PART 2: LESSONS LEARNED AND SUCCESS STORY

2.1 Lessons learned

Provide at least three key lessons learned from the implementation of the project. These can include lessons on the themes supported by the project or the project processes and management.

| Lesson 1 (1000 character limit) | Legitimacy of and trust in the UN played an important role in working with government and in the UN providing a platform for Government-CSO engagement. Working with locally based NGO partners that had influence, reach, knew the local landscape and were trusted was essential to the achievement of results in difficult contexts. Given the complexity of peace related work, having slightly longer time-frames would be useful. After the recent signing of a National Ceasefire Agreement (NCA) the present focus is on the political dialogue which will be the crucial step in the peace-making process. In the NCA process, very limited feed-in from agencies like UNHCR or other UN Agencies/NGOs with experience on human rights issues on the ground was used. In the future, the overall PBF project may consider further means to elaborate the experience of the projects with the authorities and seek meaningful responses to issues and challenges through the Resident Coordinator's office. |
| --- | --- |
| Lesson 2 (1000 character limit) | 1.1-1.2 A further collaboration and increased capacity building for various government bodies, as well as the judicary system will be of importance to make lasting changes that reduce GBV incidents. The understanding that GBV acts are not trivial offences but serious criminal acts and that they need to be addressed as such still needs to be further advocated for. With capacity building and involvement of police departments, UNHCR and its partner have taken the first step. Increased belief in the justice system's ability to address incidents like GBV will have a significant positive impact on the confidence in the overall peacebuilding process. |
| Lesson 3 (1000 character limit) | 1.3-1.7 In order to get the "right" youths to participate in the project, more time is required for their recruitment and to explain the project to the targeted youths and their parents and communities. It will be good to select the youths together with the responsible persons (villagers, youth leaders or CSOs) from the villages, so to increase the commitment of the youths to see the projects through. Age group of the youths should be limited to have a more homogenous group in terms of knowledge and experiences. The series of training programs should have more time for each training session, reduced number of topics and exposure to a wider variety of stakeholders working on peace processes. Community quick impact projects need time frame flexibility. Larger budgets need to be allocated tp each project so as to be more sensitive to the needs and dynamics of each community. |
| Lesson 4 (1000 character limit) | 2.1-2.3 Even when higher levels of Government and EAO leadership do not have formal channels of communication or policies of cooperation, interactions occur at lower levels. In particular, interactions occur between professionals within the social services sector at local technical level. Nurturing these interactions and building them into solid working relationships can provide an entry point to bring parallel service systems closer together. In contexts such as the south-east the UN and external interventions in general should be very "conflict-senstitive" and "do no harm". The provision of social services will continue to be a sensitive area for NSAs since they fear the encrochment of Government administration on their territories. Securing EAO endorsement before engaging in any new step or activity will help to retain their trust, maintain the UN's position as an intermidiary, and maintain the UN's humanitarian access to those most in need. |
| Lesson 5 (1000 character limit) | 2.4-2.6 The lack of previously available information on the conditions in the places of origin of Myanmar refugees currently in camps in Thailand showed the importance of data collection and sharing. UNHCR in Myanmar provided for the first time information to potential returnees which was highly appreciated. The mode for sharing such information with the relevant population, however, needs further improvements. After having focused on the capacity aspect of documentation issues for IDP and refugee returnees, the next step should be on finding ways to roll out the provision of documents. The major challenges are the remoteness of and poverty in communities. While documents can be accessed in State or Township capitals, the costs for travelling to such centres is often beyond the finanical capacities of many people. Bringing documentation centres closer to people of concern would be a positive next step. |

2.2 Success story (OPTIONAL)

Provide one success story from the project implementation which can be shared on the PBSO website and Newsletter as well as the Annual Report on Fund performance. Please include key facts and figures and any citations (3000 character limit).

Please see separately attached document for success stories and photographs.

PART 3 – FINANCIAL PROGRESS AND MANAGEMENT ARRANGEMENTS

  - Comments on the overall state of financial expenditure

Please rate whether project financial expenditures were on track, slightly delayed, or off track:

If expenditure was delayed or off track, please provide a brief explanation (500 characters maximum):

Please provide an overview of project expensed budget by outcome and output as per the table below.

| Output number | Output name | RUNOs | Approved budget | Expensed budget | Any remarks on expenditure |
| --- | --- | --- | --- | --- | --- |
| Outcome 1: Social cohesion and multi-ethnic trust are increased with vulnerable groups (IDPs, women, youth and ethnic minorities) being given a voice in peace negotiations and programming. |
| Output 1.1 | Outcome 1.1: Women's priority needs and concerns are addressed in peace negotiations and discussions on post-conflict recovery by the conflicting parties. | Outcome 1.1: UNWOMEN | Outcome 1.1: $200,000 | Outcome 1.1: *Pending* |  |
| Output 1.2 | Outcome 1.2: Increased awareness of sexual and gender-based violence and exploitation in communities. Women’s vulnerability to GBV is reduced leading to improved physical and psychological well-being, enhanced participation within the community. | Outcome 1.2: UNHCR | Outcome 1.2: $100,000 | Outcome 1.2: $100,000 |  |
| Output 1.3 | Outcome 1.3: Target youths are openly discussing the peace process and reconstruction issues. Youths’ voices (concerns and hopes) on the peace process expressed and fully documented. Outcome 1.4: Lack of trust and suspicion in target communities addressed through open dialogue and ommunity participatory activities involving youths. Outcome 1.5: Felt sense of peace dividends in communities. Outcome 1.6: Existence of mechanisms for youths to network and provide support to each other. Outcome 1.7: Proven model for engagement with youth as peace-builders in Myanmar field-tested and is available to be replicated by stakeholders in other ceasefire States. Outcome 1.8: National, local and ethnic news media outlets are engaged in conflict sensitive reportage and promote peace as a desired value. Outcome 1.9: Local community leaders and members use 20 community media as platform to actively participate in peace-building initiatives, have greater sense of ownership of the process, and confident of its full attainment. Outcome 1.10: Local communities have greater awareness, understanding, appreciation and tolerance of other ethnic groups through exposure to media content. | Outcomes 1.3 to 1.7: IOM Outcome 1.8: UNESCO Outcomes 1.9 and 1.10: UNDP | Outcome 1.3: $179,208 Outcomes 1.4 and 1.5: $77,196 Outcomes 1.6 and 1.7: $43,596 Outcome 1.8: $100,000 Outcome 1.9: $50,000 Outcome 1.10: $50,000 | Outcome 1.3: $163,778 Outcomes 1.4 and 1.5: $75,698 Outcomes 1.6 and 1.7: $42,913 Outcome 1.8: $99,773.18 Outcome 1.9: $64,870 Outcome 1.10: $35,130 | Outcomes 1.3 to 1.7: The budget for IOM was allocated by inputs rather than outcomes, so some outcomes appear combined in the approved and expended budgets. Outcome 1.9 and 1.10: UNDP received $100,000 for Outcomes 1.9 and 1.10. Originally the budget total was split evenly across the two outcomes; $50,000 for Outcome 1.9 and $50,000 for 1.10. Part of the original budget for Outcome 1.10 was redirected to Outcome 1.9. |
| Outcome 2: The Government is more responsive to the needs of vulnerable groups (IDPs, women, youth and ethnic minorities) living in ceasefire areas. |
| Output 2.1 | Outcome 2.1: State and township level authorities perform their duties effectively and become more responsive to the needs of ethnic minorities living in ceasefire areas. | Outcome 2.1: UNICEF | Outcome 2.1: $20,000 | Outcome 2.1: $15,578.29 | Outcome 2.1: Expenditure is lower than initially approved and includes funds set aside as UNICEF contribution to the overall project evaluation (USD7,465.20). |
| Output 2.2 | Outcome 2.2: State and township level government planning and response to the needs of the communities are done with active consultation, participation and collaboration of non-state actors, civil society groups and representatives from ethnic minorities. | Outcome 2.2: UNICEF | Outcome 2.2: $18,000 | Outcome 2.2: $7,081.00 | Expenditure is lower than approved expenditure given cancellation of health component (micro-planning workshops) due to policy constraints. Planned health expenditure re-allocated to Output 2.3 and towards UNICEF contribution for the final project evaluation ($3,000). |
| Output 2.3 | Outcome 2.3: Basic social services (education, health and WASH) in selected ethnic minority ceasefire areas in Mon and Kayin are established and improved. Outcome 2.4: Government and aid agencies responsiveness to needs of IDP and refugee returnees enhanced, due to improved and informed programming, and better positioning to address arising challenges. Outcome 2.5: IDP and 22 refugee returnees provided with citizenship rights and durable solutions in accordance with international standards, contributing to sustainable peace. Outcome 2.6 Sustainable return and reintegration of IDPs and refugees is supported through increased knowledge of Government officials/civil society actors on key human rights and protection standards, enabling an environment for returnees to enhance their participation and contribute to the processes involved in building a sustainable peace at different | Outcome 2.3: UNICEF Outcome 2.4 to 2.6: UNHCR | Outcome 2.3: $382,570 Outcome 2.4 to 2.6: $350,000 | Outcome 2.3: $397,904.71 Outcome 2.4 to 2.6 : $350,000 | Outcome 2.3: Expenditure is higher than approved amount given the re-allocation of funding from Output 2.2 health component. The initial budget had not been disagregated at outcome level. The global expenditures of $350,000 covered all the activities included in the following copmponent "Creating a favorable protection environment for IDP and refugee returnees and supporting durable solutions through monitoring, capacity building and documentation". |
| Outcome 3: |
| Output 3.1 |  |  |  |  |  |
| Output 3.2 |  |  |  |  |  |
| Output 3.3 |  |  |  |  |  |
| Outcome 4: |
| Output 4.1 |  |  |  |  |  |
| Output 4.2 |  |  |  |  |  |
| Output 4.3 |  |  |  |  |  |
| Total |  |  |  |  |  |

  - Comments on management and implementation arrangements

Please comment on the management and implementation arrangements for the project, such as: the effectiveness of the implementation partnerships, coordination/coherence with other projects, any South-South cooperation, the modalities of support, any capacity building aspect, the use of partner country systems if any, the support by the PBF Secretariat and oversight by the Joint Steering Committee (for PRF only). Please also mention if there have been any changes to the project (what kind and when) (2000 character maximum):

1.2 Difficulty recruiting qualified SGBV specialists meant staff were not hired until early 2014. To maintain coherence across the projects, UNHCR extended its project period to sync with other agencies'. The joint mission raised State authorities' awareness of UN activities implemented using the PBF grant.

2.4-2.6 A change in the budget was approved by PBF. The basis was a change in implementation plans for 2014. UNHCR planned to provide parts of the activities through a partner organization, but given a lack of qualified partners and sensitivities around the dissemination of data, it opted to implement the project on its own.

With regard to the external evaluation of the project, the RUNO’s had set aside a total of USD $21,865 to support this activity, with a breakdown as follows: IOM: $3,800, UNWomen: $2,600, UNDP: $1,200, UNESCO: $1,200, UNCHR: $5,600, and UNICEF: $7,465.

At the end of the 2015, as part of a discussion between PBSO and the UNCT about an extension of the programme implementation period, it was jointly decided that the final evaluation would be strengthened by increasing the budget and thus allowing for a more in-depth evaluation. To this end, PBSO agreed to a cost extension that included a supplemental grant of USD $22,000. Thus the total external evaluation budget, combining the RUNO contribution and additional PBSO funding, was $43,865. Of this funding, the total actual cost of the evaluation, including consultant fees and travel, and national travel and activities, was $39,966. The difference will be returned to PBSO as part of the final financial reporting.

The final evaluation was carried out by Marla Zapach (Canada), supported by Kyaw Thu (Myanmar).  The field work, including meeting with stakeholders in Mon and Kayin states between 25 March and 4 April.  The report submitted by Ms. Zapach was subject to several rounds of comments and revisions by both the RCO and PBSO, and a final version was submitted on 10 June.

# Footnotes

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to “Project ID” on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed.

Please note that financial information is preliminary pending submission of annual financial report to the Administrative Agent.