RUNO END PF PROJECT REPORTING		TEMPLATE 4.5

PEACEBUILDING FUND (PBF)

END OF PROJECT report

COUNTRY: Solomon Islands

REPORTING PERIOD: July 2016 to 31st December 2017

| Programme Title & Project Number |  |
| --- | --- |
| Programme Title: Supporting Peaceful and Inclusive Transition in Solomon Islands Programme Number (if applicable) 00101348 MPTF Office Project Reference Number: 11100 |  |  |

| Recipient UN Organizations |  | Implementing Partners |
| --- | --- | --- |
| List the organizations that have received direct funding from the MPTF Office under this programme: UNDP and UNWOMEN |  | List the national counterparts (government, private, NGOs & others) and other International Organizations: Ministry of National Unity Reconciliation and Peace (MNURP) 2. Ministry of Women, Youth, Children and Family Affairs (MWYCFA) 3. Prime Minister's Office (PMO) |
| Programme/Project Budget (US$) |  | Programme Duration |
| PBF contribution (by RUNO) $2.5 million USD |  |  | Overall Duration (months) 18 |  |
|  |  |  | Start Date (dd.mm.yyyy) 1st July 2016 |  |
| Government Contribution (if applicable) Government contributes in kind for some activities and co-funds some activities |  |  | Original End Date (dd.mm.yyyy) | 31st December 2017 |
| Other Contributions (donors) (if applicable) UNDP CO Resources (UNCP CPR Trust Fund) |  |  | Final End date(dd.mm.yyyy) 31st December 2017 |  |
| TOTAL: |  |  |  |  |

| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| --- | --- | --- |
| Mid-Term Evaluation / Review - if applicable please attach Yes No Date: End of project Evaluation– if applicable please attach Yes No Date: |  | Name: Osnat Lubrani Title: Resident Coordinator Participating Organization (Lead): Email address: osnat.lubrani@one.un.org |

PART 1 – RESULTS PROGRESS

  - Assessment of the project implementation status and results

For PRF projects, please identify Priority Plan outcome and indicators to which this project has contributed:

Priority Plan Outcome to which the project has contributed. Support the implementation of peace agreements and political dialogues

Priority Plan Outcome indicator(s) to which project has contributed. Support national reconciliations

For both IRF and PRF projects, please rate this project’s overall achievement of results to date:

For both IRF and PRF projects, outline progress against each project outcome, using the format below. The space in the template allows for up to four project outcomes.

Outcome Statement 1:   Inclusive space established for dialogue and reconciliation and national capacity strengthened for implementation of peace policy

Rate the current status of the outcome:

| Indicator 1: Increased national capacity and effectiveness to lead the post-conflict/RAMSI transition; resulting in visible signs of improvements in SIG’s response to transition and peacebuilding implementation needs and challenges Indicator 2: Confidence/trust to channel people's voices through new coordination mechanism for engagement/dialogue with national and provincial authorities Indicator 3: National Action Plan on 1325/WPS is being implemented, increasing women's effective participation in national policy formulation and decision making | Baseline: No coordination mechanism in place, ad hoc initiatives, no sharing of data including for planning and programmatic responses Target: Transition coordination mechanisms are formally established and functioning, resulting in implementation progress of the peacebuilding policy and negotiated closure of some of the unfeasible demands and challenging issues by December 2017 Progress:Coordination is in place with national stakeholders under the leadership of the Ministry of National Unity, Reconciliation and Peace and the Prime Minister's Office. Meetings have been held regularly to address issues of transition and the closure of some of the unfeasible demands and challenging issues. By the end of the project, the joint efforts and coordination between PMO, MNURP and other institutions resulted in actions on the way forward dealing with RAMSI's exit, TRC follow up, demands from ex-combatants and reconciliations in hotspot communities. Baseline: Analysis by scoping mission Target: Number of men, women and youth that have increased understanding of and access to engagement mechanisms and participate in the follow-up consultations Progress:An inclusive space for discussion and reconciliation in Solomon Islands through dialogues attended by 531 tribal leaders, women, youth, MPs and provincial premiers. Key dialogues were organized in hotspot provinces and the national dialogue hosted by the Prime Minister attended by provincial, women and youth leaders. Baseline: Finding from UN Women internal assessment on women and politics. Target: Tangible success of advocacy efforts informed by a newly formulated government affirmative action strategy to increase women’s effective participation in decision making. Progress: In 2016-2017 with the support of PBF, progress is made with the consensus among women's groups in the National Women's Summit, the launch of the National Action Plan on Women's Peace and Security and the pilot project in Western Province for increasing women's participation in decision making in Western Province and the adoption of gender strategies in key provinces (Guadalcanal, Malaita and Honiara. |
| --- | --- |

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

The project supported the provincial dialogues in Guadalcanal, Malaita and Western provinces addressing issues on stability, governance, decentralization and borders.

Through support to the National Dialogues, the project helped national stakeholders to reach a bipartisan consensus between provinces and national government with a national communique agreed prioritizing a common agenda on key national issues that need to be addressed collectively.

Technical and logistical support to women leaders and the Ministry for Women finalized the National Action Plan on WPS and a mechanism to implement it and hold National Women's Summit.

Provincial support led to the integration of a gender strategy at the provincial level in conflict provinces and TSM policy.

Support to Prime Minister's team to work on reparations, provided expert on reparations, deploying gender advisor provided advice and input.

Peace outreach to hotspot and remote communities conducted through radio programmes.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

The UNPBF project – implemented from mid-2016 to end 2017 – provided support to the creation of an inclusive space for dialogue and reconciliation. The provincial dialogues and the Women and Youth Summits. The National Dialogue on Sustaining Peace and Stability reinforced national capacity and commitment to sustaining peace after RAMSI.

The dialogues were inclusive with participants representing Members of Parliament, women, youth, the private sector, religious groups and academics. They lead to a consensus and commitment to address issues considered impediments to peace and security in Solomon Islands. Issues covered by the consensus and communique of the dialogues ranged from reparations to law and order, security, constitutional and governance reform, land reform, natural resources management and women and youth empowerment, which are considered the root causes of the tension. Resolutions and a communique were adopted through a participatory process committing all stakeholders to cooperate on the issues discussed.

The dialogues also led to the serious effort to finalize the National Reparations Strategy, which will form the basis for a comprehensive approach to follow TRC recommendations. A report on the status of the Guadalcanal ‘bona fide’ demands and related demands from other provinces and bodies who have suffered from the Bougainville Crisis and the Civil Unrest from 1998 to 2002 was presented to the Prime Minister. This support provided stronger engagement between the government and the communities with visible signs of improvements in SIG’s response to transition and peacebuilding implementation needs and challenges.

The support to provincial dialogues enabled more than 500 tribal leaders and women from key provinces to participate in dialogues with Government on key issues pertaining to the country’s future. These have led to a wide consensus between central government, the provincial government and communities' crucial issues affecting stability, including on border security, decentralization framework and inclusive development. After provincial dialogue, the provincial government has started to work on increasing women’s participation in the provincial councils and addressing security issues within communities.

Achieving an increase in women’s effective participation in national policy formulation and decision making was supported and accomplished through support to provincial women dialogues and National Women's Summit discussing key national issues and integration of gender strategy at the provincial level whereby four key provinces have launched their provincial gender strategy. This is in addition to the launch of the National Action Plan on Women, Peace and Security – a first in the Pacific – providing a very strong basis and platform for women in Solomon Islands to advocate for further inclusion of women in peacebuilding and development.

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

The relative weakness of involved institutions and the continued political instability of the country have, in some cases, slowed down the implementation of activities. Achievement of this outcome is linked to the national leadership efforts in engaging and prioritizing a national peace and women agenda. In Solomon Islands, political priority is constantly shifting and reducing focus on urgent peacebuilding and needs maintaining stability. There were at least three serious efforts to replace the sitting Prime Minister, and the last attempt was successful with the new PM and government elected and formed. This led to the reduced capacity of the project to implement various programmes faster.

However, to mitigate this, the project engaged with all leaders in the country to stay abreast of changes and reach out and engage significantly with consistency throughout. The project regularly consulted the project advisory members, the steering committee, and sought advice from national stakeholders.

Outcome Statement 2:  Youth engaged in peace with society and leadership.

Rate the current status of the outcome:

| Indicator 1: Degree and state of youth engagement and participation in social, political and economic areas in Solomon Islands Indicator 2: Perception of youths disaggregated by sex/geographical location of their chances/ability to participate in peace and reconciliation and the future of their country Indicator 3: | Baseline: 0 Target: % of the increase in youth engagement and participation in peace advocacy work and engagement with national leadership Progress:Achieved Baseline: None Target: Positive perception of youth groups on their ability to engage with issues related to peace, reconciliation and the future of their country Progress:Achieved Baseline: Target: Progress: |
| --- | --- |

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

Youth leaders in Solomon Islands supported with youth dialouges dicussing youth agenda in partnership with SINU in July 2016 and others in 2017. Collaborative partnership saw 10,000 copies of a youth publication distributed nationwide in February 2017. 50 youths came together to celebrate International Youth Day in August 2016 and promoted and discussed  the Future We Want for Solomon Islands. CTC and Youth@Work as potential partners provided targeted training to more than 200 marginalized youths from targeted areas in Malaita, Guadalcanal and Honiara. 54 youths from informal settlements in and around Honiara attended Young Entrepreneurship training, which Youth@Work supported. 80 youths representing different youth groups in and around Honiara were trained and provided with capacity building and mentoring opportunities through five peacebuilding pre-acceleration user experience prototyping workshops. More than 200 youths attended and participated in the 2017 youth innovation summit.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

In 2016, activities related to this outcome started with the organization of the project youth forums, aimed at supporting engagement with policymakers; these forums resulted in agreements being concluded on an agenda for improving youth participation and engagement. Recommendations were adopted by the Youth Ministry to be incorporated into the National Youth Policy. The forums, meetings, workshops and trainings stimulated dialogue among relevant stakeholders on selected themes and were extremely useful and exposed the policymakers to the concerns and issues raised by young people. The project also created a space for policymakers to hear evidence-based feedback from youth representatives. These forums and workshops stimulated youths and involved them in the national issues and youth-related programme design, implementation and monitoring. Moreover, they have advanced youth participation in the development processes. The collaboration and knowledge sharing from the youth forums and workshops enhanced the structures for engagement of youth with national actors and instigated tractions to broaden youth support in the country. It must be noted that the youth dialogue sessions were critical platforms for review of the National Youth Policy and National Youth Parliament model as well as the framework for implementation of the SDGs in Solomon Islands. One of the most significant contributions was the organization of the National Youth Summit, which helped create nationwide engagement at the highest level and also promoted social entrepreneurship and innovation among young people. Activities supported have provided opportunities for youth to be part of the dialouge on national issues with youth taking part in the national and provincial dialogues and representing the voice of young people discussing policy topics from reparations and decentralization to good governance and transition in Solomon Islands. Young people's engagement with the Ministry of Women and Youth, RAMSI and the police provided them an opportunity to directly connect and partner with the three institutions and empowered them to work in their communities that previously had little access to decision making processes. Young people felt very valued, respected and had a sense of belonging and pride in their provinces and communities as key components of their personal sense of peace and peace in the broader community. Youths equipped with peacebuilding and lifeskills have started advocating for peace and at the same time initiated some livelihood schemes that have already benefited them, made them self-reliant and have improved their long-term economic prospects. In addition, youths acquired improved knowledge, skills, attitudes, experiences and behaviors of YECP and started their sustainable and profitable enterprises in their own communities. Innovation support equipped young people with peacebuilding, leadership and entrepreneurial skills.

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

Youth@Work, which was previously identified as a key partner to implement a significant portion on youth economic and cultural engagement under this outcome, could not implement outputs until much later in the second year. Their capacity on the ground was stretched after receiving a new funding scheme and recent expansion. The project managed to identify a new partner, CTC, and decided to work closley to provide support to youth from hotspot areas in Guadalcanal and Malaita. They managed to succesfully implement the youth livelihood and lifeskills training, and now the scheme has been used by others as a good example of training for marginalized and rural youths. For PBF, the youth peacebuilding and livelihood programme at the end were implemented by both CTC and later by Youth@Work.

Outcome Statement 3:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

Outcome Statement 4:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

  - Assessment of project evidence base, risk, catalytic effects, gender at the end of the project

| Evidence base: What was the evidence base for this report and for project progress? What consultation/validation process has taken place on this report (1000 character limit)? | The project conducted the final evaluation, which highlighted the impact of the project on peacebuilding efforts in Solomon Islands. In May, representatives from government, civil society, women and youth participated in the academic consultation to design the second PBF project outcomes and outputs using achievements analysis of the first PBF as the basis. Throughout the implementation process an inclusive consultation continued to take place and validation of results show in activities, reports and follow-up after the event. Validation and consultations with the project advisory group members, technical working group and steering committee members have been conducted on a regular basis. Regularly, representatives of key ministries took part in the project board meetings and discussed project progress. |
| --- | --- |
| Funding gaps: Did the project fill critical funding gaps in peacebuilding in the country? Briefly describe. (1500 character limit) | Since establishment of the project, it addressed immediate peacebuilding needs in SOI at a time when sufficient resources are not available and critical peacebuilding interventions remain unfunded by SIG. These include substantive and technical support to MNURP and PMO, e.g. establishment of Technical Committee and focal point for coordination, research on priority topics, e.g. provincial dialogues among youth groups through issue mapping of youth in Weathercoast and North Malaita, joint scoping mission and analysis, including women and youth, formulation of reparation/reconciliation policy, e.g. initial consultations on reparation and reconciliation framework, support to dialogues and reconciliation events and activities, e.g. logistical/mediation support for reconciliation in Kwaio. These are critical funding gaps that would not have happened given the establishment of the PBF project in SI and funding support it rendered towards these activities. |
| Catalytic effects: Did the project achieve any catalytic effects, either through attracting additional funding commitments or creating immediate conditions to unblock/ accelerate peace relevant processes? Briefly describe. (1500 character limit) | Since the high level and successful launch of the project by the Prime Minister of Solomon Islands, the project managed to accelerate the national agenda on women, peace and security, efforts to advance the national programme on reparations, and a better coordination of national agencies, including creating stronger synergies between the UN PBF project outputs and activities with some national programs separately funded in the government budget. The government also took part in cost sharing of some activities including work on reparations, dialogue, public outreach and consultation. On the youth component, UNDP managed to formulate a long-term programme that is expected to expand from the existing youth activities into more comprehensive support, which improves linkages between peacebuilding, livelihoods and support for marginalized youth. |
| Risk taking/ innovation: Did the project support any innovative or risky activities to achieve peacebuilding results? What were they and what was the result? (1500 character limit) | During this transitional period in Solomon Islands, addressing sensitive, important national issues is critical to ensuring long-term stability and peace. The PBF project is taking a risk through promoting dialogue and providing inclusive space for various national actors to discuss sensitive national issues, which are important to address grievances and the underlying causes of the tension and to rectify the social contract. On the youth component, the project is taking risks by engaging with the marginalized youth who are the actors at the core of the conflict dynamics through providing support in communities where government presence is limited. Through the women’s component, promotion of stronger women's participation in social and political life in a country where the majority of women are experiencing domestic violence is a worthy risk-taking activity. An innovative approach applied with support to 500 youths representing different youth groups in and around Honiara, Guadalcanal, Malaita and Western provinces were trained and provided with capacity building and mentoring opportunities that have enabled them to ideate and prototype solutions for social challenges, coalition-building and cross-networking between fields of development, peacebuilding, business, technology and innovation through prototyping workshops and peacebuilding and lifeskills trainings. |
| Gender marker: How have gender considerations been mainstreamed in the project to the extent possible? Is the original gender marker for the project still the right one? Briefly justify. (1500 character limit) | Gender consideration is both addressed directly through the specific outputs on women’s participation and removing barriers to political participation, as well as through an output on increasing young female participation with policymakers. Gender is mainstreamed in all other outputs of the project through the integration of gender perspectives in all areas and levels of the project activities. At the earlier stage, the design of the project used strong consultation with women's groups. At the implementation level, in activities such as the provincial dialogues and youth forums, women’s voices and participation were promoted and supported to ensure gender equality is achieved. Capitalizing on the existing environment and platforms, the project facilitated a three-day National Women’s Summit that brought together women from across the country for consultations and endorsement of the draft NAP on WPS. This is a framework that ensures WPS activities are not seen as stand alone efforts but rather as an integral part of the ongoing peace and security discussions and in line with government efforts of promoting gender consideration and mainstreaming. |
| Other issues: Are there any other issues concerning project implementation that should be shared with PBSO? This can include any cross-cutting issues or other issues which have not been included in the report so far. (1500 character limit) | Political instability continued to be a serious issue with the constant possibility of changes of government and key personnel that could lead to a reprioritization and reduction of momentum. The project is working in a volatile political environment at the critical juncture of the transition with RAMSI leaving. Additionally, substantial time has passed since the formal peace accord was signed. The project has and will remain constantly involved with all sides to reach out and engage throughout. |

1.3 INDICATOR BASED PERFORMANCE ASSESSMENT: Using the Project Results Framework as per the approved project document- provide an update on the achievement of key indicators at both the outcome and output level in the table below. Where it has not been possible to collect data on indicators, state this and provide any explanation in the qualitative text above. (250 characters max per entry)

|  | Performance Indicators | Indicator Baseline | End of project Indicator Target | Current indicator progress | Reasons for Variance/ Delay (if any) | Adjustment of target (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 Inclusive space established for dialogue and reconciliatio n and national capacity strengthened for implementati on of peace policy | Indicator 1.1 Increased national capacity and effectiveness to lead the post-conflict/RAMSI transition; resulting in visible signs of improvements in SIG’s response to transition and peacebuilding implementation needs and challenges | No coordination mechanism in place, ad hoc initiatives, no sharing of data, including for planning and programmati c responses | Transition coordination mechanisms are formally established and functioning, resulting in implementatio n progress of the peacebuilding policy and negotiated closure of some of the unfeasible demands and challenging issues | Facilitation of coordination between national and provincial governments, communities, RAMSI and development partners that lead to design and endorsement of coordination and transition mechanisms, including the gender coordination forum |  |  |
|  | Indicator 1.2 Confidence/trust to channel people’s voices through new coordination mechanisms for engagement/dialog ue with national and provincial authorities | There has not been an analysis by scoping mission to establish new coordination mechanisms | Number of men, women and youth that have increased understanding of and access to engagement mehcanisms and participate in the follow-up consultations | Activities including the National Women's Summit, International Youth Day dialogue and Youth and Peacebuilding Workshop are contributing to improving engagement and dialogue between governments and communities |  |  |
|  | Indicator 1.3 National Action Plan on 1325/WPS is being implemented, increasing women’s effective participation in national policy formulation and decision making | Although several consultations were conducted by the women's forum, very little was focused on a unified women's voice on TSM and national peace/ development policies in the past | Tangible success of advocacy efforts informed by a newly formulated government affirmative action strategy to increase women’s effective participation in decision making. | National Women's Summit in October 2016 brought together over 80 women from across the country to discuss and validate the NAP. The space enabled a dialogue on peacebuilding through consensus. After the summit, an MOU was signed between government |  |  |
| Output 1.1 MNURP/PM O capacity strengthened and evidence base and coordination improved | Indicator 1.1.1 Progress towards the establishment and implementation of the institutional mechanism to coordinate and implement peace policy established and implemented | No functioning coordination mechanism in existence | Monthly meetings convened, provincial dialogue initiatives regularly reviewed and strategies adapted | Regular meetings have been held. Participatory design supported key stakeholders to reach consensus on way forward with reconciliation and peacebuilding through reconciliation with hotspot communities and national reparations framework and provincia |  |  |
|  | Indicator 1.1.2 Number of peacebuilding activities unfunded through the national programme is supported | Zero number of peacebuildin g activities unfunded | Number of new peacebuilding initiatives funded for both government and CSO initiatives | Project supported three MNURP peacebuilding initiatives in hotspot areas in Kwaio, Malaita; Marau, Guadalcanal; and Weather Coast, Guadalcanal. Project facilitated 2 consensus-building dialogues for Malaita and Guadalcanal leaders on MNURP provinc |  |  |
| Output 1.2 Effective national reconciliatio n initiated | Indicator 1.2.1 Number of experts deployed on TRC action plans and implementation strategy led by the government | Zero experts deployed to provide technical assistance for reparation & reparation policy framework | 3 experts deployed to provide technical assistance to do consultation for the reconciliation and reparation policy framework | 2 experts deployed and project provided technical advice and supported 4 meetings of Prime Minister's Reparations Steering Committee. Draft Reparations Framework and national consultation plan developed for PM's approval |  |  |
|  | Indicator 1.2.2 Outreach of Government peacebuilding and reconciliation policy and programmes boosted through dialogues, radio programmes, newspaper articles etc. also informing new policymaking | No systematic outreach undertaken/ conducted | Outreach and media strategy developed and launched to effectively communicate PMO, MNURP, MWYCFA’s peacebuilding policies and programmes | Post-conflict and peacebuilding journalism training organised for SOI journalists and key government communications officers. Project developed posters and stickers under theme 'One People, One Country, One Future' and disseminated |  |  |
| Output 1.3 Women’s voice unified | Indicator 1.3.1 Unified women's voice on TSM and national peace/ development policies to effectively influence policies | None | Three provincial pre-dialogue Women’s Forums held to formulate joint messages and appoint delegates for the provincial dialogues. National Women’s Summit to influence PB and reconciliation policies planned for 2017 | TSM workshop held at National Women's Summit in 2016. MOU signed between government and key NGOs for NAP implementation. |  |  |
|  | Indicator 1.3.2 National Action Plan on SCR1325 finalised and endorsed by the cabinet | Draft NAP not finalized | NAP validated and endorsed in national stakeholders’ workshop in August 2016 | National Women's Summit in October brought together over 80 women from across SOI to validate the NAP. The space enabled a dialogue on peacebuilding thorugh consensus. Following the Summit, an MOU was signed between government and key NGOs for NAP |  |  |
| Outcome 2 | Indicator 2.1 Tangible increase in youth engagement and participation in national peace advocacy initiatives and regular, structured engagement between youth and national leaders. Peacebuilding recommendations from youth summits are considered and incorporated | Youth Resolution Document, result of 28 Youth Workshops | Active youth engagement in dialogue and public life through media (printed and radio) and provincial and national forums results in their enhanced participation in social, political and economic areas in Solomon Islands | Increase in opportunities for youth to be involved in peacebuilding through youth-specific events, workshop on topic of youth and peacebuilding, and youth participation in broader provincial dialogues. Further, youth participation in development and |  |  |
|  | Indicator 2.2 Positive perception of youth groups on their ability to engage with issues related to peace, reconciliation and future of their country | No research has ever been done on this topic | Positive perception of youth groups on their ability to engage with issues related to peace, reconciliation and future of their country | Research project commenced to develop greater understanding of 'status of youth' in hotspots. Positive response from first youth and peacebuilding events |  |  |
| Output 2.1 Youth leaders upheld as peace advocates | Indicator 2.1.1 Youth leaders identified and trained are peace advocates in their comunities and facilitate regular interaction between youth and national authorities to resolve outstanding issues peacefully | Limited and uncoordinate d peacebuilding training for youth leaders in hotspots areas | 250 young leaders in three former conflict provinces trained in peacebuilding, conflict resolution and reconciliation. Small grants provided to youth organisations to organize peace events | Activities under this output commenced in 2017 with 200 young people from marginalized communities trained |  |  |
|  | Indicator 2.1.2 Formal engagement mechanisms between youths and national government institutions established to ensure youth voices are channeled through appropriate authorities | No formal engagement mechanisms in place by December 2017, a formal/written document is formulated and endorsed to facilitate ongoing engagement between youth and national authorities | By December 2017, a formal/written document is formulated and endorsed to facilitate ongoing engagement between youth and national authorities | Youth Workshop brought together 20 young people with government, NGO and private sector. International Youth Day Forum gave more than 50 youths opportunity for dialogue on "Future We Want". Youth will be involved in 2 provincial dialogues in Malaita |  |  |
| Output 2.2 Economic and cultural engagement increased for enhanced national unity | Indicator 2.2.1 Number of additional marginalized youth who participated in Youth@Work programme | In generalYouth @Work programme over the years has provided youth with training, practical experience and support to increase their potential for workforce participation but has not focused on peacebuildin g activities | 300 marginalized youths to participate in Youth@Work Programmes and other NGOs conducting related peacebuilding programmes for peacebuilding and livelihoods by 2017 | The project managed to train 300 marginalised youth through both Youth @ Work ad the Coconut Pacific livelihood and peacebuilding programme. |  |  |
|  | Indicator 2.2.2 Number of events supported to engage youth groups in peacebuilding activities, such as sports, music, art and cultural activities | Zero events supported | At least 5 events supported to engage youth groups in these peacebuilding activities | Development and distribution of 10,000 copies of a Peace Edition of the YOSI magazine in October and November 2016. Magazine was designed by youth for youth on the theme of peacebuilding |  |  |
| Output 2.3 Young women included in nation-wide peacebuildin g | Indicator 2.3.1 Level of engagement in dialogues between young women groups and the national leadership, including parliament | Very low level of engagement | At least 2 dialogue platforms supported | The project supported two dialogue platform with women groups |  |  |
|  | Indicator 2.3.2 Number of young women's groups and national consultations supported | None | At least 1 young women's group consultation supported | The project faciliated young women groups to participate fully in the national dialogue and the three provincial dialogues |  |  |
| Outcome 3 | Indicator 3.1 |  |  |  |  |  |
|  | Indicator 3.2 |  |  |  |  |  |
| Output 3.1 | Indicator 3.1.1 |  |  |  |  |  |
|  | Indicator 3.1.2 |  |  |  |  |  |
| Output 3.2 | Indicator 3.2.1 |  |  |  |  |  |
|  | Indicator 3.2.2 |  |  |  |  |  |
| Output 3.3 | Indicator 3.3.1 |  |  |  |  |  |
|  | Indicator 3.3.2 |  |  |  |  |  |
| Outcome 4 | Indicator 4.1 |  |  |  |  |  |
|  | Indicator 4.2 |  |  |  |  |  |
| Output 4.1 | Indicator 4.1.1 |  |  |  |  |  |
|  | Indicator 4.1.2 |  |  |  |  |  |
| Output 4.2 | Indicator 4.2.1 |  |  |  |  |  |
|  | Indicator 4.2.2 |  |  |  |  |  |
| Output 4.3 | Indicator 4.3.1 |  |  |  |  |  |
|  | Indicator 4.3.2 |  |  |  |  |  |

PART 2: LESSONS LEARNED AND SUCCESS STORY

2.1 Lessons learned

Provide at least three key lessons learned from the implementation of the project. These can include lessons on the themes supported by the project or the project processes and management.

| Lesson 1 (1000 character limit) | Inclusive consultations are imperative both to manage expectations and risks. It should be continued in every step of the project implementation. The Solomon Islands Government has made peace and reconciliation its top priority and has undertaken steps towards reaching a national process and consensus. A formal apology was issued by the Prime Minister during the 2016 National Apology Week. This new momentum for the national peace process has raised expectations, which has made it critical to have more effective engagement with the communities and different interest groups. The UN PBF team is working closely with national stakeholders and partners to chart the course for the national-led peace process, including identifying issues for the national and provincial dialogues. The aim is to have the process inclusive and widely consulted to solidify the gains made by the existing RAMSI interventions and realize peace for Solomon Islands. |
| --- | --- |
| Lesson 2 (1000 character limit) | Coordination, information management and neutrality are processes that should be carefully managed. The UN PBF team has needed to balance between the need to address the remaining issues from the tension and assist the country to move forward with the future. There is a need to ensure the focus of all parties is on building consensus across many disputed and sensitive issues through political dialogue, despite the challenges. The Project is facilitating these processes, supporting national actors, especially women and youth, to actively participate while ensuring UN neutrality and an impartial position. It is important to ensure that the team’s role is to facilitate and provide a neutral space for all parties, and such efforts assist the national stakeholders to achieve the national agenda. |
| Lesson 3 (1000 character limit) | Regular and adequate flow of information between implementing agencies is essential to grant quality outputs and agreed upon, consistent outcomes. It is advisable to have formalized communication mechanisms, such as regular project meetings, where operational decisions are jointly taken and communicated to the Project Board for endorsement. |
| Lesson 4 (1000 character limit) | It is critical to establish a solid foundation for the project to support peacebuilding work in a complex environment. This needs to be done efficiently while also providing immediate assistance to the national peacebuilding activities led by the government. With a short project timeframe, effective utilization of key international and national staff from related UN projects is helpful, especially where synergies between outputs are present. Mobilizing regional expertise and support from UN regional and country teams like Suva and Bangkok, are crucial to ensuring immediate capacity for the project to be effective on the ground. Without this support, the Project may not be fully prepared with a structure and mechanisms to support the immediate plan for the implementation. Consultations for the project have taken place since inception. In May, representatives from government, civil society, and women and youth participated in the academic consultation to design the project outcome. |
| Lesson 5 (1000 character limit) |  |

2.2 Success story (OPTIONAL)

Provide one success story from the project implementation which can be shared on the PBSO website and Newsletter as well as the Annual Report on Fund performance. Please include key facts and figures and any citations (3000 character limit).

The UN PBF project successfully supported the first-ever Solomon Islands’ National Women’s Summit to discuss systematic inclusion of women in peacebuilding and policymaking processes. It was held in Honiara from 10-12 October 2016 and jointly coordinated between UN Women, UNDP and the Ministry of Women, Youth, Children and Family Affairs. The Summit brought women’s leaders and representatives from each province.

Consensus was reached on efforts to ensure women’s inclusion through the National Action Plan on Women, Peace and Security. This is the first national framework of its kind in the country, and it presents a mechanism to advance the implementation of Solomon Islands’commitments to women’s participation in peacebuilding and policymaking. The Summit provided women with an opportunity to have substantial discussions with national leaders on key national agendas, including security transition, RAMSI withdrawal, reparations and removing barriers for women’s participation in politics.

Government representative Permanent Secretary Ethel Sigimanu acknowledged that the peacebuilding process following the ethnic tensions (post 2003) marginalized women from negotiations, decision making, and reconstruction efforts. The Government used the Summit to commit to ensuring that the diverse experiences of Solomon Islands women will be fully integrated into all peacebuilding, peacemaking and reform processes.

Women from provinces demanded a clear, visible voice and participation of women in future provincial dialogues and policymaking discussions. As a participant said, “peace means not only a life free of violence from those they share their lives with (husbands, partners), the right to choose (education, self-respect, safe sex, marriage, number of children, when to have children, when not to), but also an equal partnership in all spheres of development and political processes”. The quote summarizes the complex challenges women face in Solomon Islands, and the need for equality in the home, the community and at the national level.

Participants were presented with action plans and recommendations, including from the truth and reconciliation report (TRC), which was the basis for the dialogue and reconciliation process after the ethnic tensions. The presentation was the first time many women learned about the findings and recommendations in detail. The findings acknowledged that women played an important role in persuading warring parties to put down the weapons and facilitate local peace processes. Participants were supportive of the TRC recommendations, including one that called for reserved seats in parliament for women to be respected and implemented. The Summit resulted in an agreement and MOU for cooperation between community-level women’s groups and the Government to fully implement the National Action Plan and other efforts to advance women’s participation in peacebuilding and policymaking at both the national and provincial level.

PART 3 – FINANCIAL PROGRESS AND MANAGEMENT ARRANGEMENTS

  - Comments on the overall state of financial expenditure

Please rate whether project financial expenditures were on track, slightly delayed, or off track:

If expenditure was delayed or off track, please provide a brief explanation (500 characters maximum):

The full financial report is provided separately

Please provide an overview of project expensed budget by outcome and output as per the table below.

| Output number | Output name | RUNOs | Approved budget | Expensed budget | Any remarks on expenditure |
| --- | --- | --- | --- | --- | --- |
| Outcome 1: |
| Output 1.1 |  |  |  |  |  |
| Output 1.2 |  |  |  |  |  |
| Output 1.3 |  |  |  |  |  |
| Outcome 2: |
| Output 2.1 |  |  |  |  |  |
| Output 2.2 |  |  |  |  |  |
| Output 2.3 |  |  |  |  |  |
| Outcome 3: |
| Output 3.1 |  |  |  |  |  |
| Output 3.2 |  |  |  |  |  |
| Output 3.3 |  |  |  |  |  |
| Outcome 4: |
| Output 4.1 |  |  |  |  |  |
| Output 4.2 |  |  |  |  |  |
| Output 4.3 |  |  |  |  |  |
| Total |  |  |  |  |  |

  - Comments on management and implementation arrangements

Please comment on the management and implementation arrangements for the project, such as: the effectiveness of the implementation partnerships, coordination/coherence with other projects, any South-South cooperation, the modalities of support, any capacity building aspect, the use of partner country systems if any, the support by the PBF Secretariat and oversight by the Joint Steering Committee (for PRF only). Please also mention if there have been any changes to the project (what kind and when) (2000 character maximum):

The existing project management and implementation arrangements were relevant. As originally designed, this project was managed under the direct implementation modality of UNDP and UN Women in Solomon Islands, with support from the UNDP Pacific Office in Fiji and UN Department of Political Affairs in New York. In order to ensure a coordinated project implementation as one UN, there has been one project management unit/team comprised of UNDP and UN Women staff with matrix reporting to their respective agencies. For the second PBF, there will be a single work plan and one consolidated budget. This arrangement will be maintained, but stronger coordination between UNDP and UN Women will be instigated to ensure improved communication, visibility and partnership. To assist with the project capacity to mitigate risks and provide a contextual understanding of the political dynamic in Solomon Islands, the project set up the Project Advisory Group. This is a voluntary position consisting of eminent individuals from Solomon Islands. The key responsibilities of the advisory board members are to provide advice and general input to the PBF project, to alert the PBF project to any potential risks and negative repercussions, to provide support in facilitating targeted outreach and dialogue through print media and radio to encourage and promote reconciliation and unity among the public, and to visit some of the hotspot/marginalized areas when it is required.

# Footnotes

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to “Project ID” on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed.

Please note that financial information is preliminary pending submission of annual financial report to the Administrative Agent.