## SUIVI BUDGETAIRE Apui au ST
Intitulé | Budget approuve 2018-2019 | avril 2018 | mai 2018 | juin 2018 | juillet 2018 | aout 2018 | septembre 2018 | octobre 2018 | novembre 2018 | decembre 2018 | Solde au 31/12/2018 | janvier 2019 | fevrier 2019 | mars 2019 | Solde au 31/03/2019 | avril 2019 | Solde au 30/04/2019 | mai 2019 | juin 2019 | juillet 2019 | aout 2019 | septembre 2019 | octobre 2019 | novembre 2019 | decembre 2019 | janvier 2020 | fevrier 2020 | mars 2020 | avril 2020 | Budget total May 2019 - April 2020 | SOLDE | % | Requete de fonds additionnels May 2019 - 2020 | correction
Objectif spécifique 1
Salaire Assistant technique national | 51070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51070 | 1840 | 3400 | 3400 | 42430 | 3400 | 39030 | 4255.83 | 4255.83 | 4255.83 | 4255.83 | 4255.83 | 4255.83 | 4255.83 | 4255.83 | 4255.83 | 4255.83 | 4255.83 | 4255.83 | 51069.96 | -12039.96 | -23.58%
Frais de mission assistant technique Sud Kivu | 3531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3531 | 0 | 0 | 2050 | 1481 | 564 | 917 | 820 | 564 | 0 | 0 | 528 | 0 | 528 | 0 | 0 | 528 | 0 | 563 | 3531 | -2614 | -74.03%
Frais de mission assistant technique Ituri | 3531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3531 | 0 | 3138 | 0 | 393 | 1500 | -1107 | 0 | 0 | 546 | 1500 | 0 | 546 | 0 | 0 | 0 | 0 | 939 | 0 | 3531 | -4638 | -131.4%
Frais de mission assistant technique Kinshasa | 3531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3531 | 0 | 0 | 0 | 3531 | 1415 | 2116 | 1415 | 0 | 1132 | 0 | 0 | 0 | 0 | 984 | 0 | 0 | 0 | 0 | 3531 | -1415 | -40.07%
Frais de mission assistant technique NK (Beni-Kitshanga) | 3531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3531 | 0 | 0 | 1410 | 2121 | 0 | 2121 | 846 | 0 | 0 | 0 | 707 | 0 | 707 | 0 | 564 | 0 | 707 | 0 | 3531 | -1410 | -39.93%
Frais de mission UAS en appui au FCS (M&E, Visite bailleurs, engagement Politique) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 2000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 30000 | -30000
Sous total Assitant technique ( B3+B4+B5+B6+B7+B8) | 65194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65194 | 1840 | 6538 | 6860 | 49956 | 6879 | 43077 | 7336.83 | 6819.83 | 7933.83 | 7755.83 | 8490.83 | 7801.83 | 8490.83 | 8239.83 | 7819.83 | 7783.83 | 8901.83 | 7818.83 | 95193.96 | -52116.96 | -79.94%
Ateliers des 3 Groupes de travail restreints en Ituri, SK et NK (3X/an) | 15245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15245 | 0 | 0 | 6327 | 8918 | 0 | 8918 | 0 | 0 | 5027 | 0 | 5027 | 0 | 5027 | 0 | 0 | 5027 | 0 | 5027 | 25135 | -16217 | -106.4%
Frais de facilitation pour les membres des Groupes restreints Ituri, SK et NK | 43200 | 0 | 0 | 5466.11 | 0 | 1379 | 6277.25 | 3130 | 4528 | 0 | 22419.64 | 0 | 0 | 7390.9 | 15028.74 | 4500 | 10528.74 | 0 | 0 | 4500 | 2000 | 3000 | 2000 | 3000 | 0 | 2000 | 3000 | 2000 | 3000 | 24500 | -13971.26 | -32.34%
Sous total Groupe engagement politique et frais de facilitation (B10+B111) | 58445 | 0 | 0 | 5466.11 | 0 | 1379 | 6277.25 | 3130 | 4528 | 0 | 37664.64 | 0 | 0 | 13717.9 | 23946.74 | 4500 | 19446.74 | 0 | 0 | 9527 | 2000 | 8027 | 2000 | 8027 | 0 | 2000 | 8027 | 2000 | 8027 | 49635 | -30188.26 | -51.65%
Sous-total OS1 | 123639 | 0 | 0 | 5466.11 | 0 | 1379 | 6277.25 | 3130 | 4528 | 0 | 102858.64 | 1840 | 6538 | 20577.9 | 73902.74 | 11379 | 62523.74 | 7336.83 | 6819.83 | 17460.83 | 9755.83 | 16517.83 | 9801.83 | 16517.83 | 8239.83 | 9819.83 | 15810.83 | 10901.83 | 15845.83 | 144828.96 | -82305.22 | -66.57% | 82305.22
Objectif spécifique 2 | [30 empty] | 0 |  |  | 0
Campagnes d'info communautaires annuelles (information/mobilisation) | 9000 | 0 | 0 | 0 | 0 | 596 | 596 | 0 | 0 | 596 | 7212 | 0 | 0 | 0 | 7212 | 0 | 7212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | -2788 | -30.98%
Frais forfaitaire production de matériel de communication | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 1900 | 0 | 0 | 0 | 1900 | 0 | 1900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400 | -1500 | -50%
Prise en charge STAREC: mission "communication" (collecte et production) | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307.5 | 3442.5 | 0 | 0 | 787.5 | 2655 | 528.75 | 2126.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4126.25 | -2000 | -53.33%
Forfait formation STAREC en communication stratégique | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 0 | 0 | 0 | 1250 | 0 | 1250 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | -1250 | -100%
Sous-total OS2 (B15+B16+B17+B18) | 17000 | 0 | 0 | 0 | 0 | 596 | 596 | 0 | 0 | 2003.5 | 13804.5 | 0 | 0 | 787.5 | 13017 | 528.75 | 12488.25 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20026.25 | -7538 | -44.34% | 7538
Objectif spécifique 3 | [30 empty] | 0 |  |  | 0
Prise en charge STAREC: mission de suivi sur le terrain | 71500 | 0 | 0 | 4830.06 | 5830.06 | 3830.06 | 5830.06 | 5830.06 | 5830.03 | 3000 | 36519.67 | 0 | 246 | 8797.85 | 27475.82 | 4790 | 22685.82 | 0 | 7807.6 | 0 | 6631.6 | 10665.6 | 5701,60 | 5403.6 | 2701.6 | 5716 | 6951 | 6840 | 2858 | 55575 | -32889.18 | -46%
Formation des équipes du STAREC (province et national) en gestion projets | 12000 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | -50000 | -416.7% |  | 0
Couts de support operationnel STAREC (telephone + internet pour 5 bureaux) | 9505 | 0 | 0 | 1357.86 | 1357.86 | 1357.86 | 1357.86 | 1357.86 | 1357.86 | 1357.84 | 1.819e-12 | 0 | 0 | 0 | 0 | 0 | 0 | 792.08 | 792.08 | 792.08 | 792.08 | 792.08 | 792.08 | 792.08 | 792.08 | 792.08 | 792.08 | 792.08 | 792.08 | 9504.96 | -9504.96 | -100% |  | 0
Sous-total OS3 (B21+B22+B23) | 93005 | 0 | 12000 | 6187.92 | 7187.92 | 5187.92 | 7187.92 | 7187.92 | 7187.89 | 4357.84 | 36519.67 | 0 | 246 | 8797.85 | 27475.82 | 4790 | 22685.82 | 792.08 | 8599.68 | 792.08 | 7423.68 | 11457.68 | 792.08 | 6195.68 | 3493.68 | 6508.08 | 7743.08 | 7632.08 | 3650.08 | 115079.96 | -92394.14 | -99.34% | 92394.14
TOTAL GENERAL (B13+B19+B24) | 233644 |  | 12000 | 6187.92 | 7187.92 | 7162.92 | 14061.17 | 10317.92 | 11715.89 | 6361.34 | 153182.81 | 1840 | 6784 | 30163.25 | 114395.56 | 16697.75 | 97697.81 | 8128.91 | 17919.51 | 18252.91 | 17179.51 | 27975.51 | 10593.91 | 22713.51 | 11733.51 | 16327.91 | 23553.91 | 18533.91 | 19495.91 | 279935.17 | -182237.36 | -78% | 182237.36
Cout GMS 7% de B25 | 16355.08 | 0 | 840 | 433.1544 | 503.1544 | 501.4044 | 984.2819 | 722.2544 | 820.1123 | 445.2938 | 10851.63 |  |  |  | 10851.63 |  | 10851.63 | [12 empty] | 23608.2452 | -12756.6152 | -78% | 12756.6152
Total | 249999.08 | 0 | 12840 | 6621.0744 | 7691.0744 | 7664.3244 | 15045.4519 | 11040.1744 | 12536.0023 | 6806.6338 | 164034.44 | 1840 | 6784 | 30163.25 | 125247.19 | 16697.75 | 108549.44 | 8128.91 | 17919.51 | 18252.91 | 17179.51 | 27975.51 | 10593.91 | 22713.51 | 11733.51 | 16327.91 | 23553.91 | 18533.91 | 19495.91 | 303543.4152 | -194993.9752 | -78% | 194993.9752
279935.17
19595.4619
Note on O5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mission Djugu conflict analysis Aurelien+Famba
Note on B8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ligne budgetaire additionnelle pour assurer les descentes terrain de la SSU que le budget MONUSCO ne peut couvrir et liees directment au management du FCS
Note on B15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Change to: Campagne d'information communautaires (information/mobilisation)
Note on AF15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: les campagnes d'information communautaires seront plannifiees dans le temps une fois le budget aprouve
Note on AG15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If the FRPI process goes as planned, we will need these funds to assure PTS can accompany the process (as in go to the field and sensitize where needed and possibly get key messages diffused on community radios).
Note on B16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: change to: Frais forfaitaire production de matériel de communication et de visibilite
Note on AF16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: L'utilisation du budget sera determine lors de l'atelier de Juin avec tous les pints focaux communication et depnese dans l'annee selon cette decision collective.
Note on AG16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To print ISSSS anual report and get additional visibility items for ISSSS
Note on B17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: change to: Prise en charge STAREC: mission "communication"
Note on P17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7 nights Bunia Gama support Comms focal point in Bunia on communiaction plan for futur FRPI DDR process
Note on R17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Jackson 5 nights Kitshanga (M&E visit/press visit)
Note on AG17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For STAREC focal points in all provinces to go on all the monitoring missions to document.
Note on B18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: change to: forfait atelier en communication strategique
Note on U18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Atelier de communication avec tous els poitns focaux communication du STAREC plannifie initialement en avril mais decale a Juin faute de place sur vol MONUSCO. budget double par rapport a celui planifie en 2018-2019 pour assurer 2 jours datelier au lieu de 1 juge trop court.
Note on AG18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Additonal funds required so the event can be 2 days long and have the option to hold it in Kinshasa.
Note on B22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Organisation de deux retraites STAREC – UAS avant fin 2019 : Mise au point sur la conduite des activités de stabilisation par le tandem STAREC-UAS. Debut 2020 : Partage de la vision des nouvelles autorités sur la STABILISATION et orientations.
Note on AG22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2 retraites STAREC-UAS

## Synthese
Intitulé | Budget approuve 2018-2019 | Budget consomme 2018-2019 | Solde au 30/04/2019 | Budget plannifie Mai 2019-2020 | Extension Budgetaire demandee 2019-2020 | Budget Total 2018-2020
Objectif spécifique 1
Sous total Assitant technique | 65194 | 22117 | 43077 | 95193.96 | 52116.96 | 117310.96
Sous total Groupe engagement politique et frais de facilitation | 58445 | 38998.26 | 19446.74 | 49635 | 30188.26 | 88633.26
Sous-total OS1 (A3+A4) | 123639 | 61115.26 | 62523.74 | 144828.96 | 82305.22 | 205944.22
Objectif spécifique 2
Sous-total OS2 | 17000 | 4511.75 | 12488.25 | 20026.25 | 7538 | 24538
Objectif spécifique 3
Sous-total OS3 | 93005 | 70319.18 | 22685.82 | 115079.96 | 92394.14 | 185399.14
TOTAL GENERAL (A5+A7+A9) | 233644 | 135946.19 | 97697.81 | 279935.17 | 182237.36 | 415881.36
Cout GMS 7% | 16355.08 | 5503.45 | 10851.63 | 23608.2452 | 12756.6152 | 29111.6952 | Verification: | 29111.6952
Total | 249999.08 | 141449.64 | 108549.44 | 303543.4152 | 194993.9752 | 444993.0552 | Verification: | 444993.0552

## budget recapitulatif
Intitulé | Budget approuve 2018-2019 | Solde au 30/04/2019 | Budget total May 2019 - April 2020 | Requet des fonds additionnels | % | categorie de depense
Objectif spécifique 1
Salaire Assistant technique national | 51070 | 39030 | 51069.96 | -12039.96 | -24% | 1. Personnel et autres employés
Frais de mission assistant technique Sud Kivu | 3531 | 917 | 3531 | -2614 | -74% | 5. Frais de déplacement
Frais de mission assistant technique Ituri | 3531 | -1107 | 3531 | -4638 | -131% | 5. Frais de déplacement
Frais de mission assistant technique Kinshasa | 3531 | 2116 | 3531 | -1415 | -40% | 5. Frais de déplacement
Frais de mission assistant technique NK (Beni-Kitshanga) | 3531 | 2121 | 3531 | -1410 | -40% | 5. Frais de déplacement
Frais de mission UAS en appui au FCS (M&E, Visite bailleurs, engagement Politique) | 0 | 0 | 30000 | -30000 |  | 5. Frais de déplacement
Sous total Assitant technique ( B3+B4+B5+B6+B7+B8) | 65194 | 43077 | 95193.96 | -52116.96 | -80%
Ateliers des 3 Groupes de travail restreints en Ituri, SK et NK (3X/an) | 15245 | 8918 | 25135 | -16217 | -106% | 5. Frais de déplacement
Frais de facilitation pour les membres des Groupes restreints Ituri, SK et NK | 43200 | 10528.74 | 24500 | -13971.26 | -32% | 5. Frais de déplacement
Sous total Groupe engagement politique et frais de facilitation (B10+B111) | 58445 | 19446.74 | 49635 | -30188.26 | -52%
Sous-total OS1 | 123639 | 62523.74 | 144828.96 | -82305.22 | -67%
Objectif spécifique 2 |  |  |  | -
Campagnes d'info communautaires annuelles (information/mobilisation) | 9000 | 7212 | 10000 | -2788 | -31% | 2. Fournitures, produits de base, matériels
Frais forfaitaire production de matériel de communication | 3000 | 1900 | 3400 | -1500 | -50% | 2. Fournitures, produits de base, matériels
Prise en charge STAREC: mission "communication" (collecte et production) | 3750 | 2126.25 | 4126.25 | -2000 | -53% | 5. Frais de déplacement
Forfait formation STAREC en communication stratégique | 1250 | 1250 | 2500 | -1250 | -100% | 5. Frais de déplacement
Sous-total OS2 (B15+B16+B17+B18) | 17000 | 12488.25 | 20026.25 | -7538 | -44%
Objectif spécifique 3 |  |  |  | -
Prise en charge STAREC: mission de suivi sur le terrain | 71500 | 22685.82 | 55575 | -32889 | -46% | 5. Frais de déplacement
Formation des équipes du STAREC (province et national) en gestion projets | 12000 | 0 | 50000 | -50000 | -417% | 5. Frais de déplacement
Couts de support operationnel STAREC (telephone + internet pour 5 bureaux) | 9505 | 0 | 9504.96 | -9505 | -100% | 7. Frais généraux de fonctionnement et autres coûts directs
Sous-total OS3 (B21+B22+B23) | 93005 | 22685.82 | 115079.96 | -92394 | -99%
TOTAL GENERAL (B13+B19+B24) | 233644 | 97697.81 | 279935.17 | -182237 | -78%
Cout GMS 7% de B25 | 16355.08 | 10851.63 | 23608.2452 | -12757 | -78% | 8. Coûts indirects*
Total | 249999.08 | 108549.44 | 303543.4152 | -194993.98 | -78%
Catégories de dépense | total | pourcentage
1. Personnel et autres employés | 51069.96 | 16.82%
2. Fournitures, produits de base, matériels | 13400 | 4.415%
3. Équipement, véhicules et mobilier (compte tenu de la dépréciation)
4. Services contractuels
5. Frais de déplacement | 205960.25 | 67.85%
6. Transferts et subventions aux homologues
7. Frais généraux de fonctionnement et autres coûts directs | 9504.96 | 3.131%
Sous-total | 279935.17 | 92.22%
8. Coûts indirects* | 23608.2452 | 7.778%
TOTAL | 303543.4152
Note on A8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ligne budgetaire additionnelle pour assurer les descentes terrain de la SSU que le budget MONUSCO ne peut couvrir et liees directment au management du FCS
Note on A15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Change to: Campagne d'information communautaires (information/mobilisation)
Note on A16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: change to: Frais forfaitaire production de matériel de communication et de visibilite
Note on A17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: change to: Prise en charge STAREC: mission "communication"
Note on A18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: change to: forfait atelier en communication strategique
Note on A22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Organisation de deux retraites STAREC – UAS avant fin 2019 : Mise au point sur la conduite des activités de stabilisation par le tandem STAREC-UAS. Debut 2020 : Partage de la vision des nouvelles autorités sur la STABILISATION et orientations.