## Sheet1
Annex D - PBF project budget
Note: If this is a budget revision, insert extra columns to show budget changes.
Table 1 - PBF project budget by Outcome, output and activity
Outcome/ Output number | Outcome/ output/ activity formulation: | Budget by recipient organization in USD - Please add a new column for each recipient organization | Percent of budget for each output reserved for direct action on gender eqaulity (if any): | Expense by recipient organization in USD - Please add a new column for each recipient organization | Level of expenditure/commitment in % to date | Any remarks (e.g. on types of inputs provided or budget justification, for example if high TA or travel costs)
OUTCOME 1:
Output 1.1: | Increased Women's knowledge and capacity to demand respect of their rights, engage in effective advocacy and community conflict mediation in the management of disputes around the use of natural resources and land in the 23 selected communities. | 126225 | 100% | 127921.25 | 101.3% | Budget was made for 1 training, but there was a need for a second training
Activity 1.1.1: | Develop and Print Training Curriculum | 4500 |  | 1923 | 42.73%
Activity 1.1.2: | Conducts Training of Peer Enumerators | 9516 |  | 21267 | 223.5%
Activity 1.1.3: | Conduct Trainings to build capacity of women and create awareness, confidence and leadership. | 54709 |  | 46736.75 | 85.43%
Activity 1.1.4: | Build Women Group's ability to sustain their peace building activities in line with the exit strategy | 57500 |  | 57994.5 | 100.9%
Output 1.2: | Established Concession Community Women Development Structures are linked to stakeholders and engage in dialogues to negotiate issues around natural resource management including land use in the 23 target communities. | 2300 | 100% | 2300 | 100%
Activity 1.2.1: | Mobilize and Identify and form Women into Community Development Structures responsible for PB around Concessions | 2300 |  | 2300 | 100%
Output 1.3: | Support and advisory services as well as Conflict Mediation Services are provided for the Concession Community Development Structures as well as the Concessions. | 47745 | 100% | 67315 | 141% | Cost for Community and County level Supervision became necessary, County level was not originally budgeted for
Activity 1.3.1: | Provide continual support and advisory services for these newly formed “Concession Community Women Development Structures” as well as other existing structures within the concession communities | 42750 |  | 63300 | 148.1% | Cost for County level Supervision became necessary, it was not originally budgeted for
Activity 1.3.2: | Establish ICT citizen feedback mechanisms to help to alert stakeholders and create a knowledge sharing network. | 1495 |  | 1240 | 82.94%
Activity 1.3.3: | Media coverage; (Electronics, Print, Communications, Webpage, Social Media) | 3500 |  | 2775 | 79.29%
Output 1.4: | Women groups carry out effective advocacy, sensitization and awareness raising at community level and their Voices are heard on issues around Natural Resources in the 23 target communities | 45330 | 100% | 22380 | 49.37%
Activity 1.4.1: | Plan and Conduct Dialogues sessions with Community Leadership Structures, the Concessions and the County Leadership Structures and relevant duty bearers | 27080 |  | 9540 | 35.23%
Activity 1.4.2: | Plan and Conduct Dialogues sessions at National Level engaging all Concession Stakeholders and relevant duty bearers | 18250 |  | 12840 | 70.36%
TOTAL $ FOR OUTCOME 1: |  | 221600 | 100% | 219916.25 | 99.24%
Other Costs |  |  |  | 208174.18
Project personnel costs if not included in activities above | Project personnel costs if not included in activities above | 68750 |  | 60909.18 | 88.6%
Project operational costs if not included in activities above | Project Visibility | 9375 |  | 9030 | 96.32%
| Equipment, Vehicles and Furniture | 36000 |  | 44795 | 124.4% | Cost for County level Supervisors required 5 Bikes for County Supervisors that was not originally budgeted for
Project M&E budget | Coordinate, Supervise and Monitor all activities in the communities. | 60240 |  | 61608 | 102.3%
| Conduct Baseline Surveys | 12000 |  | 13098 | 109.1%
| Conduct midline qualitative assessments to measure outcomes of the peacebuilding project as well as be able to document lessons learnt of program to determine trend and see if there needs for changes in programming | 1000 |  | 1200 | 120%
| Conduct Endline Surveys | 12000 |  | 11834 | 98.62%
| Conduct Project Financial Audit | 3000 |  | 2000 | 66.67%
| Conduct Final Evaluation | 4500 |  | 3700 | 82.22%
SUB-TOTAL PROJECT BUDGET: |  | 428465 | 100% | 428090.43 | 99.91%
Indirect support costs (5%): |  | 21423.25 |  | 21711.3 | 101.3%
TOTAL PROJECT BUDGET: |  | 449888.25 | 100% | 449801.73 | 99.98%

## Sheet2
Table 2 - PBF project budget by UN cost category
Note: If this is a budget revision, insert extra columns to show budget changes.
CATEGORIES | Amount Recipient Agency - EDUCARE | [6 empty] | Comments
| Tranche 1 (50%) | Tranche 2 (40%) | Tranche 3 (10%) | Project Total | Total Expenses | Balance | Delivery (%)
1. Staff and other personnel | 34375 | 27500 | 6875 | 68750 | 60909.18 | 7840.82 | 88.6%
2. Supplies, Commodities, Materials | 9789.5 | 7831.6 | 1957.9 | 19579 | 14456.75 | 5122.25 | 73.84%
3. Equipment, Vehicles, and Furniture (including Depreciation) | 18000 | 14400 | 3600 | 36000 | 44795 | -8795 | 124.4% | Cost for County level Supervisors required 5 Bikes for County Supervisors that was not originally budgeted for
4. Contractual services | 26000 | 20800 | 5200 | 52000 | 48407 | 3593 | 93.09%
5.Travel | 31370 | 25096 | 6274 | 62740 | 61608 | 1132 | 98.2%
6. Transfers and Grants to Counterparts | 0 | 0 | 0 | 0 | 0 | 0 | 100%
7. General Operating and other Direct Costs | 94698 | 75758.4 | 18939.6 | 189396 | 197914.5 | -8518.5 | 104.5%
Sub-Total Project Costs | 214232.5 | 171386 | 42846.5 | 428465 | 428090.43 | 374.57 | 99.91%
8. Indirect Support Costs (set at 5%) | 10711.625 | 8569.3 | 2142.325 | 21423.25 | 21711.3 | -288.05 | 101.3%
TOTAL | 224944.125 | 179955.3 | 44988.825 | 449888.25 | 449801.73 | 86.52 | 99.98%

## Sheet3 (hidden)
Outcome/ Output number | Output name | UN budget category (see table below for list of categories) | Output budget by RO | Budget | Any remarks (e.g. on types of inputs provided or budget justification)
Outcome 1: Communal Conflicts including disputes as a result on natural resource management are reduced thus removing obstacles to sustainable National Recovery within the 23 communities.
Output 1.1: | Increased Women's knowledge and capacity to demand respect of their rights, engage in effective advocacy and community conflict mediation in the management of disputes around the use of natural resources and land in the 23 selected communities. | Staff and other personnel | Direct Project and Support Staff | 17187.5
|  | Supplies, Commodities, Materials | Community Level Training Materials and Supplies | 4894.75
|  | Equipment, Vehicles, and Furniture (including Depreciation) | Project Vehicle for Project Coordination and Monitoring | 9000
|  | Contractual Services | Training and Meeting Venue Rentals | 11500
|  |  | Evaluation Surveys and Reporting (for all components) | 6250
|  |  | Legal Services Retainership (consultation services) | 750
|  |  | Curriculum Development, Testing and Printing for the Communities | 4500
|  |  | Capturing, documentation and publications of concrete achievements and success stories. | 1125
|  |  | Media coverage; (Electronics, Print, Communications, Webpage, Social Media) | 875
|  | Travel | Travel for mobilization, assessment, monitoring and mentoring in the counties | 15685
|  | General Operating and other Direct Costs | Community Engagement, Assessment and Mobilization in 23 Communities | 575
|  |  | Capacity Building of Women for Effective Engagement | 101516
|  |  | Facilitators/Animators (peer groups) Monthly Stipends | 7187.5
|  | Sub Total |  | 181045.75
Output 1.2: | Established Concession Community Women Development Structures are linked to stakeholders and engage in dialogues to negotiate issues around natural resource management including land use in the 23 target communities.B3 | Staff and other personnel | Direct Project and Support Staff | 17187.5
|  | Supplies, Commodities, Materials | Community Level Training Materials and Supplies | 4894.75
|  | Equipment, Vehicles, and Furniture (including Depreciation) | Project Vehicle for Project Coordination and Monitoring | 9000
|  | Contractual Services | Evaluation Surveys and Reporting (for all components) | 6250
|  |  | Legal Services Retainership (consultation services) | 750
|  |  | Capturing, documentation and publications of concrete achievements and success stories. | 1125
|  |  | Media coverage; (Electronics, Print, Communications, Webpage, Social Media) | 875
|  | Travel | Travel for mobilization, assessment, monitoring and mentoring in the counties | 15685
|  | General Operating and other Direct Costs | Community Engagement, Assessment and Mobilization in 23 Communities | 575
|  |  | Capacity Building of Women for Effective Engagement | 56830
|  |  | Facilitators/Animators (peer groups) Monthly Stipends | 7187.5
|  | Sub Total |  | 120359.75
Output 1.3: | Support and advisory services as well as Conflict Mediation Services are provided for the Concession Community Development Structures as well as the Concessions. | Staff and other personnel | Direct Project and Support Staff | 17187.5
|  | Supplies, Commodities, Materials | Community Level Training Materials and Supplies | 4894.75
|  | Equipment, Vehicles, and Furniture (including Depreciation) | Project Vehicle for Project Coordination and Monitoring | 9000
|  | Contractual Services | Evaluation Surveys and Reporting (for all components) | 6250
|  |  | Legal Services Retainership (consultation services) | 750
|  |  | Capturing, documentation and publications of concrete achievements and success stories. | 1125
|  |  | Media coverage; (Electronics, Print, Communications, Webpage, Social Media) | 875
|  | Travel | Travel for mobilization, assessment, monitoring and mentoring in the counties | 15685
|  | General Operating and other Direct Costs | Community Engagement, Assessment and Mobilization in 23 Communities | 575
|  |  | Facilitators/Animators (peer groups) Monthly Stipends | 7187.5
|  | Sub Total |  | 63529.75
Output 1.4: | Women groups carry out effective advocacy, sensitization and awareness raising at community level and their Voices are heard on issues around Natural Resources in the 23 target communities | Staff and other personnel | Direct Project and Support Staff | 17187.5
|  | Supplies, Commodities, Materials | Community Level Training Materials and Supplies | 4894.75
|  | Equipment, Vehicles, and Furniture (including Depreciation) | Project Vehicle for Project Coordination and Monitoring | 9000
|  | Contractual Services | Evaluation Surveys and Reporting (for all components) | 6250
|  |  | Legal Services Retainership (consultation services) | 750
|  |  | Capturing, documentation and publications of concrete achievements and success stories. | 1125
|  |  | Media coverage; (Electronics, Print, Communications, Webpage, Social Media) | 875
|  | Travel | Travel for mobilization, assessment, monitoring and mentoring in the counties | 15685
|  | General Operating and other Direct Costs | Community Engagement, Assessment and Mobilization in 23 Communities | 575
|  |  | Facilitators/Animators (peer groups) Monthly Stipends | 7187.5
|  | Sub Total |  | 63529.75
|  | Total Project Costs |  | 428465
|  | Indirect Support Costs |  | 21423.25
|  | TOTAL COST |  | 449888.25

## Sheet5 (hidden)
EDUCARE - PBF Project Budget
Women in Peacebuilding in 23 Communities
Location:
Implementation Period: | Budget | Total Expended to Date |  | Total Expended to Date
Description | Total (US$) | Total (US$) | ACTIVITY | Total (US$)
General Operating and other Direct Costs |  |  | Conduct Baseline Surveys | 13098
Curriculum Development, Testing and Printing for the Communities | 2000 | 1923 | Develop and Print Training Curriculum | 1923
Training of Trainers | 21274.5 | 21267 | Moblize and Identify and form Women into Community Development Structures responsible for PB around Concessions | 2300
Community Engagement, Assessment and Mobilization | 2300 | 2300 | Conducts Training of Peer Enumerators | 21267
Catering Services for 1150 Participants at the various trainings in all 5 counties | 28750 | 28750 | Conduct Trainings to build capacity of women and create awareness, confidence and leadership. | 32936.75
Program Costs; Sustenance and Transportation Allowance cost for 1150 Participants based on attendance | 57500 | 57994.5 | Plan and Conduct Dialogues sessions with Community Leadership Structures, the Concessions and the County Leadership Structures and relevant duty bearers | 9540
Engagement with Relevant Government Agencies and Concessions - Engagement Forum (Creating Spaces for linkages and engagement) | 10000 | 9540 | Conduct midline qualitative assessments to measure outcomes of the peacebuilding project as well as be able to document lessons learnt of program to determine trend and see if there needs for changes in programming | 1200
Engagement with all stakeholders - Engagement Forum (Creating Spaces for linkages and engagement) | 12800 | 12840 | Plan and Conduct Dialogues sessions at National Level engaging all Concession Stakeholders and relevant duty bearers | 12840
Community Women Groups Activities Support Cost; Transportation and Scratch Cards for Communication | 13800 | 11500 | Provide continual support and advisory services for these newly formed “Concession Community Women Development Structures” as well as other existing structures within the concession communities | 70675
County Level Supervision Team Monitoring and Support Cost; Transportation and Scratch Cards for Communication | 15000 | 13750 | Establish ICT citizen feedback mechanisms to help to alert stakeholders and create a knowledge sharing network. | 1240
Facilitators/Animators (peer groups) Monthly Stipends | 34500 | 31625 | Coordinate, Supervise and Monitor all activities in the communities. | 53468
Sub Total | 197924.5 | 191489.5 | Build Women Group's ability to sustain their peace building activities in line with the exit strategy | 57994.5
Supplies, Commodities, Materials |  |  | Project Visibility | 9030
Training Supplies at Community Level | 2800 | 3186.75 | Media coverage; (Electronics, Print, Communications, Webpage, Social Media) | 2475
Facilitator's Guides, Illustrative materials | 1200 | 1000 | Project personnel costs if not included in activities above | 49070
ID Cards | 145 | 140 | Project operational costs if not included in activities above | 44795
Visibility | 2875 | 2890 | Indirect support costs (5%): | 21033.99
Communication; Promotional Smart Phone (1 per Community) for Text Messages, and Complaint Hot Line | 900 | 1240 | Total | 404886.24
IE materials; Flyers, Banners, Tee Shirts, etc. | 6000 | 6000
Venue Maintenance; Brooms, Brushes, Buckets, Mops, Toiletries, etc. | 0 | 0
Sub Total | 13920 | 14456.75
Staff and other personnel
Executive Director (25% Working time) | 14400 | 11520
Program Manager - Idrisa Kamara | 9000 | 7200
Monitoring and Evaluation Officer - Albert Somah | 6750 | 5400
Finance Officer - Bosede Johnson | 9750 | 7800
Admin/Logistics Officer - Madea Moore | 5250 | 4600
Quality Monitors/Field Officers - 3 | 13303.5 | 10150
Driver (100% of working Time) - 1 Driver | 3000 | 2400
Sub Total | 61453.5 | 49070
Contractual services
Training and Meeting Venue Rentals | 13800 | 13800
Contractual Services; Evaluation Surveys and Reporting | 26132 | 14298
Capturing, documentation and publications of concrete achievements and success stories. | 3000 | 0
Media coverage; (Electronics, Print, Communications, Webpage, Social Media) | 2400 | 2475
Sub Total | 45332 | 30573
Equipment, Vehicles, and Furniture (including Depreciation)
Project Vehicle for Project Coordination and Monitoring (Vehicle - Pickup van purchased @ $30,400.00US) | 30400 | 30400
Project Motor Bikes for Project Coordination and Monitoring (5 Motorbikes for County Use purchased @ $10,000.00US) | 10000 | 10000
Project Equipment and Furniture for Project Support Team | 4395 | 4395
Sub Total | 44795 | 44795
Travel
Other Local Transportation Cost | 15400 | 15400
Project Vehicle for Project Coordination and Monitoring (Vehicle - Insurance for Pickup van) | 630 | 315
Project Vehicle for Project Coordination and Monitoring (Vehicle - Government Registration for Pickup van) | 400 | 200
Project Motor Bikes for Project Coordination and Monitoring (Insurance for 5 Motorbikes for County Use) | 900 | 450
Project Motor Bikes for Project Coordination and Monitoring (Registration for 5 Motorbikes for County Use) | 250 | 250
Gasoline (8 gal x 5 x 4 wks.) | 12000 | 6000
Maintenance of 1 vehicle | 5220 | 5935
DSA and Lodging (6 staff X 7 days trip per month in the counties) | 30240 | 24918
Subtotal: | 65040 | 53468
TOTAL PROJECT COST | 428465 | 383852.25
Administrative Cost @5% of Project Cost | 21423.25 | 21033.99
GRAND TOTAL PROJECT COST | 449888.25 | 404886.24