IRAQ UNDAF TRUST FUND

MPTF OFfice GENERIC finalprogramme NARRATIVE report

REPORTING PERIOD: from October 2013 to June 2015

| Programme Title & Project Number |  | Country, Locality(s), Priority Area(s) / Strategic Results |
| --- | --- | --- |
| Programme Title: Enhancing Transparent Participatory Governance and Human Rights Programme Number: 83653 MPTF Office Project Reference Number: P1-04 |  | Iraq, nationwide |
|  |  | UNDAF Priority Area Outcome: The Iraqi state has a more inclusive and participatory political process reflecting improved national dialogue. Priority 1: Improved governance, including protection of human rights. |
| Participating Organization(s) |  | Implementing Partners |
| UNDP |  | National counterparts (government, private, NGOs & others) and other International Organizations High Commission of Human Rights. The Iraqi Commission of Integrity. KRG Prime Minister's Office. Kurdistan Board of Supreme Audit. Baghdad University. |
| Programme/Project Cost (US$) |  | Programme Duration |
| Total approved budget as per project document: USD 3,091,526 MPTF /JP Contribution: by Agency (if applicable) |  |  | Overall Duration (months) 24 Months |  |
| Agency Contribution by Agency (if applicable) |  |  | Start Date 5 April 2012 |  |
| Government Contribution (if applicable) |  |  | Original End Date June 2014 |  |
| Total approved budget as per project document: USD 3,091,526 MPTF /JP Contribution: by Agency (if applicable) |  |  | Overall Duration (months) 24 Months |  |
| Agency Contribution by Agency (if applicable) |  |  |  |  |
| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| Assessment/Review - if applicable please attach Yes X No Date: Mid-Term Evaluation Report – if applicable please attach Yes X No Date: |  | Name: Nahid Hussein Title: Project Manager Participating Organization (Lead): UNDP- Iraq Email address: nahid.hussein@undp.org |

# LIST OF ACRONYMS

LIST OF KEY ACRONYMS

COR               Council of Representatives (Parliament)

CPA               Coalition Provisional Authority

CPAP             Country Programme Action Plan

CSOs             Civil Society Organisations

IBHR             Independent Board of Human Rights (based in Kurdistan)

IHCHR          Independent High Commission for Human Rights

KRBSA         Kurdistan Region Board of Supreme Audit

KRCI             Kurdistan Region Commission of Integrity

KRG              Kurdistan Regional Government

NACS           National Anti-Corruption Strategy

UNDAF        United Nations Development Assistance Framework

UPR              Universal Periodic Review (Human Rights monitoring tool)

# FINAL PROGRAMME REPORT

# EXECUTIVE SUMMARY

UNDP has provided under this initiative technical, policy and legal support to a variety of state and non-state actors in order to better safeguard and promote human rights, render governmental entities more transparent and accountable and promote the capacities of civil society to interact with relevant governmental counterparts as a check and balance on executive authority. It should be highlighted that the state or governmental actors that have benefitted from this project are mainly independent, oversight bodies, such as the Independent High Commission of Human Rights (IHCHR), the Independent Board of Human Rights in the Kurdistan Region (IBHR), the Kurdistan Region Board of Supreme Audit (K-RBSA), the Kurdistan Region Commission of Integrity (K-COI). It has also interacted with the Human Rights Committee of the Parliament and the Ministry for Women’s Affairs. The non-state actors have mainly been NGOs, certain parts of the independent media and academia with Baghdad University.

Also UNDP has focused on establishing the legal, policy and strategic frameworks for the beneficiary entities, whilst also providing some direct operational support for their better functioning. There has also been nationwide survey, information and awareness campaign work requiring strong coordination between all the various stakeholders around specific topics such as the human rights based Universal Periodic Review (UPR) and the National Anti-Corruption Awareness Campaign.

UNDP has developed an innovative grant model to support Iraqi CSOs (Civil Society organizations) with a two-fold approach combining grants and capacity development. The participatory and consultative approach to establishing this grant mechanism is a ground- breaking innovation for Iraq that has been appreciated by Iraqi counterparts as the first of its kind.

A total of 100 local CSOs has been engaged in the grant application process either as lead applicants or members of a CSO consortium. After a thorough and transparent selection process, 8 CSO consortia (with a total membership of 31 CSOs) has been selected to implement projects in three thematic areas (i) promotion of adequate service delivery, (ii) anti-corruption, (iii) human and civil rights. The combination of grants and capacity development that is benefiting 31 local CSOs has allowed them to effectively engage in citizen-led oversight mechanisms and taking actions to hold the government to account. At the same time, the CSOs have benefited from a comprehensive accompaniment mechanism that is addressing demand-based capacity issues. As a result, CSOs have gained credibility and professionalism and public authorities are increasingly accepting them as partners for positive change in Iraq. The project has developed trust-based partnerships with the CSO parliamentary Committee, the NGO Directorate, equivalent authorities at Kurdistan Regional level and the CSO community at large.

# Purpose

UNDAF: Priority 1 Improved Governance, including the protection of human rights. Priority Outcome 1.4 The Iraqi State has more efficient, accountable and participatory governance at national and sub-national levels. UNDP CPAP: Outcome 3 Strengthened regulatory frameworks, institutions and processes in place for accountable, transparent and participatory governance at national and local levels.

Output 1: The Iraq Human Rights Commission has enhanced capacity to execute its mandate. Output 2: Iraq has a national platform for an expanded human rights dialogue. Output 3: The Iraqi state is able to promote and undertake governance process in an accountable and transparent manner. Output 4: Civil society organisations have enhanced capacity to engage with parliament and relevant parliamentary committees on policy issues.

# Assessment of Programme Results

Narrative reporting on results:

## Promoting and protecting human rights

In 2013 the Independent High Commission for Human Rights (IHCHR) strengthened its capacity to execute its mandate by successfully undergoing a multi-stakeholder needs assessment out of which formed the basis for the development of a strategic plan, an action plan, as well as an organizational framework including terms of reference for key staff. This was essential for the efficient operating of the IHCHR which was supported by an administrative expert recruited by UNDP. With the support of the UNDP deployed Human Rights Expert, the IHCHR also saw its outreach capacity enhanced, its departments fully functioning and the daily work of the Commissioners better organized. A training plan for key IHCHR management staff was established relating to their core functions and a communication plan has been drafted approved, and implemented. The outreach of the IHCHR was also improved through the creation of a specific website.

In terms of its supervisory role on human rights abuses, 25 IHCHR core staff underwent training on investigating, monitoring and reporting human rights violations, the handling of complaints and the filing and documenting of human rights violation cases. This supervisory role was also improved at the regional level with the Kurdistan Region Independent Board of Human Rights (IBHR) benefitting from international expertise. This expertise assisted the IBHR in reviewing the law establishing the Board, guiding its new strategic plan and having key staff trained up on international human rights standards and the operating frameworks of national human rights institutions.

Finally, both the Federal and Kurdistan Human Rights Commissions were also provided guidance and expertise in handling the Universal Periodic Review (UPR). This included institution-wide training on UPR mechanisms and report writing which also managed to interface with 25 human rights based civil society organisations as part of the process.  These organizations were also trained in UPR processes and were supported in the establishment of a nation-wide human rights civil society network. Two welcome derivatives from this process were that CSOs had the opportunity to meet IHCHR and the IBHR in a formal platform and that the IHCHR and IBHR agreed to work on a common project for the very first time (on the UPR).

## Promoting accountability, transparency and anti-corruption

In 2012, the outcome was to combat corruption through the promotion of accountability, integrity and transparency at all levels of government including support for the establishment of a new KRG Commission of Integrity. Five senior level meetings were conducted in 2012 and resulted in two key decisions: to define requirements to establish a KRG Commission of Integrity and to initiate the discussion of who will do what within the Kurdistan Region. A comparative analysis was completed on KRG Commission of Integrity Law 3/2012 and two laws at the Federal level: Commission of Integrity Law 30/2011 and CPA 55/2004. Recommendations and ways forward were proposed including bi-laws, internal policies and structure. Full scale discussions have been planned regarding the establishment of a KRG Commission of Integrity with relevant institutions. Consultation and planning continued regarding the Kurdistan Board of Supreme Audit with a decision that the most closely aligned good practice was the National Audit Office of the UK with dialogue opening. The Anti-Corruption Campaign has materials in final development and plans in place for 96 sessions. Discussions initiated regarding Investigative Journalism with the University of Baghdad.

In 2013, In terms of accountability, transparency and anti-corruption, the results of this project do not stand alone but interface to the larger programme. This project made two outcome level gains during 2013. One effort from this project raised awareness on the National Anti-Corruption Strategy through a campaign within all fifteen Governorates outside of the Kurdistan Region. The campaign found a strong desire by those attending to participate and a strong interest from the press. One of the recommended results was the building of coalitions and networks to “work as a team to fight corruption”. Secondly, as a result of the work of this project and the ongoing partnership with the Kurdistan Region Prime Minister’s Office and the Kurdistan Parliament, a Kurdistan Commission of Integrity was formed as an oversight agency in line with the United Nations Convention against Corruption.

On an institutional level, significant gains were made during 2013 including; the establishment of a key integrity institutions in the autonomous region of Kurdistan, in-roads for direct work with the Parliamentary Committees responsible for oversight and accountability and increased civil society engagement on anti-corruption issues through a national anti-corruption campaign. UNDP also made a substantial contribution towards the operationalization of the Kurdistan Region Commission of Integrity in 2013. The Kurdistan Region Commission of Integrity was approved by KRG Law No.3 of 2011, though up until 2013 had not yet moved forward or had a commissioner appointed. In terms of the Kurdistan Region Supreme Board of Audit (KBSA), a medium to long term strategy for the development of the Kurdistan Region was developed in May 2013. The Strategy presents indicative activities to address the gaps identified under all the six components of the Needs Assessment and sets out a roadmap for the KBSA to transform into a modern effective state audit institution that ensures public sector transparency and accountability.

In this sector, UNDP was able to address significant legal shortfalls in the Kurdistan Region in terms of anti-corruption and accountability. An analytical review identified strengths and weakness of KRG Law No. 3 of 2011 compared to the corresponding Federal Law No. 30 of 2011 and CPA Order No. 55. This review assisted in: drafting amendments to address gaps in the current law; developing a draft by-law on the establishment of the Kurdistan Region Commission of Integrity, including roles, responsibilities and organogram; and providing instructions on the work related to illicit enrichment and regulation of investigative work.

As the consultant agency award for the investigative journalism curriculum went at risk during 4th Quarter 2013 since the Consultant Agency Board decided that their staff cannot provide training in Baghdad due to the deterioration in the security situation, and accordingly this activity could not move ahead until the security situation improves, this issue could not be resolved and resulted in re-advertisement in the 1st Quarter 2014. Following the advertisement placed by the project, a specialised consultancy firm in investigative journalism (CLIC consultants) was appointed through a normal procurement process. The CLIC consultants started by researching the needs of the Iraqi’s universities on academic level relevant to investigative journalism; similarly they assessed the professional requirement on the topic. It developed outlines on investigative journalism at academic level and professional level. These outlines were discussed with the universities and the Anti-Corruption Academy to insure that it fulfilled the requirements. Based on the agreed outlines, CLIC started developing two curricula;

  - Investigative journalism specific to the college of media – University of Baghdad and the Iraqi universities.

  - Technical curriculum to be used for existing reporters wanting to specialize in investigative journalism.

Draft curriculum on both “a” and “b” above were completed, consultations with the university of Baghdad and other universities on the contents took place, feedback received from the universities, discussed and final version finalized in 2015

To support MP’s and staff from targeted committees for effective follow up on cases of administrative and financial corruption, in 2014 procurement procedures were finalized. A specialised consultant was recruited to conduct a need assessment on the federal and Kurdistan Council of Representatives – the integrity committee and the legal committee. During this year, and in line with the United Nation Convention Against Corruption, asset recovery was discussed with CSOs and NGOs as a mean to raise awareness amongst the general public through a series of meeting with 16 different CSOs and NGOs from 14 different governorates a plan is getting developed to conduct awareness sessions to advocate and promote the role of CSOs and Asset recovery to minimize its impact on society. Also, an Initial meeting took place between the head of the (Federal and KRG) integrity Parliamentarian committee and the legal committee with the specialized consultant on the Parliamentarian issues for the UNDP. These meetings facilitated acquiring information on each of these committees pertaining to their mandate, legal frame work and operational procedures, additionally, in depth discussions on the challenges these committees are facing and the ways of improving their performance.

Analysis of all the information took place and a draft assessment of the current situation on each of these committees is underway. A final need assessment draft on each of the committees will be finalized in 2015 and will be presented to the committees after further discussions and review of the results

Continues technical support to the Kurdistan commission of Integrity (KCOI) was provided during this year to compliment the initial work done through this project. Such continues support included cross boarder financial investigations, asset recovery and proposal on improving the legislative contents of the Kurdistan Commission of Integrity.

- The capacity of the KRG’s Board of Supreme Audit enhanced with the Needs Assessment completed and a Medium to Long Term Strategy for development presented.

Need assessment was conducted on the Kurdistan Board of Supreme Audit following this a medium to long term strategy was developed and discussed with the Board of Supreme Audit and finally a comprehensive capacity building program was developed in consultation with the Board of Supreme Audit. During this period a president to the Board of Supreme Audit was appointed after the position was vacant for almost two years. This gives an indication that the strategy developed for the Board was accepted by the Kurdistan Region Government and provided indication of the KRG interest in implementing the proposed strategy and the proposed capacity building program

In 2015, UNDP provided support has been provided through technical advices from UNDP       to the Kurdistan Region Commission of Integrity,

- The curriculum on the two levels through a printing house that has been awarded the contract to print out 6500 copies of the curriculums to the Iraqi universities, The Iraqi universities will teach these curriculums from next semester.

        - Developing curriculum on investigative journalism specific to the college of media – University of Baghdad and other Iraqi universities.

        - Developing technical curriculum to be used for existing reporters wanting to specialize in investigative journalism.

        - Support the development of a curriculum on investigative journalism and Organization a workshop to approve training curriculum to conduct in 2015.

Based on above, consultations has been done and achieved:

- Training the Iraqi universities staff on delivering the topic of the Investigative Journalism curriculums that has been developed.

- Agreeing a (30) week teaching at the media colleges in the Iraqi universities.

- Support MP’s and staff from targeted committees for effective follow up on cases of administrative and financial corruption.

Board meeting took place on 17 June 2015, between UNDP –Iraq, Commission of Integrity of KRG and the Parliament of KRG in Erbil to insurance that the agreed outputs is provided. A requested by KRG Parliament to UNDP - Iraq for continuous provision of technical support even after the end of this project.

A request has been submitted to the procurement unit to conduct 68 workshops in 15 governorates inside Iraq. Based on the rules and the regulation in the procurement unit a company awarded the contract to conduct 68 workshops in 15 governorates inside Iraq and started conducting these workshops, 68 workshops have been completed, the company completed the implementation of these workshops in spite of the challenges that they are facing inside Iraq. The final report and the recommendation has been submitted for this campaign.

Promote the work with civil society by awareness-raising on corruption issues as a key element of the roll-out of the NACS. This builds on the previous anti-corruption campaign which was designed to contribute to the prevention of corruption across the whole of Iraq. Capitalize on the successes of the roll-out campaign by working with civil society.

regulation of investigative work.

## Heightened engagement of civil society in promoting human rights and accountability

The civil society dimension of this project cuts across both the human rights and the accountability, transparency and anti-corruption, or Outputs 1, 2 and 3. Engagement with NGOs has therefore happened directly through the human rights pillar of the project and through Output 4. Under the UPR process, ground-breaking engagement happened between specialized human rights NGOs (25 of them) that were trained alongside the IHCHR and IBHR in the process and that were supported to establish a wider network of NGOs that would be involved in the UPR process. The UPR therefore provided a unique opportunity for state and non-state actors to work together on a concrete process.

Linked to this activity, 6 consultations took place around Iraq with interested NGOs in order to develop the most appropriate strategy for establishing a Human Rights Advisory Board for the IHCHR. To this end, representatives of the Human Rights Commission, the Human Rights parliamentary Committee and the CSO parliamentary Committee attended half of the events. The outcome of the consultations is the establishment of the NGO Human Rights Advisory Board to be supporting the Parliamentary Human Rights Committee.

Narrative Project Outcomes

The UNDAF priority Outcome area addressed by this project is “Improved Governance, including the protection of human rights”. The more specific priority Outcome is “The Iraqi State has more efficient, accountable and participatory governance at national and sub-national levels”

Seen in this light, the project has a mixed picture of success in meeting these Outcomes. It is a mixed picture because, despite the ongoing political and security crisis since 2013, proved to be an almost insuperable obstacle to making a tangible impact on the daily lives of Iraqis.

When answering the question, “are human rights better protected and promoted than before this initiative started?” one can confidently say that all the institutional capacity building (IHCHR, IBHR, The CoR Committee on Human Rights, etc), advocacy and practical support provided by UNDP means that Iraq is equipped and core civil servants and experts sufficiently trained to ensure that this is the case. However, until the IHCHR is provided the proper leadership it requires, until all the different institutional actors involved in this area – including CSOs – are interacting in a meaningful manner, and until the IHCHR has sufficient sub-offices open, the impact of this project will not equal the significant inputs that have been mobilized on this front.

When answering the hypothetical question of whether the Iraqi state entities are more accountable and transparent than before this initiative started, one has to look carefully at both the institutional transformation as well as cultural and attitudinal shifts from citizens.

Regarding the notion of ‘participation’, much effort has been put into this initiative to get state (albeit mainly independent, autonomous oversight bodies) and non-state actors to work more closely together. The policy and institutional frameworks are in place for this interaction but it will take more time to get both sides to trust each other and not deal with each other as ‘opponents’. Civil Society is the key to greater citizen participation in all areas of the country’s governance and especially the protection of human rights and the promotion of transparency and accountability as well as fighting corruption. The UPR process has done much to get state authorities and civil society to work constructively together on human rights and the media and campaign work on anti-corruption has also demonstrated that more momentum can be achieved when state and non-state actors work hand in hand. However, in a country where the state authority was the object of fear (and understandably so) for so long and where civil society is a relatively new concept, the relationship between the two needs time to mature and bear fruit.

Narrative Project Outputs

Output 1: The Iraq Human Rights Commission has enhanced capacity to execute its mandate.

At the Federal level:

UNDP continued to advocate for promotion of Human Rights in Iraq through provision of direct support to the national and regional human rights institutions, support to the Council of Representatives Human Rights Committee and support to civil society. In doing so, comprehensive consultations and technical advisory support took place during the project. To ensure long term capacity building of and institutional development support to the Independent High Commission of Human Rights (IHCHR), UNDP; UNAMI Human Rights Office and Office of the High Commissioner for Human Rights Documentation and Training Centre for South West Asia and Arab Region conducted a needs assessment, led by the Director of the Centre. The mission resulted in clear and well defined immediate, medium and long-term support to assist the Board of Commissioners and core staff to effectively perform their duties as stipulated in Law 53/2008. UNDP provided the technical advisory support to the Commissioners to identify 14 thematic areas of work. It is worth mentioning that among the thematic areas are: women, minorities, children, prisoners and detainees.

As a direct result of the mission and based on the urgent and immediate needs, UNDP, provided managerial and technical support to the Board of Commissioners through a human rights expert. The expert assisted the development and the adoption of terms of reference of three different offices within the Commission, namely, the Terms of Reference for establishing and mandating the Baghdad Branch Office of the Commission, complaints, and the documentation offices of the Commission. To enhance the capacity of the core staff of the Commission, training courses were conducted targeting 25 core staff which focused on monitoring and reporting human rights violations, receiving complaints and initiating investigations on human rights violations, filing and documenting cases. This was heightening the functioning abilities of the Commission, its ability to respond more professionally to cases of human rights abuse brought before it. Moreover, in order to increase the outreach of the Independent High Commission of Human Rights (IHCHR), UNDP initiated the development of the Board of Commission website which was handed over during 2013 to the IT team at the IHCHR.  The website gives important information on the concept of human rights, the role of the IHCHR as well as guidance to citizens on how to report cases to it.

During the project, UNDP developed a regulatory framework to link the IHCHR and IBHR that established a strong coordination and cooperation between the two institutions in Iraq.

At the regional level:

UNDP facilitated a meeting between IHCHR and national human rights national institutions from Palestine, Morocco, and Qatar. This activity assisted the meaningful engagement of the Office of the IHCHR on a Regional level. This is considered as a preparatory step to assist the IHCHR to obtain the international accreditation as required. Similarly, and to ensure that all national human rights actors in Iraq have the capacity to engage with the IHCHR in promoting human rights in Iraq, UNDP continued to regularly consult with the Council of Representatives Human Rights Committee on the progress of the work of the Commission, and ensure that there is adequate capacity to follow up and provide oversight support to work of the Board of Commission.

Joint meetings took place between the Board of Commissioners and the Council of Representatives Human Rights Committee to follow up on the work and the achievements of the Office of the High Commissioner for Human Rights. As a result of this, recommendations have been made to facilitate the creation of strong linkages between the Board of Commissioners and Human Rights Civil Society. UNDP did this by recruiting a civil society expert to develop and establish a Civil Society Board with all Human Rights institutions at the legislation and executive levels. This Board enabled the IHCHR to fully engage with CSOs from all parts of Iraq; in turn, the relevant CSOs being able to voice the concerns of their communities. also it allows for the sharing of the CSO perspective and institutionalize the engagement of the IHCHR. Bearing in mind the importance of prompting Gender equality approach through the IHCHR, UNDP initiated discussions with the Board of Commissioners on the establishment of the Gender Coordination mechanism. This mechanism helped the IHCHR to tackle Gender related issues with the support of different actors, namely the Council of Representatives, CSOs and the Ministry of Women’s Affairs.

UNDP also supported the Council of Representative Human Rights Committee, where regular meetings were held to follow up on the implementation of the strategic action-plan of the Committee. As a result, the Parliamentary committee reviewed the IHCHR annual report and adopted it.

Through this project, UNDP was also committed to support the establishment of Human Rights Regional mechanism. UNDP carried out substantive and intensive consultations with the Independent Board for Human Rights (IBHR) in Kurdistan, including a review of the organisational structure of the IBHR in line with Law 4/2010 and Paris Principles. Additionally, UNDP supported the identification of priority areas of work by the newly established Independent Board for Human Rights in Kurdistan. During 2013, UNDP provided technical advisory support to the IBHR in Kurdistan to examine different experiences from Canada, South Africa and Palestine which enabled the IBHR Kurdistan members to inform and guide their vision and outline their statement. As result of this support, a vision and mission has been adopted by the IBHR members. One of the main recommendations from the workshop was the development of the strategic action-plan for the year 2014 outlining the roles and the responsibilities of the joint UNDP, UNAMI Human Rights Office and IBHR as well as the respective timeframes for achieving the strategy. Thereafter, the strategic action-plan was developed and adopted by the Board. As a result of this strategy, UNDP has intensified follow-up with KRG Ministry of Planning on the cost-sharing of this project which has been rewarded by the approval of KRG Vision 2020 funding facility of USD 1.7 million cost-sharing to support the capacity building and technical support of the IBHR in Kurdistan

Output 2: Iraq has a national platform for an expanded human rights dialogue.

Taking into account the importance of supporting meaningful engagement of the IHCHR with other national human rights actors in Iraq, and through support to the expanding human rights national dialogue, UNDP provided direct support to Council of Representatives Committee, IBHR in Kurdistan, and Civil Society Organisations. In that regard and under this specific output, UNDP support to the IHCHR aimed to enhance the capacity of the Commissioners and the core staff to effectively engage and consult with CSOs on the drafting of the Universal Periodical Review (UPR).

During the project UNDP and UNAMI Human Rights Office jointly organised two training courses, targeting members of the IHCHR, IBHR, and representatives of 25 civil society organisations nationwide.  Under this training, mechanisms of the UPR process were explained. Additionally, the representatives of civil society organizations agreed to create an internet-based network using social media for Iraqi non-governmental organizations working on the UPR as a platform to share reports, information, and inputs as well as to strengthen communication on relevant human rights trends and concerns in Iraq.

CSOs that participated in the workshop also acquired the knowledge of the procedures of the UPR. A wide network of NGO and CSOs from all parts of Iraq was established and a consensus reached between the IHCHR and the IBHR to present one UPR on the situation of Human Rights in Iraq. This action is considered to be a milestone of this project as rarely do Federal and Kurdistan Region based organisations get to cooperate so tangibly in this manner; and for these to then work with CSOs so effectively is also rarely seen in the country. UNDP provided direct support to Human Rights Civil Society Organisations, where small grant agreements were signed between UNDP and Civil Society Organizations. Six (6) CSOs have been selected to carry out different activities to promote women’s rights, status of prisoners, review the role of the IHCHR as a national human rights institution and freedom of expression. An amount of USD 15,000 for each CSO for the period of 6 months has been disbursed.

The above-mentioned efforts resulted in a series of workshops and trainings in Iraq and Kurdistan Region to promote human rights. Different topics and subjects have been discussed through trainings and conferences such as Status of prisoners, freedom of expression. These workshops and trainings directly contribute to promotion of human rights and expand the national dialogue for human rights to community level. Parallel to this, UNDP recruited a Civil Society expert to assist the establishment of the NGO Human Right Advisory Board.

UNDP facilitated the participation of Iraq in the HuriLab. HuriLab is an international social innovation initiative that is devoted to promoting human rights and access to justice. Iraq’s participation was supported by the UNDP Regional Office in Bratislava. UNDP Iraq invited young Iraqis to submit their proposals on the use of the digital tools to build web-based solutions to social and human rights related problems. Forty-two proposals were received from youth in Iraq. One idea was shared with seven UNDP Country Offices: Belarus, Bosnia and Herzegovina, Kyrgyzstan, Moldova, Montenegro and Ukraine. The Iraqi proposal won the competition. The project is focused on creating a platform that monitors and flags comments that misrepresent women in the local media.

Output 3: The Iraqi state is able to promote and undertake governance process in an accountable and transparent manner

- The Iraqi state is able to promote and undertake governance process in an accountable and transparent manner.

  - Support MPs and staff from targeted committees (i.e. the Integrity and Finance Committees) for effective follow up on cases of administrative and financial corruption.

  - Terms of reference developed to support the Parliament Integrity and Legal Committees related to financial and administrative issues.

Support the consultations and establishment of the KRG Commission of Integrity.

A comparative analysis on KRG Commission of Integrity Law 3/2012 and two laws at the Federal level: Commission of Integrity Law 30/2011 and CPA 55/2004 completed. Recommendations based on the identified strengths and weaknesses for the establishment of a KRG Commission of Integrity provided. Bi-laws, internal policies and a structure for the KRG Commission of Integrity developed and proposed to key

  - Provide a need assessment, capacity building recommendations to the KRG BSA.

Multiple meetings with the Prime Minister’s Office and the Kurdistan Board of Supreme Audit resulted in the commitment, conducted a needs assessment for Kurdistan Board of Supreme Audit and develop a framework. A working group is under formation and decision made that the international standard is that of the UK. needs assessment has been conducted with the National Audit Office (NAO) of the UK,

  - Support the development of a curriculum on investigative journalism.

Discussions initiated and are on-going with Baghdad University Media College to develop a curriculum and training on investigative journalism.

  - Plan and organise a workshop to approve training curriculum investigative journalism when review completed.

Review not yet complete as linked to action in 3.4

- Civil society organizations have enhanced capacity to engage with parliament and relevant parliamentary committees on policy issues.

  - Selection of teams and identification of partners for continued NACS campaigns.

  - Ways forward and multiple trainers identified including those who train the trainers.

  - Identify relevant materials to conduct training and awareness campaigns on NACS.

Output 4: Civil society organisations have enhanced capacity to engage with parliament and relevant parliamentary committees on policy issues.

An extensive consultation process led to the development of a set of CSO Grant Guidelines that integrate UNDP best practices as well as practical local context aspects. The innovative, participatory and open approach to the development of these guidelines has been appreciated both by the parliamentary CSO Committee and the CSO community. These guidelines are being tested through the UNDP project “Empowering CSOs in Iraq” that is being implemented in parallel to the project reported on herein and will set the ground for any future CSOs small grants.

The implementation of 6 NGO projects has been successfully completed, NGOs have received grants of USD15,000 and the Office of the High Commissioner for Human Rights (UNAMI) is kept informed in case specific technical guidance is required on sensitive issues. Below is a brief of the achievements by the 6 grantees:

  - HR1/ Bustan Association for Children Protection and Education

Combating women's self-immolation in KRG

Bustan Association for Child Protection and Education managed to target youth, men and stakeholders from 16 rural areas (30 Communities) in Sulymaniyah and Erbil to address the issue of women’s self-immolation in KRG. The organization used different tools such as focus groups, workshops and TV spots to generate debate about this important issue. In addition, to introduce different mechanisms to help women when they face social problem or women rights violation. The project helped the organization to establish good relationship with local communities, local authorities and other NGOs working on similar topics.

  - HR2/ Baghdad Women Association (BWA)

Raising awareness on violence against women in Sader city

Baghdad Women Association managed to highlight and generate community debate about violence against women in Al- Sader city, especially among men, tribal leaders and religious men. Addressing issues like early marriages, contract marriages outside the courts, Depriving girls of education…etc. About 160 male leaders have participated in the activities of this project to enhance their understanding of women rights. A set of recommendations has been developed with the participation of stakeholders. The organization managed to get the municipal council and other institutions involved in implementing the activities of the project, establishing promising partnership that would lead to further cooperation.

  - HR3/ NFDO

Special Needs Rights - Awareness Campaign

The project aims to raise awareness about the rights of people with special needs in Dhuk and Zakhow. The organization used different tools to reach more than 400 people (Special Needs, their families and service providers). The project highlighted the role of media in addressing such issues and led to the establishment good relation and starting cooperation with the Journalists Association and most of the media channels in Dhuk and Zakhow.

  - HR4/ PAO

Eye on Prisons

Through the activities of this project, the organization managed to collect information about 18 prisons located in 13 different governorates, and comparing this information to international standards. The organization established very good relationship with the Ministry of Justice in KRG among other governmental institutions to facilitate and guarantee access to prisons. On the other hand, the organization established relations with other organizations to conduct field visits to prisons in the rest of Iraq, which highlighted the importance of the topic and increased interest in carrying out such monitoring activities. A report with a set of observations and recommendations about prisons in Iraq has been prepared and published to provide a reference for future advocacy, awareness or monitoring projects and activities.

  - HR5/ Equality for Human Rights

Human Rights Defenders Network

This is project is the first of its kind in Al-Mothana governorate, which aims to establish a foundation for a Human Rights defenders network. About 60 participants (NGOs, media, activists, academics and college students) have been involved in a set of training workshops to enhance their knowledge and skills in Human Rights monitoring. The project highlighted the importance of Human Rights monitoring mechanisms among the target group and their communities. A report has been published about Human Rights situation in the governorate, based on the monitoring activities of the members of the network. Direct contact and cooperation with government institutions has been established such as the Ministry of Human Rights, the Human Rights High Commission and the Iraqi Parliament.

  - HR6/ Orphans Mother

The path to the Human Rights High Commission

The project aims to introduce practical mechanisms to report Human Rights violations to the Human Right High Commission. The organization managed to sign an MOU with the commission to allow direct contact and cooperation with the committee that is responsible for collecting the Human Rights complains and Human Rights violations. Boxes to collect HR complains have been placed in three government institutions including the Baghdad Governorate Council. This project contained different activities and tools to introduce and to raise awareness about the role of Human Right High Commission in Iraq in governmental and non-governmental institutions in Baghdad, Babil, Najaf and Dyala governorates.

After discussion with the Human Rights Commission, extensive consultations on the establishment of a NGO Human Rights advisory board were launched across the country. Representatives of the Human Rights Commission, the Human Rights Parliamentary Committee and the CSO parliamentary Committee attended half of the events. The NGO Human Rights Advisory Board officially launched at January 2015 to provide technical support to the Iraqi Human Rights institutions including Human Rights Parliamentary Committee, and Human Rights High Commission.

In terms of support to CSO and parliamentary committee engagement, a trust-based dialogue has been established with the parliamentary CSO Committee that has led to mutual consultations on various issues related to civil society affairs in Iraq and to high levels of support to the UNDP project.

Enhancing CSO Anti-corruption intervention capacities, the implementation of 11 NGO projects has been successfully completed on August 2014 after 5 months of implementation. 11 NGOs had received micro-grants (USD 5,000) to start their anti-corruption initiatives on 1 April 2014. The table below summarizes the micro-grants initiatives:

| Ref. | Name | Project Title | Geographic Coverage |
| --- | --- | --- | --- |
| AC1 | ALManahil Association for Women Development | The role of technology in improving governance and anti corruption education and awareness promotion | Basra |
| AC2 | Al-Tadhamun Iraqi League for Youth | Civil Observatory to monitor and evaluate the government's performance and to address administrative corruption in Anbar | Anbar |
| AC3 | Child Rights and Family Protection Association | promote integrity, transparency and accountability | Mosul |
| AC4 | Children and Woman Affairs Organization | To promote and strengthen measures to combat corruption in government institutions in Diwaniyah | Qadisiya |
| AC5 | Hannah Youth Organization | Corruption food scourge of society and everyone is responsible to detect fight and eliminate it | Baghdad |
| AC6 | Iraqi Civic Action Network | The role of the marginalized groups in fighting corruption | Babil |
| AC7 | Iraqi Civil Awareness Team | yes we can | Baghdad |
| AC8 | Negotiation & Strategic Studies Organization | Identify the sources and forms of corruption in real estate loans and how to address them | Erbil |
| AC9 | Shaaub for Democracy Culture Foundation | Promote community participation in the monitoring of local service sectors | Baghdad |
| AC10 | Um Al Yateem Foundation | CSOs alliance for accountability | Baghdad |
| AC11 | Wand Alkhair Human Organization | Promote proper behavior in public office and empowering civil society | Diyala |

Using the Programme Results Framework from the Project Document / AWPs - provide details of the achievement of indicators at both the output and outcome level in the table below. Where it has not been possible to collect data on indicators, clear explanation should be given explaining why.

|  | Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification |
| --- | --- | --- | --- |
| Outcome 1 The Iraqi state has more efficient, accountable and participatory governance at national and sub national levels Indicator: Baseline: Planned Target: |  |  |  |
| Output 1.1 The Iraq Human Rights Commission has enhanced capacity to execute its mandate Indicator 1.1.1 Regulatory framework of the Commission in place; Baseline: No regulatory framework in place Planned Target: Functioning Commission in place Indicator 1.1.2 Sub-national IHCHR Offices established at governorate level Baseline: 0 sub-national offices Planned Target: 4 sub-national offices Indicator 1.1.3 Number of Human Rights commissioners disaggregated by federal/KRG levels. Baseline: 0 (zero) in Baghdad, 0 (zero) in KRG Planned Target: 25 HR commissioners (central (14) and KRG (11)) Indicator 1.1.4 Number of core staff trained to execute their services effectively. Baseline: 0 staff Planned Target: 20 staff Indicator 1.1.5 %of those trained fully satisfied with the relevance, quality and usefulness of the training provided. Baseline: 0 % Planned Target: 80% | Draft Regulatory framework is developed and adopted by the Board of Commission | The IHCHR has an organizational structure, regulatory framework and strategic action plan. | Official endorsement letter from Council of Representatives’ |
|  | 1 office established in Baghdad as Main IHCHR Office. Office has been established in Baghdad |  | Field visits, IHCHR reports, UNDP monitoring reports |
|  | Target met | 5 roundtables have been organized in Basra, Amara, Najaf, Erbil and Baghdad to formalize the dialogue process through the establishment of the Human Rights Civil Society Advisory Board | IHCHR reports, UNDP monitoring reports |
|  | Target met. Total of 37 Human Rights commissioners, core staff, out of which are 10 technical staff from IBHR in KRG have been trained in different specialized areas 100% of trained staff are satisfied with the training |  | UNDP training reports |
| Output 1.2 Iraq has a national platform for an expanded human rights dialogue Indicator 1.2.1 IHCHR outreach strategy is drafted Baseline: no draft Planned Target: document draft Indicator 1.2.2 Number of IHCHR public information campaigns undertaken and disaggregated by federal/KRG level Baseline: Planned Target: 3 (three) public information campaigns at central level; 3 (three) at KRG level. Indicator 1.2.3 Number of Human Rights CSOs engaged in a formal national dialogue on human rights Baseline: 18 Planned Target: 43 Indicator 1.2.4 Number of staff of the COR Human Rights Committee trained on Human Rights Baseline: 0 Planned Target: 18 Indicator 1.2.5 COR Human Rights strategic framework and action plan developed Baseline: No Planned Target: Yes Indicator 1.2.6 Percentage of CSOs engaged in the national dialogue process satisfied with the level and quality of engagement with regards to human rights Baseline: 0 Planned Target: 80% | In progress, Draft outreached strategy is shared with Board of Commission for discussion. Civil Society Expert is recruited to develop ToRs for engagement with CSOs |  | IHCHR strategy document |
|  | Not yet initiated. This will be achieved upon the development of the outreach strategy. 5 workshops organized in different Governorates to promote the work of the IHCHR |  | NDP quarterly fiches and IHCHR reports |
|  | Target met. CSOs Human Rights Advisory Board established with membership of 19 members in addition to 3 representing Iraqi Minorities. |  | National dialogue minutes from UNDP |
|  | 24 members of the COR HRC trained on Human Rights Strategic Planning |  | Trainings report |
|  | Strategic action plan developed and adopted. This target indicator has been achieved |  | Strategic framework and action plan documents |
|  | Target met. |  | National dialogue evaluation forms |
| Output 1.3 The Iraqi state is able to promote and undertake governance processes in an accountable and transparent manner Indicator 1.3.1 Number of trainers deployed in the CoR Committees and in the Governorates Baseline: 0 Planned Target: 8 Indicator 1.3.2 Consultations to establish framework on KR Commission of Integrity Baseline: None Planned Target: Framework for establishment approved Indicator 1.3.3 Investigate journalism curriculum developed Baseline: No curriculum Planned Target: Curriculum developed | Sixteen trainers deployed | Surpassed target of eight | Training records and those who conducted the 96 workshops. |
|  | Target surpassed. Five high level consultations took place in 2012 regarding the framework on the KR Commission of Integrity; The Kurdistan Parliament appointed a Kurdistan Commissioner of Integrity in May 2013; Reached agreement on the structure, legal and operational framework of the Cof I; | Surpassed schedule and may require variance as UNDP has received a letter from the Kurdistan Commission of Integrity requesting support | Consultation meeting minutes |
|  | Immediate needs identified in March 2013 in improving skills of journalists in investigating and reporting corruption. Conducted needs assessments. Developed medium to long-term capacity development strategy. A consultant agency award initiated but collapsed due to increase of insecurity in Iraq | Ahead of schedule at beginning of the year but delayed due to the consultant agency board decision that their staff cannot provide training in Baghdad due to the deterioration of the security situation. Variance action taken and new consultant agency trying to be identified. | Curriculum document |
| Output 1.4 CSOs have enhanced capacity to engage with parliament and relevant parliamentary committees on policy Indicator 1.4.1 Number of informal citizens’ oversight mechanisms at governorate level reflecting diverse CSO stakeholder influence and participation. Baseline: 4 Planned Target: 10 Indicator 1.4.2 Percentage of CSOs trained fully satisfied with quality of training provided in terms of relevance and usefulness an quality of training provided. Baseline: 0 Planned Target: 80% | 25 NGOs trained in the UPR process 6 NGOs given grants and training on specific human rights based campaigns 11NGOs given grants and training on specific Anti-corruption initiatives |  | Workshop reports |
|  | 100% |  | UNDP training evaluation forms |

iii) Evaluations, delays in implementation, challenges, lessons learned & best practices:

In general, the project was going well towards the expected results considering the constraints of the implementation context in Iraq. However, delays in implementation have taken place due to the complex combination of security, political and social challenges that Iraq is facing. This has created delays in securing certain project resources locally (particularly technical expertise), obtaining decisions or participation of local counterparts, logistical arrangements for meetings, activities and events. In addition, the delays of the formation of the government have created a disruption both in terms of security, availability of national counterparts and their decision making.

In detail and regarding the Human Rights component this project, the highly politicized environment and the very tense security situation in Iraq constituted a major challenge that has direct impacted on the election of the leadership of the IHCHR. The absence of the necessary leadership within the Board of the Human Rights Commission has negatively impacted the decision making process. All Commissioners have different perspectives mainly influenced by the political blocs which has prevented the IHCHR from adopting a unified approach to human rights situation in the country. This created significant delay in the IHCHR in directly contributing to Iraqi human rights public policy and to some extend affected public confidence in the institution. The positive side of the work of the commission is the fact that, based on the IHCHR report on ISIS human rights violations, the Security Council has agreed to field a fact finding mission to investigate human rights violations committed by ISIS against the people of Iraq.

The formation of new government and the election of new Parliament Members in the Council of Representatives provides a good opportunity for true constitutional and political reform which will directly contribute to the political pressure applied on the IHCHR. The new leadership in the Iraqi Parliament is committed to human rights, peace and stability, therefore it is expected that more support will be provided to the IHCHR, especially with the selection of the new Board, which is supposed to take place in February 2016.

At the Kurdistan regional level the challenge has been to review the Law 4/2010 and ensure that the mandate and the structure of the IBHR is in line with the international standards. Creating linkages with the IHCHR is crucial and a legal framework organizing the relationship between the two institutions will assist the provision of a unified country report as well as clarify the geographical jurisdiction of each institution.

The humanitarian crisis and the influx of IDPs and refugees in the KR-I region and some parts of Iraq remains a huge challenge. Donors, Government institutions and some of UN agencies are redirecting their resources to respond the IDPs and refugees needs. Thus, at policy level the priority of the Government is now on peace and stability in Iraq. To mitigate this challenge, UNDP continues to advocate to the new Government to meet its commitment towards the international development agenda, to promote social cohesion and ensure protection of human rights as a key for stopping the ISIS aggression on ground.

Concerning transparency, accountability and anti-corruption, one of the key lessons learned is that an integrated approach is fundamental to tackling this sector. Public transparency and accountability are corner stones of good governance. Strengthening these aspects requires not only building the capacity of state institutions to promote rule of law but also ensuring greater engagement of non-state actors such as civil society and media in holding state institutions to account. Towards this end and given the different incentives of various stakeholders, different context specific, yet integrated, approaches need to be adopted.

Also required is flexible but consistent programming support. The security and political context in Iraq makes is difficult for prioritizing activities and setting timeframes for delivery of results. Therefore, all programme support has to be flexible but at the same time, programme support should be consistent and sustained to ensure sustainability of results. As soon as any momentum drops off, it becomes a challenge to reactivate the necessary traction. This aside, local ownership is critical and initiatives should be tailored to the local context and should be locally led and driven. This ensures not only credibility but also sustainability of the initiative. Finally, building partnerships are essential and the delivery of results depends on strong collaboration with local and international partners. Clear communication is crucial in building confidence of partners and other stakeholders.

- Programmatic Revisions

Delays in implementation have taken place due to the complex combination of security, political and social challenges Iraq is facing. This has created delays in securing certain project resources locally (particularly technical expertise), obtaining decisions or participation of local counterparts, logistical arrangements for meetings, activities and events. An additional 2-3 month delay due to this national process is to be expected. This period will lead to a slow the implementation of the project. A no-cost extension has therefore been requested to the UNDAF Steering Committee until the end of 2015 to allow the completion of the project and the fulfilment of all planned results.

# Footnotes

The term “programme” is used for programmes, joint programmes and projects.

Strategic Results, as formulated in the Strategic UN Planning Framework (e.g. UNDAF) or project document;

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as  “Project ID” on the project’s factsheet page the MPTF Office GATEWAY

The MPTF or JP Contribution, refers to the amount transferred to the Participating UN Organizations, which is available on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

The MPTF or JP Contribution, refers to the amount transferred to the Participating UN Organizations, which is available on the MPTF Office GATEWAY

Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

# Text boxes

ii) Indicator Based Performance Assessment: