SECRETARY-GENERAL’S PEACEBUILDING FUND

PBF PROJECT PROGRESS REPORT TEMPLATE

PBF PROJECT progress report

COUNTRY: Philippines

TYPE OF REPORT: semi-annual, annual OR FINAL Semi-Annual

date of report:

| Project Title: Building Capacities for Sustaining Peace in Mindanao Project Number from MPTF-O Gateway: 00107354 |
| --- |
| PBF project modality: IRF PRF | If funding is disbursed into a national or regional trust fund: Country Trust Fund Regional Trust Fund Name of Recipient Fund: |
| List all direct project recipient organizations (starting with Convening Agency), followed type of organization (UN, CSO etc): UNDP, UNICEF, UN Women List additional implementing partners, Governmental and non-Governmental: Office of the Presidential Advisor to the Peace Process |
| Project commencement date: September 2017 Project duration in months: Eighteen months |
| Does the project fall under one of the specific PBF priority windows below: Gender promotion initiative Youth promotion initiative Transition from UN or regional peacekeeping or special political missions Cross-border or regional project |
| Total PBF approved project budget* (by recipient organization): UNDP: $ 1878920 UNICEF : $ 821040 UN Women : $ 300040 : $ Total: USD 3 million *The overall approved budget and the release of the second and any subsequent tranche are conditional and subject to PBSO’s approval and subject to availability of funds in the PBF account How many tranches have been received so far: |
| Report preparation: Project report prepared by: Chetan Kumar Project report approved by: UN Resident Coordinator Did PBF Secretariat clear the report: Any comments from PBF Secretariat on the report: Has the project undertaken any evaluation exercises? Please specify and attach: To be undertaken at 12 month mark |

NOTES FOR COMPLETING THE REPORT:

- Avoid acronyms and UN jargon, use general / common language.

- Be as concrete as possible. Avoid theoretical, vague or conceptual discourse.

- Ensure the analysis and project progress assessment is gender and age sensitive.

PART 1: RESULTS PROGRESS

  - Overall project progress to date

Briefly explain the status of the project in terms of its implementation cycle, including whether all preliminary/preparatory activities have been completed (1500 character limit):

The project has completed a fifth of its implementation at the conclusion of its first nine months from September 15 2017 to June 15 2018. 23% of project funds have been expended, with significantly greater expenditure expected during the next nine months of its duration as the autonomous Bangsamoro entity is established by the Philippines Congress in July 2018. During this initial period, critical assistance has been provided to the parties to the peace process to ensure the successful passage of the Bangsamoro Basic Law. Civic groups as well as crucial "insider mediators," or senior intermediaries, have been supported to carry out advocacy in the favor of the law; help members of Congress, political leaders, and the parties to the peace process bridge significant differences through back-channel diplomacy; and mobilize women and youth to champion nationally the cause of an autonomous Bangsamoro. On PVE, progress has been made towards bridging the institutional and policy gaps obstructing the formulation of a National Plan of Action based on the UN Framework. On the ground, early efforts to prevent the further alienation and radicalization, especially among children and youth, have been successfully implemented. Women in the most vulnerable communities have been sensitized to the roles that they can play in this regard, and have organized themselves to address early signs of risk to their families and communities.

Given the recent/current political/peacebuilding/ transition situation/ needs in the country, has the project been/ does it continue to be relevant and well placed to address potential conflict factors/ sources of tensions/ risks to country’s sustaining peace progress? Please illustrate. If project is still ongoing, are any adjustments required? (1500 character limit)

During the meeting of the Steering Committee of the project in March 2018, the Presidential Advisor to the Peace Process, Secretary Dureza, specifically highlighted the significance of the project to helping parties to the peace process, as well as the wider group of governmental and civic stakeholders to addressing both the risks to the peace process, as well as the threat of violent extremism. In particular, the Secretary highlighted the critical role that the project will play in advance of the plebisicte on the Bangsamoro Basic Law currently scheduled for November 2018. Members of the Steering Committee also highlighted that flexible and catalytic support had to be provided to women's groups, youth organizations, and faith-based leaderships in communities vulnerable to violent extremism, as they were on the frontline of countering radicalization and recruitment. The project's focus on building networks for partnership and collaboration at the community level between these groups was highlighted as being especially critical in preventing further fallout from the violent siege of Marawi from May to October 2017 by ISIS-linked militants. The focus on preventing the radicalization and recruitment of minors, especially those orphaned by violence or recruited as child combatants, was also highlighted as a especially useful feature of the project.

In a few sentences, summarize what is unique/ innovative/ interesting about what this project is trying/ has tried to achieve or its approach (rather than listing activity progress) (1500 character limit).

As opposed to building institutional capacities or providing technical knowledge alone, the project has had a particular--and in the current Philippines context a unique--focus on supporting processes, spaces and forums through which relevant actors can build confidence, achieve consensus on key policies, and form alliances and coalitions for bringing about transformation change. Groups such as the high-level Friends of Peace; the Insider Mediators' Group; and the network of women peacebuilders now retooling themselves to take on violent extremism are all relevant examples. Also unique is the project's targeted focus on the spaces that are the primary arenas for radicalization, i.e. schools and Friday prayers at mosques. The project is engaging the ulama community to develop curricula that provide viable alternatives to the more radical discourses.

Considering the project’s implementation cycle, please rate this project’s overall progress towards results to date:

In a few sentences summarize major project peacebuilding progress/results (with evidence), which PBSO can use in public communications to highlight the project (1500 character limit):

The Insider Mediators' Group--a group of senior advisors to the parties in the Bangsamoro peace process as well as the wider Moro leadership--has with PBF support helped members of the Philippines Congress and their principals find common ground necessary to establishing the Bangsamoro autonomous region, and thus fulfilling a key provison of the 2014 peace agreement. A Speakers' Bureau was conducted with PBF support to enable 33 previously trained women leaders to mobilize support for the Bangsamoro peace process among Moro diaspora communities in Luzon, Visayas and Mindanao, thus adding to the momentum for the law's passage in the Philippines Congress. At the same time, and on the ground and thanks to PBF support, none of the 1,869 children and youth disengaged from the military wing of the Moro Islamic Liberation Front, which had signed the 2014 peace agreement with the Government, and deemed to be at risk of re-association with more radical ISIS-linked armed groups, have so far been found to have re-associated.

In a few sentences, explain how the project has made real human impact, that is, how did it affect the lives of any people in the country – where possible, use direct quotes that PBSO can use in public communications to highlight the project (1500 character limit):

As tensions had arisen between Task Force Bangon Marawi, the national inter-departmental committee leading the rebuilding of Marawi city after the siege by the ISIS-linked Maute Group, and IDPs displaced from the destroyed downtown, PBF support was deployed by UNDP for an informal dialogue between IDP leaders and the land sub-committee of the Task Force to find practical solutions to disputes over land and property. Imam Sharief, a prominent Muslim scholar and an IDP himself said that "efforts to differentiate between private and public properties during reconstruction were critical, and the dialogue on this issue will help prevent future conflict."

In its efforts to prevent the radicalization of minors, UNICEF has sought to engage the ulama community to develop sermons that provide alternative narratives to extremism in parochial schools and in mosques. Coupled with strengthened curricula on secular and scientific subjects, the lives of many young persons in MILF camps and communities have been significantly impacted for the better.

If the project progress assessment is on-track, please explain what the key challenges (if any) have been and which measures were taken to address them (1500 character limit).

i)	The overall combined utilization rate for the three agencies currently stands at 22.11 %. UNICEF and UNDP are at 15% and 19% respectively, and will reach the requisite 75% by approximately end-October.

ii)	The bulk of the spending for both organizations will happen in the aftermath of the meeting of the Bicameral Conference Committee of the Philippines Congress in mid-July which will reconcile the Senate and House versions of the BBL, and of the passing of the bill thereafter.

iii)	For UNDP, Secretary Dureza of OPAPP had directed during the meeting of the Steering Committee in March 2018 that the project should focus on BBL-related advocacy and dialogue (Outcome 1 of the current project) in the context of the plebiscite that will be held in November following the passage of the BBL in July. PVE efforts (Outcome 2) involving the MILF and other Moro organizations will also gather momentum following the adoption of the BBL, when key stakeholders are less distracted by political engagements in Manila. In the interim, critical political initiatives to advance the BBL in Congress have been supported through the PBF project by UNDP and UN Women (these will be detailed in the report), as have efforts to prevent further radicalization as part of the fallout from Marawi by all PBF partners.

If the assessment is off-track, please list main reasons/ challenges and explain what impact this has had/will have on project duration or strategy and what measures have been taken/ will be taken to address the challenges/ rectify project progress (1500 character limit):

See previous comments.

Please attach as a separate document(s) any materials highlighting or providing more evidence for project progress (for example: publications, photos, videos, monitoring reports, evaluation reports etc.). List below what has been attached to the report, including purpose and audience.

These materials are currently under preparation and will be uploaded by the end of the year. However, copies of sermons and curricula developed by ulama with UNICEF support are available.

  - Result progress by project outcome

The space in the template allows for up to four project outcomes. If your project has more approved outcomes, contact PBSO for template modification.

Outcome 1:

Rate the current status of the outcome progress:

Progress summary: Describe main progress under this Outcome made during the reporting period (for June reports: January-June; for November reports: January-November; for final reports: full project duration), including major output progress (not all individual activities). If the project is starting to make/ has made a difference at the outcome level, provide specific evidence for the progress (quantitative and qualitative) and explain how it impacts the broader political and peacebuilding context. Where possible, provide specific examples of change the project has supported/ contributed to as well as, where available and relevant, quotes from partners or beneficiaries about the project and their experience. (3000 character limit)?

While definitive outcome-level impact will become more evident towards end-2018, key results have been achieved during the first period of implementation. During the initial period of its implementation, the project has contributed significantly towards increasing the passage by the Philippines Congress of a Bangsamoro Basic Law that will be satisfactory for both the Government as well as the MILF. While the initial versions of the BBL passed separately by the House and the Senate in May 2018 were deemed by the MILF Chair as being watered down, subsequent work by the UNDP-supported Insider Mediators' Group has helped ensure that the prospects of a stronger BBL emerging from the Bicameral Conference Committee of the two bodies in July 2018 have increased. In addition, the work done by the IM Group to converge different Moro interests and factions will increase the prospects for a "yes" vote for the new legislation in the plebiscite scheduled for November 2018. The IM Group's role has been especially visible in one crucial area that was missing during the last failed attempt of the Congress to pass the BBL in 2015: an informal but substantive dialogue between leaders of the different Moro armed groups; the Congress; the Bangsamoro Transiton Comission; and the Office of the President. In 2018, coordination between these actors has been essential to moving the BBL along. Advocacy by women leaders, supported by UN Women, on behalf of the BBL has had discernible impact on drawing national attention to this issue, including among the now substantial Moro diaspora throught the Philippines. Sustained UN and UNDP support for the joint bodies of the peace process--especially the Bangsamoro Transition Commission--has also helped ensure that the parties to the peace process have been able to engage directly with the Congress, unlike during the first effort to pass the BBL in 2015, to push for the legislation. In this regard, the current PBF-supported project has drawn successfully from the lessons learned from the last one.

Outcome 2:

Rate the current status of the outcome progress:

Progress summary: (see guiding questions under Outcome 1)

Interim results have been achieved for this outcome (definitive results will be more apparent by year end) by mid-2018. In end-September 2017, PBF support was applied to the implementation of a regional meeting on PVE in Manila as part of the Philippines' chair of ASEAN. This meeting allowed governments in the region to adapt the UN Framework on PVE to their own national priorities, and helped set in place the Philippines own process of development of a National Action Plan. In November 2017, ASEAN member states adopted the Manila declaration calling for regional cooperation to address transboundary factors driving violent extremism, and also for each country to develop its own national action plan. In May 2018, PBF support was used to bring on board with the Resident Coordinators' Office Maj-Gen (retd) Feliciano, one of the country's leading strategists on PVE, and team of national experts to give further impetus to the development of the National Action Plan and to bring together different institutional interests and priorities. Meanwhile, on the ground, UNICEF has bee able to ensure--working closely with the MILF and with the ulama community--that minors have been protected from the concerted recruitment efforts of ISIS-linked militants. UNDP suported dialogues that have helped diffuse tension between the national government and IDPs from Marawi have also helped blunt the militant recruiting pitch. Concrete planning has been conducted for ten municipalities in areas must vulnerable to ISIS-linked militancy for the development and implementation of community security platforms that will bring together civic groups, the security sector, local governments, and religious leaders to provide an effective response to early signs of violent militancy.

Outcome 3:

Rate the current status of the outcome progress:

Progress summary: (see guiding questions under Outcome 1)

Outcome 4:

Rate the current status of the outcome progress:

Progress summary: (see guiding questions under Outcome 1)

  - Cross-cutting issues

| National ownership: How has the national government demonstrated ownership/ commitment to the project results and activities? Give specific examples. (1500 character limit) | USD 300, 000 from PBF UNDP funds is directly managed by the Office of the Presidential Advisor to the Peace Process for initiatives to generate momentum for the passage and ratification of the Bangsamoro Basic Law. Government agencies, particularly OPAPP and the Department of Interior and Local Government, have taken a particular interest in the design and implementation of project activities, and explored the possibility of moving towards the PRF modality in the next phase of PBF support. The Steering Committee for current PBF project is co-chaired by Secretary Dureza, the current Presidential Advisor, who has indicated that the project is an essential part of OPAPP's current toolkit for advancing the peace process. |
| --- | --- |
| Monitoring: Is the project M&E plan on track? What monitoring methods and sources of evidence are being/ have been used? Please attach any monitoring-related reports for the reporting period. (1500 character limit)? | In April 2018, project partners undertook a joint risk analysis exercise and technical review, following which two key modifications were made to the project: Monies allocated to advocacy for the draft Bangsamoro Basic Law were reallocated for efforts to ensure the a successful approval of the law in then plebiscite scheduled for November 2018. Second, and given the critical impact of the pace and content of the recovery process of Marawi on the wider issue of PVE in the Lanao del Sur province, USD 150, 000 in project monies were reallocated to ensuring a conflict sensitive process of recovery, and in particular in ensuring that the processes of debris management, and those of managing claims and disputes over land and property among IDPs as well as between the government and returning IDPs, included a significant component of consultation and joint planning. Both these issues have significant emotional value for IDPs given that some of the debris and affected homes are from properties that have been with families for centuries, and their mismanagemnt could heighten alienation and radicalization. |
| Evaluation: Provide an update on the preparations for the external evaluation for the project, especially if within last 6 months of implementation or final report. Confirm available budget for evaluation. (1500 character limit) | External evaluation for the project will be undertaken by end-2018, and will involve experts from national and local universities that have significant experience with analysis of peacebuilding efforts, especially in Mindanao. Funding is currently available for this evaluation. |
| Catalytic effects (financial): Did the project lead to any specific non-PBF funding commitments? If yes, from whom and how much? If not, have any specific attempts been made to attract additional financial contributions to the project and beyond? (1500 character limit) | USD 3 million was received by UNDP from Japan in early 2018 as additonal support for PVE related activities. Ateneo de Davao University, a critical partner for the PBF project, also played a key role in mobilizing these additional resources. A wider programme for "Stabilization, Recovery, and Transformation for Peace"--START-PEACE--is currently being developed for the conflict-affected areas of Mindanao building on the catalytic support from PBF. Support will be sought from Australia, Canada, the US, and Japan for this programme. For UNICEF, PBF support has been leveraged into a wider package of donor support for a comprehensive programme to prevent the radicalization and recruitment of minors by terror groups. |
| Catalytic effects (non-financial): Did the project create favourable conditions for additional peacebuilding activities by Government/ other donors? If yes, please specify. (1500 character limit) | PBF support has been instrumental in bringing together national institutions with divergent frameworks on PVE to start jointly developing a National Action Plan on the issue, and to align policies and programmes. The Office of the Presidential Advisor to the Peace Process has been able to leverage the support to launch a successful series of "peace tables" for youth, women, and indigenous peoples. |
| Exit strategy/ sustainability: What steps have been taken to prepare for end of project and help ensure sustainability of the project results beyond PBF support for this project? (1500 character limit) | All current PBF support is already being leveraged to establish longer term programmes. In addition, the National Action Plan on PVE will form the basis for expenditures and allocations for this issue by the national government for the foreseeable future. The successful establishment of the Bangsamoro Transition Authority with PBF support will lead eventually to a viable autonomous region for Bangsamoro with strong self-sustaining capacity, and the ability to ensure both lasting peace and sustainable development in Muslim Mindanao. |
| Risk taking: Describe how the project has responded to risks that threatened the achievement of results. Identify any new risks that have emerged since the last report. (1500 character limit) | In April 2018, the lower house and the Senate in the Philippines Congress passed significantly watered down versions of the Bangsamoro Basic Law, thereby threatening to derail the peace process. With UNDP support, the Insider Mediators' Group, the Friends of Peace, and the Consortium on Bangsamoro Civil Society conducted sustained back-channel diplomacy, advocacy with high level government officials and actors, and focused efforts to find bridging language to restore necessary provisions into the BBL right through the Bicameral Conference Committee of the two houses that met from July 9-12 2018. By July 11, many of the key provisions that had originally been deleted had been restored and the overall process was back on track. PBF funds were used to support these efforts. For UN Women's contribution, please see the below. |
| Gender equality: In the reporting period, which activities have taken place with a specific focus on addressing issues of gender equality or women’s empowerment? (1500 character limit) | For UN Women, a Speakers' Bureau was conducted to enable 33 previously trained women leaders to deliver messages to gather support of the Bangsamoro peace process, most especially the passage of the law on the Bangsamoro, among Moro diaspora communities in Luzon, Visayas and Mindanao. Additional study sessions were conducted to strengthen capacities of these women last May. These women were 'deployed' in various diaspora communities throughout June to July, in time for the deliberations on the Bangsamoro Basic Law, and had a significant impact on generating wider support for the law's passage. |
| Other: Are there any other issues concerning project implementation that you want to share, including any capacity needs of the recipient organizations? (1500 character limit) | Only 24 per cent of project funds have been spent by mid-July. However, spending will be ramped up significantly in Fall 2018 in the afternath of the passage of the BBL as preparations are undertaken for the plebiscite, and also as the ARMM government is assisted to ensure a speedy and effective transition to the Bangsamoro Transition Authority. |

1.3 INDICATOR BASED PERFORMANCE ASSESSMENT: Using the Project Results Framework as per the approved project document or any amendments- provide an update on the achievement of key indicators at both the outcome and output level in the table below (if your project has more indicators than provided in the table, select the most relevant ones with most relevant progress to highlight). Where it has not been possible to collect data on indicators, state this and provide any explanation. Provide gender and age disaggregated data. (300 characters max per entry)

|  | Performance Indicators | Indicator Baseline | End of project Indicator Target | Current indicator progress | Reasons for Variance/ Delay (if any) | Adjustment of target (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 Enabling environment for the successful implementation of the Comprehensive Agreement on the Bangsamoro established | Indicator 1.1 Intra-Moro consensus achieved, with the participation of youth, women, and minorities, on power-sharing and governance within the new autonomous Bangsamoro entity | Consensus has not yet been achieved across the entire cross-section of Moro leadership | Sufficient consensus achieved by November 2017, and reflected in the formation of the Bangsamoro Transitional Authority, as well as the subsequent autonomous Bangamoro entity, by end-2018. | Consensus on power sharing has been achieved between the MILF and the largest MNLF group, and will be reflected in the BTA. Other Moro groups may join once the BBL is passed by end-July 2018 and an all-Moro dialogue held. The final BBL reflects inputs from women, youth, and minorities. | Indicator is on track. |  |
|  | Indicator 1.2 Inputs from women and youth, as well as their direct participation, significantly enhanced in the process leading to the formation of the autonomous Bangsamoro entity, as well as in the overall implementation of the Comprehensive Agreement on the Ban | No formal or systematic mechanism for participation by youth and women in the Bangsamoro peace process. | Systematic “peace tables” for women and youth established by end-2017 to accompany the Bangsamoro peace process, and their outputs fully reflected in the work of the Bangsamoro Transitional Authority and the subsequent autonomous Bangsamoro entity by end-2018 | OPAPP has established peace tables for youth and women, but these have not been fully sustained beyond initial conversations. With the BBL passed by end-July, efforts will be made to consolidate and sustain these peace tables for providing inputs into the transition from the ARMM to the BTA. | The indicator was delayed in part of 2018, but is now expected to be on track. |  |
|  | Indicator 1.3 UN Country Team fully equipped to support the implementation of the Strategic Framework for Peace and Development in Mindanao. | No integrated baselines and indicators currently exist for UNCT support, which is ad hoc and has not been framed as an integrated programme offer. | Integrated programmatic offer developed by October 2017, and capacities related to women, peace and security developed and applied by end-2018. | The integrated programmatic offer was to be developed in support of the Government's Mindanao Peace and Development Funding Facility. However, the Marawi siege put the Government's plan on hold. The UNCT is now developing an integrated offer to support Marawi recovery as well as transition to BTA. | The delay was created due to the length of the Marawi siege, which only concluded in November 2017, and the subsequent focus of the government on Marawi recovery rather than wider peace and development in Mindanao. | Target has been adjusted to focus on post-conflict recovery in Marawi, and on the transition from ARMM to BTA, to reflect Government priorities for UNCT support. |
| Output 1.1 Platform for intra-Moro dialogue developed and implemented, including to achieve consensus on Bangsamoro legislation; Moro positions with regard to federalism; and on the constitution of the autonomous Bangsamoro government, including the Bangsamoro Transitional Authority; and special autonomy for B | Indicator 1.1.1 Insider mediators successfully able to support consensus on enabling legislation in Congress, and on the constitution of the Bangsamoro Transitional Authority betwee the MILF and the MNLF. | Insider mediators have achieved convergence of the three peace agreements, and also developed an informal draft of the enabling law that reflects substantive convergence. | Consensus on the enabling law achieved by October 2017, and agreement on power sharing and joint governance in the BTA achieved by early 2018. Accompaniment for the formation and work of the BTA provided through 2018. | Internal Mediators' Group successfully established as a dialogue platform; peace agreements reconciled in 2017; an all-Moro consensus draft of a charter for a Bangsamoro federal state submitted to the President in June 2018; and the amended BBL was passed by Congress in July 2018. | Indicator is on track. |  |
|  | Indicator 1.1.2 Credible platform for intra-Moro dialogue constituted under the auspices of the BTC as appropriate, or otherwise, and sustained through the period of the formation of the autonomous Bangsamoro entity. Indicator1.1.3 Bangsamoro in new federal charte | Platform currently does not exist Federalism does not include Bangsamoro. | Constitutional Review Committee includes special autonomy for Bangsamoro in federal charter. | Insider Mediators' Group has transformed into a platform for intra-Moro dialogue and sustained through 2017 and 2018. Draft federal charter submitted to the President and Congress in July 2018 recognizes special autonomy for Bangsamoro as a result of efforts of Insider Mediators' Group. | Indicator is on track.Cred |  |
| Output 1.2 | Indicator 1.2.1 Two national peace tables for youth and women developed, and outputs from the tables successfully integrated into the processes leading to the formation of the Bangsamoro autonomous entity. | : Preliminary activities have been conducted, but systematic forums not yet launched. | Two national peace tables for youth and women are credibly established by end-2017, and are sustained through the period of formation of the Bangamoro autonomous entity. | National peace tables for women and youth have been successfully launched by the Office of the Presidential Advisor to the peace process; with the BBL process concluded, these will now be more systematically expanded and consolidated. | Indicator is largely on track. |  |
|  | Indicator 1.2.2 Women able to participate in ceasefire, normalization and transition processes and mechanisms and pursue measures on women, peace and security | Dialogue and networking around women’s leadership roles in the Bangsamoro autonomous entity has taken place in a sporadic and ad hoc manner, and not yielded a reliable capacity. | 200 trained women on the Bangsamoro peace process able to participate and pursue gender agenda in local decision-making processes and mechanisms | One Speakers' Bureau conducted; 2 study session conducted, participated by 33 and 22 women speakers, respectively. | Indicator on track. |  |
| Output 1.3 | Indicator 1.3.1 Integrated programme offer in support of the Strategic Framework for Peace and Development in Mindanao developed by the UN Country Team. | The programme offer exists in early draft stage, but will require further technical support from UNHQ, especially on cross-cutting issues, before being finalized. | Programme offer finalized by August 2017. | New UNCT frameworks for Marawi recovery; prevention of violent extremism; and support from transition from ARMM to BTA will be finalized by October 2018. | Implementation of the indicator had been held up due to the Marawi siege and its aftermath but is now on track. | Indicator has been adjusted to include UNCT frameworks on Marawi recovery and PVE. |
|  | Indicator 1.3.2 UNCT members able to integrate issues related to women, peace, and security in all initiatives related to peacebuilding and to the prevention of violent extremism Indicator 1.3.3PBF support for the Philippines effectively monitored. | No systematic capacity outside UN Women and UNICEF Current PBF project was launched in September 2017. | : Training of all relevant UNCT staff implemented by end-2017; and tool to guide programming developed and implemented by June 2018 PBF support effectively implemented by December 2018. | While the gender lens has been fully integrated into the new 2019-2022 UNDAF, the development of a specific tool for pertaining to gender and PVE remains to be undertaken Joint stakeholder reviews of the PBF project have been conducted in March and April 2018. | Indicator is delayed due to exigencies created by the aftermath of the Marawi siege; will be on track in fall 2018. Indicator is on track. |  |
| Outcome 2 Factors driving alienation, radicalization, and violent extremism identified, and capacities to address them developed and implemented | Indicator 2.1 A least three credible online and physical forums established and sustained for dialogue between youth, women, and faith-based leaderships in communities at risk, and systematic dialogue established between government civil society on the issue of PV | No forums currently exist for systematic and broad-based dialogue. | At least three forums each, sustained by universities, in at least three of the five ARMM provinces, with each forum able to engage at least three hundred individuals (with half women, and half in the age group 18-35, in dialogue. Network for systematic dialogue between government and civil society | The National Council on Muslim Filipinos; Ateneo de Davao University; and Mindanao State University have been engaged to deliver networks/ platforms for youth and women to engage with the PVE issue. | The indicator is only partly on track as many of the key interlocutors were displaced or otherwise adversely impacted by the Marawi siege, and others have seen their resources consumed by the BBL effort as well as post-conflict resovery in Marawi. The indicator will be on better course in 1-2 months |  |
|  | Indicator 2.2 Significant increase (with at least a hundred ulama across at least three ARMM provinces engaged) in numbers of ulama and madrassas conveying messages of positive struggles for peace, social justice and inclusion, and in the number of individuals participating in these sermons and classes. | The top ulama institutions of ARMM have issued calls against violent extremism, but there is no evidence of impact, and the calls are not sustained. | At least 50% increase (equivalent to at least a hundred ulama across at least three ARMM provinces) in individual ulamas and madrasahs offering sermons or courses on peaceful struggle for social justice in at least three ARMM provinces. | Core group of ulama in Lanao del Sur and Maguindanao provinces has been established to form a platform on new teaching and preaching. Based on initial actions in their own institutions, ulama can be said to have achieved a ten per cent increase in positive messages, | Indicator is partly on track, and is being accelerated. |  |
|  | Indicator 2.3 No return to armed groups by underage adherents of these groups who have now been rehabilitated, and a significant increase in educational opportunities that reduce the risks of radicalization for these individuals | A hundred percent of rehabilitated youth, and a practically zero percent participation by these youth in educational opportunities that reduce the risks of radicalization. | At least eighty percent of rehabilitated children are prevented from rejoining armed groups, and at least 1000 individuals from this cohort are afforded opportunities for education that reduces the risk of radicalization. | Currently none of the rehabilitated individuals have reverted to violence. | Indicator is on track. |  |
| Output 2.1 Role of women, youth and faith-based leaderships in preventing violent extremism enhanced, including through the development and dissemination of positive narratives in social media | Indicator 2.1.1 Number of youth in MILF communities reached with key messages on positive struggles for peace and social justice through religious leaders’ sermons, and number of such leaders equipped to engage in this manner. | 0 | Training of 200 religious leaders completed by December 2017, and outreach to 10, 000 MILF youth conducted by these religious leaders by end-2018. | 0 | Delay in identification of MILF focal points for this component delayed implementation by three months. This will be recovered by end 2018 by acceleration of planned activities. |  |
|  | Indicator 2.1.2 At least two dialogue spaces per province for three provinces of ARMM, with the active participation of three hundred individuals. Indicator 2.1.3 Credible intermediaries Indicator 2.1.4 Regional meeting and action plan. | The Davao-based Salam network, oriented towards youth, is currently the only such entity with rudimentary dialogue capabilities No intermediaries are currently deployed on the ground to work systematically with the affected communities. There is currently no systematic dialogue between government | At least six dialogue platforms should be fully functional by mid-2018, with the rest by end-2018. At least 15 intermediaries will be trained and deployed by end 2018, and will support at least one research initiative in three select regions by end-2018 Regional meeting by end-2017. | Dialogue platforms will be launched by September by Ateneo de Davao, Mindanao State University and the NCMP Approximately fifty intermediaries have been identified and have received training on mediation. Regional meeting was conducted in September 2017. | Indicator is partially delayed but being accelerated. |  |
| Output 2.2 Children and youth at risk of association or re-association with armed groups | Indicator 2.2.1 Percentage of disengaged children who have not re-associated with armed groups | 100 per cent | 80 percent | 100 per cent | Performance currently exceeeds target. Based on direct assessment of 86% of the total 1,869 disengaged children |  |
|  | Indicator 2.2.2 Percentage of disengaged and at risk youth and children received culturally sensitive and flexible learning opportunities (education) Indicator 2.2.3 Percentage of disengaged and at risk youth and children received psychosocial and life skills supp | 0 0 | 1000 individuals 1500 individuals | Delayed by 3 months 1383 individuals. | Delayed due to Marawi siege but expected to be back on track by September. Indicator on track. |  |
| Output 2.3 | Indicator 2.3.1 |  |  |  |  |  |
|  | Indicator 2.3.2 |  |  |  |  |  |
| Outcome 3 | Indicator 3.1 |  |  |  |  |  |
|  | Indicator 3.2 |  |  |  |  |  |
|  | Indicator 3.3 |  |  |  |  |  |
| Output 3.1 | Indicator 3.1.1 |  |  |  |  |  |
|  | Indicator 3.1.2 |  |  |  |  |  |
| Output 3.2 | Indicator 3.2.1 |  |  |  |  |  |
|  | Indicator 3.2.2 |  |  |  |  |  |
| Output 3.3 | Indicator 3.3.1 |  |  |  |  |  |
|  | Indicator 3.3.2 |  |  |  |  |  |
| Outcome 4 | Indicator 4.1 |  |  |  |  |  |
|  | Indicator 4.2 |  |  |  |  |  |
|  | Indicator 4.3 |  |  |  |  |  |
| Output 4.1 | Indicator 4.1.1 |  |  |  |  |  |
|  | Indicator 4.1.2 |  |  |  |  |  |
| Output 4.2 | Indicator 4.2.1 |  |  |  |  |  |
|  | Indicator 4.2.2 |  |  |  |  |  |
| Output 4.3 | Indicator 4.3.1 |  |  |  |  |  |
|  | Indicator 4.3.2 |  |  |  |  |  |

PART 2: INDICATIVE PROJECT FINANCIAL PROGRESS

  - Comments on the overall state of financial expenditures

Please rate whether project financial expenditures are on track, delayed, or off track, vis-à-vis project plans and by recipient organization:

How many project budget tranches have been received to date and what is the overall level of expenditure against the total budget and against the tranche(s) received so far (500 characters limit): The first tranche has been received so far. Overall project expenditure as of mid-June 2018 was 22.11 percent.

When do you expect to seek the next tranche, if any tranches are outstanding: October 2018

If expenditure is delayed or off track, please provide a brief explanation (500 characters limit): The overall combined utilization rate for the three agencies currently stands at 22.11 %. UNICEF and UNDP are at 15% and 19% respectively, and will reach the requisite 75% by approximately end-October. The bulk of the spending for both organizations will happen in the aftermath of the meeting of the Bicameral Conference Committee of the Philippines Congress in mid-July which will reconcile the Senate and House versions of the BBL, and of the passing of the bill thereafter.

Please state what $ amount was planned (in the project document) to be allocated to activities focussed on gender equality or women’s empowerment and how much has been actually allocated to date: USD 300, 000 from UN Women and USD 180, 000 by UNDP. Approximately USD 250, 000 has been expended so far.

Please fill out and attach Annex A on project financial progress with detail on expenditures/ commitments to date using the original project budget table in Excel, even though the $ amounts are indicative only.

# Footnotes

Note: commencement date will be the date of first funds transfer.

Maximum project duration for IRF projects is 18 months, for PRF projects – 36 months.