SECRETARY-GENERAL’S PEACEBUILDING FUND

PBF PROJECT PROGRESS REPORT TEMPLATE

PBF PROJECT progress report

COUNTRY: Liberia and Cote d'Ivoire

TYPE OF REPORT: semi-annual, annual OR FINAL FINAL

date of report: October 2019

| Project Title: Cross-Border Cooperation between Côte d’Ivoire and Liberia for Sustainable Peace and Social Cohesion Project Number from MPTF-O Gateway: 00104898 |
| --- |
| PBF project modality: IRF PRF | If funding is disbursed into a national or regional trust fund: Country Trust Fund Regional Trust Fund Name of Recipient Fund: UNDP & IOM |
| List all direct project recipient organizations (starting with Convening Agency), followed type of organization (UN, CSO etc): UNDP & IOM List additional implementing partners, Governmental and non-Governmental: LIBERIA: Ministry of Internal Affairs, Bureau of Immigration and Naturalization, Liberia National Police, County Development Authorities. IVORY COAST: Ministry of Interior and Security, Ministry of Planning and Development, Ministry of Defense, Secretary – National Security Council, Ministry of Solidarity and Social Cohesion, CSO, and CBOs. |
| Project commencement date: April 2017 Project duration in months: 20 |
| Does the project fall under one of the specific PBF priority windows below: Gender promotion initiative Youth promotion initiative Transition from UN or regional peacekeeping or special political missions Cross-border or regional project |
| Total PBF approved project budget* (by recipient organization): UNDP Liberia: $ 899,976.90 IOM Liberia : $ 600,023.10 UNDP CDi : $ 896,873.10 IOM CdI : $ 603,126.54 Total: US$3,000,000 *The overall approved budget and the release of the second and any subsequent tranche are conditional and subject to PBSO’s approval and subject to availability of funds in the PBF account How many tranches have been received so far: 2 |
| Report preparation: Project report prepared by: Eric Opoku/Hervé Karege (Liberia); Arsene Assande/Paulette Degonzague (CdI) Project report approved by: Dr. Pa Lamin Beyai, Resident Representative (Liberia) and Luc Gregoire, UNDP Country Director (Ivory Coast). Did PBF Secretariat clear the report: Yes Any comments from PBF Secretariat on the report: Yes Has the project undertaken any evaluation exercises? Please specify and attach: YES |

NOTES FOR COMPLETING THE REPORT:

- Avoid acronyms and UN jargon, use general / common language.

- Be as concrete as possible. Avoid theoretical, vague or conceptual discourse.

- Ensure the analysis and project progress assessment is gender and age sensitive.

PART 1: RESULTS PROGRESS

  - Overall project progress to date

Briefly explain the status of the project in terms of its implementation cycle, including whether all preliminary/preparatory activities have been completed (1500 character limit):

The implementation of all project activities in both countries was completed with an execution rate of 100% in Liberia and 97% in Ivory Coast. In Liberia, project activities enhanced collaboration between stakeholders, namely UN, security agencies, local government, community leaders and members including women and youth. Through open and frank dialogues, it also improved social cohesion within and among border communities. The project was presented to the stakeholders to build synergies and avoid duplication. An initial joint-needs assessment of selected Points of Entry (POEs), national and local partners, informed logistical support provided to the security agencies. Enhanced logistical capacity of the security agencies led to an increase in patrols and boosted communities’ confidence and trust in the agencies. In addition, rehabilitated POEs have enhanced personnel’s morale to work.  Two selected local organizations carried out community outreach activities in both project areas. The constant collaboration between RUNOs  immensely supported the sensitization sessions and training of the target communities to promote social cohesion and outreach activities along the Côte d'Ivoire-Liberia border. Stakeholders in both countries attested to the project’s positive impact at the final review meeting. Findings of project evaluation rated the entire project as satisfactory and assigned an average score of 5/6.

Considering the project’s implementation cycle, please rate this project’s overall progress towards results to date:

In a few sentences, summarize what is unique/ innovative/ interesting about what this project is trying/ has tried to achieve or its approach (rather than listing activity progress) (1500 character limit).

The cross-border nature of the project itself was unique to promote peace between Liberia and Cote d'Ivoire; while the two countries share the borders, coordinated support to promote social cohesion from both sides was rarely provided, which goes beyond the agreed border protocol measures by ECOWAS. The project combined socio-cultural and sporting activities which increased interactions between the border communities of both countries  and enhanced in promoting peaceful co-existence, mutual trust and cooperation.

The joint planning of the activities through dialogue during the peace and security meetings between the two countries helped in strengthening collective approaches to peace building and joint security action and patrols. The sporting activities on the other hand, enhanced cordiality among the youth in border communities across the two countries, as well as between the communities and the security agencies.

The cross-border trade fairs organised by the project (dominated by women) enhanced livelihood and income generation among community members. These were strategically held on market days during the social cultural activities  in order to take advantage of the large number of people present. Conscious efforts to involve women in project activities have increased their interest and participation in security and peace initiatives.

In a few sentences summarize major project peacebuilding progress/results (with evidence), which PBSO can use in public communications to highlight the project (1500 character limit):

In both countries, the project has contributed to reducing tensions among border communities and improved peaceful co-existence and social cohesion. This is corroborated by the evaluation report which indicated that about 90% of community members attested to and enhanced social cohesion and peaceful co-existence against the target of 30%.  4 joint socio-cultural activities (cultural/sport and trade fairs) organized within the project communities in two countries as well as setting up two (2) Civil- Millitary Committees (CMC). 25% of participants who attended security issues were women as key actors in promotion of security and peace. The sensitization of 282 committee members has contributed positively for the citizens to be more conscious of their roles in peacebuilding in addition to closely sharing of information with the security agencies to enhance security. Logistical support (motor bikes, communication radios, solar panels, rehabilitation of POEs, water pumps, etc.) and  trainings provided to 500 security officers and community leaders have boosted their morale and increased their patrols as well as their response rate due strengthened ope. Consequently, trust and confidence between communities and security agencies have improved, leading to increased security along the border. This has helped to reduce criminal activities and created a congenial atmosphere, allowing citizens to pursue their businesses and development in the border areas peacefully.

In a few sentences, explain how the project has made real human impact, that is, how did it affect the lives of any people in the country – where possible, use direct quotes that PBSO can use in public communications to highlight the project (1500 character limit):

The testimonies of stakeholders shows that the project  made significant impact. For instance, the Police Commander in Maryland at a workshop held on September 6, 2018 at Duokudi border said that prior to the project, traditional leaders obstructed arrests of community members suspected of crimes, by threatening death of any police who crossed their ‘spiritually’ lines. However, with the project interventions through dialogues and regular meetings, the traditional leaders have cooperated and  handover suspects to police.  The attitudinal change and reduced criminal activities are allowing communities, especially the women, to safely engage in  socio-economic activities. The evaluation report indicates, 'significant increase in cross-border movement, renewed economic dynamism, and increased food supply along the border'.  Also, in the Maryland the County Attorney  during a meetings held on Sept 6, 2018 said …."this  kind of meetings is an opportunity for us to strengthen our ties and partnerships in order to discuss solutions to problems that detract  our common interest in peace,”. On another instance, the  Chief of Grabo village and a member of the CMC attested that.... "through the training held on July 21, 2018 in Gnato, I  now knows how to resolve problems that my constituents may have with our brothers from Nyaaken of Liberia,”

If the project progress assessment is on-track, please explain what the key challenges (if any) have been and which measures were taken to address them (1500 character limit).

The two countries shared common challenges. Bad roads, tough terrains and poor access to some remote communities are some of the challenges encountered during the project implementation. These were worse on the Liberian side, and considering the sensitivity and importance of the project, required more of the project manager’s time. The situation was managed by combining activities in order to reduce frequency of travel on these roads for project staff and national/local partners. Efforts were also made to carry out more activities during the dry season.

Poor access to internet services and GSM coverage made communication with local partners sometimes very difficult. They were, however, resolved through identification of specific receptive areas in such communities where at certain times of the day mobile network coverage was good and allowed information-sharing with coordinators. The Field Officers in the counties also facilitated stakeholders’ engagement and execution of project activities.

The language barrier (Liberia – English and Ivory Coast - French) also posed communication challenges. This was managed by the use of bi-lingual volunteers who spoke both languages as well as local dialects to serve as interpreters.

Considering that prevailing situations in the two countries vary, at certain times, alignment of joint project activities often required rescheduling, necessitating a lot of flexibility and cooperation among stakeholders in both countries.

If the assessment is off-track, please list main reasons/ challenges and explain what impact this has had/will have on project duration or strategy and what measures have been taken/ will be taken to address the challenges/ rectify project progress (1500 character limit):

Please attach as a separate document(s) any materials highlighting or providing more evidence for project progress (for example: publications, photos, videos, monitoring reports, evaluation reports etc.). List below what has been attached to the report, including purpose and audience.

1. Two short documentary videos on project

2. Evaluation Report

  - Result progress by project outcome

The space in the template allows for up to four project outcomes. If your project has more approved outcomes, contact PBSO for template modification.

Outcome 1:  Increased confidence between security forces/agencies and border communities through enhanced capacity of joint local cross border mechanisms, as well as increased intra-/cross-border cooperation.

Rate the current status of the outcome progress:

Progress summary: Describe main progress under this Outcome made during the reporting period (for June reports: January-June; for November reports: January-November; for final reports: full project duration), including major output progress (not all individual activities). If the project is starting to make/ has made a difference at the outcome level, provide specific evidence for the progress (quantitative and qualitative) and explain how it impacts the broader political and peacebuilding context. Where possible, provide specific examples of change the project has supported/ contributed to as well as, where available and relevant, quotes from partners or beneficiaries about the project and their experience. (3000 character limit)?

Implementation of project activities in the two countries has resulted in the community members collaborating more closely with the security agencies, as confirmed by the Evaluation Report. Mirroring border communities are co-habiting peacefully, resolve their conflicts and are engaged in cross border trade and social activities. Patrols and response rate have increased  to hard-to-reach border communities, and communication has been enhanced  amongst security agencies in the two countries, thus boosted the trust and confidence of the community members with the security apparatus.

In Liberia, 36 motor bikes, 76 hand held radio, 7 laptops, 5 desktops,  5 printers, 6 solar units, 48 metal detectors and other logistics were provided to the LNP, LDEA and LIS to enhance their patrol, response rates to relevant security issues. These have boosted their operational effectiveness.  Community information-sharing and sensitization have been boosted through radio stations, regular dialogues and joint sports/ cultural activities. Women's interest and engagement in security issues have increased. In raising awareness, billboards, T-shirts, posters and airing of radio programmes were used. Two local radio stations in the counties were contracted to broadcast peace messages which has been developed in partnership with local NGOs. The messages were translated into the local dialect (Gbrebo) and endorsed by the Cross-Border working group.  1,050 community members were involved, including 80 border security officials, county authorities, chiefs, elders and CSOs. Joint security dialogues have been facilitated and need for improved collaboration and coordination between security personnel, local authorities and community members along the borders.

Cote d'Ivoire has provided 15 motor bikes, 4 laptops and security equipment for border security forces including installing 2 telephone network amplifiers at border points of Tabou and Taï  to improve communication; rehabiliaited and equipped Tabou border points and their hydraulic pump. The morale of border security personnel improved following rehabilitation and improved the Ports of Entries confirmed through testimonies during peace meetings which have  improved trust and confidence between security personnel, county and local leaders along the borders. In addition, 341 members of local authorities, security forces and border management officers and CSOs from Taï and Tabou were trained on human rights, gender, child protection etc; 02 Civil-Military Committees (CMC) were set up; complete technical equipment for the restarting of Taï radio was also provided while Tabou radio was strengthened; and 2000 people were sensitized on peace and social cohesion.

Outcome 2:  Improved social cohesion and peaceful co-existence in cross border communities through cross border community dialogues and reinforcing of cooperation between existing local conflict resolution mechanisms strengthened by cross-border cooperative socio-economic stabilization and cultural exchanges.

Rate the current status of the outcome progress:

Progress summary: (see guiding questions under Outcome 1)

Through cross border communities’ meetings and dialogues between the communities from the two countries and the security officers, security and conflict concerns have been addressed. In addition, strengthened cross-border cooperation, socio-economic stabilization and cultural exchange also led to improved social cohesion and peace coexistence among the border communities.  Further, the communities have developed trust and confidence towards security agencies following the strengthening of the capacity of the national security apparatus in the wake of UNOCI and UNMIL withdrawals, which has improved congenial atmosphere for peace and development in the border areas. Women and youth entrepreneurial skills and business management have been improved through skills training and cross border trade fairs. Some water pumps in selected communities was rehabilitate to reduce tensions and promote social cohesion and peace in Cote d’Ivoire. Moreover, Six 7-member peace committees was established in project locations; Data/information collected and shared with communities and relevant government agencies; and joint cross-border committees set up for coordinating cross border project activities. Cross-border trade fairs were facilitated, intertwined with sporting/cultural activities between the two countries, in collaboration with relevant stakeholders.  These took place at two levels: (i) In-country - among the border communities in each country; and (ii) Cross-border – between the two countries (on rotational basis)  The joint security meetings in both countries were planned for the participation of 42 people (20 from Cote d'Ivoire and 22 from Liberia) per country to discuss security issues along the borders. However, the meeting at Duokudi Border, River Gee County brought together 60 participants (41 males and 19 females). This, for instance, shows communities’ interest in project activities. A total of 240 players and officials for the 4 teams in each country were involved in the games. Over 500 community members participated in cultural performances, meetings and spectators of the games. In Cote d’Ivoire, 160 members of 16 peace and protection committees of the target villages were trained in conflict prevention and management; 2 cross-border socio-cultural and sport activities were organised in Tabou (CDI) and Nyaaken (Liberia) with over 300 participants; 1 inter-community meeting was organized in Tiboto (Tabou) between Ivorian and Liberian communities, as well as the two countries’ security officers (70 participants including 30 Liberians attended). At Ranoueke (Tabou) and Daobly (Tai), cross-border socio-cultural and sports activity were organized with over 700 participants; 4 water pumps were rehabilitated in these communities; 10 mass sensitizations were organized in Taï with NGO partners on peaceful coexistence, social cohesion, and conflict prevention/management.

Outcome 3:

Rate the current status of the outcome progress:

Progress summary: (see guiding questions under Outcome 1)

Outcome 4:

Rate the current status of the outcome progress:

Progress summary: (see guiding questions under Outcome 1)

  - Cross-cutting issues

| National ownership: How has the national government demonstrated ownership/ commitment to the project results and activities? Give specific examples. (1500 character limit) | In Liberia, the national government through the Ministry of Internal Affairs (MIA) and the Ministry of Justice (MOJ) were involved right from the conceptual stages of the project and participated in the inception meeting and the recent project review meeting in Monrovia. Entities such as the Liberia National Police (LNP), Liberia Immigration Service (LIS), Liberia Drug Enforcement Agency (LDEA), County and Local authorities have been actively involved in planning and execution of project activities with their direct participation. For instance, the communities organised peace committee meetings, where the LIS regularly participated. Similarly, conscious efforts have were made for active participation of youth and women leaders. The sense of ownership and commitment of the project is thus high among the national stakeholders at all levels. Likewise, in Cote d'Ivoire, administrative authorities at central and local levels were involved in the planning and implementation of activities. They actively participated in planning meetings such as the last project-end review meeting at Grand Bassam. This reflected their commitment and ownership of project achievements by these local actors. |
| --- | --- |
| Monitoring: Is the project M&E plan on track? What monitoring methods and sources of evidence are being/ have been used? Please attach any monitoring-related reports for the reporting period. (1500 character limit)? | Yes, the project M&E plan was fully implemented. A combination of observation, informal interviews and focused group discussions were employed during monitoring visits, which were often combined with implementation of planned activities, due to in acceasble road conditions. The project team in Cote d'Ivoire organized follow-up missions in the field, provided mission reports that indicated the level and quality of implementation of the activities. Progress reports were also sources of information and the pathways to a coherence implemnation of planned activities. This indciated the level of deliverables as well as the results achieved, changes made and lessons learned, through the testimonies of beneficiaries. |
| Evaluation: Provide an update on the preparations for the external evaluation for the project, especially if within last 6 months of implementation or final report. Confirm available budget for evaluation. (1500 character limit) | The evaluation of the project has been completed, following the recruitment of one international and two national consultants (one for each country). The evaluation team worked with PBF Secretariats in both countries and employed a combination of qualitative and quantitative methods to access primary and secondary project information and data against the project objectives. The final evaluation report is attached. |
| Catalytic effects (financial): Did the project lead to any specific non-PBF funding commitments? If yes, from whom and how much? If not, have any specific attempts been made to attract additional financial contributions to the project and beyond? (1500 character limit) | Yes, UNDP Liberia provided $150,000 to complement the PBF funding. Discussions were held with some parties, and concept notes developed to mobilize resources towards consolidating achievements thus far and to sustain its achievements in a follow-up project. |
| Catalytic effects (non-financial): Did the project create favourable conditions for additional peacebuilding activities by Government/ other donors? If yes, please specify. (1500 character limit) | Yes: the concept of the project has been highly embraced by the government, authorities and communities of both countries. They have ensured to maintain the current structures in place as part of the sustainability plan. |
| Exit strategy/ sustainability: What steps have been taken to prepare for end of project and help ensure sustainability of the project results beyond PBF support for this project? (1500 character limit) | The level of ownership and commitment demonstrated during the planning and implementation of the project's activities, clearly indicated the ability of the local stakeholders to conduct and sustain these project activities such as the peace meetings, trade fairs, cultural and sporting activities. Again, the capacity built at the local level among the stakeholders e.g. the Peace Protection Committees will enable them to continue sharing information and coordinating their activities for lasting peace and security relationship on the borders of both countries. Similarly, in Cote d'Ivoire, the involvement and commitment of central and local authorities as well as communities are opportunities for the sustainability of gains made. Communities are sufficiently sensitized to continue similar project activities in the absence of funding from the donor. The revitalization of the Joint Units of the Mano River Union and the setting up of exchange frameworks through the various committees also constituted strategies for the sustainability of the project's achievements. Focus is made on steps taken at the end of the project to ensure its sustainability. Discussions were held with the stakeholders in order to mobilise local resources and use less to achieve more in the light of dwindling donor support. In the meantime, resource mobilisation efforts are also on course and concepts notes were developed for that purpose. |
| Risk taking: Describe how the project has responded to risks that threatened the achievement of results. Identify any new risks that have emerged since the last report. (1500 character limit) | The project's risks and assumptions articulated at the conceptual stages of the project on different levels of impact and probability. With the mitigation measures that was put in place, project implementation progressed without notable disruptions. The project risks and assumptions were reviewed at the joint review meeting in Monrovia, where risks and assumptions that were found irrelevant were removed and others were revised to reflect prevailing situations. No new risks were identified up to the end of the project. |
| Gender equality: In the reporting period, which activities have taken place with a specific focus on addressing issues of gender equality or women’s empowerment? (1500 character limit) | The Project made a conscious effort to involve as many women/youth as possible in project activities such as the peace and security meetings, socio-cultural and sporting activities. The sporting activities comprised female and male football games, this was to ensure active involvement of women in these activities. Furthermore, the cross-border Trade Fairs were also dominated by the women, who are mainly engaged in informal cross border trade. Though, the project had strong security implications which were often dominated by men, it ensured the women groups had at least three women representatives compared to one representative initially. Women groups were also capacitated in entrepreneurship and business managerial skills together with the youth. The training was meant to enhance their analytical skills in identifying and exploring business opportunities in their localities. |
| Other: Are there any other issues concerning project implementation that you want to share, including any capacity needs of the recipient organizations? (1500 character limit) | None |

1.3 INDICATOR BASED PERFORMANCE ASSESSMENT: Using the Project Results Framework as per the approved project document or any amendments- provide an update on the achievement of key indicators at both the outcome and output level in the table below (if your project has more indicators than provided in the table, select the most relevant ones with most relevant progress to highlight). Where it has not been possible to collect data on indicators, state this and provide any explanation. Provide gender and age disaggregated data. (300 characters max per entry)

|  | Performance Indicators | Indicator Baseline | End of project Indicator Target | Current indicator progress | Reasons for Variance/ Delay (if any) | Adjustment of target (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 Increased confidence between security forces/agencies and border communities through enhanced capacity of joint local cross border mechanisms, as well as increased intra-/cross-border cooperation. | Indicator 1.1 Indicator 1a: % of community members identified in target areas indicating improved community safety and security. | Baseline TBD Target: TBD | 30% | About 90%. | Though no survey has been conducted, informal interactions with community members (at peace/security meetings, sensitization programmes and at the review meeting) have all been positive, expressing appreciation for the project's participatory approaches, resulting in improved cooperation/security. |  |
|  | Indicator 1.2 Indicator 1b: % of local authorities and traditional leaders who report having contributed to the peaceful resolution of conflicts. | TBD | 30% | About 60% | High participation of local leaders in planning and execution of project activities including peace/security meetings, expressing efforts made to resolve cross-border tensions and successes made, resulting in the prevailing peace. |  |
|  | Indicator 1.3 Indicator 1c: % community members from the identified target zone indicating an increase in confidence in security actors | Current confidence of the population in the security agencies is low due to harassment and their alleged engagement in illicit activities as per assessments conducted | Increased level of confidence in security agencies in 20 communities | Over 70% | Based on expressed appreciation by community members/leaders at peace and security meetings, sensitization campaigns and the recent review meeting for the improved trust and confidence in the security agencies due to their increased patrols, respect and cooperation with communities. |  |
| Output 1.1 Local authorities, security forces, border management agents and other key actors in border areas are trained and equipped on relevant issues/topics e.g. human rights, gender equality, child protection, conflict prevention, management and resolution. | Indicator 1.1.1 The Capacity of institutions and PoEs is enhanced, based on the findings of the needs assessment. | TBD | Capacity of at least 20 Ports of Entry (PoEs) enhanced. | About 50% operations capacity of 12 PoEs enhanced. | Provided logistical support & trainings to LIS, LNP and LDEA at 12 PoEs, and rehabilitation of 3 PoE are completed . |  |
|  | Indicator 1.1.2 Number of stakeholders trained Indicator 1.1.3 The number of conflicts resolved peacefully by border actors have increased Indicator 1.1.4 Number of institutions equipped and trained to use the new equipment. | 0 TBD Most border post lack the needed equipment to operate efficiently | At least 200 community leaders and security officers trained TBD 16 Institutions (local leaders, local government offices, police and border security agencies / forces) capacitated in the use of equipment | 565 members of the security forces, authorities and community leaders trained. Five (5) cases of conflict resolution were peaceful resoved. Equipment including motor bikes provided to LNP,LDEA, LIS, local leaders and security agencies and other border management authorities |  |  |
| Output 1.2 Relationships between security forces and communities including women, youth and vulnerable groups are enhanced through regular engagements and awareness campaigns on relevant issues: e.g. relevant laws, human rights, conflict resolution, social cohesion, peaceful coexistence & other relevant topics | Indicator 1.2.1 Number of dialogues and socio-cultural activities, involving security forces and populations held in target zones | 0 | 116 | 6 dialogues (3 per country) | The variance is due to participatory and innovative engagement of stakeholders during the joint security meetings organized by project teams, meetings of peace committees and other community structures to promote peace and social cohesion. |  |
|  | Indicator 1.2.2 Number of advocacy and IEC, materials, as well as radio programmes developed Indicator 1.2.3 Number of joint outreach initiatives supported | 0 | 18 radio broadcasts, 8,000 assorted IEC materials produced and disseminated 8 sporting/cultural activities including 2 cross-border; 15 joint clean-up for peace & trust-building activities | 14 radio broadcasts (7 per country) and 1 in Cote d'Ivoire, assorted IEC materials produced and distributed; 18 billboards located in the target communities. 10 organized sports and cultural activities 4 other cross-border organizations | The variation is due to differences in prices of various IEC materials such as billboards, fliers, T-shirts, etc. The following were procured: 40 slots radio jingles, 7 days call-in radio programs, 1,000 T-shirts (500 per county), 4 Billboards (2 per county), 200 fliers, project banners. |  |
| Output 1.3 Cross border security is enhanced through regular dialogues, relevant information sharing among appropriate institutions, and joint patrols by relevant institutions | Indicator 1.3.1 Number of cross-border security agencies/Forces engagement sessions | 0 | 12 joint cross border engagement sessions | 6 peace security meetings (3 per county) |  |  |
|  | Indicator 1.3.2 Number of joint patrols organized Indicator 1.3.3 Number of regular meetings held by the coordination platforms | 0 0 | 12 joint patrols 3 Joint coordination forums | 4 Joint cross border security patrols organised 3 joint coordination forums held | Two was done is Cote d'Ivoire side in Tabou and Tai and two in Liberia in Marlyand and River Gee Counties.The implementation of these activities required a long preparation between the two forces of both countries, given the organization structure of the insititution. |  |
| Output 1.4 | Indicator 1.4.1 |  |  |  |  |  |
|  | Indicator 1.4.2 |  |  |  |  |  |
| Outcome 2 Improved social cohesion and peaceful co-existence in cross border communities through cross border community dialogues and reinforcing of cooperation between existing local conflict resolution mechanisms strengthened by cross-border cooperative socio-economic stabilization and cultural exchanges | Indicator 2.1 % of community members from the identified target zones indicating reduction in tensions and enhanced inter-community conflict prevention. | 0 | 30% | About 90% | As indicated above, though no survey has been done, community members feedbacks have all been positive, expressing appreciation for the project's participatory approaches, resulting in reduction in tensions and enhanced inter-community conflict prevention. |  |
|  | Indicator 2.2 % of community members from the identified target zones indicating an increased level of confidence and social cohesion within and between communities. | 0 | 30% | About 80% | Again, community members feedbacks have all been positive, expressing appreciation for the project's participatory approaches, indicating an increased level of confidence and social cohesion within and between communities. |  |
|  | Indicator 2.3 |  |  |  |  |  |
| Output 2.1 Cross-border community stabilization and cohesion strengthened through joint socio-cultural activities | Indicator 2.1.1 Number of existing local EWER mechanisms (including peace committees) identified/established and functional in target areas | Some communities have established peace committees, while others do not have any. | Establish/strengthen EWER mechanisms including peace committees in all 24 project communities. | 16 peace committees established; and 16 of these committees equipped in conflict prevention and resolution. |  |  |
|  | Indicator 2.1.2 Number of conflicts resolved peacefully by local peace committees Indicator 2.1.3 Number of training sessions organized to capacitate the field monitors and county focal points on EWER mechanisms | TBD 0 | TBD 28 participants in total (26 monitors and 2 county focal points in total) | 35 conflicts settled peacefully by the peace committee set up and /or reinforced within the framework of the project. 16 trainings organised, 16 committee members trained. |  |  |
| Output 2.2 Cross-border community stabilization and cohesion strengthened through joint socio-cultural and economic activities | Indicator 2.2.1 Number of cross border trade fairs and cultural activities organized | 0 | Joint committee to facilitate organization of cross border activities set up | 2 CMC (Civil-Military Committees) set up |  |  |
|  | Indicator 2.2.2 Number of CBOs, including women and youth-based CBOs, involved in cross-border cultural exchanges and sporting activities. Indicator 2.2.3 Number of CBOs including women and youth based CBOs involved in cross border cultural | 0 0 | 4 cross-border trade fairs and sporting/cultural activities 20 | 23 peace protection committees have been strengthened and are involved in socio-cultural and sport activities 18 | While invitation was extended to all CBOs to participate in project activities 7 were most active in Liberia and 16 in Cote d'Ivoire. While invitation was extended to all CBOs, some ended up not actively involving in the community cross border cultural activities. |  |
| Output 2.3 | Indicator 2.3.1 Output 2.2 , Indicator 2.2.4 Biannual joint visits and review meetings ( one in Liberia and Cote D'Ivoire) to assess progress of work | 0 | 3 | 3 meetings held (April 2017, May 2018, September 2018) |  |  |
|  | Indicator 2.3.2 |  |  |  |  |  |
| Output 2.4 | Indicator 2.4.1 |  |  |  |  |  |
|  | Indicator 2.4.2 |  |  |  |  |  |
| Outcome 3 | Indicator 3.1 |  |  |  |  |  |
|  | Indicator 3.2 |  |  |  |  |  |
|  | Indicator 3.3 |  |  |  |  |  |
| Output 3.1 | Indicator 3.1.1 |  |  |  |  |  |
|  | Indicator 3.1.2 |  |  |  |  |  |
| Output 3.2 | Indicator 3.2.1 |  |  |  |  |  |
|  | Indicator 3.2.2 |  |  |  |  |  |
| Output 3.3 | Indicator 3.3.1 |  |  |  |  |  |
|  | Indicator 3.3.2 |  |  |  |  |  |
| Output 3.4 | Indicator 3.4.1 |  |  |  |  |  |
|  | Indicator 3.4.2 |  |  |  |  |  |
| Outcome 4 | Indicator 4.1 |  |  |  |  |  |
|  | Indicator 4.2 |  |  |  |  |  |
|  | Indicator 4.3 |  |  |  |  |  |
| Output 4.1 | Indicator 4.1.1 |  |  |  |  |  |
|  | Indicator 4.1.2 |  |  |  |  |  |
| Output 4.2 | Indicator 4.2.1 |  |  |  |  |  |
|  | Indicator 4.2.2 |  |  |  |  |  |
| Output 4.3 | Indicator 4.3.1 |  |  |  |  |  |
|  | Indicator 4.3.2 |  |  |  |  |  |
| Output 4.4 | Indicator 4.4.1 |  |  |  |  |  |
|  | Indicator 4.4.2 |  |  |  |  |  |

PART 2: INDICATIVE PROJECT FINANCIAL PROGRESS

  - Comments on the overall state of financial expenditures

Please rate whether project financial expenditures are on track, delayed, or off track, vis-à-vis project plans and by recipient organization:

How many project budget tranches have been received to date and when do you expect to request the next tranche if applicable: Two tranches

What is the overall level of expenditure/ commitment against the total budget and against the tranche(s) received so far: The two tranches of 70% and 30% planned were received totaling US$3,000,000 and the overall level of financial expenditure of the two countries is 98% to date.  The balance was utilised to contract one international and one national consultants who  prepared the final evaluation of the project. Details are provided in the finacial report in Excel.

If expenditure is delayed or off track, please provide a brief explanation (500 characters limit): NA

Please state what $ amount was planned (in the project document) to be allocated to activities focussed on gender equality or women’s empowerment and how much has been actually allocated to date: NA

Please fill out and attach the project document Excel budget Annex showing current project financial progress (expenditures/ commitments to date), using the original project budget table in Excel, even though the $ amounts are indicative only.

# Footnotes

Note: commencement date will be the date of first funds transfer.

Maximum project duration for IRF projects is 18 months, for PRF projects – 36 months.