SECRETARY-GENERAL’S PEACEBUILDING FUND

PBF PROJECT PROGRESS REPORT TEMPLATE

PBF PROJECT progress report

COUNTRY: LIBERIA

TYPE OF REPORT: semi-annual, annual OR FINAL FINAL

date of report: November 12, 2019

| Project Title: Reel Peace Project Number from MPTF-O Gateway: 109098 |
| --- |
| PBF project modality: IRF PRF | If funding is disbursed into a national or regional trust fund: Country Trust Fund Regional Trust Fund Name of Recipient Fund: Accountability Lab |
| List all direct project recipient organizations (starting with Convening Agency), followed type of organization (UN, CSO etc): List additional implementing partners, Governmental and non-Governmental: Visual Storytellers, Liberian TV, Liberia Film School, Leemah, Citizens’ Bureau |
| Project commencement date: February 28, 2018 to June 30, 2019 Project duration in months: 16 Months |
| Does the project fall under one of the specific PBF priority windows below: Gender promotion initiative Youth promotion initiative Transition from UN or regional peacekeeping or special political missions Cross-border or regional project |
| Total PBF approved project budget* (by recipient organization): Accountability Lab: $ 433,129.72 : $ : $ : $ Total: $ 433,129.72 *The overall approved budget and the release of the second and any subsequent tranche are conditional and subject to PBSO’s approval and subject to availability of funds in the PBF account How many tranches have been received so far: 4 |
| Report preparation: Project report prepared by: Accountability Lab Liberia Project report approved by: W. Lawrence Yealue II Did PBF Secretariat clear the report: Yes Any comments from PBF Secretariat on the report: YES and addressed Has the project undertaken any evaluation exercises? Please specify and attach: Yes, the Extenal Evaluation has been Completed and Submitted |

NOTES FOR COMPLETING THE REPORT:

- Avoid acronyms and UN jargon, use general / common language.

- Be as concrete as possible. Avoid theoretical, vague or conceptual discourse.

- Ensure the analysis and project progress assessment is gender and age sensitive.

PART 1: RESULTS PROGRESS

  - Overall project progress to date

Briefly explain the status of the project in terms of its implementation cycle, including whether all preliminary/preparatory activities have been completed (1500 character limit):

The Reel Peace project implementation was officially completed on 30 June 2019. Beyond the date mentioned, the project staff were engaged in gathering field activity reports for the development of a final report and the conduct of the program evaluation which measures its performance agaist the targets set.

Forty-five Liberian women (three from each of the fifteen political sub-divisions of the country) were selected, brought to Monrovia, trained/mentored in filmmaking by a team of professional filmmakers and communications experts. The female participants were selected through consultations in the counties involving local leaders and women groups including CSOs. The selection particularly focused on the work of the women in the counties, their interest in advocacy and the promotion of gender equity issues for women and girls in pursuit of peace and stability.

The project lasted for a period of sixteen months and produced fifteen films that were shown initially at the Reel Peace Film Festival organized in Monrovia. The films were also viewed in different parts of the country through the production and distribution of 300 DVDs reaching a recorded filming audience of 3,777 viewers in 70 community screenings and with discussions hosted at video clubs. These screenings brought together program participants, community members and leaders, local authority as well as civil society organizations. The project also developed a website and established a network of filmakers.

Considering the project’s implementation cycle, please rate this project’s overall progress towards results to date:

In a few sentences, summarize what is unique/ innovative/ interesting about what this project is trying/ has tried to achieve or its approach (rather than listing activity progress) (1500 character limit).

For the first time and at this scale, it's remarkable that local women are able to find their voice and actively participate in leadership and governance, articulating issues affecting their communities through filmaking. It is a known fact that women are visibly under-represented in differet aspects of leadership in this country including the media. The are rarely involved in key decision-making processes. And as such, training them in film-making, especially those from rural areas who are often excluded from important national conversations is a unique approach and adds a new perspective to the peacebuilding conversations in Liberia.

The Reel Peace project used an interesting approach of small intimate gatherings in order to get the most out of the participants. Convening small groups allowed for a safe space to engage on topics of interest to the women. These gatherings, coupled with training, gave them the space to build the confidence and creativity required to create content around complex themes, such as tribal divisions, education, maternal health, disabilities and harmful cultural practices. A number of them noted that while they covered sensitive, and even potentially dangerous topics, they felt strongly about the importance of telling their stories and were willing to go the extra mile to do so despite the risks.

In a few sentences summarize major project peacebuilding progress/results (with evidence), which PBSO can use in public communications to highlight the project (1500 character limit):

Forty-five women, mostly from rural areas with no prior filmmaking and or advocacy skills, now have both the confidence and skills to contribute to nation building initiatives. These skills acquired have provided for them and ultimately their communities, a sustainable way to add their voices to advocacy around peace and policy-making in spaces where they may not have been included prior to the project. In the program attachments, you will find their project contracts, training attendance records and photo and videographs.

A network of trained Liberian female peace filmmakers, called Women Filmmakers Netork (WFN), was established and includes all the filmmakers trained on the project. These women are now telling critical stories about the importance of peacebuilding and using their experience gained on the Reel Peace project. The network is active, has over members and serves as a platform to coordinate around peacebuilding and advocacy, promote peer-to-peer learning and mentorship, as well as, seek project opportunities for its members.

In addition to the training received by the 45 women and the filmmakers network formed (WFN), the project was also able to established a website to showcase the female artist talents and participation in governance and decision making processess. The web address is; www.reelpeacefilms.org

In a few sentences, explain how the project has made real human impact, that is, how did it affect the lives of any people in the country – where possible, use direct quotes that PBSO can use in public communications to highlight the project (1500 character limit):

In Bong, Margibi and Nimba counties, nine of the 45 women trained in advocacy skills and peacebuilding are involved in advocacy campaign that promotes the legal justic system and discourages the use of traial by ordeal. They are collaborating with other community stakeholders, especially influential community leaders using the skills gained.

Vanesa Seckie one of the women trained from Grand Bassa remarked, “I learned a lot from Reel Peace project. I was trained how to use the computer and camera in recording, something I knew nothing about before.

Another participant, Salina Doe from Sinoe said, “Reel Peace has really helped me a lot, they brought me to learn computer [skills] and now I can do something on my own computer.”

Elizabeth Kollison another participant from Lofa said the project is very good for the community. She stated that, “The benefit of the project is that sometimes when you tell the stories of the women in the community and send it to an organisation that can support them, any help they receive is an improvement in the community.”

If the project progress assessment is on-track, please explain what the key challenges (if any) have been and which measures were taken to address them (1500 character limit).

Internet Access: This remain a huge challenge especially during the raining season.  Most of the participants complained about accessing the internet or being able to acess the website fpr updates and information. They were encouraged to  sometimes involves them in traveling long distances to be able to get accsss to the internet.

Professional Renumeration from Mentorship Activities. It was reported that most of the professionals recruited to serve as mentors during the project and those experienced filmakers that joined the network were demanding some form of renumeration for film development services offered. To resolve this challenge, a WhatsApp group was created, enabling the trainees to follow up with both their mentors and the AL team directly.

Attrition rate: A few participants became less involved, because they moved on to obtain higher education or were involved in other activities that did not afford them the time to work on the project. To resolve this, we found alternative ways to keep them engaged. For example, we asked them to select schedule that suits them to go in the field. If there was no commitment, we replaced them with other active community members, who were given training.

If the assessment is off-track, please list main reasons/ challenges and explain what impact this has had/will have on project duration or strategy and what measures have been taken/ will be taken to address the challenges/ rectify project progress (1500 character limit):

NA

Please attach as a separate document(s) any materials highlighting or providing more evidence for project progress (for example: publications, photos, videos, monitoring reports, evaluation reports etc.). List below what has been attached to the report, including purpose and audience.

1. External Evaluation Report
2. Other supporting Documents

i. Film Screening Attendance List

ii. Participants and Consultant Contracts

iii.Film Distribution List

iv. Videos and Audios

v. Photos
3: Policy document for each of the 15 counties

4. Policy Statements:

i. Women in Cross Border Trade

ii. Tribal Divide: The Case of Sapo & Kru

iii. The Plight of Less Privileged females (zogos) in Monrovia

  - Result progress by project outcome

The space in the template allows for up to four project outcomes. If your project has more approved outcomes, contact PBSO for template modification.

Outcome 1:  A network of trained Liberian female peace film makers who can work over time to tell critical stories about the importance of peacebuilding in Liberia.

Rate the current status of the outcome progress:

Progress summary: Describe main progress under this Outcome made during the reporting period (for June reports: January-June; for November reports: January-November; for final reports: full project duration), including major output progress (not all individual activities). If the project is starting to make/ has made a difference at the outcome level, provide specific evidence for the progress (quantitative and qualitative) and explain how it impacts the broader political and peacebuilding context. Where possible, provide specific examples of change the project has supported/ contributed to as well as, where available and relevant, quotes from partners or beneficiaries about the project and their experience. (3000 character limit)?

All 45 women from 15 political sub-divisions of Liberia (3 participants per county) received training in film making, interview techniques, editing and effective advocacy. These skills were used to produce 15 short films as part of this project deliverables. The films highlighted the various issues that affect women both in rural and urban Liberia. ALab established a network of filmmakers to keep participants connected and engaged. Participants have used the platform to share information and seek advice about their professional for growth and advancement.

Further, visual storytelling through film has enabled project participants to share experiences, challenges, lessons learned and provide input around the country they wish to see in a non-violent, inviting manner. The project led to mass dissemination of intriguing stories reaching communities across Liberia. The project impacts the broader political and peacebuilding context by equipping women with the skills to share their communities’ stories, and specifically the voices of the most marginalized. It adds a variety of voices, including women from rural areas, to political and peacebuilding conversations by providing a safe space for conversation that allows women to grow more confident in their ability to express themselves.

One of our participants, Patience Baye Koromah from Zwedru, of Grand Gedeh County expressed the value of the program as follows: “I embrace the idea of Reel Peace coming to identify women’s problems, to find solutions by bringing out the voices of the voiceless, making women’s voices to be heard".

The Reel Peace project conducted a final evluation of the program's activities and achievements. The final evaluation which will be annexed to this report captured the extent to which the program accomplished its overall goal, built the capacities of women around the country to empower them through increased skills, self-confidence, to meaningfully participate and contribute to the country’s national reconciliation and peacebuilding efforts. It pointed to the impact of human efforts as well as the sustainability of the skills gained. It identified the elements of the program that best contributed to that goal and any elements that made the goal more difficult to realize.

Outcome 2:  Liberian women have greater impact and influence on policy-making processes as it relates to gender, peace and stability in Liberia

Rate the current status of the outcome progress:

Progress summary: (see guiding questions under Outcome 1)

All forty-five Liberian female filmmakers have been trained in advocacy and peacebuilding. They have also been trained in gender euity related issues, particularly to girls and women. The overall purpose of the trainings have been to: 1) acquire meaningful skills and tools to be able to adequately assess in a given context, the needs of men, women, boys and girls; and 2) develop advocacy strategies involving collaboration and community stakeholders buy-ins to influence decision-making in their various communities as it relates to gender, peace and stability.

The 15 films produced during this reporting period provide participants with tangible advocacy tools. Our team is working alongside the women to ensure that these films and accompanying policy documents reach power holders and is continuously following up to show substantive results even after the end of the project.

As already mentioned, there are are nine women who are also currently championing the abolishment of trail by ordeal in 3  (Bong, Margibi and Nimba) of the 15 counties in Liberia. They are conducting town hall meetings, meeting influential stakeholders, developing podcasts and hosting talkshows raising the awareness of the harmful effects of the trials.

In addition participants took part in a number of radio shows in Monrovia, where they had the opportunity to talk about their work and advocate for change on air.  Some of the radio stations they visited include;

1. Fabric FM (101.1)

2. OK FM (95.5)

3. Radio Maria (87.9)

4. Power FM (93.3)

5. Sky FM - 50-50 (107.1)

6. ELBC - Super Morning Show (99.9)

Outcome 3:  Increased awareness and support among the Liberian and global populations of the critical role of women in peacebuilding in Liberia.

Rate the current status of the outcome progress:

Progress summary: (see guiding questions under Outcome 1)

WFM network continues to exist beyond the project span. Beneficiaries (87%) have become career film producers, which is an indicative continuation of the project objectives. The filmmakers network established with significant inputs by local authorities is a platform for continuously recruiting talents. Accountability Lab and these local authorities are poised to ensuring the survival of the network.

The primary focus of the Reel Peace Project was working with women to develop new and innovative skills that spur and strengthen women's active participation in promoting national peace and stability. The role of peacebuilding and stability is cardinal especially at a time when the Liberian government has assumed responsibility for national security following the drawdown and departure of UNMIL. Throughout the implementation of the project, the WFMs conducted awareness through the electronic media using dramas, community town criers and focus group discussions to talk about the various peacebuilding issues such as trial by ordeal, the impact of circumcision on girls’ education, abandonment and neglect, women’s property rights especially in traditional marriage among other sensitibution to the growth of society. As the project continued, the women met various stakeholders to continue awareness about the critical role of women in peacebuilding. The participation of the women, some of whom were media practitioners, contributed to the overall achievements of the project, thereby promoting and sustaining the peace. To maintain the momentum of project, some of these women were well-positioned to continue the conversation even in the absence of project funding.

The role played by the project to sensitize powerholders on its importance built relationships and ensured that the content, advocacy and policy tools created to get the right audience and have an impact beyond the parameters of this project.

The film festival reached a large and diverse audience. Additionally, featuring the films on  a website (www.reelpeacefilms.org) will create international exposure. Accountability Lab partnered with the Bushwick Film Festival (BFF), an annual festival in Brooklyn, New York, to spark international conversations around the films. In addition to assisting with the promotion of the festival in Monrovia, BFF aired the best films in New York in October 2019. Please see an example of the film's marketing campaign here: https://tinyurl.com/y528rugh .

A Women Advocacy Network has also been built around Trials By Ordeals in 3 Counties: Nimba, Bong and Margibi with 12 Women (4 from each county) through a community justice program, Canadian Fund Local Initiatives (CFLI).

Outcome 4:  N/A

Rate the current status of the outcome progress:

Progress summary: (see guiding questions under Outcome 1)

N/A

  - Cross-cutting issues

| National ownership: How has the national government demonstrated ownership/ commitment to the project results and activities? Give specific examples. (1500 character limit) | The Reel Peace project engaged and work with majoor national stakeholders. The project worked with the Ministry of Gender, Children and Social Protection at national and county levels including superintendents, city mayors as well as county peacebuilding committee leaders to get their buy-in for ownership and sustainability. These meetings with the leaders also highlighted the need for collaboration on gender and peacebuilding related issues. The Ministry of Gender, County officials, and the County Peacebuilding Committee Chairpersons committed to sustain the impact of project. County Gender Coordinators of the Government played a meaningful role in the production of the films, including granting interviews to the mentees. |
| --- | --- |
| Monitoring: Is the project M&E plan on track? What monitoring methods and sources of evidence are being/ have been used? Please attach any monitoring-related reports for the reporting period. (1500 character limit)? | An M&E plan was developed at the beginning of the project and updated in January 2019 and implemented through the duration of the project. The participants training experiences were tracked through surveys, testimonial evidence from the women, and measured county team’s progress based on reports from the mentors and professional filmmaker who engaged with the women to edit their final products. Examples of methods used to assess teams progress include: • Transcription • Field reports • Film festival attendance • Participants in Action Photos Film Festival Photos |
| Evaluation: Provide an update on the preparations for the external evaluation for the project, especially if within last 6 months of implementation or final report. Confirm available budget for evaluation. (1500 character limit) | A Terms of Reference was developed and finalized to recruit a consultant to conduct a final evaluation of the project. The vacancy for an external evaluator was advertised for two weeks and the manager of the project at ALab received several applications from the public. Media Foundation for Accountability and Transparency was hired in a petitive process to conduct the evaluation. The evaluation was concluded after closure of the project and the report submitted. The consultant was paid the full amount of Three Thousand, Five Hundred United States Dollars (U$3,500.00), which was lower than PBF's requirement of between 5-7% of the project budget. The evaluation report was shared with the PBF Secretariat and UNPBF. |
| Catalytic effects (financial): Did the project lead to any specific non-PBF funding commitments? If yes, from whom and how much? If not, have any specific attempts been made to attract additional financial contributions to the project and beyond? (1500 character limit) | There has been a commitment of US$10,000 from European Union used to hold a film festival in December 5-6 2019. The film festival help informed the 16 days of activism against gender and sexual abuse of women and girls. Five films from the 15 films were screened on gender and advocacy. |
| Catalytic effects (non-financial): Did the project create favourable conditions for additional peacebuilding activities by Government/ other donors? If yes, please specify. (1500 character limit) | Over time, the project engagement with local county officials, county peacebuilding committee chairpersons and the Ministry of Gender, Children and Social Protection grew. This has led to further opportunities and collaboration. At the close of the project, the necessary tools related to the films and policy documents were created, which can be used to reach and influence Liberian powerholders are: (1) Involvement of rural women who have proximity to traditional leaders and are able to influence the decisions of these leaders to call for change. (2) Strong visual representations of the challenges women face in post-conflict Liberia, as well as the ways in which they worked to uplift their communities and country; (3) A network of media filmmakers who are able to act as advocates for their communities, and through this program are connected through shared social media spaces and the network website (4) A set of policy documents / inputs that can be shared with powerholders by women, with the support of the Accountability Lab and other civil society organizations within our network. |
| Exit strategy/ sustainability: What steps have been taken to prepare for end of project and help ensure sustainability of the project results beyond PBF support for this project? (1500 character limit) | At first, the project started with a network of three women per county but was later clustered to create a national network of women film makers. The project has an established WhatsApp chat room that keeps the participants together and also a web page. They used this medium to share their work, ideas and challenges and successes made on individual fronts. Even when the project ended, these women are stay connected through these platforms. Participants have gained transferable skills and knowledge like film making, editing, post-production, advocacy techniques to women who participated in the project. These women have continue to use these skills and knowledge to engage the community, gather stories and amplify the voices of women. |
| Risk taking: Describe how the project has responded to risks that threatened the achievement of results. Identify any new risks that have emerged since the last report. (1500 character limit) | As mentioned in the other report about Kathleen Flynn’s, lead trainer, involvement in a documentary in Liberia was the biggest risk in January 2019. This was resolved with the recruitment of Chris Peters to replace Kathleen as lead trainer for filmmakers (45 women). Another risk that threatened the project was the June 7, 2019 national citizens protest organized by Council of Patriots (COP). The National Women Film Festival was initially planned for June 7, 2019; unfortunately for Accountability Lab Liberia, the COP selected the same date. Some citizens were worried about the protest and felt the peace would be threatened. The date of the festival as therefore changed to the 5th and 6th of June and vigorous mobilization was done, from house to house and through media publicity to get people to attend the film festival on the 5th & 6th of June, |
| Gender equality: In the reporting period, which activities have taken place with a specific focus on addressing issues of gender equality or women’s empowerment? (1500 character limit) | The project was focused on Women empowerment. The emphasis was to bridge the gap in female participacipation in media related activities. The skills developed and knowledge transferred to them for film making can be used as a source of employment and empowerment. During a short discussion with some of the film makers, they said they want to be photo journalists, videographers, advocates and actresses. Many women, like Salina Doe from Sinoe said if the project is over she will continue advocating. This is what she said, “If the project is over I won’t just stop. I will not just stop in computer school. I will take my own money and buy camera. From there on we will join activism [advocacy].” |
| Other: Are there any other issues concerning project implementation that you want to share, including any capacity needs of the recipient organizations? (1500 character limit) | We did conclude all stages within the project cycle and all activities were completed. |

1.3 INDICATOR BASED PERFORMANCE ASSESSMENT: Using the Project Results Framework as per the approved project document or any amendments- provide an update on the achievement of key indicators at both the outcome and output level in the table below (if your project has more indicators than provided in the table, select the most relevant ones with most relevant progress to highlight). Where it has not been possible to collect data on indicators, state this and provide any explanation. Provide gender and age disaggregated data. (300 characters max per entry)

|  | Performance Indicators | Indicator Baseline | End of project Indicator Target | Current indicator progress | Reasons for Variance/ Delay (if any) | Adjustment of target (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 A network of trained Liberian female peace film-makers able to tell critical stories about the importance of peace-building in Liberia. | Indicator 1.1 a- Network of women film-makers | 0 | A Women Female Network (WFM) of filmmakers was established and included all 45 women | 100% | NA | NA |
|  | Indicator 1.2 Outcome Indicator 1 b: Number of women who indicate, and can demonstrate that the network has been beneficial to their individual project | 0 | 45 Women (Final Evaluation Report) | 100% | NA | NA |
|  | Indicator 1.3 Outcome Indicator 1c: Number of women who indicate an increased understanding of peacebuilding | 0 | 45 | 100% |  |  |
| Output 1.1 45 women trained in film-making | Indicator 1.1.1 Number of women trained in film-making | 0 | 45 | 100% |  |  |
|  | Indicator 1.1.2 Number of women trained in editing | 0 | 45 | 100% |  |  |
| Output 1.2 Ongoing mentorship, support and feedback to the film-makers | Indicator 1.2.1 Women supported to develop films | 0 | 45 | 100% |  |  |
|  | Indicator 1.2.2 Number of women who indicate that the mentorship has improved their Indicator 1.2.3 Women receive advice from professional film-makers on film making | 0 | 33 | 73.% | All participants were partnered with a mentor, but managing mentors remotely over the span of a long project and ensuring constant contact with all the teams has been challenging. 33 out of 45 women reported that they've built skills through mentorship. |  |
| Output 1.3 15 films on issues of peace and gender | Indicator 1.3.1 # of film storyboards | 0 | 15 | 15 | The remaining 5 storyboards along with films were produced and delivered |  |
|  | Indicator 1.3.2 # of 1st drafts of films | 0 | 15 | 100% |  |  |
| Output 1.4 | Indicator 1.4.1 | 0 |  |  |  |  |
|  | Indicator 1.4.2 | 0 |  |  |  |  |
| Outcome 2 45 Liberian women empowered with tools to positively impact and influence the policy making process as it relates to gender, peace and stability | Indicator 2.1 a % number of women who indicate that they have a better understanding of the policy environment | 0 | 45 | 100% |  |  |
|  | Indicator 2.2 # of film-makers who participate in issue-related policy discussions | 0 | 45 | 100% |  |  |
|  | Indicator 2.3 # of policy shifts as a result of training | 0 | 2 | 0 |  |  |
| Output 2.1 Training of 45 women on policy advocacy techniques | Indicator 2.1.1 # of Women trained on advocacy techniques | 0 | 45 | 100% | 45 film makers received training in Advocacy techniques. |  |
|  | Indicator 2.1.2 # of provincial advocacy campaigns on an issue chosen by the women | 0 | 3 | 100% |  |  |
| Output 2.2 90 film showings and community conversations about the films nationally including at least 60 local power-holders | Indicator 2.2.1 # of film showings in target communities | 0 | 90 | 100% | All 15 counties has been engaged with the screening. The showing were achieved. |  |
|  | Indicator 2.2.2 # community dialogues with power-holders | 0 | 70 communities | 100% | Community screenings were completed and the target were reached by the end of the project. |  |
| Output 2.3 15 Reel Stories Policy Agenda Documents to be used as inputs for decision-making | Indicator 2.3.1 Reel Stories policy agenda resource documents produced on key issues | 0 | 15 | 100% | The 15 policy documents were produced. |  |
|  | Indicator 2.3.2 Agenda documents used as a resource for decision-making | 0 | 15 | 100% |  |  |
| Output 2.4 | Indicator 2.4.1 |  |  |  |  |  |
|  | Indicator 2.4.2 |  |  |  |  |  |
| Outcome 3 Increased awareness and support among the Liberian and global populations of the critical role of women in peacebuilding in Liberia. | Indicator 3.1 a % of Liberians who indicate an increased knowledge of the key issues as a result of watching the films | 0 | 10 | 33.6% | Community screenings completed and the project gathered feedback from 174 viewers who expressed learning something from the films screened. |  |
|  | Indicator 3.2 # of international mentions of issues highlighted in films | 0 | 3 | 3 | Medium-www.medium,com, Bushwick-www,bushwickfilms.com, Brookly Film Festival-www,indingoink.net |  |
|  | Indicator 3.3 A dedicated project website with all films | 0 | 1 | 100% | Completed. www.reelpeacefilms.org |  |
| Output 3.1 Film CDs distributed and played in 300 video clubs around the country, with conversations around the issues | Indicator 3.1.1 CDs produced with the films | 0 | 300 | 100% | Completed |  |
|  | Indicator 3.1.2 Films played in video clubs | 0 | 300 | 100% | Community screenings were fully completed by the end of the project cycle. |  |
| Output 3.2 A national 2 day women’s film festival with 1000+ attendees | Indicator 3.2.1 National film festival took place | 0 | 1 | 100% | A successful film festival was held in Monrovia City Hall and iCampus. |  |
|  | Indicator 3.2.2 Attendees over 2 days | 0 | 1000 | 52% (517) | The festival had less attendees than expected, as tensions around the June 7th protests led to people staying home. The protest also had an impact on power holders and policy makers invited to the event, as a number of them withdrew at the last minute. |  |
| Output 3.3 Output 3.3- A dedicated project website with all films | Indicator 3.3.1 Website created | 0 | 1 | 100% |  |  |
|  | Indicator 3.3.2 Films uploaded on website | 0 | 15 | 100% | The films were all edited, with subtitled and uploaded to the Reel Peace website: www.reelpeacefilms.org |  |
| Output 3.4 | Indicator 3.4.1 |  |  |  |  |  |
|  | Indicator 3.4.2 |  |  |  |  |  |
| Outcome 4 | Indicator 4.1 |  |  |  |  |  |
|  | Indicator 4.2 |  |  |  |  |  |
|  | Indicator 4.3 |  |  |  |  |  |
| Output 4.1 | Indicator 4.1.1 |  |  |  |  |  |
|  | Indicator 4.1.2 |  |  |  |  |  |
| Output 4.2 | Indicator 4.2.1 |  |  |  |  |  |
|  | Indicator 4.2.2 |  |  |  |  |  |
| Output 4.3 | Indicator 4.3.1 |  |  |  |  |  |
|  | Indicator 4.3.2 |  |  |  |  |  |
| Output 4.4 | Indicator 4.4.1 |  |  |  |  |  |
|  | Indicator 4.4.2 |  |  |  |  |  |

PART 2: INDICATIVE PROJECT FINANCIAL PROGRESS

  - Comments on the overall state of financial expenditures

Please rate whether project financial expenditures are on track, delayed, or off track, vis-à-vis project plans and by recipient organization:

How many project budget tranches have been received to date and when do you expect to request the next tranche if applicable: 4

What is the overall level of expenditure/ commitment against the total budget and against the tranche(s) received so far: 100%

If expenditure is delayed or off track, please provide a brief explanation (500 characters limit):  NA

Please state what $ amount was planned (in the project document) to be allocated to activities focussed on gender equality or women’s empowerment and how much has been actually allocated to date: 100%

Please fill out and attach the project document Excel budget Annex showing current project financial progress (expenditures/ commitments to date), using the original project budget table in Excel, even though the $ amounts are indicative only.

# Footnotes

Note: commencement date will be the date of first funds transfer.

Maximum project duration for IRF projects is 18 months, for PRF projects – 36 months.