## ProjectSchedule
Empowering Yemeni youth towards peace: ensuring access to information and participation
GANTT Chart June-December 2020
|  |  | June | July | August | September | October | November | December
Activities | PROGRESS | DAYS
#REF!
UNPB Project activities |  | #REF!
Identify software and personnel needs, identify training needs
Carry out consultations with youth and journalists
Develop a youth and gender-sensitive content strategy on the platform focused on peace building including analysis and mapping of understanding of the peace building process among young women and men |  | #REF!
Create or optimize a website page dedicated for the project that will host multimedia materials targeting the youth and focused on peace-building coverage | 60% | #REF!
Produce at least 14 Arabic gender and youth-sensitive multimedia materials focused on peacebuilding (7 written, 7 video) | 50% | #REF!
Organize a ToT for 10 Journalists
Organize at least 5 trainings of local trainers with at least 10 trainees per training (total of additional trained journalists is at least 50 | 25% | #REF!
Develop editorial guidelines for information sharing on the platform and guide the young journalists in producing content
Produce 126 content pieces (articles, essays, cartoons) (28 from each governorate of the 5, 50% by women) 42 in 2020
Produce 10 videos
Social media moderation and digital marketing
Produce 8 VR videos
Launch at least 2 open calls for submissions with the aim of obtaining at least 20 solutions
Organize a committee to evaluate the initiatives and provide logistical support to facilitate the selection process
Film and produce at least 14 “My Solution” video series with at least 50% of videos feature solutions developed by women.
Develop surveys methedology
launch 6 online surveys and 6 social media listening projects to understand youth priorities and narratives on PB
12 Media reports on survey results
Develop debating toolkit to support youth in debating peace- building. The toolkit should include code of conduct
ToT on using the toolkit |  | #REF!
Launch and organize a series of at least 5 trainings for youth on debating
Organize at least 5 youth debates with at least 200 youth participating
Training for community radios on youth engagement
Quarterly narrative report on outputs and outcomes
Events evaluation reports
Quarter Financial reporting + progress reporting
Designs for all platforms and events
#REF!
Insert new rows ABOVE this one |  | #REF!