## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) Report must be a well-written, succinct summary about what was done during the reporting period and results achieved, prioritizing on concrete activities, beneficiaries reached, and achievements beyond processes; b) Report must be factual and evidence-based against the outcome and output indicators presented in the original project document; c) In case certain indicators are no longer relevant, report must provide an explanation therefor; d) Report must explicate how it is in line with the overall SERP joint workplan and its relation to the global-level SERP indicators; e) Report must indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project; f) Report must include a honest analysis of challenges faced, the responses to these challenges, and the extent to which these responses were successful or unsuccessful; g) Reporting must go beyond the generic, standard and well-documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and what could enable replication efforts.
3 | Please complete and submit this workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). If you are unsure of your project number, please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31st of January 2021
4 | Complete annual report must be submitted for ALL projects receiving funds in 2020. HOWEVER, if your project ends on the 31st of December 2020, your FINAL report is your annual report.
5 | If you received a no-cost extension for your project, please provide an annual report. You may update the annual report in a few months time to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework for your report here as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31st of January 2021
7 | Complete annual report must be submitted for ALL projects receiving funds in 2020. HOWEVER, if your project ends on the 31st of December 2020, your FINAL report is your annual report.
8 | Please make sure you use the RBM framework for your report here as per your approved Prodoc.

## General Information-Annual
Programme Title & Project Number |  | Programme Duration
Programme Title: | Protecting People: Supporting the Government of Indonesia and Key Stakeholders to Scale Up Inclusive Social Protection Programmes in Response to COVID-19 | Overall Duration (months) | 10 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 01.05.2020
MPTF Office Project Reference Number: | 121443 | Original End Date (dd.mm.yyyy) | 31.12.2020
Country | Indonesia | Current End date (dd.mm.yyyy) | 31.03.2021
Recepient UN Organizations |  | Implementing Partners
Organizations receiving direct funding from the MPTF Office under this programme | UNICEF, UNDP, WFP, and UN WOMEN | National counterparts (government, private sector, NGOs, & others) and other International Organizations | BAPPENAS, Ministry of Social Affairs, Ministry of Agriculture, Ministry of Finance, Ministry of Women Empowerment and Child Protection, Ministry of Villages, Development of Disadvantaged Regions, and Transmigration, CARE Indonesia, University of Indonesia, University of Padjajaran, and Bogor Agriculture Institute
Report Cleared by
o Name: | Valerie Julliand
o Title: | Residence Coordinator
o Email address: | valerie.julliand@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF/JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Annual
# | Questions | Guidance to Respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results as well as any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (maximum up to 500 words). | From May to December 2020, under the leadership of UN Resident Coordinator, UNDP, UNICEF, WFP, and UN WOMEN supported the government in rolling out social protection programmes that are more effective (reaching the most vulnerable with limited inclusion and exclusion errors) and truly inclusive (leaving no one behind). There are at least four main strategic results that were achieved in 2020: First, the UN played the key roles behind the national programme namely Unified Database Update (UNICEF-UNDP). This database registers the bottom 40% of populations eligible for social protection programme in Indonesia. The UN advocated the registration of homeless people and/or people without formal registration to the database. The UN also promoted inclusive approach during the update of the database namely by involving the community in the nomination and validation of the beneficiaries for social protection programme. This initiative would ensure no one is left behind. The support has also facilitated the government to develop the Standard Operating Procedures (SOP) for the Grand Design of Socioeconomic Registration for Social Protection. This SOP will be the reference for the government to improve the coverage of social protection programme from 40% to 60%. Secondly, in other initiative, the UN strengthened the expenditure tracking mechanism both at the national and sub-national levels by providing better information on the analysis of public funding for children–one of the population groups with the highest risk of exclusion from social protection. Thirdly, as part of the innovative data analysis, WFP strengthened the methodology of VAMPIRE, a cloud-based Platform of risk and vulnerability assessment related to climate hazard by combining near real-time evidence of vulnerability and socioeconomic impacts of the current and future pandemics. This platform allows for monitoring and analysis on the vulnerability and impacts caused by pandemics. Fourthly, the UN advocated that the social protection response during COVID-19 pandemic should be gender responsive and respond to the needs of women and children. UN Women has been playing a key role in using the data inovation combining big data and quantitative and qualitative surveys to produce a rapid assessment of the COVID-19 impacts on gender including impacts on women-owned micro and small businesses. It has led a pilot initiative on gender-responsive cash for work programme targeting female beneficiaries who have been adversely impacted in the garment industry. UN Women supported the Ministry of Women Empowerment and Child Protection (MoWECP) as well as CSO engagement in strengthening essential services for women and children experiencing violence during the COVID-19 pandemic as part of the comprehensive social protection package under the UN COVID-19 MPTF. The project has been able to facilitate adaptation of service provision to the vulnerable populations especially children in context of COVID 19 pandemic and capacity building of frontline workers.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached, and disaggregate the data by gender, age, and any other groups. | The programme has reached direct beneficiaries up to 443,160 individuals with the details as follows: (1) Mapping of the vulnerable children in institutional care: 359,818 children (Girls:178,570; Boys: 181,248) (2) Identification of the vulnerable children in West Nusa Tenggara: 171 children (G: 82; B: 89) (3) Gender-responsive cash for work programme: 300 women (4) Training on Case Management, Psychosocial Support, Self-Care, and Ethical Dilemma for Social Workers: 852 individuals (F: 472; M: 380) (5) Training on Social Service Provision for Social Workers (psychological first aid and counselling, facilitation skills, ethics, case management, identification of vulnerable children and families, and Prevention of Sexual Exploitation and Abuse and Gender-Based Violence): 1,985 individuals (F: 1,241; M: 744) (7) Training for Parents and Caregivers on Good Parenting, PHBS, and Prevention of VAC: 1,337 individuals (F: 810; M: 527) (8) Dissemination of Learning Kit for Public Communication by MoSA: 78,697 individuals The indirect beneficiaries of the programme include those of the current and expanded social protection programmes for COVID-19, comprising 10 million households receiving unconditional cash transfers (PKH); 20 million households receiving food assistance programmes (Kartu Sembako); and 11.6 million households receiving Village Cash Transfer.
3.1 | Results: Outcome Level | Please include outcome level results achieved. | The UN's intervention has contributed to the improvement of more effective and inclusive social protection programme in the country by reaching the most vulnerable populations (i.e. by mapping and registration of children in the unregistered instititutional care, reaching women in garment industry that are deeply affected by the pandemic, advocating the enrollment of homeless people and/or people without formal registration in regular social protection programme, advocating inclusive process during the update of unified database, and improving the Unified Database of Social Protection). The programme has introduced innovative data analysis to better inform the socioeconomic impacts of the pandemic to the government through the use of big data in the assessment of socioeconomic impacts of pandemic on women. This also includes strengthening PRISM, a cloud-based platform to monitor and detect the socioeconomic impacts of the pandemic.
3.2 | Results: Output Level | Please include output level results achieved. | Overall, the JP has achieved three main outputs: (i) the government and key partners have enhanced policy and capacity to scale up and expand social protection coverage and fiscal space to include the affected and marginalised populations, particularly women and children from marginalised groups (ii) the COVID-19 Task Forces, volunteer mechanism operating under the Ministry of Social Affairs (MoSA) at the national and sub-national level, have increased capacity to plan, communicate, build partnerships, and deliver social protection response to COVID-19 crisis; and (iii) the adoption of data analysis as well as financial and digital innovations to better inform the government on effective gender-responsive social protection has been promoted. Specifically, the JP has generated the following outputs: (1) The capacity of 4767 social workers to deliver social protection has been strengthened (2) Two integrated rights-based, equitable, and gender-responsive policy solutions including umbrella guidelines and protocols for protecting the rights of women and girls during the COVID-19 pandemic have been developed and GBV services have been integrated into the social protection policy and response (SOPs on the Grand Design of Socioeconomic Registration for Social Protection, mapping of the vulnerable children and women affected by the COVID-19 pandemic, and link to access social support including that for children in institutional care/orphanages (there are 5,505 institutions, 1,804 of which are unregistered)). Total children identified: 349,841 (Girls:172,941; Boys: 171,397) (3) 2 nationwide surveys on socioeconomic impacts of the COVID-19 pandemic as well as the COVID-19 impacts on gender have been facilitated (4) 300 beneficiaries in West Java have received cash for work programme focusing on value chain and entrepreneurship development programme (5) The capacity of COVID-19 task forces at the national and sub-national level has been strengthened in Central Java, East Java and West Nusa Tenggara (6) The methodology of VAMPIRE, a cloud-based platform, namely by combining the near real-time evidence of additional vulnerability imposed by the socioeconomic impacts of the current and future pandemics has been strengthened. This platform ensures that such impacts are detected and monitored. (7) The government has been facilitated to adopt mobile data collection (mVAM) to assess and monitor food security in hard-to-reach areas, during pandemics and other crises (8) Policy framework in the context of COVID-19 pandemic related to service provision for vulnerable children, especially children in institutions has been improved (9) The use of data innovation and technology to produce new evidence-based policy recommendations by conducting face-to-face survey, commencing Interactive Voice Response (IVR) Household survey on Socioeconomic Impact of COVID-19 with 17,000 respondents has been promoted and a report on the COVID-19 impacts on gender has been launched under the collaboration with INDOSAT Ooredoo (10) Policy research “Leveraging Digitalization to Cope with COVID-19 Pandemic: Indonesia Case Study on Women-owned Micro and Small Businesses” which contitutes an innovative initiative as it employed data and technologies that combine big data analysis as well as quantitative and qualitative surveys to assess the impact of COVID-19 pandemic on micro and small businesses from gender perspective have been produced. This report gives important insights into how Indonesia can leverage digitalization to support women entrepreneurs to survive the pandemic. It calls for the government stimulus packages to have greater focus on women-owned micro and small business in COVID-19 response and recovery.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken. | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them. and changes introduced (any course of corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words). | Looking into the expectations of the programme and the time pressure of implementation, there were some challenges faced during the production of COVID-19 MPTF outputs, namely: 1. Coordination has been proven to be challenging within the government i.e. between line ministries, from central to sub-national/local level governments. as well as among various partners outside of the government. The government's intention to expand the involvement of ministries and agencies in the programme has triggered questions not only among UN agencies but also within the newly appointed ministries in charge. At the initial stage, there were 8 ministries & agencies listed as government partners. In September, the UN received proposal from the government to incorporate additional 9 ministries and agencies into the programme. On one side, the UN appreciates the intention of National Development Planning Agency (BAPPENAS)–as the coordinating ministry–to enrich the programme by engaging more ministries and agencies in the COVID-19 MPTF; however, this has triggered questions not only among the UN organizations but also the newly appointed ministries. Some ministries are questioning to what extent they could contribute to the programme. This concern is also shared by the agencies asking for more clarity on the expected engagement and contribution. In mitigating the risk, the UN and the government plan to discuss in more detail the expectation and contribution for the additional 9 ministries to each of COVID-19 MPTF lower-level output. 2. Social protection response of the government traditionally focused on mitigating immediate income risks and poverty reduction. Addressing structural inequalities, particularly gender inequality, is generally not the primary objective of the social protection interventions. There are still challenges to ensure that eligibility criteria and the beneficiary selection/targeting process take into account other types of social vulnerabilities in the design and implementation of social protection response, which have gaps in inclusion and exclusion errors. The UN has been pushing for a more inclusive and gender-responsive social protection. It also requires stronger ownership and engagement from the government to continue to drive this agenda forward. 3. The COVID-19 pandemic is a force majeure which leads to unprecedented measures. This pandemic has been affecting not only different life sectors but also the way people work. Due to precautionary measures such as travel restriction and large events cancelation, the programme has been implemented virtually. As the consequence, some activities took longer than expected and the dominant interventions include conducting studies and assessment.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic, and/or operational lessons or findings from the programme that could inform similar responses at country or global level. Please focus on the knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) and include reflections on the implementation of gender markers and any impacts they have had on programming quality and results (up to 500 words). | The JP worked to ensure the scale-up of inclusive social protection programme in response to COVID-19 pandemic in Indonesia. During the pandemic, the government expanded the social protection programme by redirecting and retargeting the existing social protection programmes including launching different new programmes to provide safety net for the most affected populations. The JP aimed to support the government by filling the gap appearing due to the absence of updated unified database, lack of interlinkage with civil registration database, and minimum monitoring system as well as programme assessment for the COVID-19 expanded social protection programme.  For the purpose of identifying the alternative/innovative schemes to augment GoI’s social protection, the JP has initiated the innovative financing study for social protection programme in two target provinces and undertaken further engagement with private sector as well as philanthropic and religion-based organizations to explore their potential contribution to strengthen the government’s social protection programme.  Specifically, through this programme, WFP strengthened the methodology of VAMPIRE, a cloud-based platform, by combining the near real-time evidence to detect and monitor the additional vulnerability incurred by socioeconomic impacts of the current and future pandemics, including drought and floods. The programme also explored the feasibility of mobile data collection to assess and monitor food security in hard-to-reach areas, including during pandemics and other crises. Given gender equality is not necessarily the primary objective of the government’s social protection response, building strong linkages with the national priorities is imperative to gain the government’s attention. MPTF has made it possible for UN Women to leverage technologies and innovations to capture data and conduct analysis on gender and put a spotlight on the impact of the COVID-19 pandemic on women and children from marginalized groups, during the time in which in-person data collection at the household level was improbable to do in Indonesia. This was critical to inform policy and strategies of GoI to integrate stronger gender dimensions into the national economic recovery programme. Specific area in which progress has been made is related to the attempt to address GBV during the pandemic. In light of this, UN Women has led the support of MoWECP to issue both policy and programme interventions to ensure that GBV is integrated into the social protection response and that GBV services continue to provide support for women and girls experiencing increased level of violence during the crisis. • JP managed to produce a simple web-based tool to identify vulnerable children, women, and the elderly (dubbed APEM KETAN). Realizing that the existing system used by the government in identifying individual at risk is mainly based on poverty level, the tool integrates disability, pregnancy, and female family heads into the vulnerability factors.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative, and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. Further, explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words). | Partnership has been an essential aspect enabling the JP to create collective impacts to support the government in enhancing policy and capacity to scale up and expand social protection coverage and fiscal space to include the affected and marginalized populations. For the partnership with the government, the JP's work has alligned and strengthened the government response to the pandemic. In different initiatives, the UN supported the government in enhancing policy, capacity. and data analysis for the COVID-19 response. The work in the Unified Database for Social Protection (DTKS), strengthening of the budget monitoring & analysis for social protection programme both in the Ministry of Social Affairs, Ministry of Village and Disadvantage Regions, & Transmigration, as well as support provision in the development of four SOPs and Guidelines in relatively short period (8 months) has clearly shown the trust and strong partnership between the government and the UN. Further, in the past seven months of implementation, the JP has been working with 10 implementing partners ranging from universities, Non-Government Organizations (NGOs), private sector, survey firms, and civil society organizations. Jointly, our implementing partners have been supporting us in three different areas of work: (a) data analysis and financial and digital innovation (e.g., online applications and platforms) (b) research/empirical evidence generation on the adequacy of social protection programmes provided by government (c) targeted advocacy and awareness raising. The followings are three partnerships which served as significant catalysts for the programme outcomes:  UN Women led the joint policy research with Pulse Lab Jakarta with the support from GOJEK (multi-service tech platform) to provide evidence-based policy recommendations to the National Economic Recovery Programme (PEN) and government social protection strategy to ensure the effective provision of cash to micro/small enterprises targeting women entrepreneurs and women-owned micro/small businesses. GOJEK is the first on-demand tech platform in Indonesia. This partnership has leveraged the programme in two ways: (1) collaboration with private sector integrated gender equality into business practices and culture through the application of Women’s Empowerment Principles and enabled women entrepreneurs affected by the COVID-19 pandemic to have increased access to markets and finance (2) the development of this report managed to involve the Coordinating Ministry of Economic Affairs. Leveraging partnerships with private sector such as GOJEK and Indosat Ooredo, one of the major telecommunication companies in Indonesia, have made it possible to conduct a rapid assessment and provide the most comprehensive data and evidence on the impact of the COVID-19 pandemic on gender through a survey on the socioeconomic impacts of the COVID-19 pandemic on women and men launched via SMS and web-link data collection mechanism during April and July 2020.  Our partnership with Indonesian Child Protection Body (Lembaga Perlindungan Anak Indonesia/LPAI)–an independent organization actively advocating for children rights and needs–has strengthened our work at the sub-national level. LPAI has trained community volunteers to identify vulnerable children and families and promote engagement with the multi-sector COVID-19 Task Force by advocating the prevention of violence against children through: enhancing the dissemination of adolescents’ reproductive health services as well as incorporating this issue into the development of child friendly village/city.  The programme also worked with survey firms to provide data for the analysis of socioeconomic impacts of the pandemic. The survey we conducted was exceptional in which the face-to-face survey and Interactive Voice Response (IVR) household survey managed to reach 17.000 respondents which allowed us to deliver reliable results.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | 1. Report on the Grand Design of Socioeconomic Registration for Social Protection 2. Policy Brief on the Locally-funded Child-Sensitive Social Protection Programme in Papua Province (BANGGA Papua Program) 3. Face-to-face survey and Interactive Voice Response (IVR) Household survey on Socioeconomic Impacts of the COVID-19 Pandemic 4. Study on innovative social financing to better explore different schemes viable for the implementation of social protection in seven provinces 5.The Final Results Assessment for COVID-19 MPTF will be conducted from the 31st of January–31st of March 2021. The ToR has been shared to the Secretariat of COVID-19 MPTF and the revision thereof has been made based on the input from the Secretariat 6. Study on the budget monitoring and analysis at national and sub-national level 7. Study on the influence of Rumah Zakat programme to PKH beneficiaries 8. Joint market assessment to examine the impacts of the pandemic on 12 critical market systems 9. Study on the budget monitoring and evaluation of Village Fund-Based Social Protection Programme 10. Assessment report on the effectiveness of the targeting mechanism for cash assistance from Village Fund 11. Policy Brief on the role of CSO and women’s organisations and their engagement in social protection response for the COVID-19 pandemic 12. Report on national economic recovery and government social protection strategy to provide cash to micro/small enterprises 13. Bulletin on the socioeconomic and food security implications of the COVID-19 pandemic 14. Study on the use of mVAM to explore the feasibility of mobile data collection to assess and monitor food security in hard-to-reach areas, including during pandemics and other crises 15. Fill the Nutrient Gap report 16. Methodological review to strengthen the Food Security and Nutrition Surveillance System of BKP, useful to monitor transitory food insecurity during pandemics and other crises
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets, or key outcomes and outputs that took place. | The programme is extended until the 31st of March 2021 with no major adjustments in strategies, targets, outcomes, and outputs.
5 | Resources (Optional) | • Provide any information on financial management, procurement, and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | In implementing COVID-19 MPTF, the programme also mobilized resources from the Joint SDG Fund which aims to support the GoI in transforming the existing social protection schemes into an Adaptive Social Protection system.

## RBM-Annual
| Achieved Indicator Targets | Reasons for Variance from Planned Target (if any) | Source of Verification
Outcome: By December 2020, Indonesia’s most vulnerable populations, particularly women and children from marginalised groups are protected and safeguarded from the adverse socioeconomic impact of the COVID-19 crisis |  |  | MoSA institutional records on the Unified Database for Social Protection (Data Terpadu Kesejahteraan Sosial/DTKS))
Indicator 1 SDG 1.3.1 Proportion of population covered by social protection floors/systems, by sex, distinguishing children, unemployed persons, older persons, persons with disabilities, pregnant women, newborns, work-injury victims, and the poor and the vulnerable
Baseline: 38%
Planned Target: 57% | 40%
Indicator 2 SDG 1.5.4 - Proportion of local governments that adopt and implement local disaster risk reduction strategies in line with national disaster risk reduction strategies
Baseline: 173/514 local governments have a DRR plan, 90 of which are partly integrated with Sendai Framework |  |  | BNPB internal report per January 2021. Data have been shared to the UN upon official request.
Planned Target: 190/514 have a DRR plan at least partly integrated with Sendai Framework | 181/514
Indicator 3 SDG 2.1.1 Prevalence of undernourishment
Baseline: 6.7% |  |  | National Socioeconomic Survey (SUSENAS) per September 2020.
Planned Target: 6.4% | 7.66%
Output 1.1 The government and key partners have enhanced policy and capacity to scale up and expand social protection coverage and fiscal space to include the affected and marginalised populations, particularly women and children from marginalised groups |  |  | MoSA training reports, August 2020
Indicator 1.1.1. Number of social welfare workers/village cadres with increased capacity for social protection response
Baseline: 0
Planned Target: 750 | 4767 (F: 3050; M: 1719)
Indicator 1.1.2 Number of integrated rights-based, equitable, and gender-responsive policy solutions (including for food security and nutrition) creating an enabling environment for pandemic response that have been implemented |  |  | (1) National Development Planning Agency (BAPPENAS) report, December 2020 (2) MoSA report, July 2020
Baseline: 0
Planned Target: 1 | 2
(1) SOP on the Grand Design of Socioeconomic Registration for Social Protection (2) Mapping of the vulnerable children affected by the COVID-19 pandemic and link to access social support including that for children in institutional care/orphanages (there are 5,505 institutions, 1,804 of which are unregistered). Total children identified: 349,841 (Girls:172,941; Boys: 171,397))
Output 1.2 COVID-19 task forces, at national and sub-national level, have increased capacity to plan, communicate, build partnerships, and deliver the social protection response for COVID-19 crisis in an inclusive and coordinated manner |  | The programme expanded the target beyond COVID-19 task forces, it also reached the volunteer mechanism operating under of the Ministry of Social Affairs (MoSA). Such an expansion was implemented by providing support to the government in the development of the COVID-19 Risk Communication Learning Kit for: Disaster Response Team (39.004), Peace Pioneer (745), and Family Hope Program (38.948). | MoSA Report, August 2020
Indicator 1.2.1: Number of coordinating mechanisms established under the COVID-19 task forces (TF) with increased capacities
Baseline: 0
Planned Target: 5 | 4
Child Protection Working Group, Volunteer of Disaster Response Team, Peace Pioneer, and Family Hope Program
Indicator 1.2.2: Number of interagency SOPs for coordination on social protection services
Baseline: 0
Planned Target: 1 (national) & 5 (sub-national) | 2
| (1) Updated National Standard on Childcare (SNPA) in the context of COVID-19 pandemic (2) Guidelines on the umbrella protocol for protecting the rights of women and children in the COVID-19 response and recovery |  | (1) MoSA report, December 2020 (2) Ministry of Women Empowerement and Child Protection, 9th of December 2020
Output 1.3 Key institutions and partners have increased capacity to adopt data analysis as well as financial and digital innovations for effect
Indicator 1.3.1. Number of data analysis as well as financial and digital innovations (e.g., online applications and platforms) that support inclusive and gender sensitive social protection response for COVID-19 crisis
Baseline: 0
Planned Target: 5 | 6 | (a)Household survey on Socioeconomic Impacts of COVID-19 (b) Socioeconomic Impacts of COVID-19 on women and men including vulnerable groups (c) Development of web application “Apem Ketan” in Central Java (d) mVAM mobile data collection to assess and monitor food security in hard-to-reach areas (e) Fill the Nutrient Gap report) (f) Bulletin on the socioeconomic and food security implications of the COVID-19 pandemic | Programme Report, December 2020
Indicator 1.3.2. Number of women in informal and vulnerable employment, female-headed households, and single mothers supported through financial and digital innovations
Baseline: 0
Planned Target: 10,000,000 (indicative) | 4002323 |  | Programme Report, December 2020
(1) For the indirect women beneficiaries supported through financial and digital innovation, particularly according to the rapid assessment of the gender impacts of COVID-19 as well as the impacts of COVID-19 on women-owned micro and small business, it is estimated that about 4 million people have been reached through survey as well as information sharing/knowledge products.
(2) UN Women WeLearn Platform has supported 2,023 women entrepreneurs in response to COVID-19 by providing online training, coaching, and mentoring
(3) Leveraging MPTF and Japan support, UN Women provided the initial model for cash for work support to 300 women affected by the pandemic in the garment industry
Please inlcude all three: Baseline, Planned Targets, and Achieved Targets.
[1] Note: Outcomes, outputs, indicators, and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3, etc.
Note on A36: hp: Incomplete sentence, more context required.

## Communication-Annual
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supported progress towards the SDGs, especially for vulnerable people. Ideally, this story features testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as applicable. When sharing videos as well pictures, please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
Cash for Work Programme Empowers Women To Regain Dignity The garment sector is often associated with hard working women. It is the world’s largest expanding industry, growing at an annual rate of over 8 percent per year. Indonesia is among the four countries producing a sizable amount of garment exports. In Indonesia, the majority (83 percent) of the sector’s workers are women. Thus, when the COVID-19 pandemic hit the garment sector, Indonesia’s significant female workforce was put at risk. In Indonesia, it is common for female factory workers to live in marginalized communities with poor civic facilities. This condition places economic and physical pressure on women in terms of access to services as well as domestic issues resolution. Mrs. Icoh, a middle-aged woman who lives in Pondok Kaso Village, Sukabumi, recently lost her husband–a tragic loss for the family. Her living condition before pandemic was already difficult. For example, she struggled to pay tuition fees for her two children by working as a washer in a home industry. With an income of less than half a million rupiah (US$35.62) per month and unstable income from her late husband, the family struggled to generate stable income. Now that she has become a single parent, the future of her economy seems uncertain. A similar challenge was faced by Mrs. Eni, another woman living in the same village. As the main provider for her family, including her parents that she lives with, her ability to generate income is crucial to the family’s livelihood and wellbeing. With the pandemic, she was forced to leave her job at the garment factory due to factory closure. Today, she is jobless and therefore, does not earn income. To make matters more challenging, she and her mother are undergoing medical treatment and as they are not yet registered to universal healthcare (BPJS), they must pay the treatment themselves and thus, creating unnecessary economic burden. These two are among the garment workers that are the most marginalized. They and their families bear the brunt of the negative effects of the pandemic such as health risks, reduction and loss of income, as well as impacts related to gender namely increased risk of gender-based violence, increased unpaid care work, and barriers to sexual and reproductive healthcare (SRH). To respond to the situation, UN Women and Yayasan CARE Peduli (YCP) supported groups of women garment workers in Sukabumi and Purwakarta Sub-District, in the West Java Province (where many garment workers reside). They did this by providing cash for work and cash transfer programme, helping women create and obtain a source of income. Both organizations targeted women who have lost their jobs or income and are entitled to receive the government safety net programme to meet daily basic needs. The connected training programme for women repurposes their existing skills for mask production. Since December 2019, the programme has been providing various capacity building activities to empower 60 female masks producers and 240 female masks marketers. This programme specifically targets to build their leadership and negotiation skills, useful for their working and living environment. Organized in groups, these women work under the programme for three months, during which they also receive cash for their monthly work. Female workers, like Mrs. Icoh and Mrs. Eni, are thankful for the programme since it helps them regain their source of income and become more independent, confident, and obtain a wider network of friends and relatives to support them. The programme has obtained support and endorsement from the local government of Sukabumi District. This condition provides local encouragement for women’s engagement in the implementation of the project and the frameworks aimed at continuing interventions following the end of the project. The local authorities also serve the function to provide an enabling environment for women and young entrepreneurs to grow. “We are optimistic that the programme will be an income solution for these women and provide an opportunity to our society to recover from the COVID-19 crisis. The programme is also aligned with our own programme to increase the capacity of the community,” said Feriana Rahman, village secretary of Pondok Kaso Village, Sukabumi.
Through the cash for work programme, it is estimated that women will be further empowered and enabled to protect themselves from the impacts of vulnerable situations and regain economic independence to meet basic household needs. “We provide women with access to life-saving information, resources, services, and skills that will reduce the spread of negative socioeconomic impacts of COVID-19. Further, we give them the opportunity to restore their dignity,” explained Rika, officer of Yayasan Care Peduli.
Link for Gender Responsive Cash for Work Programmes project visits:
https://drive.google.com/drive/folders/13e1FkT4_lttFpi9066bK5uaBSRGS_Y4w?usp=sharing
Link for high resolution footage from Cash Based Assistance (CBA) project in Lombok:
https://drive.google.com/drive/u/1/folders/1ATaVBvm6tw4YzF6JJ_9zbfWXNhrdhU5M
Please provide links to any videos that have been produced during implementation.
https://drive.google.com/drive/u/1/folders/1ATaVBvm6tw4YzF6JJ_9zbfWXNhrdhU5M
Please produce and share a social media card(s). See an example below and visit our Trello Board.
https://drive.google.com/drive/u/1/folders/1ATaVBvm6tw4YzF6JJ_9zbfWXNhrdhU5M
See - Fund's Trello Board

## General Information-Final
Programme Title & Project Number |  | Programme Duration
Programme Title: | Protecting People: Supporting the Government of Indonesia and Key Stakeholders to Scale Up Inclusive Social Protection Programmes in Response to COVID-19 | Overall Duration (months) | 10 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 01.05.2020
MPTF Office Project Reference Number: | 121443 | Original End Date (dd.mm.yyyy) | 31.12.2020
Country | Indonesia | Current End date(dd.mm.yyyy) | 31.03.2021
Recepient UN Organizations |  | Implementing Partners
Organizations receiving direct funding from the MPTF Office under this programme | UNICEF, UNDP, WFP, and UN WOMEN | National counterparts (government, private sector, NGOs, & others) and other International Organizations | BAPPENAS, National Disaster Managament Board or BNPB, Ministry of Social Affairs, Ministry of Agriculture, Ministry of Finance, Ministry of Women Empowerment and Child Protection, Ministry of Health, Ministry of Villages, Development of Disadvantaged Regions, and Transmigration, CARE Indonesia, University of Indonesia, University of Padjajaran, and Bogor Agriculture Institute, GOJEK, INDOSAT OOREDOO, DFAT PROSPERA, SMERU Institute, ADRA, BTrust, Yayasan Karampuang, and E8
Report Cleared by
o Name: | Valerie Julliand
o Title: | Resident Coordinator
o Email address: | valerie.julliand@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page of the MPTF Office GATEWAY.
The start date is the date of the first fund transfer from MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY.
Report shall be in line with the original project document approved by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised and approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date, which is when all activities for which a Participating Organization is responsible under an approved MPTF/JP have been completed. As per the MoU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results as well as any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19 (maximum up to 500 words). | For the past one year, under the leadership of UN Resident Coordinator, UNICEF, UNDP, WFP and UN WOMEN have been supporting the government in rolling out COVID-19 shock-responsive social protection. The overall objective of the programme is to improve the policies and capacity to scale up and expand social protection coverage and fiscal space to include the most affected and marginalized populations, particularly women and children. Throughout the implementation, the programme has achieved four main outputs: 1. UNICEF and UN Women supported the government in developing guideline, protocol, national standard for protecting the rights of women, girls, and children in the context of the COVID-19 pandemic including mapping the vulnerable children under registered and unregistered institutional care. UNICEF and UNDP are the key actors behind the national programme on Piloting the Unified Database Update (UNICEF-UNDP). This database registers the bottom 40% of populations eligible for social protection programme. Through this piloting, UNICEF-UNDP promoted the inclusive approach by registering homeless people, people without formal registration, and the elderly as well as involving the community to ensure no one is left behind. 2. The project has been able to facilitate the adaptation of service provision to the vulnerable populations especially women and children as well as capacity building of the frontline workers. UNICEF strengthened the capacity of social workers, COVID-19 Task Forces, and Ministry of Social Affairs volunteers by conducting training for 1,985 social workers and 1,337 parents/caregivers and disseminating Learning Kits on Public Communication to 78,697 volunteers operating under the Ministry of Social Affairs Volunteers. UN Women-UNFPA supported the piloting of the multi-sectoral integrated services for GBV survivors in DKI Jakarta and Central Sulawesi as well as the capacity building for 795 participants from the Integrated Care Center for the Empowerment of Women and Children (P2TP2A) in Greater Jakarta, North Lombok, Cirebon, and Central Sulawesi. 3. UNICEF, UNDP, WFP and UN Women introduced innovative data analysis to improve the understanding on the socioeconomic impacts of the pandemic by conducting nationally representative survey on socioeconomic impacts of the pandemic for household (UNICEF-UNDP-DFAT PROSPERA), Survey on Socioeconomic Impacts of COVID-19 on Gender Equality & SDGs Achievement (UN WOMEN-INDOSAT OOREDOO), national polling (U-Report) involving more than 14.000 youths to voice their views and opinions on social protection (UNICEF), feasibility study on the utilization of mobile data collection (mVAM) for analysing and monitoring the food security and nutrition in hard-to-reach areas. The programme also facilitated the strengthening of WFP VAMPIRE/PRISM, a cloud-based platform providing the socioeconomic data and information during the pandemic. 4. The programme provided deeper insights into the impacts of COVID-19 on gender to inform the gender responsive social protection response. UN Women has been playing a key role namely using the data innovation to produce a rapid assessment of COVID-19 impacts on gender particularly on women-owned micro and small businesses. It has led an innovative piloting of the gender responsive cash for work programme targeting female beneficiaries who have been adversely impacted in the garment industry. UN Women supported the Ministry of Women Empowerment and Child Protection (MoWECP) as well as CSO engagement in strengthening the essential services for women and children. According to the preliminary findings of Final Results Assessment COVID-19 MPTF conducted by independent consultant, the joint programme has: (1) succeeded in developing a comprehensive project document, outlining ToC, outputs, activities, immediate and end-targets, as well as working areas of each agency (2) succeeded in achieving the majority of set targets of output indicators (3) showed high commitment (and non-financial) investment in this program (completion of 42 out of 44 activities within 11 months of program implementation)
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached, and disaggregate the data by gender, age, and any other groups. | The programme has reached up to 453,530 direct beneficiaries with the details as follows: (1) Mapping of vulnerable children in institutional care: 359,818 children (Girls:181,248; Boys: 178,570) (2) Identification of vulnerable children in West Nusa Tenggara: 171 children (G: 82; B: 89) (3) Gender responsive cash for work programme: 300 women (4) Training on Case Management, Psychosocial Support, Self-Care, Ethical Dilemma for Social Workers: 852 individuals (F: 472; M: 380) (5) Training on Social Service Provision for Social Workers (psychological first aid and counselling, facilitation skills, ethics, case management, identification of vulnerable children and families, and Prevention of Sexual Exploitation and Abuse and Gender-Based Violence): 1,985 individuals (F: 1,241; M: 744) (6) Training for Parents and Caregivers on Good Parenting, PHBS, and Prevention of VAC: 1,337 individuals (F: 810; M: 527) (7) Dissemination of Learning Kit for Public Communication by MoSA: 78,697 individuals (8) 575 women respondents have been reached under the survey on the COVID-19 Impacts (9) Multi-sectoral integrated GBV services are improved in Greater Jakarta (Jabodetabek) and Central Sulawesi; the government has been scaling up the integrated GBV services in the context of COVID-19; and community engagement mechanism has been facilitated to ensure that right holders, including civil society and women organizations, are equipped to meaningfully engage in the delivery of social protection packages, including essential services for GBV survivors in COVID-19 response and recovery: capacity building of 795 participants from P2TP2A (10) In partnership with the local government in Central Java, about 9,000 vulnerable women including those with disabilities have been identified through the web-based application for mapping the vulnerable groups (APEMKETAN) and have been provided with raw materials for making masks and face shields as part of the economic safety net programme. The indirect beneficiaries of the programme include those of the current and expanded social protection programme for COVID-19, comprising 10 million households receiving unconditional cash transfers (PKH); 20 million households receiving food assistance programme (Kartu Sembako); and 11.6 million households receiving Village Cash Transfer.
3.1 | Results: Outcome Level | Please include outcome level results achieved. | The programme has supported the government in reducing the adverse socioeconomic impacts of the COVID-19 crisis on vulnerable populations, particularly women and children of marginalized groups by (1) enhancing the policy and capacity related to inclusive social protection by mainstreaming the affected and marginalised population, particularly women and children of marginalised groups into the policy guidelines, unified database, and national standards (2) increasing the capacity of COVID-19 taskforces and MoSA volunteers to plan, communicate, build partnerships, and deliver the social protection response for COVID-19 crisis in an inclusive and coordinated manner (3) increasing the capacity to adopt data analysis as well as financial and digital innovations for effective and efficient delivery of social protection response that is gender-sensitive and inclusive.
3.2 | Results: Output Level | Please include output level results achieved. | Overall, the JP has achieved three main outputs: (i) the government and key partners have enhanced the policy and capacity to scale up and expand social protection coverage and fiscal space to include the affected and marginalised populations, particularly women and children from marginalised groups (ii) the COVID-19 Task Forces, volunteer mechanism operating under the Ministry of Social Affairs (MoSA) at the national and sub-national level, have increased capacity to plan, communicate, build partnerships, and deliver social protection response for COVID-19 crisis; and (iii) the adoption of data analysis as well as financial and digital innovations to better inform the government on effective gender-responsive social protection has been promoted. Specifically, the JP has generated the following outputs: (1) The capacity of 4767 social workers employed to deliver social protection has been strengthened (UNICEF) (2) Two integrated rights-based, equitable, and gender-responsive policy solutions have been developed, including the unbrella guideline and protocol for protecting the rights of women and girls during the COVID-19 pandemic, and GBV services have been integrated into the social protection policy and response (SOP on the Grand Design of Socioeconomic Registration for Social Protection, mapping of the vulnerable children and women affected by the COVID-19 pandemic, and link to access social support including that for children in institutional care/orphanages (there are 5,505 institutions, 1,804 of which are unregistered)). Total children identified: 349,841 (Girls:172,941; Boys: 171,397) (UNICEF, UN Women) (3) 2 nationwide surveys on socioeconomic impacts of the COVID-19 pandemic as well as COVID-19 impacts on gender have been facilitated (UNICEF, UN Women) (4) 300 beneficiaries in West Java have received cash for work programme focusing on value chain and entrepreneurship development programme (UN Women) (5) The capacity of COVID-19 task forces at the national and sub-national level in Central Java, East Java, and West Nusa Tenggara has been strengthened (UNICEF) (6) The methodology of VAMPIRE, a cloud-based platform, has been strengthened namely by combining the near real-time evidence of additional vulnerability occurring due to the socioeconomic impacts of the current and future pandemics. This platform ensures that such impacts are detected and monitored (WFP) (7) The government has been facilitated to adopt mobile data collection (mVAM) to assess and monitor food security in hard-to-reach areas, during pandemics and other crises (WFP) (8) Policy framework in the context of COVID-19 pandemic related to service provision for vulnerable children, especially children in institutions has been improved (UNICEF) (9) The use of data innovation and technology to produce new evidence-based policy recommendations by conducting face to face survey, commencing Interactive Voice Response (IVR) Household survey on Socioeconomic Impacts of COVID-19 with 12,216 respondents has been promoted and report on the COVID-19 impact on gender has been launched in collaboration with INDOSAT Ooredoo (UNICEF, UNDP, UN Women) (10) Policy research, “Leveraging Digitalization to Cope with COVID-19 Pandemic: Indonesia Case Study on Women-owned Micro and Small Businesses” which contitutes an innovative initiative as it employed data and technologies that combine big data analysis as well as quantitative and qualitative surveys to assess the impact of COVID-19 pandemic on micro and small businesses from gender perspective has been produced. This report gives important insights into how Indonesia can leverage digitalization to support women entrepreneurs to survive the pandemic. It calls for the government stimulus packages to have greater focus on women-owned micro and small business in COVID-19 response and recovery (UN Women) (11) Specific studies on budget and policy analysis on social protection by focusing on budget analysis & monitoring at the sub-national level, targetting mechanism, innovative financing have been produced (UNICEF, UNDP) (12) Module 'Targetting of Village Fund Cash Assistance Programme' has been developed (UNDP) (13) In West Sulawesi, JP has engaged Yayasan Karampuang and ADRA to effectively support community affected by earthquake and the pandemic in West Sulawesi, respectively, for supporting local businesses and building supporting facilities for COVID-19 prevention. (14) The methodology of Food Security and Nutrition Surveillance System (SKPG) of the BKP useful to monitor transitory food insecurity, during pandemics and other crises has been improved (WFP) (15) Four bulletins to analyse and monitor the socioeconomic and food security implications of the COVID-19 have been produced (WFP) (16) A feasibility study on the adoption of mobile data collection (mVAM) to assess and monitor food security in hard-to-reach areas, during pandemics and other crises (WFP)
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them. and changes introduced (any course of corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words). | Looking into the expectations of the programme and the time pressure of implementation, there were some challenges faced during the production of COVID-19 MPTF outputs, namely: 1. Coordination has been proven to be challenging within the government i.e. between line ministries, from central to sub-national/local level governments, as well as among various partners outside of the government. The government's intention to expand the involvement of ministries and agencies in the programme has triggered questions not only among UN agencies but also within the newly appointed ministries in charge. At the initial stage, there were 8 ministries & agencies listed as government partners. In September, the UN received proposal from the government to incorporate additional 9 ministries and agencies into the programme. On one side, the UN appreciates the intention of National Development Planning Agency (BAPPENAS)–as the coordinating ministry–to enrich the programme by engaging more ministries and agencies in the COVID-19 MPTF; however, this has triggered questions not only among the UN organizations but also the newly appointed ministries. Some ministries are questioning to what extent they could contribute to the programme. This concern was also shared by the agencies asking for more clarity on the expected engagement and contribution. 2. Social protection response from the government traditionally focused on mitigating immediate income risks and reducing poverty. Addressing structural inequalities, particularly gender inequality, is generally not the primary objective of the social protection interventions. There are still challenges to ensure that eligibility criteria and the beneficiary selection/targeting process take into account other type of social vulnerabilities in the design and implementation of social protection response, which have gaps in inclusion and exclusion errors. The UN has been pushing for a more inclusive and gender-responsive social protection. It also requires stronger ownership and engagement from the government to continue to drive this agenda forward. 3. The COVID-19 pandemic is a force majeure which leads to unprecedented measures. This pandemic has been affecting not only different life sectors but also the way people work. Due to precautionary measures such as travel restriction and large events cancelation, the programme had to be implemented virtually. As the consequence, some activities took longer than expected and the dominant intervention had the main focus on studies and assessment commencement. In the completion of these different studies, PUNOs advocated the recommendations of the studies to the government to improve the existing policies such as study on monitoring & evaluation, targetting mechanism for village-based social protection, as well as Food Security and Survillience Mechanisms.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic, and/or operational lessons or findings from the programme that could inform similar responses at country or global level. Please focus on the knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) and include reflections on the implementation of gender markers and any impacts they have had on programming quality and results (up to 500 words). | The JP ensured the scale-up of inclusive social protection programme in response to COVID-19 pandemic in Indonesia. During the pandemic, the government expanded the social protection programme by redirecting and retargeting the existing social protection programme. These measures include the launching of different new programmes to provide safety net for the most affected populations. The JP aimed to support the government by providing catalytic support to enhance focus on women and girls of the marginalized groups, bridging the data gap due to the absence of updated unified database, lack of interlinkage with civil registration database, and minimum monitoring system as well as conducting programme assessment for COVID-19 expanded social protection programme zooming into those who are at risk of being left behind.  For the purpose of identifying the alternative/innovative schemes to augment GoI’s social protection, the JP has initiated the innovative financing study for social protection programme in two target provinces and undertaken further engagement with private sector as well as philanthropic and religion-based organizations to explore their potential contribution to strengthen the government’s social protection programme. A recent study conducted by UNDP, the Center for Economics and Development Studies at the University of Padjadjaran and Rumah Zakat revealed that most households engaged in this zakat programme are also beneficiaries of government social protection programmes (Family Hope Programme/Program Keluarga Harapan/PKH). PKH is aimed to help covering for medical treatment as well as children’s school supplies and fees. Thus, the zakat programme is seen as complementary and supporting programme for the government’s social protection programmes and goals. These efforts continue to optimize the social protection programmes aimed at facilitating poverty alleviation.  Specifically, through this programme, WFP strengthened the methodology of VAMPIRE, a cloud-based platform, by combining the near real-time evidence to detect and monitor the additional vulnerability incurred by socioeconomic impact of the current and future pandemics, including drought and floods. The programme also explored the feasibility of mobile data collection to assess and monitor food security in hard-to-reach areas, as well as during pandemics and other crises. mVAM would help the Ministry of Agriculture (Food Secuirty Agency) to speed up the national cut-off date to report daily food and price data that often suffers in Papua and other Eastern regions. Given that gender equality is not necessarily the primary objective of the government’s social protection response, building strong linkages with the national priorities is imperative to gain the government’s attention. MPTF has made it possible for UN Women to leverage technologies and innovations to capture data and conduct analysis on gender and put a spotlight on the impact of the COVID-19 pandemic on women, girls, and children from marginalized groups, during the time in which in-person data collection at the household level is improbable to do in Indonesia. This is critical to inform the policy and strategies of the GoI to integrate stronger gender dimensions into national economic recovery programme. Specific area in which progress has been made is related to the attempt to address GBV during the pandemic. In light of this, UN Women has led the support of MoWECP to issue both policy and programme interventions to ensure that GBV is integrated into the social protection response and that GBV services continue to provide support for women and girls experiencing increased level of violence during the crisis. This includes supporting the local government in Central Sulawesi Provincial DOWECP in activating sub-cluster of women’s right protection under displacement and protection cluster, improving capacity via trainings & workshops such as those on adaptation of GBV service during pandemics, and conducting monitoring and evaluation for the implementation of COVID-19 protocols; in Jakarta, important lessons learned were generated from the collaboration with P2TP2A (the integrated services center for women and children empowerment) to build capacity for 795 participants including staffs of P2TP2A in Greater Jakarta area and some of other areas where UNFPA implements its programme (North Lombok, Cirebon, and Central Sulawesi). • JP managed to produce a simple web-based tool to identify vulnerable children, women, and the elderly (dubbed APEM KETAN). Realizing that the existing system used by the government to identify individuals at risk is mainly based on poverty level, the tool integrates disability, pregnancy, and female family heads into the vulnerability factors. In partnership with the local government in Central Java, about 9,000 vulnerable women including those with disabilities have been identified through the web-based application used for mapping vulnerable groups (APEMKETAN) and have been provided with raw materials for making masks and face shields as part of the economic safety net programme.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative, and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. Further, explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words). | Partnership was an essential aspect that enabled the JP create collective impacts to support the government in enhancing policy and capacity to scale up and expand social protection coverage and fiscal space to include the affected and marginalized populations. Within the 44 activities, 12 activities has been implemented directly with the government (27%), 12 activities with NGOs & civil society (27%), 1 activity with development partners (DFAT PROSPERA, Japan Supplementary Fund) (2%), 2 activities with university (4.5%), 2 activities with private sector (4.5%), 10 activities with contractual services (22%), and only 13% implemented solely by PUNOs. For the partnership with the government, the JP's work has alligned and strengthened the government response to the pandemic. In different initiatives, the UN supported the government in enhancing policy, capacity. and data analysis for the COVID-19 response. The work in the Unified Database for Social Protection (DTKS), strengthening of the budget monitoring & analysis for social protection programme both in the Ministry of Social Affairs, Ministry of Village and Disadvantage Regions, & Transmigration, as well as support provision for the development of four SOPs and Guidelines in relatively short period (8 months) has clearly shown the trust and strong partnership between the government and the UN. Further, in the past seven months of implementation, the JP has been collaborating with 10 implementing partners ranging from universities, Non-Government Organizations (NGOs), private sector, survey firms, and civil society organizations. Jointly, our implementing partners have been supporting us in three different areas of work: (a) data analysis and financial and digital innovations (e.g., online applications and platforms) (b) research/empirical evidence generation on the adequacy of social protection programmes provided by government (c) targeted advocacy and awareness raising. The followings are partnerships which served as significant catalysts for the programme outcomes:  UN Women led the joint policy research together with Pulse Lab Jakarta with the support of GOJEK (multi-service tech platform) to provide evidence-based policy recommendations to the National Economic Recovery Programme (PEN) and government social protection strategy to ensure the effective provision of cash to micro/small enterprises targeting women entrepreneurs and women-owned micro/small businesses. GOJEK is the first on-demand tech platform in Indonesia. This partnership has leveraged the programme in two ways: (1) collaboration with private sector integrated gender equality into business practices and culture through the application of Women’s Empowerment Principles and enabled women entrepreneurs affected by COVID-19 pandemic to have increased access to markets and finance (2) the development of this report managed to involve the Coordinating Ministry of Economic Affairs. Leveraging partnerships with private sector such as with GOJEK and Indosat Ooredo, one of the major telecommunication companies in Indonesia, has made it possible to conduct a rapid assessment and provide the most comprehensive data and evidence on the impacts of the COVID-19 pandemic on gender through a survey on the socioeconomic impacts of the COVID-19 pandemic on women and men, launched via SMS and web-link data collection mechanism during April and July 2020.  Our partnership with Indonesian Child Protection Body (Lembaga Perlindungan Anak Indonesia/LPAI) in West Nusa Tenggara–an independent organization actively advocating for children rights and needs–has strengthened our work at the sub-national level. LPAI has trained community volunteers to identify vulnerable children and families and promote engagement with the multi-sector COVID-19 TASK Force by advocating prevention of violence against children through: enhancing dissemination of adolescents’ reproductive health services as well as incorporating this issue into the development of childfriendly village/city.  The programme also worked with survey firms to provide data for the analysis of socioeconomic impacts of the pandemic. The survey we conducted was exceptional in which the face-to-face survey and Interactive Voice Response (IVR) household survey managed to reach 17.000 respondents which allowed us to deliver reliable results.  In one of the interventions namely leveraging MPTF with Japan Support, JP engaged B Trust to improve SP4N ¦ LAPOR (Sistem Pengelolaan Pengadaan Pelayanan Publik Nasional ¦ Laporan Aspirasi dan Pengaduan Online Rakyat/National Management System of Public Service Delivery ¦ People’s Online Complaint and Aspiration Report) Application, specifically to set up data disaggregated by gender and age as well as to identify gaps in the business process between the prevailing regulations and their application in the framework of realizing “no wrong door policy.”
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | 1. Report on the Grand Design of Socioeconomic Registration for Social Protection 2. Policy Brief on the Locally-funded Child-Sensitive Social Protection Programme in Papua Province (BANGGA Papua Program) 3. Socioeconomic Impact of the COVID-19 Pandemic on Households and Strategic Policy Recommendations for Indonesia (https://www.unicef.org/indonesia/coronavirus/reports/socio-economic-impact-covid-19-households-indonesia) 4. Study on innovative social financing to better explore different schemes viable for the implementation of social protection in seven provinces 5.The Final Results Assessment for the COVID-19 MPTF will be conducted from the 31st of January–31st of March 2021. The ToR has been shared to the Secretariat of COVID-19 MPTF and the revision thereof has been made based on the input from the Secretariat 6. Study on the budget monitoring and analysis at national and sub-national level 7. Study on the influence of Rumah Zakat programme on PKH beneficiaries 8. Joint market assessment to examine the impacts of the pandemic on 12 critical market systems 9. Study on the budget monitoring and evaluation of Village Fund-Based Social Protection Programme 10. Assessment report on the effectiveness of the targeting mechanism for cash assistance from Village Fund 11. Policy Brief on the role of CSO and women’s organisations and their engagement in social protection response to the COVID-19 pandemic 12. Report on the national economic recovery and government social protection strategy to provide cash to micro/small enterprises 13. Bulletin on the socioeconomic and food security implications of the COVID-19 pandemic, one of the four series of the bulletins include gender analysis 14. Study on the use of mVAM to explore the feasibility of mobile data collection to assess and monitor food security in hard-to-reach areas, including during pandemics and other crises - Indonesia - COVID-19 Economic and Food Security Implications ¦ World Food Programme ( https://www.wfp.org/publications/indonesia-covid-19-economic-and-food-security-implications) - COVID-19 Economic and Food Security Implications for Indonesia - 3rd edition August 2020 ¦ World Food Programme (https://www.wfp.org/publications/covid-19-economic-and-food-security-implications-indonesia-3rd-edition-august-2020) - COVID-19 Economic and Food Security Implications for Indonesia - 4th Edition December 2020 ¦ World Food Programme (https://www.wfp.org/publications/covid-19-economic-and-food-security-implications-indonesia-4th-edition-december-2020) 15. Fill the Nutrient Gap report 16. Methodological review to strengthen the Food Security and Nutrition Surveillance System of BKP, useful to monitor transitory food insecurity during pandemics and other crises 17. Policy Brief on Self-Quarantine Protocols in Papua 18. Health Referral System Policy Effectiveness in COVID-19 Pandemic in Papua 19. Locally-led Social Protection Programme in Papua 20, UN Women COVID-19 Impact to Gender and SDG Achievement in Indonesia (https://data.unwomen.org/publications/counting-costs-covid-19-assessing-impact-gender-and-achievement-sdgs-indonesia) 21. Leveraging digitalization to cope with COVID-19: An Indonesia case study on women-owned micro and small businesses (https://data.unwomen.org/publications/leveraging-digitalization-indonesia-case-study)
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | The programme was extended until the 31st of March 2021 with no major adjustments in strategies, targets, outcomes, and outputs.
5 | Resources (Optional) | • Provide any information on financial management, procurement, and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | In implementing the COVID-19 MPTF, the programme also mobilized resources from Joint SDG Fund which continues to support the GoI in transforming the existing social protection schemes into an Adaptive Social Protection system. In addition, UNICEF and UNDP in partnership with PROSPERA DFAT and SMERU Research Institute launched the largest national survey on COVID-19 in Indonesia to identify the social and economic impacts of COVID 19 on vulnerable households.This nationally representative survey was also supported by Japan Suplementary Fund

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance from Planned Target (if any) | Source of Verification
Outcome: By December 2020, Indonesia’s most vulnerable populations, particularly women and children from marginalised groups, are protected and safeguarded from the adverse socioeconomic impacts of the COVID-19 crisis | 45% |  | MoSA institutional records on the Unified Database for Social Protection (Data Terpadu Kesejahteraan Sosial/DTKS)) + report from the Indonesian Committee for the COVID-19 Response and National Economic Recovery
Indicator 1 SDG 1.3.1 Proportion of population covered by social protection floors/systems, by sex, distinguishing children, unemployed persons, older persons, persons with disabilities, pregnant women, newborns, work-injury victims, as well as the poor and the vulnerable
Baseline: 38%
Planned Target: 57%
Indicator 2 SDG 1.5.4 - Proportion of local governments that adopt and implement local disaster risk reduction strategies in line with national disaster risk reduction strategies
Baseline: 173/514 local governments have a DRR plan, 90 of which are partly integrated with Sendai Framework | 181/514 |  | (1) BNPB internal report per January 2021. Data have been shared to the UN upon official request (2) Jitupasna Assessment Report (UNDP Restore)
Planned Target: 190/514 have a DRR plan at least partly integrated with Sendai Framework
Indicator 3 SDG 2.1.1 Prevalence of undernourishment
Baseline: 6.7% | 7.66% |  | National Socioeconomic Survey (SUSENAS) per September 2020.
Planned Target: 6.4%
Indicator 1.1.1. Number of social welfare workers/village cadres with increased capacity for social protection response | 4767 (F: 3050; M: 1719) |  | MoSA training reports, August 2020 + UNICEF Activity Report March 2021
Baseline: 0
Planned Target: 750
Indicator 1.1.2 Number of integrated rights-based, equitable, and gender-responsive policy solutions (including for food security and nutrition) creating an enabling environment for pandemic response that have been implemented | 3 |  | (1) National Development Planning Agency (BAPPENAS) report, December 2020 (2) MoSA report, July 2020
Baseline: 0
Planned Target: 1
(1) SOP for the Grand Design of Socioeconomic Registration for Social Protection (2) Mapping of vulnerable children affected by the COVID-19 pandemic and link to access social support including that for children in institutional care/orphanages (there are 5,505 institutions, 1,804 of which are unregistered). Total children identified: 349,841 (Girls:172,941; Boys: 171,397)) (3) Piloting of the multi-sectoral, integrated GBV services involving 795 participants for capacity building in DKI Jakarta and Central Sulawesi
Output 1.2 COVID-19 task forces, at national and sub-national level, have increased capacity to plan, communicate, build partnerships, and deliver the social protection response to the COVID-19 crisis in an inclusive and coordinated manner |  | The programme expanded the target beyond the COVID-19 task forces, it also reached the volunteers operating under the Ministry of Social Affairs (MoSA). Such an expansion was implemented by providing support to the government in the development of the COVID-19 Risk Communication Learning Kit for: Disaster Response Team (39.004), Peace Pioneer (745), and Family Hope Program (38.948). | MoSA Report, August 2020
Indicator 1.2.1: Number of coordinating mechanisms established under the COVID-19 task forces (TF) with increased capacities
Baseline: 0
Planned Target: 5 | 6
(1) Child Protection Working Group under COVID-19 Task Force in East Java (2) Child Protection Working Group under COVID-19 Task Force in West Java (3) Child Protection Working Group under COVID-19 Task Force in West Nusa Tenggara (4) Volunteers of Disaster Response Team, Ministry of Social Affairs (5) Volunteers of Peace Pioneer, Ministry of Social Affairs (6) Volunteers of Family Hope Program, Ministry of Social Affairs
Indicator 1.2.2: Number of interagency SOPs for coordination of social protection services
Baseline: 0
Planned Target: 1 (national) & 5 (sub-national) | National: 2
| (1) Updated National Standard on Childcare (SNPA) in the context of COVID-19 pandemic (2) Guidelines on umbrella protocol for protecting the rights of women and children in the COVID-19 response and recovery |  | (1) MoSA report, December 2020 (2) Ministry of Women Empowerement and Child Protection, 9th of December 2020
Sub- National: 3
| Establishment of child protection working group under the COVID-19 Task Force in Central Java, East Java, and West Nusa Tenggara |  | Activity Report of COVID-19 MPTF
Output 1.3 Key institutions and partners have increased capacity to adopt data analysis as well as financial and digital innovations for effect
Indicator 1.3.1. Number of data analysis as well as financial and digital innovation (e.g., online applications and platform) that support inclusive and gender responsive social protection response for COVID-19 crisis
Baseline: 0
Planned Target: 5 | 7 | (a)Household survey on Socioeconomic Impacts of COVID-19 (b) Socioeconomic Impacts of COVID-19 on women and men including vulnerable groups (c) Development of web application “Apem Ketan” in Central Java (d) m-VAM mobile data collection to assess and monitor food security in hard-to-reach areas (e) Filled out Nutrient Gap report (f) Bulletin on the socioeconomic and food security implications of the COVID-19 pandemic including gender analysis of food security (g) Support for the digitalization to cope with COVID-19: An Indonesia case study on women-owned micro and small businesses | Programme Report, March 2021
Indicator 1.3.2. Number of women in informal and vulnerable employment, female-headed households, and single mothers supported through financial and digital innovations
Baseline: 0
Planned Target: 10,000,000 (indicative) | 4002323 |  | Programme Report, December 2020
(1) For the indirect women beneficiaries supported through financial and digital innovation, particularly according to the rapid assessment of the gender impacts of COVID-19 as well as the impacts of COVID-19 on women-owned micro and small business, it is estimated that about 4 million people have been reached through survey as well as information sharing/knowledge products.
(2) UN Women WeLearn Platform has supported 2,023 women entrepreneurs in response to COVID-19 by providing online training, coaching, and mentoring (combining MPTF support with other sources of funding)
(3) Leveraging MPTF and Japan support, UN Women provided initial prototyping model for cash for work support for approximately 600 women (among them, 300 women were directly funded by MPTF) in the garment industry that are affected by the pandemic
Note on A40: hp: Incomplete sentence, more context required.

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supported progress towards the SDGs achievement, especially for the vulnerable people. Ideally, this story features testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as applicable. When sharing videos as well pictures, please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
UN Support for the National Reform on Social Protection: Piloting Socioeconomic Registration and Information System for the Elderly (SILANI) In Indonesia, since the first cases were confirmed in March 2020, the coronavirus has infected more than 1.3 million people. The pandemic has increased the poverty rate in Indonesia from 9.78% in March 2020 to 10.19% in September 2020. The recent nationally representative socioeconomic survey conducted by UNICEF, UNDP and DFAT PROSPERA under the COVID-19 Multi-Partner Trust Fund (MPTF) also revealed that the pandemic has negatively impacted families with children, namely 75% of households with children experienced income loss and 57% of which found themselves without reliable internet connection, leading to a grave chance of learning loss. In response to the severe socioeconomic impact, the Government has been able to expand and scale up its Social Protection programme. In 2020, there were at least 10 social protection programmes specifically targeting the prevention of affected populations from entering or falling deeper into poverty. However, there are also challenges in implementation. One of the underlying issues relates to the outdated data in the Unified Database for Social Protection (Data Terpadu Kesejahteraan Sosial/DTKS)–the database which registers the bottom 40% of the population has not been updated since 2015. Therefore, addressing the data-related issue is essential in ensuring the achievement of effective (reaching the most vulnerable with limited inclusion and exclusion errors), inclusive (leaving no-one behind), responsive, and adaptive social protection (contributing to the long-term recovery and climate resilience). To address this issue, the President issued the Presidential Regulation No. 86/2020 regulating the implementation of social and economic registration that will include 100% of the Indonesian population by 2024 as a way to ensure accurate targeting for social protection programme. Initial efforts were made, which include updating the DTKS data through the Village Monograph system. Said update was started from the village level up to the national level. The first goal is to increase coverage of social protection programmes to 60% by 2021. This milestone will be the basic modality for developing the Social Registration System, as part of the Indonesia One Data. As the pilot project for the unified database update, the National Development Planning Agency (Badan Perencanaan Pembangunan Nasional/BAPPENAS) conducted social and economic registration (Regsosek) and SILANI (Information System for Elderly Citizen) in Aceh and West Java. This pilot project aims to: 1. Ensure the data collection for social and economic data registration is accurate, valid, up-to-date, and accountable. 2. Identify the supporting and inhibiting factors in the implementation of the social and economic registration and SILANI. 3. Standardize the mechanism for the social and economic data registration. 4. Improve the capacity of the local government to conduct data collection and updates. UNICEF and UNDP, under the COVID-19 MPTF programme, supported the government by providing technical assistance in the piloting, development of data collection methodology, survey instrument, and guidelines, and the surveyor's capacity building. Through this support, UNICEF and UNDP advocated the inclusion of homeless people, people with no formal registration and/or vulnerable populations such as the elderly, into the database. The UN also promoted an inclusive approach during the database update, by involving the community in validating the beneficiaries for social protection programmes through the village government. The goal is to ensure that no one is left behind during and after the pandemic. "We are grateful to receive support from the UN family. It is expected that UNICEF could support the expansion of social registration piloting as well as programme replication in several areas in the future. We really hope this registration will strengthen government socioeconomic programme." - Maliki, Director for Alleviating Poverty and Development of Social Welfare, Bappenas. ***
2. Upload here: Communications and Visibility (OPTIONAL)
When sharing videos as well pictures, please make sure you include all credits and upload them in high resolution Call1 countries.
https://drive.google.com/drive/u/0/folders/1SVrGejNAz9WtcjzCI3pEkpUMAdtAq8ZA
Submit photographs. Please provide photographs that capture the programme in action with captions and in high resolution. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
The COVID-19 MPTF Branding Guidelines mentioned two types of photograph submission: high resolution and raw/untreated footage. The JP has prepared photographs of the two qualities:
https://drive.google.com/drive/u/0/folders/1hkbp-gqsB1zu8rYokH0QUNynIErfx9C2