Fostering dialogue and social cohesion in and between Bosnia and Herzegovina (BiH),

Montenegro and Serbia (Dialogue for the Future)

MPTF OFfice GENERIC ANNUAL programme NARRATIVE progress report

REPORTING PERIOD: 1 january – 31 December 2020

| Programme Title & Project Number |  | Country, Locality(s), Priority Area(s) / Strategic Results |
| --- | --- | --- |
| Programme Title: Fostering dialogue and social cohesion in and between Bosnia and Herzegovina (BiH), Montenegro and Serbia (Dialogue for the Future) Programme Number (if applicable) MPTF Office Project Reference Number: 00113873 (BiH), 00113874 (MNE), 00114184 (SRB) |  | Bosnia and Herzegovina, Montenegro, Republic of Serbia |
|  |  | Priority area/ strategic results |
| Participating Organization(s) |  | Implementing Partners |
| UNDP, UNICEF, UNESCO |  |  |
| Programme/Project Cost (US$) |  | Programme Duration |
| Total approved budget as per project document: UNDP: $ 1,753,765.71 UNICEF: $ 1,297,910 UNESCO: $ 1,132,316.80 Total: $ 4,183,992.51 MPTF /JP Contribution: by Agency (if applicable) |  |  | Overall Duration (months) 27 months |  |
| Agency Contribution by Agency (if applicable) |  |  | Start Date (07.01.2019) |  |
| Government Contribution (if applicable) |  |  | Original End Date (31.07.2020) |  |
| Other Contributions (donors) (if applicable) |  |  | Current End date(30.04.2021) |  |
| TOTAL: |  |  |  |  |
| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| Assessment/Review - if applicable please attach Yes No Date: dd.mm.yyyy Mid-Term Evaluation Report – if applicable please attach Yes No Date: dd.mm.yyyy |  | Name: Alma Mirvic Title: Joint Regional Programme Coordinator Participating Organization (Lead): UNDP Email address: alma.mirvic@undp.org |

NARRATIVE REPORT FORMAT

# EXECUTIVE SUMMARY

Since the launch of the joint program in January 2019 in Bosnia and Herzegovina, Montenegro and the Republic of Serbia, the program has successfully achieved the following:

- 1,173 (out of 1,200) adolescents and youth enhanced their skills in capacity building workshops on socio-emotional skills, mobile journalism for social cohesion, voluntarism, project ideation and creation, social innovation, digital solutions

- Over 1,300 persons actively participated in 15 (out of planned 19) youth, national and regional dialogue platforms identifying common social cohesion priorities and recommending solutions

- 221 women received capacity building in advocacy, leadership, gender mainstreaming, political literacy

- 60 teachers (out of 200) were trained in inter-cultural communication skills and media and information literacy

Despite having experienced significant restrictions, including periods of lockdown in all three program countries, the joint program has adapted and continues to adapt to ever changing and unpredictable circumstances of COVID-19. Capacity building of all target groups (Output 1) in the program was nearly completed in 2020, with teachers and media to be delivered via online platforms in early 2021.  Nineteen cross-border grants that were awarded in May under support to joint actions and priorities (Output 2) have been adapted to country-based components, with only few and small cross-border meetings taking place. UPSHIFT, social entrepreneurship platform for adolescents and youth, successfully transformed for online delivery with almost 15 small community grants in all countries. To facilitate adaptation of capacity-building activities and provide adequate mentorship, staff and grantee organizations attended learning webinars on various digital platforms. The program’s pursuit of policy recommendations and improvements (Output 3) was tailored to operational and political circumstances. Baseline survey of grantee beneficiaries, delivered via web platform, was delayed due to the pandemic, and response rates have been slowly increasing across countries, with due recognition of online fatigue. National parliamentary elections in Montenegro and Serbia have affected somewhat the continuity of relationships in the program, as well as the extent to which the program will be able to deliver on desired policy improvements given the pandemic context and related prioritization.

# Purpose

- Provide the main objectives and expected outcomes of the programme in relation to the appropriate Strategic UN Planning Framework (e.g. UNDAF) and project document (if applicable) or Annual Work Plan (AWP).

- Bosnia and Herzegovina: Outcome 2: By 2019, BiH consolidates and strengthens mechanisms for peaceful resolution of conflicts, reconciliation, respect for diversity and community security.

- Montenegro: Outcome 1:  By 2021, a people-centered accountable, transparent and effective judiciary, Parliament, public administration and independent institutions ensure security, equal access to justice and quality services for all people

- Serbia: Outcome 1: By 2020, people in Serbia, especially vulnerable groups, have their human rights protected and have improved access to justice and security and

Outcome 5: By 2020, an efficient education system is established that enables relevant, quality, inclusive and equitable education to all, particularly the most vulnerable, and increases learning and social outcomes.

Outcome 9: By 2020, Serbia has inclusive policies ensuring an enhanced cultural industries sector, promoting cultural diversity and managing cultural and natural heritage as a vehicle for sustainable development

# Results

- Narrative reporting on results:

- Outcomes:

Outcome 1: Stability and trust in the region, and especially in BiH, are enhanced.

- Outputs:

Output 1.1: Different groups in the countries of the region, and youth in particular, acquire and practice skills to help break stereotypes and constructively interact across divides.

In 2020, UPSHIFT (UNICEF’s global social innovation and entrepreneurship platform) was adapted to the online format, due to the pandemic environment, Overall, 300 adolescents and youth (212 girls and 88 boys worked in collaborative and well organized online and offline environment to identify community challenges they could jointly address. This approach was followed for national and regional e-UPSHIFTS resulting in more than a dozen funded community projects.  In Bosnia and Herzegovina (BiH), the planned capacity building of youth and women has been completed, with 24 youth across BiH participating in several months’ long training program focused on leadership, advocacy, public policy, project preparation and fund-raising, preparing youth for active roles in their local communities; and 84 women from 28 municipalities completing a series of learning seminars on leadership, advocacy, public policy and self-representation.   Established partnership with Faculties of Political Sciences in Sarajevo, Belgrade and Podgorica lead by UNESCO served to introduce core elements of Media and Information Literacy into training curriculum for primary and secondary schools’ teachers and librarians. Moreover, this partnership aimed to further capacitate media representatives to promote media and information literacy and amplify positive story-telling in the region. In Montenegro, over 40 women have participated in offline and online capacity-building seminars. Thirty young diplomats completed workshops on social cohesion and intercultural communication, with extremely positive feedback from all participants.

In Serbia, work continued on civic education (CE) reform, organizing trainings for 60 teachers, as well as continuing development of the online platform with CE resources, in cooperation with national institutions. Thirty young women from different social backgrounds across the country attended online and face-to-face sessions on women's leadership, gender equality, social cohesion, human rights, project development, public advocacy, teamwork, CV writing and personal presentation skills. These modules enabled them to exchange opinions and experiences, establish ties and gain skills to act as agents of change in their communities. Ten teams from three universities in Serbia were supported by ten mentors to participate in a competition framed around critical thinking and public advocacy of young people.

Output 1.2: Citizens from different groups jointly identify and implement actions that promote social cohesion in the region, especially in Bosnia and Herzegovina.

The Regional Dialogue for Women, hosted by UNDP Montenegro in February 2020, gathered 83 participants (79 women and 4 men from all program countries), mapping recommendations and tailored priorities for action.  Work is underway to mainstream recommendations from Regional Dialogue for Women into the drafts of upcoming Women’s Entrepreneurship Strategy and the Gender Equality Action Plan.

Nineteen cross-border projects were awarded in May 2020, and the project supported all grantee organizations with adaptations to Covid-19 circumstances.The Small Grants Facility enabled the partnership among 35 civil society organizations, six public institutions and two secondary schools.  Although originally planned as cross-border and highly interactive projects, the pandemic posed a significant challenge to implementation and grantee organizations were continually mentored and supported throughout 2020 to achieve their goals.

Output 1.3: Policy recommendations to improve social cohesion in the region are effectively advocated for, and endorsed by, authorities and relevant stakeholders.

The program mapped the current policy processes and relevant documents in all three countries against the priorities identified in youth, national and regional dialogue platforms and continued dialogue with responsible government institutions to identify avenues for integration of policy recommendations. In partnership with the Ministry of Sports and Youth in Montenegro, the joint program has successfully mainstreamed 7 recommendations from youth and national dialogues into the baseline document for the 2021 funding of NGO projects. Work is underway to mainstream recommendations from Regional Dialogue for Women into the drafts of upcoming Women’s Entrepreneurship Strategy and the Gender Equality Action Plan.

Preparations for online experts’ workshop for academia partners is underway, serving to formulate a joint publication for future use in academic institutions.  The partnership with academia, in Bosnia and Herzegovina,  with the Faculty of Political Sciences and the Institute for Social Research resulted in the proposed policy advance in promoting online open source platform for the new approach to the school subject’ Society, Culture, Religion’, an important entry point for promoting Social Cohesion concept.

- Describe any delays in implementation, challenges, lessons learned & best practices:

Delays in government formation, coupled with COVID-19 priorities have affected the availability of program’s institutional partners in the Joint Program Board. In 2020, only one electronic Board meeting was held, in June.

Through a series of in-country and regional activities, programme has successfully facilitated encounters, collaboration and joint action of people from three countries. Over 1,300 people from all sectors from three countries discussed joint challenges and solutions through regional dialogue event, whose results will enable joint action through cross-border project proposals. To enable participation of unorganized youth, programme delivers multi-country solution-generating UPSHIFT initiative which brings together young people and supports them to put their ideas into practice. This programme is a unique platform which gives voice to people and provides tools and resources to translate solicited ideas into practice. In times of broken feedback loops, participation fatigue and low trust in participation processes, such an approach serves as an example of meaningful participation and collaboration for impact.

The innovative aspect of the cross-border Small Grants Call has been that applicants were asked to identify, develop and solidify their regional partnership early on, specifically at the application stage.  This meant that as early as at the applications stage, partnerships were developed and trust and cohesion advanced at this stage as the two (and in some instances three or more) partners from three countries were jointly working together to develop the project proposal and agree on shares of funding allocations.  Not only were partnerships advanced in between countries, but also partnerships were advanced between different types of partners, where the DFF programme leveraged innovative applications and partnerships between municipalities and CSOs in different countries, breaking away from the more traditional forms of partnerships, municipality to municipality, and CSO to CSO. As an example of best practice, the project teams consolidated updated grant application forms seeking to harmonize agency grant requirements and thus simplifying grant award procedures for future grantees. Online video tutorials in three language versions for the project proposal and budget application forms were produced and widely advertised on social media and open day events, seeking to facilitate applications from prospective applicants. The application process was handled entirely in electronic form, through joint email addresses established in each programme country.

Owing to the methodology intrinsic to the Small Grants Facility, several grantee organizations focus solely on advancing gender equality and women’s empowerment in their activities. Two cross-border projects, led by organizations in Bosnia and Herzegovina, tackle the issue of inclusiveness of visually impaired women in all three countries; as well as support women’s entrepreneurship and learning. In addition, a support was provided to female artists from the region highlighting their role in society, contribution to culture and equal representation in this sector.

The opportunities for joint problem-solving and team-work, presented by the UPSHIFT platform, represent a unique tool to bring youth together in new and mixed teams, to create space for their innovation and activism.

uReport is another useful platform where youth voices are polled in real time, summaries available to all, and could serve for advocacy purposes, as the program has demonstrated in Serbia with considerations to revise the Law on Volunteering.

- Qualitative assessment:

Multi-country joint programmes require strong coordination of various components among countries and agencies, as well as continuous commitment of the programme's high-level counterparts. This is especially significant if moving in the same direction and pace is considered.  The joint DFF programme has therefore prescribed the establishment of country coordination bodies, the Joint Programme Board and the Strategic Advisory Board to allow for layered, country-specific and 'regional' perspective, stock-taking and partnership at political and programmatic levels. Additionally, the programme has established national coordination bodies to ensure a more detailed attention and direction to project activities in each country is taking place. Membership in national coordination bodies and Joint Programme Board is overlapping, with additional ministries included in national coordination bodies, to preserve institutional memory. Ensuring strategic coherence of the approach across main components, delivering and communicating as one rather than as individual agencies, while recognizing the need for country-specific interventions based on the country context can be a challenge for joint programmes. This challenge is mitigated in the DFF programme by holding regular online meetings among programme coordinators, and meetings of strategic advisory board, consisting of relevant UN agencies highest representatives. Where communications and M&E components are concerned, the agency communications specialists have developed a joint internal and external communications protocol to facilitate the flow of requests and clear decision-making lines. All joint documents are consulted broadly among all teams which is time consuming, but necessary, to reach a levelled understanding.

Using the Programme Results Framework from the Project Document / AWP - provide an update on the achievement of indicators at both the output and outcome level in the table below. Where it has not been possible to collect data on indicators, clear explanation should be given explaining why, as well as plans on how and when this data will be collected.

|  | Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification |
| --- | --- | --- | --- |
| Outcome 1 Stability and trust in the region, and especially in BiH, are enhanced. Indicator: Indicator 1.1 Rank of Bosnia and Herzegovina in the 2018 Global Peace Index. Baseline: 89, out of 163 countries. Planned Target: Improved ranking | Improved ranking, in 2020 BiH ranking has already improved – 79th - compared to the 2019 (81st). | The programme recognizes that it has no significant attribution to this indicator; however, given the nature of this composite index (GPI investigates the extent to which countries are involved in ongoing domestic and international conflicts. It also seeks to evaluate the level of harmony or discord within a nation; 23 indicators are used to establish each country's peacefulness score), it was assessed as a useful reference for the programme. | Source: https://www.visionofhumanity.org/wp-content/uploads/2020/10/GPI_2020_web.pdf |
| Indicator 1.2 Percentage of youth indicating higher levels of trust towards other ethnic groups in the region. Baseline: Low overall level of trust between youth of different ethnicities. Planned Target: 50% of surveyed youth, particularly in BIH (including youth who are direct project beneficiaries) report increased trust toward members of other ethnicities | n/a | Results not available at end of 2020. | Perception Survey Data uReport data (UNICEF led) Entry- and exit surveys for youth grantees and dialogue platform participants. |
| Indicator 1.3 Level of collaboration to address mistrust and social divides between citizens from different groups in the participating countries, with their peers in Bosnia and Herzegovina. Baseline: Low overall levels of cross-country collaboration addressing mistrust and social divides (BiH vis-a-vis neighboring countries). Planned Target: Increased level of cross-country collaboration to address mistrust and social divides between citizens, manifested through at least 20 sustainable social cohesion partnerships generated as a result of the programme. | 19 cross-border projects, based on social cohesion priories, awarded. |  | Perception study commissioned by the programme. Entry- and exit surveys for grantees and dialogue platform participants. |
| Output 1.1 Different groups in the countries of the region, and youth in particular, acquire and practice skills to help break stereotypes and constructively interact across divides. Indicator 1.1.1 Number of people (teachers, youth, women, journalists and editors, sex- and gender-disaggregated) from participating 4 countries with increased knowledge and skills to bridge social divides. Baseline: Insufficient number of people (particularly teachers, youth and women) capacitated to support social cohesion in the region. Planned Target: At least 1600, as follows: (i) 600 adolescents (10 – 18 years old); (ii) 600 young people (18 – 30 years old) among whom 50% women; (iii) 200 teachers, among whom 50% women and (iv) 120 journalists and editors Indicator 1.1.2 Number of stakeholders who apply the acquired skills and knowledge in their follow-up work as a result of the programme support. Baseline: n/a Planned Target: At least 50% of all stakeholders (in various target groups) apply the skills and knowledge acquired through the programme in their follow-up work. |  |  |  |
|  | Skill building training for 1,173 (out of 1,200) adolescents and youth (including 391 boys and 782 girls), 221 women (more than planned 200), has been completed by end of 2020. n/a |  | Entry- and exit capacity development surveys filled in by trainees. Lists of participants in training activities. Programme progress/final report. |
| Output 1.2 Citizens from different groups jointly identify and implement actions that promote social cohesion in the region, especially in Bosnia and Herzegovina. Indicator 1.2.1 Total number of people (particularly youth) from participating countries who meaningfully engage in and contribute to identification of social cohesion barriers and priorities for the 3 countries Baseline: 600 people in the national platform events in Bosnia and Herzegovina. Planned Target: At least 1,600 people (among whom at least 800 youth and women) from participating countries engage in and contribute to identification of regional social cohesion barriers and priorities. Indicator 1.2.2 Total number of dialogue platforms (gender balanced) bringing together political leaders and various stakeholders from the 3 participating countries in joint discussions on how to strengthen social cohesion in the region. Baseline: n/a Planned Target: At least 19 broad-based social cohesion dialogue platform events (gender balanced) bringing together political leaders and various stakeholders from the 3 participating countries. |  |  |  |
|  | Over 1,300 participants from participating countries contributed to identification of social cohesion challenges and solutions within and among the three participating countries. 10 youth and 3 national and 2 regional dialogue events have taken place across the three participating countries. |  | Lists of participants from the dialogue events. Programme reports. Media monitoring/press clipping. Recommendations from the dialogue platforms. Calls for Proposals and Reports from implementation of the grants. Feedback from grant facility beneficiaries (indirect and direct). Photos and videos from the implementation of social cohesion initiatives in the region. |
| Output 1.3 Policy recommendations to improve social cohesion in the region are effectively advocated for, and endorsed by, authorities and relevant stakeholders. Indicator 1.3.1 Number of effective advocacy channels (engaging equal numbers of both sexes) leveraging political and public support within participating countries for endorsement of social cohesion policy recommendations. Baseline: UN agencies in the participating countries have deployed successful advocacy efforts to promote social cohesion. Planned Target: At least 4 inter-connected and mutually-reinforcing advocacy channels help leverage political and public support for endorsement of social cohesion policy recommendations, including: (i) UN-led discussions with political leaders and policy-makers; (ii) regional dialogue platform; (iii) civil society Indicator 1.3.2 Number of social cohesion policy recommendations voiced through the regional dialogue platform that are endorsed by authorities and international community and contribute to their effective follow-up implementation. Baseline: n/a Planned Target: At least 5 policy recommendations formally endorsed by authorities and the international community. | n/a n/a | Activities surrounding this Output are planned in 2021. | Media coverage, photos, videos capturing advocacy and formal endorsement of social cohesion recommendations. Programme reports. Materials from advocacy events. Formal decisions and documents of authorities or the international community evidencing endorsement of the social cohesion recommendations. |

iii) A Specific Story (Optional)

Problem / Challenge faced: Describe the specific problem or challenge faced by the subject of your story (this could be a problem experienced by an individual, community or government). Programme Interventions: How was the problem or challenged addressed through the Programme interventions? Result (if applicable): Describe the observable change that occurred so far as a result of the Programme interventions. For example, how did community lives change or how was the government better able to deal with the initial problem? Lessons Learned: What did you (and/or other partners) learn from this situation that has helped inform and/or improve Programme (or other) interventions?

III.	Other Assessments or Evaluations (if applicable)

•	Report on any assessments, evaluations or studies undertaken.

IV.	Programmatic Revisions (if applicable)

•	Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place.

Following the no-cost extension granted in April 2020, the joint programme prepared an updated Joint M&E Plan as well as progress monitoring platform, including definitions of indicators, baseline and target values. The platform is populated at bi-annually by project coordinators, using in-country reporting mechanisms. Additionally, the programme is taking advantage of joint entry and exit questionnaires for capacity building and dialogue events. Owing to the extension in 2021, COVID-19 challenges and the non-participation of 4th country (Croatia) as originally planned, the programs targets were adjusted accordingly.

V. 	Resources (Optional)

•	Provide any information on financial management, procurement and human resources.

•	Indicate if the Programme mobilized any additional resources or interventions from other partners.

# Footnotes

The term “programme” is used for programmes, joint programmes and projects.

Strategic Results, as formulated in the Strategic UN Planning Framework (e.g. UNDAF) or project document;

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as  “Project ID” on the project’s factsheet page the MPTF Office GATEWAY

The MPTF or JP Contribution, refers to the amount transferred to the Participating UN Organizations, which is available on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

The UNDAF has been officially extended until 2020.

Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

# Text boxes

ii) Indicator Based Performance Assessment: