## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual
Programme Title & Project Number | Programme Duration
Programme Title: | Overall Duration (months)
Programme Number (if applicable) | Start Date (dd.mm.yyyy)
MPTF Office Project Reference Number: | Original End Date (dd.mm.yyyy)
Country | Current End date(dd.mm.yyyy)
Recepient UN Organizations | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | National counterparts (government, private, NGOs & others) and other International Organizations
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Annual
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum)
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups
3.1 | Results: Outcome Level | Please include outcome level results achieved
3.2 | Results: Output Level | Please include output level results achieved
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words)
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words)
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words)
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Annual
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
MPTF Annual_Final Report_to SDG Fund UNICEF_Jamaica
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification

## Communication-Annual
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board

## General Information-Final
Programme Title & Project Number |  | Programme Duration
Programme Title: | Safeguarding and Protecting the Most Vulnerable: Enhancing Jamaica’s Shock Responsive Social Protection Mechanisms in support of vulnerable Groups including children. | Overall Duration (months) | 11 MONTHS
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2020-05-19
MPTF Office Project Reference Number: | 121616 | Original End Date (dd.mm.yyyy) | 2021-03-31
Country | JAMAICA | Current End date(dd.mm.yyyy) | 31/1/2021
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNICEF, JAMAICA; FAO JAMAICA | National counterparts (government, private, NGOs & others) and other International Organizations | MINISTRY OF LABOUR AND SOCIAL SECURITY & MINISTRY OF FINANCE AN THE PUBLIC SERVICE; MINISTRY OF AGRICULTURE AND FISHERIES [MOAF]; THE RURAL AGRICULTURAL DEVELOPMENT AUTHORITY [RADA]
Report Cleared By
o Name: | Shelly Trim
o Title: | Data and Results Reporting Officer
o Email address: | shelly.trim@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The project supported the safeguarding and protection of vulnerable farmers and poor Jamaicans registered with the Ministry of Labour and Social Security [MLSS]. It formed part of a decisive response to socioeconomic needs within the context of a diminishing fiscal space and limited human capital, against the backdrop of a global pandemic. The effects of the pandemic have been particularly detrimental to the poorest and most vulnerable social groups with incalculable negative impacts on rural farm families, children, and those with a disability. Through routine cash transfers to poor vulnerable families and the marketing of agricultural farm produce of poor rural farmers the resilience of 4,552 (3937 through MLSS and 615 through MOAF) households were buttressed as part of the broader social protection system in Jamaica. Consistent with the resources provided through the Multi-Partner Trust Fund, the activities bolstered the capacity and responsiveness of the Government of Jamaica lead Agencies – Ministry of Agriculture and Fisheries [MOAF] and the MLSS - Social Protection System which commenced in August 2020 by supporting local food produce consumption, and the protection and promotion of human capital accumulation. In particular, the Social Protection System was strengthened through horizontal and vertical expansions, considering that approximately 25% of Jamaica’s children are living in poverty with those with disabilities and living in rural and peri-urban areas disproportionately affected. Parallel cash and in-kind support were provided against the backdrop of Jamaica having recorded over 5,500 positive COVID-19 cases, with over 600 being children and youth ages 0-19 years. Beneficiaries were identified through the MLSS Management Information System administered by the Programme of Advancement Through Health and Education (PATH), as well as through the Rural Agricultural Development Authority [RADA]. Recipients included: pregnant mothers; women who were lactating; families who have children with disabilities; and female farmers. Through the collaborative efforts of UNICEF and FAO care packages were also provided to children and their families registered with the Jamaica Council for Persons with Disabilities and the Early Stimulation Programme (ESP). Noteworthy is that the ESP is an early intervention programme for children (0-6 years) with various types of developmental disabilities for which the cost of services become exponentially chronic. With over 135,000 jobs being lost within the 2nd and 3rd quarters and the Planning Institute of Jamaica’s projection that the economy would have recorded declines in output ranging from 8-10 per cent, as a result of the coronavirus, strategically, the project contributed to providing a cushion for the poorest and most vulnerable, and advanced efforts to expand social protection programmes, especially for PwD’s. The MPTF resources contributed to softening the economic shock providing a 40% increase in the value of goods programmed by the Government, as well as providing an additional benefit beyond what was allocated. Altogether, 8,451 cash transfers were disbursed over the period as well as 1,000 care packages, providing a well-needed financial boost to targeted households facilitating a cushion to alleviate the harsh economic conditions; bolster the livelihoods of female farmers; and furthering a pathway that will augment social protection mechanisms and advanced efforts to expand social protection programmes, especially for PwD’s.
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | 757 Households with Pregnant and Lactating women. 2,180 Households (1,340 boys & 840 girls) with children with disabilities. 1,000 Households targeted through ESP, JCPD & PATH with girls and boys ages 3-5 years experiencing food insecurity because of the effects of Covid-19. 615 farmers have participated in the agriculture produce support programme.
3.1 | Results: Outcome Level | Please include outcome level results achieved | Result 1: 2,937 children with disabilities and pregnant/lactating women on PATH received approximately US$30 increase in PATH benefits for three (3) payments between August to December 2020. Result 2: Developed Memorandum of Understanding between UNICEF and MLSS that includes Pathways/protocol to trigger shock responsive cash interventions in the case of emergencies. Result 3: 615 Farm families have access to economic protection
3.2 | Results: Output Level | Please include output level results achieved | Output 1.1 Financial boost for 3 months provided to the most poor and vulnerable households headed by women and men to mitigate social and economic risks of COVID-19. (families with girls and boys with disabilities, pregnant and lactating women and girls and female-headed farm households in rural areas Output 1.2 Distribution of food care packages for approximately 1,000 families at risk with girls and boys Output 1.3 Established pathways/protocol to trigger immediate humanitarian support and cash transfers in future emergencies Output 3. An upgraded programme with temperature control storage capacity of 41 tonnes to facilitate the Ministry of Agriculture and Fisheries to implement buy-back programmes Output 4. Established pathway/protocol for buy-back programme linked to social protection mechanism to support the female headed farmers and others who are in extremely vulnerable conditions during the COVID-19 recovery phase. Output 5. 615 farmers have participated in buyback programme
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | The project with the MLSS established a rigorous monitoring schedule which facilitated continuous feedback and opportunity to mitigate potential risks. In collaboration with the Government partners the project managed its processes with a view toward ensuring physical and psychological safety of beneficiaries through the transfer of resources via electronic means, limiting their exposure to Covid-19; as well as, helping to reduce the emotional strain from loss of income by supporting their food security efforts. The application of the relevant FAO’s policies and those of the Ministry of Agriculture and Fisheries (MOAF) delayed project implementation. While both organizations created a fast track process to approve and implement emergency projects, there are still process gaps that have affected the timely execution of projects in the context of disasters. There was limited capacity of the staff within the local FAO representation office to finalize all necessary documents and clearance took longer than anticipated; this was further complicated by the fact that the Letter of Agreement(LOA) to finalize the agreement between FAO and the MOAF was a novel mechanism to the technical personnel both at FAO JAM and MOAF. Data and clearances which were required from the Ministry of Agriculture and Fisheries to assist in the finalization of the documents was slow as was the spending of the funds under the programme. The FAO Jamaica team has documented the lessons learnt in particular the LOA mechanism for future reference when this mechanism is utilized. The team also recommended that: • The FAO and MOAF review its fast track mechanism. • For emergency projects which are by nature very time sensitive, the FAO should in a timely manner, engage the UN with a view to harmonize the systems and procedures used in the UN and its Specialized Agencies to reduce process friction relative to approvals of documents and fund transfers. • The MOAF need to better define what trigger mechanisms will lead to programmes more readily designated for emergencies and therefore get fast tracked through its emergency procedures. Female farmers in the project area were mainly engaged in livestock production that required specialized cold storage facilities for marketing. unfortunately, MICAF was not equipped with these facilities which created a barrier to purchase more produce from female farmers. To facilitate greater participation of farmers, MICAF is seeking to invest in more cold chain storage facilities across the country. about the difficulty in accessing female farmers-you weren't able to reach the number targeted; how can that be addressed in the future? or the need for the cold storage facility? Covid-19 restricted movement and health concerns of FAO, partner personnel and beneficiaries. The FAO team implemented remote meetings using ICT video conferencing – Zoom, Microsoft Teams, Google Meet to protect staff, partner, and beneficiaries During the period of highest mobilization and execution, owing to heavy and extended rainfall; produce availability and first choice agricultural produce was reduced significantly and their cost increased by multiples. The FAO had to adjust to produce that were able to withstand the then weather conditions and remain wholesome. Funds were delayed reaching the[MOAF] from the FAO because of the GOJ procedures. The funds first had to be sent to a consolidated fund and then transferred from that Fund to the MOAF. The MOAF identified funds earmarked for upcoming activities not yet started and mobilized these funds to execute the project until the FAO allocated funds became available to MOAF from the Consolidated Fund. Under the request from MOAF, a non-budgetary project extension for three months was obtained that allowed the project to offer benefits to more vulnerable farmers.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results.any comments on this? (up to 500 words) | For the first time, the resources have opened the door to continue this fruitful collaboration. Opportunities exists, including the following for future collaboration: 1. To work with the MLSS and advocate for modifications in the value of the cash transfers provided to households with children with disabilities in consideration of routine academic and medical services, which are likely to erode the residual value of the cash benefit. 2. With over twenty (20) years of implementation experience, PATH has proven to have a robust system to identify disadvantaged families through its Beneficiary Management Information System and the public assistance systems, especially in the event of an emergency. 3. In relation to its payment mechanism the MLSS has built out a consistent modality to effect payments to beneficiaries on a bi-monthly basis. Notwithstanding, these modalities are often administratively onerous, and require considerable public investments. 4.Given the existing strictures there is a level of inflexibility which does not easily accommodate humanitarian features in emergencies. Some of the costs incurred could be transferred toward enhancing the value of the benefit. 5. To advocate for an expansion of the digitization of payments, as well as consideration for features that facilitate easier access in emergencies- 6.With additional resources UNICEF would be able to assist the Government to enhance future policies on digital payments 7.To configure arrangements to focus on produce naturally in season as they tend to be able to thrive better under the expected weather conditions 8.Many female farmers are involved more in livestock than with crop production. Current intervention had a bias towards crops. Future interventions need to take this into account to enhance greater female participation. 9.Many female farmers who have participated in the programme are less visible compared to their male counterparts because of the roles that they often play in the farm family. Female farmers tend to be the ones that keep the records and makeing added value products. This role is often overlooked and not captured in reports on programmes. 10.The absence of an embedded national Agriculture Disaster Risk Management (ADRM) strategy for the agriculture industry reduces its resilience to natural and economic shocks and the speed of at which the industry is able to begin recovery actions to return normal livelihood pursuits. 11.Working with cooperatives and organized community-based farmers groups improves community level response through more efficient coordination, mobilization, and production of food resources. 12. There are significant untapped opportunities within GOJ Ministries and Agencies for the substitution of imported food staples; more local produce will support the GOJ’s policy on food security and food import reduction. 13.Trough the MOAF, we now have designated locations where farmers and buyers meet to transact business and farmers are paid immediately with cash and cheques or by electronic funds transfer the next day. This is a significant change from what used to obtain before as farmers were paid weeks after rather than the now one to two days to receive payment.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | UNICEF partnered with the MLSS and the Ministry of Finance and the Public Service (MOFP) to support horizontal and vertical expansions of Jamaica’s flagship social protection programme- PATH. The MOFP provided fiscal supervision of the project while the MLSS coordinated the delivery and reconciliation of benefits to the recipients. Consistent with the Global Humanitarian Response Plan the project complemented the coordinated appeal, in its inclusion of specific metrics to ensure that key vulnerabilities were highlighted, adding another layer of support toward Jamaica’s incremental achievement of key targets under the Sustainable Development Goals (SDGs) and Jamaica’s Vision 2030- SDG’s 1, 2 and 10, no poverty, zero hunger and reducing inequalities- through timely injection of resources and sustainable development initiatives, such as child sensitive shock responsive social protection. These partnerships have provided an opportunity for more robust discussions geared toward the development of parallel measures tailored to multiple deprivations and complement routine transfers at or above the existing value. [catalytic programmatic outcome] • The FAO in pursuing the implementation of the Programme has influenced collaborations between key partners working to provide support to affected beneficiaries. This has led to the MOAF improving coordinations, and by extension, efficiency within participating value chains. The relationship forged between MOAF and MLSS was critical in getting farmers' produce into market spaces • FAO supported the MOAF as they moved to identify select companies as purveyors and forged agreements with the purveyors to provide market outlet support to farmers under the MOAF market support purchase programme. The Purveyors were facilitated to forge new business arrangements with affected farmers through MOAF. Partnerships were also forged with key input suppliers for post-harvest materials that were used to extend the shelf-life and to maintain the wholesomeness of agriculture produce. These partnerships will be maintained beyond the life of the project. [new partnership; programmatic outcome] • A stronger partnership has been forged with MOAF and RADA on this programme as it has allowed the FAO's technical team to glean a more in depth understanding of the partner's respective capacities in value chain development, public procurement and agriculture marketing. This will inform current ongoing programmes which have strong public procurement components and inform future programmes with the agencies. • The FAO and its sister agency UNICEF have shown that synergies can be realised while collaborating in support of the host Country. A more detailed cooperation framework could be embedded in the project development process. [synergistic programmatic outcome] • Ministry of Labour and Social Security has developed linkages with agriculture produce suppliers as part of its social safety net support to vulnerable members of the population – women, persons with disabilities, children on the PATH Programme. This is an additional market outlet for farmers affected by COVID-19 and also a nutrition boost for vulnerable populations. This will lead to greater consumption of local produce, improving food security and substituting local foods for food imports. [new partnerships, catalytic programmatic outcome]
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | Field work for MPTF Grant survey currently being administered to approximately 250 recipients to confirm receipt of funds. The process has been delayed due to restrictions on movement and work from home orders.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | FAO component was extended for two months ending on February 28, 2021. This facilitated the purchasing of greater volumes of agriculture produce from vulnerable farmers.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | UNICEF Jamaica partnered with the Ministry of Finance and the Public Service and Ministry of Labour and Social Security to support its Programme of Advancement Through Health and Education. The MOFP provided fiscal supervision of the project resources while the MLSS coordinated the targeting, delivery and reconciliation of benefits to the recipients. Procurement of goods, such as care packages and the service of an administrative focal point was executed through direct collaboration between the MLSS and UNICEF MOAF existing personnel operating an agricultural marketing programme were assigned to the MPTF programme where their experience played a critical role in the programme’s execution. The FAO received an additional USD $24, 250.00 from the Romanian Government to support upgrading of storage facility under the MOAF Agriculture Produce Acquisition Programme

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1 Existing social protection programmes extended vertically and horizontally targeting most vulnerable households (families (headed by females and males) with girls and/or boys with disability, pregnant and lactating women ) | 3,937 (aprox 13,000 people)- (Average household size 3.5 members) | The Programme of Advancement through Health and Education, PATH administered by the Ministry of Labour and Social Security is a dynamic programme and there is daily movement within the beneficiary population | PATH by Benefit Category Report MLSS Annual Review Report Data MLSS Report November 2020-January 2021
Indicator:
Baseline: 0
Planned Target: 3,750 (11,000 people)
Output 1.1 Financial boost for 3 months provided to the most poor and vulnerable households headed by women and men to mitigate social and economic risks of COVID-19. (families with girls and boys with disabilities, pregnant and lactating women and girls and female-headed farm households in rural areas | 2,937 persons Boys-1,340 Girls- 840 Women- 757 | Daily movement within the beneficiary population | Ministry of Labour and Social Security Progress Update August-November 2020
Indicator 1.1.1: Number of households headed by women and men receiving cash transfers
Baseline: 0
Planned Target: 2760
Output 1.2 Distribution of food care packages for approximately 1,000 families at risk with girls and boys
Indicator 1.2.1: Number of families headed by women and men receiving support/food packages | 1000* Males- 625 Females 375 *MPTF |  | MLSS Annual Review Report Data MLSS Report November 2020-January 2021
Baseline: 0
Planned Target: 1,000
Output 1.3 Established pathways/protocol to trigger immediate humanitarian support and cash transfers in future emergencies
Indicator 1.3.1 Establishment of pathways/ protocols for emergency preparedness and response | Signed Memorandum of Understanding for the provision of humanitarian assistance in emergencies and the technical support toward the development of shock responsive social protection measures. |  | MOU Document
Baseline: 0
Planned Target: Memorandum of Understanding
Outcome 2: Most vulnerable people have access to social and economic protection mechanisms
Number of farmers participating in the buyback programme | 615 farmers | Due to the short term of the project implementation public procurement was only done for a few months and thus limited the total number of farmers who could be reached. Furthermore, unfavourable climatic conditions (heavy rainfall) also hindered farmers and caused crop loss and reduction in supply. | Ministry of Agriculture and Fisheries Final LOA Report (March 2021)
Baseline: 0
Planned Target: 1000
Output 2.1 Livelihoods of female farmers in the parishes of St Mary, Portland and St Thomas stabilized as a result of the MICAF produce buy-back programme |  |  | Ministry of Agriculture and Fisheries Final LOA Report (March 2021)
Indicator 2.1.1 Number of female farmers participating in buy-back programme | 243 female farmers | Female farmers in the project areas were mainly engaged in livestock production that requires specialized storage and transportation system for marketing. MICAF was not equipped with these facilities to purchase livestock products and hence less procurements were made from these farmers | Ministry of Agriculture and Fisheries Final LOA Report (March 2021)
Baseline: 0
Planned Target:1000
Output 2.2 Upgraded programme to facilitate the Ministry of Agriculture to implement buy-back programmed |  |  | Ministry of Agriculture and Fisheries Final LOA Report (March 2021)
Indicator 2.2.1 Number] Adequate storage for agriculture products purchased under buy-back programme | 1 |  | Ministry of Agriculture and Fisheries Final LOA Report (March 2021)
Baseline: 0
Planned Target:1
Output 2.3.Established pathways/protocol for buy-back programme linked to social protection mechanism to support the female headed farmers and others who are in extremely vulnerable conditions during the COVID-19 recovery phase |  | Not Applicable
Indicator 2.3.1 Reduction in the number of days farmers are paid | 2 days |  | Ministry of Agriculture and Fisheries Final LOA Report (March 2021)
Baseline: 7-14 days
Target: 2- 5 days
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries:
https://jis.gov.jm/more-support-for-farmers-through-buy-back-programme/
A blog post: https://blogs.unicef.org/jamaica/sometimes-even-heroes-need-a-helping-hand/
Press release: https://www.unicef.org/jamaica/press-releases/path-gets-big-boost-unicef
https://twitter.com/floydgreenja/status/1392576707274715138
https://www.youtube.com/watch?v=qMF57cBg-iA
: http://www.fao.org/jamaica-bahamas-and-belize/news/detail-events/en/c/1366008/
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board